## 000-K-GRD-70001-001-RAP
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | Raj | Owner has reviewed and commented on the MR package submitted on Contractor’s request to solicit quotations from vendors at the earliest. This MR stands reviewed with Status Code 3.
2 | Text Box | 1 | Mahdi Ali | Add document title in the header
3 | Callout | 1 | Mohamed Ayyash | No. (Typo) apply to all sheets
4 | Callout | 1 | Mohamed Ayyash | What is 000M? should be 7CDU/2HCU
5 | Text Box | 1 | Mahdi Ali | Add equipment numbers
6 | Call-out | 3 | Ahmed Marhoon | Ensure Licensor's mandatory technical requirements are also addressed/met.
7 | Callout | 3 | Adnan Alothman | As per the Contract, Annex1-Technical documents do not have any order of precedence. Please correct this to align with EPC Contract.
8 | Call-out | 4 | Sameer Foujdar | Supplier shall provide startup procedure along with logic sequence and pre startup requisites.
9 | Text Box | 4 | Hasan Asad | 1. The vendor shall provide LCCA report considering Complete Compressor unit and major equipment. 2. The vendor shall provide maintenance manual with troubleshooting guideline for complete Compressor unit and sub-system such as lube oil, etc.
10 | Callout | 4 | Yousif Ahmadi | Remove M so it should read 000-K-ITP-70001-001
11 | Callout | 4 | alexis.martinez | Add "Scope of Supply document"
12 | Call-out | 4 | Ahmed Marhoon | What about ESD?
13 | Callout | 4 | Adnan Alothman | For all critical equipment, company representative attendance is required as per BMPS-B11.
14 | Call-out | 5 | A.Jabbar Mahmood | What about owner representatives?
15 | Call-out | 5 | Ahmed Marhoon | Change FAT to IFAT. Also, what about ESD?
16 | Call-out | 5 | Ahmed Marhoon | Add CHAZOP
17 | Cloud+ | 5 | Ahmed Marhoon | These are major milestones and shall be attended by owners' representatives. List to be updated according to the project's agreed responsibility matrix.
18 | Text Box | 6 | Sankara | HV Motors for Zone 2 shall be Ex-d or Ex-e only.
19 | Callout | 6 | Yousif Ahmadi | Add BMPS to so it should read BMSP-K1
20 | Text Box | 6 | Hasan Asad | The pulsation dampeners shall be equipped with drain facility connected to flare - Vendor experience and proposal to be requested.
21 | Callout | 7 | Mohamed Ayyash | General comment: Replace with tabs in all sheets
22 | Text Box | 8 | Hasan Asad | Required
23 | Call-out | 10 | Ahmed Marhoon | Scope of spill back system to be clarified. Will it be designed by others or the supplier?
24 | Call-out | 10 | Ahmed Marhoon | Refer to comment on the manual vs automatic Un-loaders given on the respective DS.
25 | Call-out | 10 | 986131 | Reword DCS/ESD.
26 | Text Box | 11 | Hasan Asad | Rod Drop
27 | Text Box | 11 | Hasan Asad | Is this Machine Condition Monitoring System - MCM System?
28 | Text Box | 11 | Hasan Asad | The Vendor/Supplier to clarify the difference between MCM and CMS and which signals will be send to each system for Owner understanding, review and approval.
29 | Text Box | 12 | Hasan Asad | Equipment installation shall be under Vendor supervision.
30 | Text Box | 12 | Hasan Asad | Probes to be installed by the package vendor at the their shops meeting project specification requirement for interfacing with MCM BN.
31 | Callout | 14 | Mohamed Ayyash | Enlarge font inline with others
32 | Text Box | 15 | Hasan Asad | Such requirement shall be installed in Vendor/Supplier shop.
33 | Call-out | 15 | Sameer Foujdar | Electronics for start-up sequence logics should also be included.
34 | Text Box | 15 | Hasan Asad | The Supplier shall ensure that the lube/control oil system are flushed properly to Supplier/Vendor quality control and satisfaction.
35 | Call-out | 15 | Ali Abbas | Including flow charts, refer to typical documentation in the ITB.
36 | Callout | 18 | Mohamed Ayyash | Add space
37 | Callout | 19 | Mohamed Ayyash | Should read Commissioning and Start-up (not vise versa)
38 | Text Box | 19 | Hasan Asad | Basis Vendor PM schedule, the suction and discharge valves shall be inspected after certain hours. Hence, the Owner shall consider one complete set of suction and discharge valves as Capital Spare.
39 | Callout | 19 | Mohamed Ayyash | Add "Commissioning"
40 | Text Box | 20 | Ahmed Marhoon | The following are comments related to instrumentation and control. Contractor is requested to update the other documents issued as part of this transmittal, in addition to the data sheet, based on the comments stated herein and ensure consistency prior to release of MR to suppliers. 1. Add a clear note on Design Philosophy BMPS-A3 reference section 8.5 MCM Guidelines. Monitoring system in general to meet the requirement stated in this BMPS in addition to vendor requirement. Requirement of MCM to be verified with the supplier. Reference to BMPS-J15 MCM to be added. Also, all applicable BMPS-J series to be referenced (such as J2, J3, J6, J31 …etc) for the supplier to comply with. 2. Instruct the supplier to source instrumentations from project AVL only. 3. Add a note to the supplier with reference to the applicable BMPS to design and supply the system according to the final PID. Functional design specifications covered in this MR shall be firmed based on the approved PID. Vendors to be clearly notified on the necessity to include all the Hazop3/SIL recommendations and changes made Post-EPC-Development. 4. Spill-back design shall be reviewed and confirmed with the supplier. Contractor to consider the compressors protection and process requirements according to manufacturer and licensor recommendations. 5. Suppliers to be notified on the possibility of considering wireless instruments for non-critical monitoring devices. Reference to BMPS-J10 Wireless to be added if applicable and meeting the criteria (under development) of wireless measurement. 6. All the machinery monitoring probes etc. shall be factory fitted by the vendor and not at site. 7. Narrative/flow charts/cause and effect shall be provided for any control or sequence logic. 8. Add a note to the supplier to design, fabricate and supply the instruments in accordance with the BMPS J specifications. Items such as Junction boxes, cables, wiring, ferruling, earthing, terminal strips, fitting …etc shall be installed by the vendor/contractor meeting the requirements specified on the applicable BMPS J specifications like BMPS-J31. 9. Supplier to be instructed to generate all instrument data sheets, hook ups ...etc. in project specs (according to Bapco standard formats) and to be developed in SPI format. Typical formats can be provided to the supplier at a later stage for compliance. In addition to BMPS J Specifications, all relevant BMPS J Standard/Typical Drawings to be included. 10. Compliance to licensor's mandatory and recommended requirements to be included. 11. Supplier to comply with all the applicable BMPSs and provide, as a minimum, all the documents, hardware, software and services according to the relevant sections of the BMPSs in the agreed standard formats of the project. List to reflect all the required deliverables in accordance to BMPS. 12. Vendor/TTSJV shall provide a list of deviation from BMPS specifications, in addition to the requisition specifications, for owner's review and approval.
41 | Callout | 20 | Mohamed Ayyash | Shouldn't this include commissioning phase as well ?