## 000-S-GRD-80008-001-RAP
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | Nalini Mohan | Owner has reviewed and commented on the MR package submitted on Contractors request to solicit quotations from vendors at the earliest. This MR stands reviewed with Status Code 3.
2 | Text Box | 1 | This | This stamp is the review code for MR and Data Sheet included in the MR.
3 | M¤¸ Á | 2 | User | Add as per JVD Instruction
4 | Callout | 2 | Julio.Aguilar | Please, consider a dedicated Section for Acronyms/Abbreviations to be consistent with other OCs. Standardization procedure to be considered.
5 | Callout | 3 | Julio.Aguilar | Please, consider a dedicated Section for Acronyms/Abbreviations to be consistent with other OCs. Standardization procedure to be considered.
6 | Callout | 4 | Dowon Pyun | There are many document numbers specified as PTC-XXX in the scope of supply or particular technical specification, but they are actually not shown in the document list of requisition.This is typical comment to other requisitions.
7 | Call-out | 5 | Ali Abbas | add CHAZOP
8 | Call-out | 5 | Ali Abbas | add OWNER in the attendees list
9 | Callout | 6 | Julio.Aguilar | Number of absorbers to be confirmed. e.g. Two 100%
10 | Callout | 6 | Julio.Aguilar | (2x100%)
11 | Text Box | 6 | Hasan Asad | and Lubrication System.
12 | Text Box | 7 | Hasan Asad | Machine Condition Monitoring System (MCM)
13 | Call-out | 7 | Ali Abbas | add reference to BMPS-A3 para 8.5 MCM requirement and BMPS-J15
14 | Call-out | 7 | Ali Abbas | Reference shall be given to all applicable BMPS-Js specifications, standard and typical drawings and AVL.
15 | Text Box | 7 | Nalini Mohan | Access road limitations in Bahrain/Bapco shall be clearly highlighted to the Vendor
16 | M¤¸ Á | 8 | User | Revised description as per JVD Instruction
17 | Callout | 9 | BD Mori | Duty Specification document 083-S-DAT-00001-001 and
18 | Callout | 10 | Nalini Mohan | P&ID is not attached in this requisition
19 | Text Box | 11 | Dowon Pyun | The Contractor must mention the technical requirements for the cryogenic service in the gaseous nitrogen generation.
20 | Callout | 12 | Dowon Pyun | To be added a statement for Air Cooled Heat Exchangers
21 | Callout | 13 | Dowon Pyun | In order to properly apply this table without any mistake, Contractor must show here the notes 1, 2 & 3 as highlighted in BMPS-L9
22 | Callout | 16 | BD Mori | , shutdown, special procedures and trouble shooting guidelines.
23 | Callout | 16 | Dowon Pyun | Add "as minimum"
24 | Call-out | 17 | Ali Abbas | detailed control narratives, logic, sequence narrative and flow chart and cause and effect matrix. Refer to CDRL for instrumentation deliverables.
25 | Text Box | 18 | Hasan Asad | Supplier shall provide LCCA for 20 years to serve as element for package selection and procurement and for maintenance strategy.
26 | M¤¸ Á | 20 | User | Please check this Cover sheet is acceptable. Also, page number is re-seted from this page.
27 | M¤¸ Á | 21 | User | Add Sub-supplier list
28 | Call-out | 27 | Mahdi Ali | Equipment tags format are not as per BMPS-A8. Tags are incorrect.
29 | Callout | 27 | Salman Jaffer | With reference to the SGP final design, please do not use SGP compressors as an example.
30 | Callout | 27 | Dowon Pyun | The requirement of this sheet is for Contractor not for Vendor.