## 010-E-DAT-00032-001-RAP-CS
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
| Text Box | Page 1 | MAK | General Comment: Use the modified document cover pages that was transmitted to Project Mail Box to maintain the uniformity of the documents across all the OC's. Refer to, "000-A-PRO-50006-001 HOMOGENIZATION PROCEDURE - Modified Attachments"
| Text Box | Page 1 | 986131 | Use the revised equipment number in the data sheet.
| Text Box | Page 1 | 986131 | Refer API 661: The data sheet is incomplete - provide the sheet 2 of 2 of API data sheet. And the purchase check list duly filled.
| Text Box | Page 1 | 986131 | Update data sheet and design based on Option C (i.e. Revise the LN specification to C5-105°C) - refer BMP-CON-EML-000001 - RE: CON-BMP-EML-000043 The data sheet to be revised and resubmit for review.
| Callout | Page 1 | Mohamed Ayyash | 7CDU ( apply to all sheets)
| Cloud+ | Page 1 | Mohamed Ayyash | General comment: Many figures are written in a very small font. text font to be standardized, clear & visible
| Callout | Page 1 | Mohamed Ayyash | No. (Typo) apply to all sheets
| Callout | Page 2 | Adnan Alothman | Inlet Oper. Press. is 25 as per FEED Data Sheet. Verify & confirm
| Call-out | Page 2 | 986131 | Use bigger fonts - applies to whole document.
| Text Box | Page 2 | 986131 | Note and numbers are currently not distinguishable. please mark the notes in a different manner to distinguishable Example: Write the notes with in square bracket "[1]" while the number shown in FPS unit can retail "()"
| Cloud+ | Page 3 | Adnan Alothman | In note 11; Add "-" to the pressure to be (-10psig)
| Callout | Page 4 | Mohamed Ayyash | This is Naphtha Splitter Overhead data Sheet ?