## 010-K-DAT-00001-001-RAP-CS.XLSX
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Call-out | 1 | Mahdi Ali | remove space | This comment does not apply and will not be removed. It is a mechanical data sheet and it will be kept.
2 | Call-out | 1 | Mahdi Ali | Remove p | Noted, it will be removed and updated in following document revision
3 | Call-out | 2 | Tapas | Please recheck the figures based on the unit of flow selected and correct as necessary. | These are written mistakes, the correct values are 3.914 and 2.100. Values to be corrected and updated in following document revision
4 | Call-out | 2 | Tapas | Contractor to fill in the missing data - compressibility factor, Cp/Cv etc. as this are already available with the contractor. The Vendor recalculation would serve as a double check for these critical parameters. | Data for 100% Arabian Light feed Case was not provided in FEED information. Technology provider has been requested to provide composition in this case. These values will be updated in the next document revision.
5 | Callout | 2 | alexis.martinez | The compressor suction pressure shown is a vacuum pressure (it does not match with FEED pressure). The compressor can be designed to operates in vacuum but this the normal operating pressure. | According to detailed calculation vacuum has to be considered for normal operation. This is the normal operation of the compressor obtained considering pressure drop through lines, demister of 010V1006, 010FIT0019 and strainer in the suction of the compressor (included according to BMPS-L1 item 18.2.3). Please, consider that just only for FIT0019 according to FEED information pressure drop is 0.7psi (2520-p010-SP-1500-46_PA).
6 | Callout | 2 | alexis.martinez | Normal operating case for H&MB Design and alternate case have to be included. | Normal and alternate operations cases have been already included. Khuff gas case is the start-up case and Vendor shall advise about these values (please refer to Note 3 of Data sheet).
7 | Call-out | 2 | Tapas | Contractor to fill the data. | Data for 100% Arabian Light feed Case was not provided in FEED information. Technology provider has been requested to provide composition in this case. These values will be updated in the next revision.
8 | Callout | 2 | Mohamed Ayyash | No. (Typo) apply to all document | It will be standarized by Directorate
9 | Call-out | 2 | Ahmed Ali | confirm the figures look to high | These are written mistakes, the correct values are 3.914 and 2.100. Values to be corrected and updated in following document revision
10 | Callout | 2 | alexis.martinez | Confirm the molecular weight of CDU OVHD vapour (53.83 lb/lb-mol) at the compressor inlet conditions (109°F and 13.7psia) | Confirmed. In following document revision, decimals shall be shown with punctuation mark: point instead of comma.
11 | Call-out | 2 | Tapas | The suction pressure indicated in vacuum,which is different from FEED. A vacuum in the compressor suction is prone of air leakage and is potentially dangerous and unwarranted. The FEED configuration the Pressure drop in the compressor KOD and associated pipes is about 0.7 psi. Contractor to size the KOD and piping such that the pressure drop is within the FEED specified value. | A detailed calculation has been developed. Pressure drop through lines , demister of 010V1006, 010FIT0019 and strainer (included according to BMPS-L1 item 18.2.3) in the suction of the compressor have to be considered, not only pressure drop though KOD and lines. Please, consider that just only for FIT0019 according to FEED information pressure drop is 0.7psi (2520-p010-SP-1500-46_PA).
12 | Call-out | 3 | Tapas | Please fill in the molecular weigh (MW) for the pseudo components. In case the MW weight is different for the various case. Show them below the composition in bracket and a note explaining that they indicate MW. | Noted. Data will be included in next document revision.
13 | Cloud+ | 3 | Yousif Ahmadi | Per FEED: TROPICAL, MARINE, SALT, SAND, HIGH AMBIENT TEMPERATURE | In data sheet is marked: tropicalization is required, therefore Tropical from others has been deleted High ambient temperature has been deleted because max. ambient temperatures are shon in data sheets: 110ºF Therefore, only marine and salt have been added because they are not shown in other parts of the mechanical data sheets.
14 | Call-out | 3 | Tapas | Crude unit overhead contains Chloride (as HCI or ammonium chloride) and we can expect minor quantity of chloride in the gas going to the compressors. API 618 specifies that "IF CHLORIDES ARE PRESENT, EVEN MINUTE TRACES, IN THE GAS BEING COMPRESSED, IT MUST BE INCLUDED" Therefore, Contractor to specify the expected chloride considering all operating scenarios. | FEED documentation does not contain any data about chloride in data sheet. Information of crude feed included in assays of Design Basis for 7CDU/7VDU FEED document there is no content in chloride specified neither for light ends nor whole crude.
15 | Callout | 4 | Mohamed Ayyash | Move to center of cell. (both 1st stage and 2nd stage) | Noted, to be updated in following document revision
16 | Text Box | 5 | Hasan Asad | Shall be SS material. | The material shall be as per API618+BMPS-K1. This comment will not be updated in data sheet.
17 | Callout | 6 | Mohamed Ayyash | write 54 on the 2nd line to ovoid overlaping with the line | Noted, to be updated in following document revision
18 | Text Box | 6 | Hasan Asad | Required | Noted, it will be added and updated in following document revision as per BMPS-K1 point 9.3.3.4
19 | Callout | 8 | Mohamed Ayyash | Align | Noted, to be updated in following document revision
20 | Text Box | 9 | Hasan Asad | Valve spec's will be reviewed once available. | Noted, it will be updated when the information is available.
21 | Callout | 9 | Mohamed Ayyash | rewrite ( overlapping with slashes (/) | Noted, to be updated in following document revision
22 | Text Box | 9 | Hasan Asad | Verify PTFE piston and rider rings. | As per BMPS-K1 point 6.10.3.2.1: Unless otherwise specified, TFE with filler materials shall be provided for wear bands and piston rings. This information is already shown in mechanical data sheet for reciprocating compressor
23 | Callout | 9 | Yousif Ahmadi | <31 HRC note to be written against Piston Rods Hardness | Piston rod material and coating shall be as per API 618. The paragraph 6.10.4.1 of BMPS-K1 indicates "If specified" and it is not the case. So, this paragraph shall be updated accordingly as per API 618
24 | Callout | 9 | Mohamed Ayyash | Align | Noted, to be updated in following document revision
25 | Callout | 9 | Yousif Ahmadi | add "as per BMPS-K1) point 6.10.4.1 to PISTON RODS(S): MATERIAL/YIELD, PSI | Piston rod material and coating shall be as per API 618. The paragraph 6.10.4.1 of BMPS-K1 indicates "If specified" and it is not the case. So, this paragraph shall be updated accordingly as per API 618
26 | Text Box | 10 | Hasan Asad | To be advised by Vendor | Noted, this information will be checked with manufacturer and it will be updated accordingly.
27 | Call-out | 14 | Ahmed Ali | 48F as per BMPS-A1 | Noted, to be updated in following document revision
28 | Text Box | 15 | Hasan Asad | Pulsation Suppression shall be equipped with KO drum and pot connected to flare. The process shall be automated - requirement basis Owner existing Refinery experience. | KO drum with final moisture separation is a separated equipment from pulsation dampener of reciprocating compressor package and shall be supplied by contractor in another separated requisition. Pots of distance piece vent, drain and buffer arrangement to be connected to flare are already included in reciprocating compressor pacakge's scope of supply. These vessels are completely different from pulsation dampeners.
29 | Callout | 17 | Mohamed Ayyash | Delete | Noted, to be updated in following document revision
30 | Callout | 18 | Mohamed Ayyash | Remove block | Noted, to be updated in following document revision
31 | Callout | 20 | Isamu | Delete as it has no room here | Noted, to be updated in following document revision
32 | Callout | 20 | Mohamed Ayyash | Remove block | Noted, to be updated in following document revision
33 | Call-out | 21 | Tapas | Refer to note 1 margins: Based on H&MB from FEED the margins work out to 60% and 45% for 1st and 2nd stage respectively. Contractor to review and correct as necessary. | Margin for second stage are pending to be clarified (MOC-PRO-P010/011-043). For first stage is the 57% of H&MB flow data plus 10% for spillback.
34 | Callout | 21 | Mohamed Ayyash | Align | Noted, to be updated in following document revision
35 | Cloud+ | 21 | Tapas | Refer to Note 13 - This appears to be based on a Technical clarification which is not based on the stipulated project procedures, not recorded in the project documents and Owner is not informed. Therefore, the Technical clarification is invalid. Contractor to ignore any details that they may receive on the clarification and proceed on the FEED design basis. | During EPC a detailed calculation has been developed as explained in previous answer. CONTRACTOR has confirmed that vacuum has to be considered at suction of first stage compressor.
36 | Callout | 21 | Mohamed Ayyash | Complete line | Noted, to be updated in following document revision
37 | Callout | 21 | Mohamed Ayyash | Align | Noted, to be updated in following document revision
38 | Callout | 21 | Mohamed Ayyash | Delete line | Noted, to be updated in following document revision
39 | Call-out | 21 | Raj | Ignore the comment regarding check valve | Noted, this matter applies and this note will be kept.
40 | Call-out | 21 | Ahmed Marhoon | In addition to manual operation, automatic unloading system to be considered with the necessary instrumentation (including smart positioners with FF capability). | This comment does not apply. Hydrocom is not part of this package's scope of supply (step-less capacity control). Control capacity system is by steps
41 | Callout | 21 | Mohamed Ayyash | Duplicate figure of 2. Re number. This applies to pages 21, 22& 23 | Noted, to be updated in following document revision
42 | Call-out | 21 | Tapas | A simple arithmetic calculation (without considering the effect of component partial pressure based on the recycle components) considering 5 steps indicate a that the recycle required is 12%. Contractor to recheck the number. Ignore the comment if the number is based on a rigorous calculation done using a process simulator. | This is not the data of the required spillbak flow. In this case, 10% of spillback flowing has been considered also for the design flow of the compressor (as an additional overdesign). Please note that final spillback sized will be done once Manufacturer comfirm the final compressor capacity as per API 618..
43 | Cloud+ | 21 | Yousif Ahmadi | Correct the equipment numbers | Noted, to be updated in following document revision
44 | Callout | 21 | Mohamed Ayyash | Delete line | Noted, to be updated in following document revision
45 | Callout | 21 | alexis.martinez | The use of check valve in the vents to flare is not a common practice. Evaluate the requirement of check valve on the vents lines. | This comment does not apply, please, consider line 39 of this same file.
46 | Text Box | 21 | Mahdi Ali | Use Bapco number | The number shall be as per instruction of TTSJV as per project requirements.
47 | Callout | 21 | Mohamed Ayyash | Delete lines | Noted, to be updated in following document revision
48 | Call-out | 21 | Ahmed Marhoon | The understanding is that remote will be done in DCS. The relevant PID to be updated accordingly. | Remotely mode is done by DCS and it will be shown in P&ID during Engineering phase.
49 | Call-out | 21 | Tapas | Note 14 is not clear. Please clarify who would update the gas composition. If the composition is on HOLD by the contractor. Then please indicate so. | 100% Arabian Light case H&MB was not provided as FEED documentation. Technology provider has been requested to provide composition in this case.
50 | Callout | 22 | Mohamed Ayyash | Delete lines | Noted, to be updated in following document revision
51 | Callout | 22 | Mohamed Ayyash | Delete lines | Noted, to be updated in following document revision
52 | Callout | 23 | Yousif Ahmadi | Typo error: Licensor, confirm the drawing number | Noted, to be updated in following document revision
53 | Callout | 23 | Yousif Ahmadi | Note 56: ASME VIII, Div 1 or VIII Div 1 d?? | Filters shall be designed according to ASME VIII Div 1. This is a written mistake.
54 | Text Box | 23 | Hasan Asad | Drain KO Drum shall be provided with manual/automatic draining facility. | KO drum with final moisture separation is a separated equipment from pulsation dampener of reciprocating compressor package and shall be supplied by contractor in another separated requisition.
55 | Text Box | 23 | Ahmed Marhoon | The following are comments related to instrumentation and control: 1. In addition to BMPS-J1, J2 & J6, all applicable BMPS-J series to be referenced (such as J3, J31 …etc) for the supplier to comply with. 2. TTSJV is requested to ensure that all the specific technical/functional requirements (including AVL) are covered and detailed in the requisition specification that will be sent out to suppliers. In case this document would be the only one for MR, then all the relevant BMPS to be included in the Data Sheet notes. 3. Vendors to be notified on the fact that the final design of the system shall include all the Hazop3/SIL recommendations and approved PID post-EPC-development. 4. Since the Data Sheet is issued separately, the consistency between the different documents, that may be part of the requisition, could not be verified and hence it is the contractor’s responsibility to update the other documents impacted by any of the comments on this Data Sheet and vice versa. 5. Spill back arrangement/design shall be reviewed and confirmed by the supplier. 6. Add Design Philosophy BMPS-A3 reference section 8.5 MCM Guidelines. Monitoring system in general to meet the requirement stated in this BMPS in addition to vendor requirement. 7. Requirement of MCM to be detailed with the supplier. Reference to BMPS-J15 MCM to be added accordingly. 8. Suppliers to be notified on the possibility of considering wireless instruments for non-critical monitoring devices. Reference to BMPS-J10 Wireless to be added if applicable and meeting the criteria (under development) of wireless measurement. 9. All the machinery monitoring probes etc. shall be factory fitted by the vendor and not at site. 10. Narrative/flow charts/cause and effect shall be provided for any control or sequence logic. 11. Assistance and involvement of the vendor during CHAZOP/Hazop workshops/studies to be considered. 12. Explanatory notes to be added on the requirement of having the control performed in the plant DCS and safety functions in ESD system. 13. In addition to BMPS J Specifications, all relevant BMPS J Standard/Typical Drawings to be included. 14. Add a note to the supplier to design, fabricate and supply the instruments in accordance with the BMPS J specifications. Items such as Junction boxes, cables, wiring, ferruling, earthing, terminal strips, fitting …etc shall be installed by the vendor/contractor meeting the requirements specified on the applicable BMPS J specifications like BMPS-J31. 15.Vendor/TTSJV shall provide a list of deviation from BMPS specifications, in addition to the requisition specifications, for owner's review and approval. | 1. ALL BMPS are i12. ncluded in MRQ, JVD will check and include any additional specification as required. In this RFI there are not control systems. 2.-All applicable project specifications are listed in MRQ (Requisition for enquiry) for reciprocating compressor, also AVL. 3. Final P&ID will be submitted by Pump Vendor, including all its scope and approved by CONTRACTOR. CONTRACTOR will check that HAZOP actions shall be correctly implemented. All BMPS applicable are part of the Material Requisition and included in section named MRQ. 4.Data sheets are filled in completely aligned with reciprocating compressor MRQ taking into account international standards and applicable project specifciations. 5. Noted. 6. All requirements mentioned in BMPS A-3 reference section 8.5MCM will be included in MR and Mechanical Data Sheet. It will be checked during Technical Bid Evaluation stage 7. Noted.All applicable requirements related to MCM are already implemented in data sheet/MRQ. 8. It is under discussion with JV Directorate (instrumentation) Vendor will be informed with final decision to standardize which instruments require wireless. 9. Noted. It´s standard requirement. 10. Noted. Already included in VDDR. 11.CHAZOP is not applicable to this RFI. ( PLC or MMS is not VENDOR scope). Hazop is already included in the scope of supply of reciprocating compressor package (shown in MRQ) 12.-All requirements as per BMPs are already included in reciprocating compressor's scope of supply. 13.-All applicable project specifications and standards are already listed in MRQ 14.-All applicable project specifications related to instrumentation and standards are already listed in MRQ of reciprocating compressor. Also some of them are already mentioned in compressor data sheet. 15.-Noted, this is an standard procedure during Enginnering phase (technical vendor's offers evaluation)
56 | Call-out | 23 | Ahmed Marhoon | All applicable BMPS-J series to be added. | All applicable project specifications related to instrumentation are listed in document MRQ part of requisition material of reciprocating compressor. This list is not part of mechanical data sheet, only the most important ones are mentioned.
57 | Callout | 23 | Mohamed Ayyash | Complete missing sections of table line in all pages | Noted, to be updated in following document revision
58 | Text Box | 24 | Sankara | Delete Ex-p | Noted. Modification will be included document revision. Nevertheless based on BMPS-P1 Ex-p will be offered as and option.
59 | Callout | 24 | Mohamed Ayyash | Add space | Noted, to be updated in following document revision
60 | Callout | 24 | Mohamed Ayyash | Add space | Noted, to be updated in following document revision
61 | Callout | 24 | Mohamed Ayyash | move the number to center of cell | Noted, to be updated in following document revision
62 | Text Box | 24 | Mahdi Ali | Remove p from unit number | Noted, to be updated in following document revision
63 | Cloud+ | 24 | Yousif Ahmadi | The number to be changed 010K0001A/B | Noted, to be updated in following document revision
64 | Text Box | 25 | Ahmed Ali | Compressor casing shall be provided with N2 connection to purge the casing in case of shutdown | This comment does not apply, therefore, it is not going to be added.