## 018-A-PFD-00001-015-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Cloud |  | Fatema Hashem
2 | Callout |  | Fatema Hashem | THIS LINE HAS BEEN DELETED FROM P&IDS. DELETE FROM PFD.
3 | Cloud |  | Fatema Hashem
4 | Callout |  | Fatema Hashem | ADD THE SOURCE DETAILS FOR THE DIESEL AND VGO LINES
5 | Cloud |  | Fatema Hashem
6 | Callout |  | Fatema Hashem | SHOW ALL THE BYPASS LINES AROUND THESE TWO EXCHANGERS.
7 | Cloud |  | Fatema Hashem
8 | Callout |  | Fatema Hashem | THIS LINE IS MISSING ON SHEET 8. SHOW
9 | Arrow |  | Fatema Hashem
10 | Arrow |  | Fatema Hashem
11 | Text Box |  | Fatema Hashem | SHOW LINE TO FEED SURGE DRUMS
12 | Text Box |  | Fatema Hashem | SHOW LINE TO SLOP
13 | Highlight |  | Fatema Hashem
14 | Callout |  | Fatema Hashem | "TRAIN 2 FEED SURGE"
15 | Highlight |  | Fatema Hashem