## 018-H-DAT-00001-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Call-out | 6 | Rashed Almudahka | a note to be added as per T1630, as follows; "Bundle cage that includes baffles, tie-rods and spacers shall be SS material."
2 | Callout | 3 | Fatema Hashem | ADD A NOTE: VENDOR TO CONSIDER SHORT-TIME CONDITION OF GENERAL POWER FAILURE SCENARIO FOR THE CONDENSER SHELL-SIDE DESIGN TEMPERATURE
3 | Callout | 4 | Fatema Hashem | ADVISE THE REASON FOR REMOVING THE SPECIFICATION TABLE OF INLET AND OUTLET LINES AT PACKAGE BATTERY LIMITS
4 | Callout | 5 | Fatema Hashem | DELETE DOTTED LINE AND FIX THE DRAWING GAPS
5 | Callout | 1 | Fatema Hashem | GENERAL COMMENT: PLEASE REFER TO BMPS-A8 SECTION 4.5.1: DO NOT INDICATE FIGURES IN EUROPEAN STYLE (WHICH USES COMMAS FOR DECIMAL POINTS AND PERIODS FOR THOUSANDS SEPARATORS), USE UK/US STYLE WITH PERIODS FOR DECIMAL PLACES AND COMMAS FOR THOUSANDS SEPARATORS. CHECK AND CORRECT ALL FIGURES
6 | Callout | 4 | Fatema Hashem | NOTE 4 "DESIGN FLOWRATE ALREADY INCLUDES 20% OVERDESIGN ON THE DESIGN CASE" DOES NOT APPLY HERE, IT APPLIES TO FLOW ON SHEET 3.
7 | Callout | 3 | Fatema Hashem | NOTE 4 TO BE ADDED HERE
8 | Call-out | 5 | Hasan Al Noaimi | Package instrumentaion to be checked in details as operations want full coverage in DCS.
9 | Callout | 6 | Fatema Hashem | RE-WRITE NOTE 4 FOR CLARITY. SHOULD THIS BE "DESIGN FLOWRATE INCLUDES 20% OVERDESIGN ON OPERATING CASE"??