## 019-C-GAD-10004-001-RAP
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Call-out | 1 | MAK | 4
2 | Call-out | 2 | MAK | 4
3 | Call-out | 3 | MAK | 4
4 | Call-out | 4 | MAK | 4
5 | Call-out | 2 | MAK | 2
6 | Call-out | 3 | MAK | 3
7 | Text Box | 1 | MAK | 4
8 | Call-out | 4 | MAK | 4
9 | Text Box | 1 | MAK | 019 - 2HCU
10 | Text Box | 2 | MAK | 019 - 2HCU
11 | Text Box | 3 | MAK | 019 - 2HCU
12 | Text Box | 4 | MAK | 019 - 2HCU
13 | Call-out | 3 | A.Jabbar Mahmood | Add reference to Licensor drawing RB 910354 as per FEED process D/S.
14 | Text Box | 2 | A.Jabbar Mahmood | As agreed during the P&IDs review sessions, the level taps and pressure taps shall be heat traced. An appropriate note shall be included to cover this requirement.
15 | Cloud+ | 1 | A.Jabbar Mahmood | As per the FEED D/S, the design temperature is 543 F across the whole column. TR to advise the basis for specifying higher design temp of 714 F for the bottom part only.
16 | Callout | 1 | Yousif Ahmadi | Change to SA 194 2H
17 | Cloud+ | 4 | A.Jabbar Mahmood | Correct the dimension to 900 mm as per Licensor and FEED process D/S
18 | Text Box | 4 | A.Jabbar Mahmood | Detail C in the FEED process datasheet for the liquid distributor above bed 1&2 shall be included.
19 | Cloud+ | 1 | A.Jabbar Mahmood | Indicate the external design pressure in "negative" values.
20 | Cloud+ | 1 | A.Jabbar Mahmood | The bottom operating temp is 504 F as per the process D/S. Update for consistency.
21 | Text Box | 1 | MAK | Use the latest A3 Border
22 | Text Box | 2 | MAK | Use the latest A3 Border
23 | Text Box | 3 | MAK | Use the latest A3 Border
24 | Text Box | 4 | MAK | Use the latest A3 Border