## 019-C-GAD-10006-001-RAP
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box |  | A.Jabbar Mahmood | A note should be added indicating that the sizes of the column nozzles may change during the development of the detailed design.
2 | Cloud+ |  | A.Jabbar Mahmood | External design pressures shall be reported as negative values (vacuum) i.e. as -14.7 psig
3 | Callout |  | A.Jabbar Mahmood | The Liquid bottom outlet nozzle size is 10" per the FEED datasheet and P&IDs. TR to check and confirm.
4 | Callout |  | Adnan Alothman | Corr. for heads are (6.4mm) per FEED data sheet. TR to verify
5 | Callout |  | alexis.martinez | The equipment TAG number and the description shall be shown in all the sheets.
6 | Call-out |  | bapco-user | Change the note number to 24 as note with 23 number is available
7 | Call-out |  | bapco-user | Remove this " Fixed in CS: 1/4" CA as it is duplicated
8 | Call-out |  | bapco-user | In note 21 change the word Reactor to column
9 | Call-out |  | bapco-user | Add another note: PMI shall be executed per BMPS-B9
10 | Cloud+ |  | Ahmed Marhoon | Based to the PID, EDP's GAD and to avoid dead-legs in the level bridle, lower level tapping (45B) needs to be relocated to the side of the column. The new tapping elevation shall still cover the LLL of the operating range.