## BAPCO DOC. CODE-REV-CS
ID N° | Subject | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | Harshad.K.Patel | Please revise and re-submit PEP per comments shown on this document. | Agreed.
2 | Callout | A.Jabbar Mahmood | The design pressure of C0002R is 2515 psig per the FEED datasheet and Licensor datasheet. Is the new value (2575 psig) based on revised hydrualic calculations and due to reaching a line size constraint in the HP circuit. TR to advise the basis for this change and provide the calculations. CLG's concurrence is required. | Waiting answer from Chevron to make them official, once receive them will be sent to you.
3 | Callout | A.Jabbar Mahmood | The inlet and outlet pressures of C0002R are 2404 and 2284 psig per the FEED datasheet and Licensor datasheet. Are the new values (2453/2333 psig) based on revised hydrualic calculations and due to reaching a line size constraint in the HP circuit. TR to provide the calculations and obtain CLG's concurrence. | Waiting answer from Chevron to make them official, once receive them will be sent to you.
4 | Text Box | Ahmed Marhoon
5 | Call-out | Ahmed Marhoon | According to the GAD, T23 - 25 are at different elevation than T26 - 28. If there is no technical reason for combining these two groups; split into two line items similar to the rest of Thermowell connections. | This nozzle will be deleted and updated in next emission of the GAD, by other hand this it has been informed to Process to correct and update the P&ID.
6 | Call-out | Ahmed Marhoon | Refer to the typical comments on 019C0001R | Agreed.
7 | Stamp | Raj
8 | Cloud+ | Yousif | Should be selected as we are referring to them in ITP | This was already corrected, deleted, and updated because these specifications don't apply to this type of equipment.
9 | Callout | A.Jabbar Mahmood | This nozzle (N31) does not exist in the FEED drawings or Licensor drawings. The nozzle however is depicted in the EDP and FEED P&IDs. We believe that this is a graphical error in the P&IDs and this additional nozzle shall not exist . TR to seek confirmation from CLG and update the P&IDs | This nozzle will be deleted and updated in next emission of the GAD, by other hand this it has been informed to Process to correct and update the P&ID.
10 | Text Box | A.Jabbar Mahmood | The ID (overlay to overlay) of 4250 mm shall be indicated in the drawing | Agreed. This will be included and updated in next emission.