## 019-C-GAD-30002-001-RAP
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Call-out | 1 | A.Jabbar Mahmood | As commented in a previous transmittal, the design pressure of C0002R is 2571 psig per the FEED and licensor datasheet. It seems that this revised design pressure is due to reaching hydrualic limitations in the HP circuit. TR to provide the hydrualic calculations and obtain CLG's conccurence.
2 | Call-out | 1 | A.Jabbar Mahmood | The inlet and outlet pressures are 2404 and 2284 psig per the FEED datasheet. It seems that this revised design pressure is due to reaching hydrualic limitations in the HP circuit. TR to provide the hydrualic calculations and obtain CLG's conccurence
3 | Text Box | 1 | Mahdi Ali | General Notes: 1. Use latest drawing border that includes different disclaimer note. 2. Always put the general arrangement drawing as sheet 1. 3. Utilize the drawing number for sheet numbering, i.e. 019-C-GAD-xxxxx-002 to indicate sheet number 2. The last 3 digits are the sheet number. 4. Unit number c019 is incorrect, it should be 019.
4 | Text Box | 1 | Ahmed Marhoon | In addition to the comments shown on this transmittal, refer to the comments provided on GAD under BMP-MOC-TRE-00001 - CON-BMP-TRA-040001.
5 | Call-out | 2 | Mahdi Ali | Refer to general notes in first sheet.
6 | Cloud | 2 | Mahdi Ali | The ID (overlay to overlay) of 4250mm shall be indicated in the drawing
7 | Cloud | 2 | Mahdi Ali | As commented in a previous transmittal, the nozzle (N31) does not exist in the FEED drawings nor in the Licensor drawings. The nozzle is however depicted on the FEED and EDP P&IDs. We believe that this is a graphical error in the P&IDs abd this additional nozzle shall not exist. TR to seek confirmation from CLG and update the P&IDs.
8 | Cloud | 2 | Mahdi Ali | Refer to general notes in first sheet.