## 019-E-DAT-00009-001-RAP
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Call-out | 4 | A.Jabbar Mahmood | "ppm wt"
2 | Call-out | 2 | A.Jabbar Mahmood | 2212 psig as per FEED D/S and PFD. TR to provide the basis for this change and update other documents.
3 | Callout | 4 | Yousif Ahmadi | Add note 10 of FEED data sheet: "Two fans per bay shall be provided as minimum"
4 | Call-out | 4 | Ahmed Marhoon | Contractor to add reference to the applicable BMPS specifications such as BMPS-P20/P21 and relevant BMPS-J specifications. Typical for all air coolers with Variable Speed Drives.
5 | Call-out | 4 | Mahdi Ali | Do not use FEED drawing numbers
6 | Call-out | 2 | A.Jabbar Mahmood | Font is too small
7 | Callout | 1 | Mohamed Ayyash | General Comment: Fonts are too small throughout the data sheets and unreadable.
8 | Call-out | 3 | Mahdi Ali | Move table to clear the overlap
9 | Cloud+ | 1 | Mohamed Ayyash | On cover sheet correct unit number. Delete c, should read 019
10 | Call-out | 4 | Ahmed Marhoon | The scope for instrumentation and control is not limited to the alarms in DCS. All the control functions will be done in the DCS with the necessary interconnections with the electrical MCC. The final design of the system shall be based on the BMPS specifications (including relevant J class) and the final PID post detail design and Hazop3/SIL analysis. Suppliers to be instructed accordingly. This is a typical comment for all fin fan air coolers.
11 | Callout | 1 | Mohamed Ayyash | Top of cover page: add Unit name 2HCU. Apply to all sheets.
12 | Call-out | 4 | A.Jabbar Mahmood | typo