## 019-E-GAD-00013-001-RAP
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Call-out | 1 | Mahdi Ali | Add C/L denoting center line in all views
2 | Call-out | 1 | Mahdi Ali | Detail is not shown on view A-A
3 | Callout | 1 | Yousif Ahmadi | Note 7: Per FEED data sheet it is 0.4mm
4 | Callout | 1 | Yousif Ahmadi | Note 8: ASCE 7-10
5 | Cloud+ | 1 | Yousif Ahmadi | Per data sheet thickness is 18.2 mm. check and confirm
6 | Cloud+ | 1 | Yousif Ahmadi | PWHT all or only FH. Check and confirm
7 | Call-out | 1 | Mahdi Ali | Remove U from unit number
8 | Cloud+ | 1 | Yousif Ahmadi | SS 304L KAMPROFILE Per FEED data sheet
9 | Call-out | 1 | A.Jabbar Mahmood | The design pressure for the CW is 165 psig per BMPS A1. TR to confirm and advise the basis.
10 | Call-out | 1 | A.Jabbar Mahmood | The design pressures are different than those in the FEED D/S. We assume that they will be further updated based on the vendor confirmation.
11 | Call-out | 1 | Sameer Foujdar | Title should read as 019K0002 MAKE-UP HYDROGEN SECOND STAGE INTERCOOLER
12 | Cloud+ | 1 | Mohamed Ayyash | View B-B does not shoe baffle plate and impingement plate along with its partial support plate.