## 019-F-DAT-00002-001-RAP
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Call-out | 1 | A.Jabbar Mahmood | All other datasheets which have been issued so far, does not have a border. A single format should be followed for all datasheets.
2 | Call-out | 1 | Mahdi Ali | Unit number shall not have prefix
3 | Call-out | 1 | Mahdi Ali | Unit number shall not have prefix
4 | Text Box | 1 | MAK | Use the latest cover page template that is part of the Homogenization Procedure. MOC shall coordinate with JV Directorate.
5 | Text Box | 2 | A.Jabbar Mahmood | General: 1- TR to retain the grid lines for better presentation and to facilitate the understanding of the datasheets. 2- Decimal points shall be used as decimal separator and commas for as thousand separator to avoid confusions
6 | Cloud+ | 2 | A.Jabbar Mahmood | The reported inlet and outlet pressures are significantly higher than those in the FEED D/S. TR to provide the basis for this change and consult with CLG.
7 | Cloud+ | 2 | A.Jabbar Mahmood | 0.355 as per FEED D/S
8 | Call-out | 2 | A.Jabbar Mahmood | The viscosity data of the oil side (UCO) needs to be checked considering the UCO viscosity correction made at the end of the FEED (refer to WP2 SOW document)
9 | Cloud+ | 3 | A.Jabbar Mahmood | The inlet pressures for the superheating coils are 85 psig as per FEED D/S. If this is not a typo, the pressure drop across the coil will be excessively high (110-75). TR to check and confirm
10 | Cloud+ | 9 | A.Jabbar Mahmood | Much higher than the value reported in the FEED D/S of 2368 psia. TR to advise the basis for this change
11 | Call-out | 9 | A.Jabbar Mahmood | Not attached yet in the MR. TR to ensure that this drawing is attached.
12 | Call-out | 9 | A.Jabbar Mahmood | CLG drawing shall be attached.
13 | Cloud+ | 10 | A.Jabbar Mahmood | Typo: EPC
14 | Cloud+ | 10 | A.Jabbar Mahmood | What does the fuel skid refer to...fuel gas KO drum? clarify.
15 | Cloud+ | 10 | A.Jabbar Mahmood | The liquid phase (feed oil) should not have H2S. TR to advise the basis of this number.
16 | Call-out | 10 | A.Jabbar Mahmood | (Max/Norm/Min)
17 | Cloud+ | 10 | A.Jabbar Mahmood | Typo: Design
18 | Text Box | 12 | A.Jabbar Mahmood | General for Heat Curve tables: The inlet operating pressures have been increased from the FEED and the given heat curve data do not cover the revised pressure range. CLG shall be requested to provide updated heat curve data.