## 045-A-PFD-00001-002-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Call-out | 1 | MAK | Are these nos. as per the agreed equipment list?
2 | Call-out | 1 | MAK | General Comment: Where possible, always align the equipment data block with the respective equipment icon.
3 | Callout | 1 | BD Mori | Provide bed number
4 | Callout | 1 | BD Mori | Provide bed numbers
5 | Callout | 1 | BD Mori | Provide chimney all tray numbers
6 | Text Box | 1 | BD Mori | This unit PFDs were prepared during FEED, based on the Licensor EDP PFDs. The PFDs were reviewed by Licensor, Bapco and FEED contractor. The process flow configuration was finalized based on the reviews, Bapco’s operating experience with similar units, lessons learned and industry best practices. The PFDs have also under gone Hazop at EDP and FEED stage. Therefore, the deletion of amine tanks, associated facilities and process modifications, to the FEED stage PFDs are not acceptable. TTSJV shall discuss any changes to the FEED PFDs and P&IDs before it is issued in EPC. TTSJV shall also clearly mark such changes and obtain Owner’s approval. If any PFD and P&ID is issued without Owner’s approval, the transmittal shall be summarily rejected.