## 098-A-MSD-00001-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Callout | 1 | Syed Ahmed | /098V0003
2 | Callout | 1 | Robert.Kawitzki | equipment labels as per BMPS-A8 - typ comment
3 | Text Box | 1 | MAK | General Comment: Where possible, always align the equipment data block with the respective equipment icon.
4 | Text Box | 1 | Salman Jaffer | General comment: Incorporate comments from IPMT's on (TRI-00023 - UNIT 098 – PFD) for consistency between MSDS and PFD
5 | Text Box | 1 | MAK | General Comments applies to all MSDs: 1. Use the latest PFD border and off-page connectors that are part of the Homogenization Procedure. SOC shall coordinate with TTSJV. 2. Total Sheet to be shown as e.g. 005 on all the sheets. 3. Always use NTS for MSD scale. 4. Always use A1 for MSD border size.
6 | Callout | 1 | Saeed Taher | Material to be specified
7 | Callout | 1 | Saeed Taher | Material to be specified
8 | Callout | 1 | Saeed Taher | Material to be specified
9 | Callout | 1 | Saeed Taher | Material to be specified
10 | Text Box | 1 | Mahdi Ali | Scale: NTS Size: A1 TTL SHT: 005
11 | Callout | 1 | Syed Ahmed | Steam drum
12 | Text Box | 1 | Mahdi Ali | Use the latest border
13 | Text Box | 1 | MAK | Verify the equipment nos. with the agreed equipment list.
14 | Callout | 1 | Saeed Taher | What is Note 7