## 098-A-PFD-00001-001-RA-CS
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Callout | 1 | balagangadhar.k | Change in vessel tag numbers shall be captured at all places (ex. OPCs, Notes, etc..), Typical
2 | Text Box | 1 | balagangadhar.k | 098V0010
3 | Text Box | 1 | balagangadhar.k | EXPORT
4 | Text Box | 1 | balagangadhar.k | 098V0012
5 | Text Box | 1 | balagangadhar.k | Font and overall presentation shall be consistent across all BMP PFD.
6 | Text Box | 1 | balagangadhar.k | STEAM TO REFOEMER
7 | Text Box | 1 | balagangadhar.k | 098V0013
8 | Text Box | 1 | balagangadhar.k | 098V0014
9 | Callout | 1 | BD Mori | 98C0001R/02R
10 | Callout | 1 | BD Mori | The design pressure margin in comparison to operating pressure ( stream 6) is only 542psig/512 psig =2.3%. Further discussion required with Licensor.
11 | Callout | 1 | BD Mori | General comment: Refer BMPS-A-8, section 7.2.5. Equipment number shall be preferably indicated inside the equipment.
12 | Callout | 1 | BD Mori | General comment :Separate PFDs required for each unit as 3 and 4 H2 Plant unit numbers are different and the equipment prefix is different. Also delete these notes.
13 | Callout | 1 | BD Mori | General comment: "Diameter " can be O.D. or I.D. Specify I.D.
14 | Callout | 1 | BD Mori | Move here
15 | Callout | 1 | BD Mori | General comment, indicate reference PFD number where it is not shown.
16 | Call-out | 1 | MAK | Always show the border size A1
17 | Text Box | 1 | MAK | Move/stretch to the right edge and in line with the rest of the OPCs
18 | Call-out | 1 | MAK | Total Sht. shall be indicated only, 011
19 | Call-out | 1 | MAK | Always use NTS for PFDs
20 | Call-out | 1 | MAK | 099 INSTEAD OF 098
21 | Text Box | 1 | MAK | Use the latest PFD border template that is part of Homogenization Procedure. SOC shall coordinate with JV Directorate.
22 | Callout | 1 | Robert.Kawitzki | Text height and width to project standards - typ comment
23 | Callout | 1 | Salman Jaffer | Align process gas line with 098V0014 outlet (drafting)
24 | Callout | 1 | Syed Ahmed | General comment: complete all controller numbers.
25 | Callout | 1 | Syed Ahmed | from 2&3 BAGRUs
26 | Callout | 1 | Syed Ahmed | Keep this valve black as per BMPS-A-50003 Normally close for PFD only.
27 | Callout | 1 | Syed Ahmed | 098V0002/0003