## 098-F-DAT-00001-001-RAP
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Arrow |  | Jeung.Kim
2 | Text Box |  | Jeung.Kim | What is pending?
3 | Text Box |  | Jeung.Kim | This Data Sheet has to be updated as result of FEED Validation and Detail design development.
4 | Callout |  | Nalini Mohan | Modify the equipment number as per latest equipment numbering convention
5 | Stamp |  | Nalini Mohan
6 | Arrow |  | Jeung.Kim
7 | Text Box |  | Jeung.Kim | What is pending?
8 | Callout |  | BD Mori | The following design notes shall be incorporated at appropriate place in this data sheet: 1. The vendor shall design the reformer radiant and convection section to ensure uniform heat distribution within the reformer to prevent overheating of the reformer tubes, its outlet five hot headers and pigtails at normal operating conditions and also transient operating conditions, i.e. start-up, shutdown, and turndown operation. This is essential to prevent failure of the tube pigtails due to overheating. The vendor shall use appropriate design tools e.g. computational fluid dynamic (CFD) or vendors proprietary tools for the reformer heat distribution study. The vendor shall provide detail reports and calculations to the client for their review. 2.Vendor shall provide adequate temperature measurement instruments on reformer tube outlet five hot headers in consultation with the technology licensor Technip. This is required for monitoring of the temperature of hot headers and in turn it will help monitoring and ensuring uniform heat distribution within reformer to prevent overheating of the tubes in some location in comparison to others. 3. Temperature indication is required on each nozzles connecting hot header to cold header for monitoring the nozzle temperatures to ensure that it is not exceeding its design limit. 4. The vendor shall provide detail reformer burner start-up and shutdown procedure with sequence of burner light-up to prevent non-uniform heat distribution at transient operating condition. This procedure is essential to prevent over heating of the tubes in some location in comparison to other.
9 | Callout |  | BD Mori | Comments on this data sheet are also applicable to comments on 099F9900 data sheet
10 | Text Box |  | Salman Jaffer | Please explain why this S beside the unit number
11 | Arrow |  | Salman Jaffer
12 | Callout |  | BD Mori | Meaning of note is not clear. Make the note very clear for easy understanding
13 | Callout |  | BD Mori | What is 'KG'? It is confusing. Is it "Khuff gas"? Avoid using 'KG' for Khuff gas. General comment applicable to all data sheets
14 | Arrow |  | BD Mori
15 | Arrow |  | BD Mori
16 | Arrow |  | BD Mori
17 | Callout |  | Salman Jaffer | Correct the number to 098F9800 in all pages
18 | Callout |  | BD Mori | Hours minimum ?
19 | Callout |  | BD Mori | Bapco's 2H2P Reformer manifold ( cold collector) was replaced in 2011due to failure. The new manifold metallurgy was upgraded and its design temperature was increased to 800°F. TTSJV shall consult Licensor to explain rationale for selection of 650°F design temperature for this unit and make necessary changes as required.
20 | Callout |  | Saeed Taher | ASTM specification to be specified. This is applicable to all material in both reforming furnaces
21 | Arrow |  | Jeung.Kim
22 | Text Box |  | Jeung.Kim | Please provide the shipping constraint to the vendor ?
23 | Callout |  | BD Mori | ID fan and Reformer stack to be designed for Economizer dry run. Refer note on Economizer design temperature.