## 382-A-PFD-00001-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | Sameer.Ahmed | This drawing is given CODE-2 as a special case to allow TTSJV to proceed with development of subsequence deliverables and procurement activities. However, TTSJV shall be responsible to incorporate the comments and complete the design before finalizing the equipment PO. TTSJV to advise when the first utilities balance will be submitted for review. PFD shall be modified to incorporate the updated utilities streams data and H&M balance.
2 | Text Box | 1 | Mahdi Ali | General Comments applicable to all PFDs 1. Follow the Homogenization procedure for the Off-page Connectors. 2. Modifications shall be clouded as per BMPS-A8. 3. Use latest drawing borders.
3 | Text Box | 1 | Bernard.Grace | Include details on Contaminated Stormwater, Clean Stormwater, any EHS (Environmental Health & Safety Requirements), Firewater, First Flush and oily water and Process Wastewater.
4 | Text Box | 1 | Bernard.Grace | Include Holding Capacity
5 | Text Box | 1 | Bernard.Grace | Include Holding Capacity
6 | Callout | 1 | Bernard.Grace | Include in Legend
7 | Text Box | 1 | Bernard.Grace | Include in Legend
8 | Callout | 1 | Bernard.Grace | Include type and position of valve (closed or open) toand notes denoting discharge/ flow sequence
9 | Callout | 1 | Syed Ahmed | Keep this valve black as per BMPS-A-50003 Normally close for PFD only.
10 | Call-out | 1 | Edgardo | Please confirm the assignment of a new PFD number. Note that Unit 386 is an existing unit and this line is connected to existing PFD BRA-200784.
11 | Call-out | 1 | Mahdi Ali | Scale: NTS TTL SHT: 3 Size: A1
12 | Cloud+ | 1 | Sameer.Ahmed | Show capacity and dimensions as per BMPS-A8, section 7.2.6
13 | Call-out | 1 | Ali Abbas | show correct signal representation
14 | Call-out | 1 | Ali Abbas | show LC
15 | Call-out | 1 | Mahdi Ali | The number quoted in the Off-page connector is correct but the format is not.
16 | Callout | 1 | Julio.Aguilar | These streams collect Oily and Contaminated Storm water from the new BMP units so a collecting drawing have to be developed in further stage showing all units streams and the assignation of a drawing number shall be provided.