## 010-C-GAD-10005-001-RAP
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Callout |  | alexis.martinez | Include the conical section as part of the top section. As per Data Sheet Note 5. "TOP SECTION (INCLUDING CONICAL SECTION):"
2 | Callout |  | alexis.martinez | The equipment TAG number and the description shall be shown in all the sheets.
3 | Call-out |  | 986131 | Tag number of the equipment would change and needs to be update based on revised tag numbering.
4 | Call-out |  | 986131 | Repeat the clouded section on all the pages.
5 | Callout |  | alexis.martinez | Change the note 22 "The design temperature can be raised to 500°F unless the resulting combination of design pressure and temperature exceeds the ANSI B16.5 flange rating" as per BMPS-A3.
6 | Callout |  | alexis.martinez | Add the note "Column will be subjected to steam-out operation. Additional design conditions shall be -10 psig at 300 °F"
7 | Call-out |  | Ahmed Marhoon | Note 23 needs to be reworded to be addressed to the manufacturer. Instrumentation nozzles details will be finalized at a later stage of the detail design and confirmed post Hazop3/SIL studies. Refer to Typical comment on sheet 1 of 019-C-GAD-10010-001-RAP.
8 | Call-out |  | 986131 | Consider relocating the manway on the other side of baffle for better accessibility. And accordingly M4 location to be checked.
9 | Call-out |  | 986131 | Arrangement shown to be reviewed and modified based on the re-boiler configuration (i.e. once through or circulating). Current arrangement shown is prone to liquid entrainment and foaming. Review during detail engineering.
10 | Call-out |  | 986131 | Update P&ID representation accordingly.