## 019-C-GAD-00008-001-RAP-CS
ID N° | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | Mahdi Ali | Utilize sheet numbers in the document number, i.e. 019-C-GAD-00003-003 to indicate sheet 3. | With respect to this comments, TTSJV is checking Owner comments related to format and will instruct accordingly to be implemented in all OC deliverables.
2 | Text Box | 1 | Mahdi Ali | remove 'c' from unit number | Agreed, removed and updated. | Y
3 | Text Box | 1 | MAK | Use the latest drawing borders as in BMPS-A-50009 Rev. 1 dated 09-04-2018. | Agreed. | Y
4 | Call-out | 1 | MAK | 019 - NO. 2 HYDROCRACKING UNIT | Agreed, included and updated. | Y
5 | Cloud+ | 1 | A.Jabbar Mahmood | The design pressure per FEED D/S and Licensor D/S is 2340 psig. CLG to be consulted on the revised design pressure. | The Section of Process has informed that they are waiting answer from Chevron to make them official.
6 | Text Box | 1 | A.Jabbar Mahmood | CLG's detailed mechanical drawing with the "Fabrication notes" in RD-140639 shall be included when the vendor is selected, | Agreed.
7 | Cloud+ | 1 | Jawad Alawi | Confirm material type and Swap material spec for shell and heads | Confirmed material type.
8 | Call-out | 1 | Sameer Foujdar | Operating Pressure as per FEED data sheet is 2227 psig to be confirmed. | The Section of Process has confirmed the Operating Pressure.
9 | Text Box | 1 | A.Jabbar Mahmood | This drawing shall be reviewed and approved by the Licensor | Agreed.
10 | Cloud+ | 1 | bapco-user | Is the vessel exposed to high H2S during start up (catalyst sulfiding). This to be checked with licensor and if required add a note. | Agreed.
11 | Text Box | 2 | Mahdi Ali | remove 'c' from unit number | Agreed, removed and updated. | Y
12 | Text Box | 2 | Mahdi Ali | Utilize sheet numbers in the document number, i.e. 019-C-GAD-00003-003 to indicate sheet 3. | With respect to this comments, TTSJV is checking Owner comments related to format and will instruct accordingly to be implemented in all OC deliverables.
13 | Callout | 2 | Mohamed Ayyash | Allign | Agreed, aligned and updated. | Y
14 | Call-out | 2 | Sameer Foujdar | It is separator not reactor | Agreed, corrected and updated. | Y
15 | Cloud+ | 2 | bapco-user | Note 18: Do not match with the CA in table "DESIGN DATA" in page 1 of 3 | The CA is indicated in that table for shell and head, internally (WOL) and externally (1,5 mm). The Note 18 indicates the CA for fixed and removable internals.
16 | Callout | 2 | bapco-user | Add: High-Alloy Clad Pressure Vessels - PVM-SU-1322 | Agreed, this document will be included to the list of specifications. | Y
17 | Text Box | 3 | Mahdi Ali | 1. Always put the general arrangement as sheet 1. 2. Indicate the equipment number inside the equipment. | With respect to this comments, TTSJV is checking Owner comments related to format and will instruct accordingly to be implemented in all OC deliverables.
18 | Text Box | 3 | Mahdi Ali | This shall be sheet 1 of 3 | With respect to this comments, TTSJV is checking Owner comments related to format and will instruct accordingly to be implemented in all OC deliverables.
19 | Text Box | 3 | Mahdi Ali | Utilize sheet numbers in the document number, i.e. 019-C-GAD-00003-003 to indicate sheet 3. | With respect to this comments, TTSJV is checking Owner comments related to format and will instruct accordingly to be implemented in all OC deliverables.
20 | Text Box | 3 | Mahdi Ali | remove 'c' from unit number | Agreed, removed and updated. | Y
21 | Text Box | 3 | Mahdi Ali | Use latest border that includes a different disclaimer note. | Agreed.