## Sheet1
Document Code | Document Date | Doc. Description | Note | Action | Expected Date | Response | Response Date | Topic
BMP-BOC-TRE-000001 | 2018-03-27 | COMMENTS TO MOM - CON-BMP-MOM-00007 | REF.: CON-BMP-TRA-000003
BMP-BOC-TRE-000002 | 2018-03-28 | COMMENTS TO MOM - CON-BMP-MOM-00008 | REF.: CON-BMP-TRA-000003
BMP-BOC-TRE-000003 | 2018-03-28 | COMMENTS TO MOM - CON-BMP-MOM-00009 | REF.: CON-BMP-TRA-000003
BMP-BOC-TRE-000004 | 2018-03-28 | COMMENTS TO MOM - CON-BMP-MOM-00012 | REF.: CON-BMP-TRA-000003
BMP-BOC-TRE-000005 | 2018-03-28 | COMMENTS TO MOM - CON-BMP-MOM-00011 | REF.: CON-BMP-TRA-000003
BMP-BOC-TRE-000006 | 2018-03-28 | COMMENTS TO MOM - CON-BMP-MOM-00004 | REF.: CON-BMP-TRA-000003
BMP-BOC-TRE-000007 | 2018-03-28 | COMMENTS TO MOM - CON-BMP-MOM-00001 | REF.: CON-BMP-TRA-000003
BMP-BOC-TRE-000008 | 2018-03-28 | COMMENTS TO MOM - CON-BMP-MOM-000010 | REF.: CON-BMP-TRA-000003
BMP-BOC-TRE-000009 | 2018-03-28 | COMMENTS TO PROJECT DOCUMENT CODING | REF.: CON-BMP-TRA-000002
BMP-BOC-TRE-000010 | 2018-03-28 | COMMENTS TO TTSJV ENGINEERING MANAGEMNT PLAN | REF.: CON-BMP-TRA-000001
BMP-BOC-TRE-000011 | 2018-03-28 | COMMENTS TO BMP PROJECT 90 DAYS STARTER SCHEDULE | REF.: CON-BMP-TRA-000005
BMP-BOC-TRE-000012 | 2018-04-03 | COMMENTS TO PRICE LIST FOR SOIL INVETIGATION AND TECHNICAL SPECIFICATIONFOR SOIL INVESTIGATION REFINERY AREA | REF.: CON-BMP-TRA-010001
BMP-BOC-TRE-000013 | 2018-04-03 | COMMENTS TO COORDINATION PROCEDURE FOR PROJECT | REF.: CON-BMP-TRA-000001
BMP-DIR-TRE-000001 | 2018-04-09 | COMMENTS TO CONFIDENTIALITY PLAN | REF.: CON-BMP-TRA-000016
BMP-DIR-TRE-000002 | 2018-04-09 | COMMENTS TO PROCUREMENT PROCEDURE AND PLAN | REF.: CON-BMP-TRA-000007
BMP-DIR-TRE-000003 | 2018-04-16 | COMMENTS TO REQUIREMENTS FOR EQUIPMENT SUPPLIER 3D MODEL | REF.: CON-BMP-TRA-000022
BMP-DIR-TRE-000004 | 2018-04-16 | COMMENTS TO SOIL INVESTIGATION | REF.: CON-BMP-TRA-010018
BMP-DIR-TRE-000005 | 2018-05-02 | COMMENTS TO 000-A-PRO-50040-001 CONFIDENTIALITY PLAN | REF.: CON-BMP-TRA-000043
BMP-DIR-TRE-000006 | 2018-04-16 | COMMENTS TO PROJECT MANAGEMENT PLAN | REF.: CON-BMP-TRA-000024
BMP-DIR-TRE-000007 | 2018-04-16 | COMMENTS TO COMPLETION MANAGEMENT | REF.: CON-BMP-TRA-000003
BMP-DIR-TRE-000008 | 2018-04-16 | COMMENTS TO PRESCRIPTIONS FOR PREPARATION OF MANUFACTURING DATA RECORD BOOK (MDRB) | REF.: CON-BMP-TRA-000006
BMP-DIR-TRE-000009 | 2018-04-17 | COMMENTS TO BIDDERS LISTS | REF.: CON-BMP-TRA-000004
BMP-DIR-TRE-000010 | 2018-04-17 | COMMENTS TO PLANNING AND SCHEDULING PROCEDURE | REF.: CON-BMP-TRA-000030
BMP-DIR-TRE-000011 | 2018-04-18 | COMMENTS TO PROGRESS MEASUREMENT AND MILESTONE CERTIFICATE PROCEDURE | REF.: CON-BMP-TRA-000036
BMP-DIR-TRE-000012 | 2018-04-19 | COMMENTS TO DEVIATION WAIVER AND TECHNICAL QUERY REQUEST PROCEDURE | REF.: CON-BMP-TRA-000026
BMP-DIR-TRE-000013 | 2018-04-20 | COMMENTS TO OVERALL PROJECT QUALITY PLAN | REF.: CON-BMP-TRA-000042
BMP-DIR-TRE-000014 | 2018-04-24 | COMMENTS TO INVOICING PROCEDURE | REF.: CON-BMP-TRA-000028
BMP-DIR-TRE-000015 | 2018-05-04 | COMMENTS TO VENDOR PRE-QUALIFICATION PROCEDURE | REF.: CON-BMP-TRA-000020
BMP-DIR-TRE-000016 | 2018-04-26 | COMMENTS TO 000-A-PRI-50004-HSSE REQUIREMENTS FOR VENDORS | REF.: CON-BMP-TRA-000034
BMP-DIR-TRE-000017 | 2018-04-26 | COMMENTS TO 000-A-PRO-50041-001 - PROJECT HSSE PLAN | REF.: CON-BMP-TRA-000014
BMP-DIR-TRE-000018 | 2018-04-26 | COMMENTS TO 000-A-PRO-50036-001 - VARIATION PROCEDURE | REF.: CON-BMP-TRA-000029
BMP-DIR-TRE-000019 | 2018-04-29 | COMMENTS TO 000-A-PRO-50003-001 - COORDINATION PROCEDURE | REF.: CON-BMP-TRA-000051
BMP-DIR-TRE-000020 | 2018-05-03 | COMMENTS TO 000-A-PRO-50027-001 3D MODELLING CIVIL PROCEDURE | REF.: CON-BMP-TRA-000044
BMP-DIR-TRE-000021 | 2018-05-03 | COMMENTS TO 000-A-PRO-50001-001 PROJECT EXECUTION PLAN | REF.: CON-BMP-TRA-000027
BMP-DIR-TRE-000022 | 2018-05-04 | COMMENTS TO JOB SUPPLY SPECIFICATION | REF.: CON-BMP-TRA-000054
BMP-DIR-TRE-000023 | 2018-05-07 | COMMENTS TO 000-A-SCH-50002 LEVEL 1 PROJECT CONTRACT SCHEDULE | REF.: CON-BMP-TRA-000035
BMP-DIR-TRE-000024 | 2018-05-08 | COMMENTS TO INVOICING PROCEDURE | REF.: CON-BMP-TRA-000057
BMP-DIR-TRE-000025 | 2018-05-10 | COMMENTS TO HSSE REQUIREMENTS FOR SUBCONTRACTORS | REF.: CON-BMP-TRA-000060
BMP-DIR-TRE-000026 | 2018-05-11 | COMMENTS TO INVOICING PROCEDURE | REF.: CON-BMP-TRA-000086
BMP-DIR-TRE-000027 | 2018-05-15 | COMMENTS TO 000 QA QC/INSPECTION AND EXPEDITING REQUIREMENT FOR VENDORS | REF.: CON-BMP-TRA-000071
BMP-DIR-TRE-000028 | 2018-05-15 | COMMENTS TO WORK BREAKDOWN STRUCTURE | REF.: CON-BMP-TRA-000063
BMP-DIR-TRE-000029 | 2018-05-15 | COMMENTS TO UNIT 000 - VARIATION PROCEDURE & TREND PROCEDURE | REF.: CON-BMP-TRA-000076
BMP-DIR-TRE-000031 | 2018-05-16 | COMMENTS TO CONSTRUCTION EXECUTION PLAN | REF.: CON-BMP-TRA-000061
BMP-DIR-TRE-000032 | 2018-05-16 | COMMENTS TO QUALITY PROJEC AUDIT & NON CONFORMANCE CONTROL PROCEDURES | REF.: CON-BMP-TRA-000066
BMP-DIR-TRE-000033 | 2018-05-16 | COMMENTS TO COMMENT MANAGEMENT PROCEDURE | REF.: CON-BMP-TRA-000059
BMP-DIR-TRE-000034 | 2018-05-18 | COMMENTS TO ENGINEERING DELIVERABLE LIST | REF.: CON-BMP-TRA-000032-REV.1
BMP-DIR-TRE-000035 | 2018-05-22 | COMMENTS TO BIDDERS LIST FOR OVERALL PILING WARK AND TEMPORARY CONSTRUCTION FACILITIES | REF.: CON-BMP-TRA-000062
BMP-DIR-TRE-000037 | 2018-05-22 | COMMENTS TO PIPING MATERIAL MANAGEMENT PROCEDURE | REF.: CON-BMP-TRA-000056
BMP-DIR-TRE-000038 | 2018-05-22 | COMMENTS TO REQUIREMENTS FOR VENDOR DOCUMENTATION AND EXCHANGE OF CORRESPONDENCE | REF.: CON-BMP-TRA-000072
BMP-DIR-TRE-000039 | 2018-05-22 | COMMENTS TO SITE HSSE PROCEDURE FOR GEOTECHNICAL WORKS | REF.: CON-BMP-TRA-000091
BMP-DIR-TRE-000040 | 2018-05-22 | COMMENTS TO INSPECTION PROCEDURE | REF.: CON-BMP-TRA-000069
BMP-MOC-TRE-000001 | 2018-04-09 | COMMENTS TO MOC MATERIAL REQUISITION FOR HCU REACTORS INTERNALS | REF.: CON-BMP-TRA-040001
BMP-MOC-TRE-000002 | 2018-04-06 | COMMENTS TO MOC MATERIAL RQUISITION FOR HP SHELL AND TUBE H.E. | REF.: CON-BMP-TRA-040003
BMP-MOC-TRE-000003 | 2018-04-11 | COMMENTS TO MOC MATERIAL REQUISITION FOR CS COLUMNS - | REF.: CON-BMP-TRA-040002
BMP-MOC-TRE-000004 | 2018-04-10 | COMMENTS TO MOC MATERIAL RQUISITION FORCDU-VCU FIRED HEATEARS | REF.: CON-BMP-TRA-040004 | REPLIED
BMP-MOC-TRE-000005 | 2018-04-19 | COMMENTS TO MOC MECHANICAL DATA SHEET FEED FILTER 019U0001 | REF.: CON-BMP-TRA-040005
BMP-MOC-TRE-000006 | 2018-04-19 | COMMENTS TO MOC SETTING PLAN FOR MAKE UP HYDROGEN FIRST STAGE INTERCOOLER | REF.: CON-BMP-TRA-040007
BMP-MOC-TRE-000007 | 2018-04-20 | COMMENTS TO MOC MECHANICAL DATA SHEETS | REF.: CON-BMP-TRA-040006
BMP-MOC-TRE-000008 | 2018-04-20 | COMMENTS TO MOC MECHANICAL DATA SHEETS | REF.: CON-BMP-TRA-040009
BMP-MOC-TRE-000009 | 2018-04-20 | COMMENTS TO MOC AIR COOLED HEAT EXCHANGERS DATA SHEET | REF.: CON-BMP-TRA-040008
BMP-MOC-TRE-000010 | 2018-04-24 | COMMENTS TO MOC PROCESS FLOW DIAGRAM | REF.: CON-BMP-TRA-040011
BMP-MOC-TRE-000011 | 2018-04-24 | COMMENTS TO MOC PROCESS FLOW DIAGRAM | REF.: CON-BMP-TRA-040010
BMP-MOC-TRE-000012 | 2018-04-25 | COMMENTS TO MOC MATERIAL REQUISITION FOR BB5 PUMPS | REF.: CON-BMP-TRA-040013
BMP-MOC-TRE-000013 | 2018-04-25 | COMMENTS TO MOC MATERIAL REQUISITION FOR SEPARATORS CR-MO | REF.: CON-BMP-TRA-040015
BMP-MOC-TRE-000014 | 2018-04-25 | COMMENTS TO MOC MATERIAL REQUISITION FOR REACTORS HCU | REF.: CON-BMP-TRA-040014
BMP-MOC-TRE-000015 | 2018-04-25 | COMMENTS TO MOC PROCESS FLOW DIAGRAM | REF.: CON-BMP-TRA-040024
BMP-MOC-TRE-000016 | 2018-04-26 | COMMENTS TO MOC MATERIAL REQUISITION FOR VACUUM UNIT PACKAGES | REF.: CON-BMP-TRA-040016
BMP-MOC-TRE-000017 | 2018-04-26 | COMMENTS TO MOC PROCESS FLOW DIAGRAMS | REF.: CON-BMP-TRA-040012
BMP-MOC-TRE-000018 | 2018-04-27 | COMMENTS TO MOC - COMPRESSORS DATA SHEETS | REF.: CON-BMP-TRA-040017
BMP-MOC-TRE-000019 | 2018-04-27 | COMMENTS TO MOC - COMPRESSORS DATA SHEETS | REF.: CON-BMP-TRA-040023
BMP-MOC-TRE-000020 | 2018-04-27 | COMMENTS TO MOC - DESALTERS DATA SHEET | REF.: CON-BMP-TRA-040019
BMP-MOC-TRE-000021 | 2018-04-27 | COMMENTS TO MOC - UNIT 010 PUMPS MECHANICAL DATA SHEETS | REF.: CON-BMP-TRA-040018
BMP-MOC-TRE-000022 | 2018-04-29 | COMMENTS TO MOC - HEAT EXCHANGERS AND VESSELS DRAWINGS | REF.: CON-BMP-TRA-040021
BMP-MOC-TRE-000023 | 2018-04-29 | COMMENTS TO MOC - HEAT EXCHANGERS AND VESSELS DRAWINGS | REF.: CON-BMP-TRA-040026
BMP-MOC-TRE-000024 | 2018-04-29 | COMMENTS TO MOC - MR FOR RECIPROCATING COMPRESSOR | REF.: CON-BMP-TRA-040027
BMP-MOC-TRE-000025 | 2018-04-29 | COMMENTS TO MOC -MR FOR DESALTER PACKAGE | REF.: CON-BMP-TRA-040028
BMP-MOC-TRE-000026 | 2018-04-29 | COMMENTS TO MOC MR FOR CENTRIFUGAL COMPRESSOR | REF.: CON-BMP-TRA-040029
BMP-MOC-TRE-000027 | 2018-04-29 | COMMENTS TO MOC MATERIAL REQUISITON FOR FEED FILTER | REF.: CON-BMP-TRA-040030
BMP-MOC-TRE-000028 | 2018-04-30 | COMMENTS TO MOC MATERIAL REQUISITON FOR API HIGH SPEED MULTISTAGE PUMPS | REF.: CON-BMP-TRA-040031
BMP-MOC-TRE-000029 | 2018-04-30 | COMMENTS TO MOC HEAT EXCHANGERS DATA SHEETS | REF.: CON-BMP-TRA-040022
BMP-MOC-TRE-000030 | 2018-05-02 | COMMENTS TO MOC 085-S-DAT-00012 TO 00015 -FILTERING DATASHEET | REF.: CON-BMP-TRA-040033
BMP-MOC-TRE-000031 | 2018-05-02 | COMMENTS TO MOC 019E-DAT-00045/45-001 AIR COOLERS DATA SHEETS | REF.: CON-BMP-TRA-040034
BMP-MOC-TRE-000032 | 2018-05-02 | COMMENTS TO MOC MATRIAL REQUSITION FOR HCU FIRED HEATERS | REF.: CON-BMP-TRA-040035
BMP-MOC-TRE-000033 | 2018-05-02 | COMMENTS TO MOC MATRIAL REQUSITION FOR STAINLESS STEEEL AND CALD VESSELS | REF.: CON-BMP-TRA-040037
BMP-MOC-TRE-000034 | 2018-05-02 | COMMENTS TO MOC MATRIAL REQUSITION FOR H.P. VESSELS (LLC) | REF.: CON-BMP-TRA-040036
BMP-MOC-TRE-000035 | 2018-05-02 | COMMENTS TO MOC MATERIAL REQUISITION FOR BB1 BB2 BB3 PUMPS | REF.: CON-BMP-TRA-040032
BMP-MOC-TRE-000036 | 2018-05-03 | COMMENTS TO MOC UNIT085 DATA SHEETS FOR PUMPS | REF.: CON-BMP-TRA-040020
BMP-MOC-TRE-000037 | 2018-05-04 | COMMENTS TO MOC MATERIAL REQUISITION FOR SIDE STREAM FILTERS | REF.: CON-BMP-TRA-040041
BMP-MOC-TRE-000038 | 2018-05-04 | COMMENTS TO MOC MATERIAL REQUISITION FOR INDUCED DRAFT COOLING TOWER | REF.: CON-BMP-TRA-040039
BMP-MOC-TRE-000039 | 2018-05-06 | COMMENTS TO MOC AIR COOLERS AND HEAT EXCHANGERS DATA SHEETS AND DRAWINGS | REF.: CON-BMP-TRA-040043
BMP-MOC-TRE-000040 | 2018-05-06 | COMMENTS TO MOC DATA SHEET FOR AIR COOLED | REF.: CON-BMP-TRA-040042
BMP-MOC-TRE-000041 | 2018-05-06 | COMMENTS TO MATERIAL REQUISITION FOR AIR COOLERS | REF.: CON-BMP-TRA-040044
BMP-MOC-TRE-000042 | 2018-05-06 | COMMENTS TO MATERIAL REQUISITION FOR CLADDED COLUMNS | REF.: CON-BMP-TRA-040038
BMP-MOC-TRE-000043 | 2018-05-07 | COMMENTS TO MATERIAL REQUISITION 000M-MR-0570-001 FOR TRAYS AND INTERNALS COLUMNS | REF.: CON-BMP-TRA-040040
BMP-MOC-TRE-000044 | 2018-05-10 | COMMENTS TO COORDINATION PROCEDURE | REF.: CON-BMP-TRA-040045
BMP-MOC-TRE-000045 | 2018-05-10 | COMMENTS TO PROCESS BASIS OF DESIGN 2HCU HYDROCRACKER UNIT | REF.: CON-BMP-TRA-040046
BMP-MOC-TRE-000046 | 2018-05-10 | COMMENTS TO ITEM INDEX - EQUIPMENT LIST | REF.: CON-BMP-TRA-040048
BMP-MOC-TRE-000047 | 2018-05-15 | COMMENTS TO 000 MOC MANAGEMENT PLAN | REF.: CON-BMP-TRA-040050
BMP-MOC-TRE-000048 | 2018-05-15 | COMMENTS TO EQUIPMENT LIST - ITEM INDEX | REF.: CON-BMP-TRA-040049
BMP-MOC-TRE-000049 | 2018-05-15 | COMMENTS TO MOC MATERIAL SELECTION DIAGRAMS | REF.: CON-BMP-TRA-040051
BMP-MOC-TRE-000050 | 2018-05-20 | COMMENTS TO MOC MATERIAL REQUISITION FOR CALCITE BED PACKAGE | REF.: CON-BMP-TRA-040052
BMP-MOC-TRE-000051 | 2018-05-23 | COMMENTS TO MOC KEY SINGLE LINE DIAGRAM | REF.: CON-BMP-TRA-040054
BMP-MOC-TRE-000052 | 2018-05-23 | COMMENTS TO MOC LOAD BALANCE | REF.: CON-BMP-TRA-040053
BMP-MOC-TRE-000053 | 2018-05-24 | COMMENTS TO MOC 019 UNFIRED PRESSURE VESSEL DESIGN SPECIFICATION | REF.: CON-BMP-TRA-040056
BMP-ROC-TRE-000001 | 2018-03-28 | COMMENTS TO PROJECT EXCUTION PLAN | REF.: CON-BMP-TRA-000001
BMP-ROC-TRE-000004 | 2018-03-28 | COMMENTS TO DOCUMENT ISSUED DISTRIBUTION TO AND APPROVAL BY BAPCO | REF.: CON-BMP-TRA-000002
BMP-ROC-TRE-000005 | 2018-03-28 | COMMENTS TO MOM - CON-BMP-MOM-00005 | REF.: CON-BMP-TRA-000003
BMP-ROC-TRE-000006 | 2018-03-30 | COMMENTS TO WORK BREADOWN STRUCTURE | REF.: CON-BMP-TRA-000010
BMP-ROC-TRE-000007 | 2018-03-30 | COMMENTS TO INVOICING PROCEDURE | REF.: CON-BMP-TRA-000009
BMP-ROC-TRE-000008 | 2018-05-08 | COMMENTS TO MATERIAL REQUISITION FOR CENTRIFUGAL COMPRESSOR | REF.: CON-BMP-TRA-010033
BMP-ROC-TRE-000009 | 2018-04-04 | COMMENTS TO COORDINATION PROCEDURE AMONG THE BAHRAIN PETR. COMPANY BAPCO AND TTSJV AND LICENSORS | REF.: CON-BMP-TRA-000008
BMP-ROC-TRE-000010 | 2018-04-04 | COMMENTS TO HOMOGENIZATION PROCEDURE | REF.: CON-BMP-TRA-000015
BMP-ROC-TRE-000011 | 2018-04-05 | COMMENTS TO PROCESS DESIGN BASIS 1 FLARE SYSTEM | REF.: CON-BMP-TRA-010003
BMP-ROC-TRE-000012 | 2018-04-06 | COMMENTS TO PROCESS DESIGN BASIS SPENT CAUSTIC TREATING PLANT | REF.: CON-BMP-TRA-010002
BMP-ROC-TRE-000013 | 2018-04-06 | COMMENTS TO MATERIAL RQUISITION FOR 2.25CR-1MO-V REACTOR AND INTERNALS | REF.: CON-BMP-TRA-010017
BMP-ROC-TRE-000014 | 2018-04-06 | COMMENTS TO MATERIAL RQUISITION FOR 2.25CR-1MO-VH.P. VESSELS | REF.: CON-BMP-TRA-010016
BMP-ROC-TRE-000015 | 2018-04-06 | COMMENTS TO REPORTING PROCEDURE | REF.: CON-BMP-TRA-000018
BMP-ROC-TRE-000016 | 2018-04-06 | COMMENTS TO OVERALL PROJECT QUALITY PLAN | REF.: CON-BMP-TRA-000016
BMP-ROC-TRE-000017 | 2018-04-09 | COMMENTS TO PROCESS DESIGN BASIS LSDP FLARE SYSTEM REVAMPING | REF.: CON-BMP-TRA-010012
BMP-ROC-TRE-000018 | 2018-04-09 | COMMENTS TO PROCESS DESIGN BASIS LSFO FLARE SYSTEM MODIFICATIONS | REF.: CON-BMP-TRA-010011
BMP-ROC-TRE-000019 | 2018-04-09 | COMMENTS TO PROCESS DESIGN BASIS SITRA WHARF & ASSOCIATED MARINE FACILITIES | REF.: CON-BMP-TRA-010010
BMP-ROC-TRE-000020 | 2018-04-09 | COMMENTS TO PROCESS FLOW DIAGRAMS | REF.: CON-BMP-TRA-010005
BMP-ROC-TRE-000021 | 2018-04-09 | COMMENTS TO PLOT PLANS | REF.: CON-BMP-TRA-010004
BMP-ROC-TRE-000022 | 2018-04-09 | COMMENTS TO PROCESS DESIGN BASIS REFRIGERATED LPG STORAGE | REF.: CON-BMP-TRA-010008
BMP-ROC-TRE-000023 | 2018-04-09 | COMMENTS TO PROCESS DESIGN BASIS SITRA TANK FARM | REF.: CON-BMP-TRA-010009
BMP-ROC-TRE-000024 | 2018-04-09 | COMMENTS TO PROCESS DESIGN BASIS REFINERY TO SITRA TRANSFER LINES | REF.: CON-BMP-TRA-010013
BMP-ROC-TRE-000025 | 2018-04-09 | COMMENTS TO PROCESS FLOW DIAGRAM | REF.: CON-BMP-TRA-010006
BMP-ROC-TRE-000027 | 2018-04-09 | COMMENTS TO GENERAL LAYOUT INTERFACE | REF.: CON-BMP-TRA-010015
BMP-ROC-TRE-000028 | 2018-04-16 | COMMENTS TO PROCESS FLOW DIAGRAMS | REF.: CON-BMP-TRA-010019
BMP-ROC-TRE-000029 | 2018-04-18 | COMMENTS TO TECHNICAL SPECIFICATION FOR TOPOGRAPHIC SURVEY FOR REFINERY TANK FARM TRANSFER LINE SITRA TANK FARM & WHARF | REF.: CON-BMP-TRA-010020
BMP-ROC-TRE-000030 | 2018-04-23 | COMMENTS TO MATERIAL REQUISITION FOR 1RHCU FIRE HEATER | REF.: CON-BMP-TRA-010026
BMP-ROC-TRE-000031 | 2018-04-24 | COMMENTS TO MATERIAL REQUISITION FOR EBULLATING PUMPS | REF.: CON-BMP-TRA-010021
BMP-ROC-TRE-000032 | 2018-04-24 | COMMENTS TO PROCESS FLOW DIAGRAMS | REF.: CON-BMP-TRA-010031
BMP-ROC-TRE-000033 | 2018-04-24 | COMMENTS TO DOCUMENTATION FOR TOPOGRAPHIC SURVEY | REF.: CON-BMP-TRA-010029
BMP-ROC-TRE-000034 | 2018-05-10 | COMMENTS TO ESIA & ESAP IMPLEMENTATION REPORTS | REF.: CON-BMP-TRA-010042
BMP-ROC-TRE-000035 | 2018-04-24 | COMMENTS TO PROCESS FLOW DIAGRAM HEAT AND MATERIAL BALANCE | REF.: CON-BMP-TRA-010037
BMP-ROC-TRE-000036 | 2018-04-24 | COMMENTS TO PROCESS DESIGN BASIS FUEL GAS SYSTEM | REF.: CON-BMP-TRA-010025
BMP-ROC-TRE-000037 | 2018-04-26 | COMMENTS TO 050-A-BOD-50001-PROCESS DESIGN BASIS REFINERY TANK FARM | REF.: CON-BMP-TRA-010028
BMP-ROC-TRE-000038 | 2018-04-26 | COMMENTS TO UNIT 082 PROCESS FLOW DIAGRAM | REF.: CON-BMP-TRA-010032
BMP-ROC-TRE-000039 | 2018-04-27 | COMMENTS TO MATERIAL REQUISITION FOR RECIPROCATING COMPRESSORS | REF.: CON-BMP-TRA-010035
BMP-ROC-TRE-000040 | 2018-04-29 | COMMENTS TO COORDINATION PROCEDURE BETWEEN BAPCO IPMT AND ROC | REF.: CON-BMP-TRA-010022
BMP-ROC-TRE-000041 | 2018-04-29 | COMMENTS TO MATERIAL REQUISITION FOR BB5 PUMPS | REF.: CON-BMP-TRA-010036
BMP-ROC-TRE-000042 | 2018-04-29 | COMMENTS TO PROCESS FLOW DIAGRAMS | REF.: CON-BMP-TRA-010044
BMP-ROC-TRE-000043 | 2018-04-29 | COMMENTS TO PROCESS FLOW DIAGRAMS | REF.: CON-BMP-TRA-010030
BMP-ROC-TRE-000044 | 2018-05-03 | COMMENTS TO MATERIAL REQUISITION FOR FEED FILTERS | REF.: CON-BMP-TRA-010038
BMP-ROC-TRE-000045 | 2018-05-06 | COMMENTS TO PROCESS FLOW DIAGRAMS | REF.: CON-BMP-TRA-010041
BMP-ROC-TRE-000046 | 2018-05-07 | COMMENTS TO MATERIAL REQUISITION 000R-MR-0570-001 | REF.: CON-BMP-TRA-010040
BMP-ROC-TRE-000047 | 2018-05-07 | COMMENTS TO MATERIAL REQUISITION FOR LARGE COLUMN | REF.: CON-BMP-TRA-010039
BMP-ROC-TRE-000048 | 2018-05-07 | COMMENTS TO MATERIAL SELECTION DIAGRAMS | REF.: CON-BMP-TRA-010043
BMP-ROC-TRE-000049 | 2018-05-11 | COMMENTS TO MATERIAL REQUISITION FOR AIR COOLERS | REF.: CON-BMP-TRA-010034
BMP-ROC-TRE-000050 | 2018-05-11 | COMMENTS TO MATERIAL REQUISITION FOR H.P. AND SPECIAL MATERIAL AIR COOLERS | REF.: CON-BMP-TRA-010045
BMP-ROC-TRE-000051 | 2018-05-11 | COMMENTS TO MATERIAL SELECTION DIAGRAM | REF.: CON-BMP-TRA-010048
BMP-ROC-TRE-000052 | 2018-05-13 | COMMENTS TO MATERIAL REQUISITION FOR VACUUM UNIT PACKAGE | REF.: CON-BMP-TRA-010046
BMP-ROC-TRE-000053 | 2018-05-13 | COMMENTS TO PROCESS FLOW DIAGRAMS | REF.: CON-BMP-TRA-010049
BMP-ROC-TRE-000054 | 2018-05-15 | COMMENTS TO MATERIAL SELECTION DIAGRAMS | REF.: CON-BMP-TRA-010052
BMP-ROC-TRE-000055 | 2018-05-13 | COMMENTS TO 000 MATERIAL REQUISITION 3HDU | REF.: CON-BMP-TRA-010053
BMP-ROC-TRE-000056 | 2018-05-16 | COMMENTS TO JOB SPECIFICATION FOR QUANTITATIVE RISK ASSESSMENT | REF.: CON-BMP-TRA-010050
BMP-ROC-TRE-000057 | 2018-05-22 | COMMENTS TO TEMPORARY CONSTRUCTION FACILITIES | REF.: CON-BMP-TRA-010054
BMP-ROC-TRE-000058 | 2018-05-22 | COMMENTS TO PROCESS FLOW DIAGRAMS | REF.: CON-BMP-TRA-010056
BMP-ROC-TRE-000059 | 2018-05-23 | COMMENTS TO 000 HSSE REQUIREMENTS FOR WORKING IN THE WHARF | REF.: CON-BMP-TRA-010057
BMP-SOC-TRE-000001 | 2018-04-09 | COMMENTS TO MATERIAL REQUISITION FOR SRU REACTION FURNACE-WASTE HEAT BOILER AND STEAM DRUM | REF.: CON-BMP-TRA-070002
BMP-SOC-TRE-000002 | 2018-04-10 | COMMENTS TO MATERIAL REQUISITION FOR INCINERATOR PACKAGE | REF.: CON-BMP-TRA-070003
BMP-SOC-TRE-000003 | 2018-04-10 | COMMENTS TO MATERIAL REQUISITION FOR MULTI EFFECT DESALINATION PACKAGE | REF.: CON-BMP-TRA-070005 | REPLIED |  | CS REPLIED | 2018-05-08
BMP-SOC-TRE-000004 | 2018-04-10 | COMMENTS TO MATERIAL REQUISITION FOR HYDROGEN PLANT STEAM REFORMER | REF.: CON-BMP-TRA-070001 | REPLIED |  | CS REPLIED | 2018-04-13
BMP-SOC-TRE-000005 | 2018-04-10 | COMMENTS TO MATERIAL REQUISITION FOR MATERIAL REQUISITION FOR AUXILIARY STEAM BOILERS | REF.: CON-BMP-TRA-070004
BMP-SOC-TRE-000006 | 2018-04-17 | COMMENTS TO MATERIAL REQUISITION FOR REACTORS | REF.: CON-BMP-TRA-070011
BMP-SOC-TRE-000007 | 2018-04-17 | COMMENTS TO BMP SULPHUR SOLIDIFICATION PACKAGE | REF.: CON-BMP-TRA-070006 | CON RESPONSE REQUIRED
BMP-SOC-TRE-000008 | 2018-04-17 | COMMENTS TO MATERIAL REQUISITION FOR BMP SOLID SULPHUR HANDLING PACKAGE | REF.: CON-BMP-TRA-070007 | CON RESPONSE REQUIRED
BMP-SOC-TRE-000009 | 2018-04-23 | COMMENTS TO BASIS OF DESIGN | REF.: CON-BMP-TRA-070010 | CON RESPONSE REQUIRED
BMP-SOC-TRE-000010 | 2018-04-23 | COMMENTS TO BASIS OF DESIGN | REF.: CON-BMP-TRA-070009 | CON RESPONSE REQUIRED
BMP-SOC-TRE-000011 | 2018-04-24 | COMMENTS TO MATERIAL REQUISITION FOR AIR COOLERS | REF.: CON-BMP-TRA-070008 | CON RESPONSE REQUIRED
BMP-SOC-TRE-000012 | 2018-04-25 | COMMENTS TO MATERIAL REQUISITION FOR NITROGEN GENERATION, STORAGE AND VAPORIZATION | REF.: CON-BMP-TRA-070012 | CON RESPONSE REQUIRED
BMP-SOC-TRE-000013 | 2018-04-26 | COMMENTS TO BASIS OF DESIGN 3H2,4H2 PLANT (UNIT 098,099) NO.3 NO.4 HYDROGEN PLANT | REF.: CON-BMP-TRA-070014 | CON RESPONSE REQUIRED
BMP-SOC-TRE-000014 | 2018-04-27 | COMMENTS TO BASIS OF DESIGN RLPG (UNIT 005) LPG C3-C4 STORAGE FACILITY AT REFINERY | REF.: CON-BMP-TRA-070013 | CON RESPONSE REQUIRED
BMP-SOC-TRE-000015 | 2018-04-27 | COMMENTS TO BASIS OF DESIGN 2IAS (UNIT 341) AIR VOMPRESSOR AND DRYERS | REF.: CON-BMP-TRA-070015 | CON RESPONSE REQUIRED
BMP-SOC-TRE-000016 | 2018-04-30 | COMMENTS TO BASIS OF DESIGN STM G AND D (UNIT 371) STEAM GENERATION AND DISTRIBUTION | REF.: CON-BMP-TRA-070016 | CON RESPONSE REQUIRED
BMP-SOC-TRE-000017 | 2018-04-30 | COMMENTS TO BASIS OF DESIGN 2 BFW AND COND(UNIT 372) BOILER FEED WATER ANDCONDENSATE DISTRIBUTION | REF.: CON-BMP-TRA-070017 | CON RESPONSE REQUIRED
BMP-SOC-TRE-000018 | 2018-05-07 | COMMENTS TO PROCESS FLOW DIAGRAM UNIT 098 | REF.: CON-BMP-TRA-070037 | CON RESPONSE REQUIRED
BMP-SOC-TRE-000019 | 2018-05-07 | COMMENTS TO PROCESS FLOW DIAGRAM UNIT 047 | REF.: CON-BMP-TRA-070027 | CON RESPONSE REQUIRED
BMP-SOC-TRE-000020 | 2018-05-07 | COMMENTS TO PROCESS FLOW DIAGRAM UNIT 041 | REF.: CON-BMP-TRA-070021 | CON RESPONSE REQUIRED
BMP-SOC-TRE-000021 | 2018-05-07 | COMMENTS TO PROCESS FLOW DIAGRAM UNIT 042 | REF.: CON-BMP-TRA-070022 | CON RESPONSE REQUIRED
BMP-SOC-TRE-000022 | 2018-05-07 | COMMENTS TO PROCESS FLOW DIAGRAM - UNIT 043 | REF.: CON-BMP-TRA-070023 | CON RESPONSE REQUIRED
BMP-SOC-TRE-000023 | 2018-05-07 | COMMENTS TO PROCESS FLOW DIAGRAM UNIT 094 | REF.: CON-BMP-TRA-070036 | CON RESPONSE REQUIRED
BMP-SOC-TRE-000024 | 2018-05-07 | COMMENTS TO PROCESS FLOW DIAGRAM UNIT 083 | REF.: CON-BMP-TRA-070030 | CON RESPONSE REQUIRED
BMP-SOC-TRE-000025 | 2018-05-07 | COMMENTS TO PROCESS FLOW DIAGRAM UNIT 088 | REF.: CON-BMP-TRA-070032 | CON RESPONSE REQUIRED
BMP-SOC-TRE-000026 | 2018-05-07 | COMMENTS TO BASIS OF DESIGN NITROGEN PLANT (UNIT 83) | REF.: CON-BMP-TRA-070046 | CON RESPONSE REQUIRED
BMP-SOC-TRE-000027 | 2018-05-08 | COMMENTS TO UNIT 005-PROCESS FLOW DIAGRAM | REF.: CON-BMP-TRA-070041 | CON RESPONSE REQUIRED
BMP-SOC-TRE-000028 | 2018-05-08 | COMMENTS TO UNIT 382-PROCESS FLOW DIAGRAM | REF.: CON-BMP-TRA-070040 | CON RESPONSE REQUIRED
BMP-SOC-TRE-000029 | 2018-05-08 | COMMENTS TO UNIT 311-PROCESS FLOW DIAGRAM | REF.: CON-BMP-TRA-070043 | CON RESPONSE REQUIRED
BMP-SOC-TRE-000030 | 2018-05-08 | COMMENTS TO UNIT 310-PROCESS FLOW DIAGRAM | REF.: CON-BMP-TRA-070042 | CON RESPONSE REQUIRED
BMP-SOC-TRE-000031 | 2018-05-08 | COMMENTS TO UNIT 087-PROCESS FLOW DIAGRAM | REF.: CON-BMP-TRA-070031 | CON RESPONSE REQUIRED
BMP-SOC-TRE-000032 | 2018-05-08 | COMMENTS TO UNIT 016-PROCESS FLOW DIAGRAM | REF.: CON-BMP-TRA-070018 | CON RESPONSE REQUIRED
BMP-SOC-TRE-000033 | 2018-05-09 | COMMENTS TO UNIT 341-DATA SHEET | REF.: CON-BMP-TRA-070039 | CON RESPONSE REQUIRED
BMP-SOC-TRE-000034 | 2018-05-09 | COMMENTS TO UNIT 042-DATA SHEET | REF.: CON-BMP-TRA-070033 | CON RESPONSE REQUIRED
BMP-SOC-TRE-000035 | 2018-05-09 | COMMENTS TO UNIT 041-DATA SHEET | REF.: CON-BMP-TRA-070029 | CON RESPONSE REQUIRED
BMP-SOC-TRE-000036 | 2018-05-09 | COMMENTS TO UNIT 043-DATA SHEET | REF.: CON-BMP-TRA-070034 | CON RESPONSE REQUIRED
BMP-SOC-TRE-000037 | 2018-05-09 | COMMENTS TO UNIT 341-PROCESS FLOW DIAGRAM | REF.: CON-BMP-TRA-070044 | CON RESPONSE REQUIRED
BMP-SOC-TRE-000038 | 2018-05-09 | COMMENTS TO UNIT 341-DATA SHEET | REF.: CON-BMP-TRA-070035 | CON RESPONSE REQUIRED
BMP-SOC-TRE-000039 | 2018-05-09 | COMMENTS TO UNIT 382 BASIS OF DESIGN FOR SEWER SYSTEMS | REF.: CON-BMP-TRA-070047 | CON RESPONSE REQUIRED
BMP-SOC-TRE-000040 | 2018-05-09 | COMMENTS TO UNIT 016 MATERIAL SELECTION DIAGRAM | REF.: CON-BMP-TRA-070020 | CON RESPONSE REQUIRED
BMP-SOC-TRE-000041 | 2018-05-10 | COMMENTS TO UNIT-005 MATERIAL SELECTION DIAGRAM | REF.: CON-BMP-TRA-070019 | CON RESPONSE REQUIRED
BMP-SOC-TRE-000042 | 2018-05-10 | COMMENTS TO UNIT 382 MATERIAL SELECTION DIAGRAM | REF.: CON-BMP-TRA-070028 | CON RESPONSE REQUIRED
BMP-SOC-TRE-000043 | 2018-05-10 | COMMENTS TO UNIT 311 MATERIAL SELECTION DIAGRAM | REF.: CON-BMP-TRA-070025 | CON RESPONSE REQUIRED
BMP-SOC-TRE-000044 | 2018-05-10 | COMMENTS TO UNIT 310 MATERIAL SELECTION DIAGRAM | REF.: CON-BMP-TRA-070024 | CON RESPONSE REQUIRED
BMP-SOC-TRE-000045 | 2018-05-10 | COMMENTS TO MATERIAL REQUISITION FOR RECIPROCATING COMPRESSOR | REF.: CON-BMP-TRA-070048 | CON RESPONSE REQUIRED
BMP-SOC-TRE-000046 | 2018-05-11 | COMMENTS TO BASIS OF DESIGN UNIT 036-037-041-042-043-044-045-046-047-048-049 | REF.: CON-BMP-TRA-070038 | CON RESPONSE REQUIRED
BMP-SOC-TRE-000047 | 2018-05-11 | COMMENTS TO UNIT 098 PROCESS DESIGN BASIS | REF.: CON-BMP-TRA-070049 | CON RESPONSE REQUIRED
BMP-SOC-TRE-000048 | 2018-05-16 | COMMENTS TO UNIT 042 MATERIAL SELECTION DIAGRAM | REF.: CON-BMP-TRA-070051 | CON RESPONSE REQUIRED
BMP-SOC-TRE-000049 | 2018-05-16 | COMMENTS TO UNIT 043 MATERIAL SELECTION DIAGRAM | REF.: CON-BMP-TRA-070052 | CON RESPONSE REQUIRED
BMP-SOC-TRE-000050 | 2018-05-16 | COMMENTS TO UNIT 041 MATERIAL SELECTION DIAGRAM | REF.: CON-BMP-TRA-070050 | CON RESPONSE REQUIRED
BMP-SOC-TRE-000051 | 2018-05-16 | COMMENTS TO UNIT 047 MATERIAL SELECTION DIAGRAM | REF.: CON-BMP-TRA-070055 | CON RESPONSE REQUIRED
BMP-SOC-TRE-000052 | 2018-05-16 | COMMENTS TO UNIT 046 MATERIAL SELECTION DIAGRAM | REF.: CON-BMP-TRA-070054 | CON RESPONSE REQUIRED
BMP-SOC-TRE-000053 | 2018-05-16 | COMMENTS TO UNIT 098 MATERIAL SELECTION DIAGRAM | REF.: CON-BMP-TRA-070058 | CON RESPONSE REQUIRED
BMP-SOC-TRE-000054 | 2018-05-17 | COMMENTS TO UNIT 045 MATERIAL SELECTION DIAGRAM | REF.: CON-BMP-TRA-070053 | CON RESPONSE REQUIRED
BMP-SOC-TRE-000055 | 2018-05-17 | COMMENTS TO UNIT 088 MATERIAL SELECTION DIAGRAM | REF.: CON-BMP-TRA-070056 | CON RESPONSE REQUIRED
BMP-SOC-TRE-000056 | 2018-05-17 | COMMENTS TO UNIT 048 PROCESS FLOW DIAGRAM | REF.: CON-BMP-TRA-070074 | CON RESPONSE REQUIRED
BMP-SOC-TRE-000057 | 2018-05-17 | COMMENTS TO UNIT 094 MATERIAL SELECTION DIAGRAM | REF.: CON-BMP-TRA-070057 | CON RESPONSE REQUIRED
BMP-SOC-TRE-000058 | 2018-05-17 | COMMENTS TO UNIT 045 PROCESS FLOW DIAGRAM | REF.: CON-BMP-TRA-070072 | CON RESPONSE REQUIRED
BMP-SOC-TRE-000059 | 2018-05-17 | COMMENTS TO UNIT 048 PROCESS FLOW DIAGRAM | REF.: CON-BMP-TRA-070073 | CON RESPONSE REQUIRED
BMP-SOC-TRE-000060 | 2018-05-17 | COMMENTS TO UNIT 044 PROCESS FLOW DIAGRAM | REF.: CON-BMP-TRA-070071 | CON RESPONSE REQUIRED
BMP-SOC-TRE-000061 | 2018-05-17 | COMMENTS TO UNIT 036 PROCESS FLOW DIAGRAM | REF.: CON-BMP-TRA-070069 | CON RESPONSE REQUIRED
BMP-SOC-TRE-000062 | 2018-05-17 | COMMENTS TO UNIT 037 PROCESS FLOW DIAGRAM | REF.: CON-BMP-TRA-070070 | CON RESPONSE REQUIRED
BMP-SOC-TRE-000063 | 2018-05-18 | COMMENTS TO UNIT 341 - MATERIAL SELECTION DIAGRAM | REF.: CON-BMP-TRA-070059 | CON RESPONSE REQUIRED
BMP-SOC-TRE-000064 | 2018-05-18 | COMMENTS TO UNIT 378 - MATERIAL SELECTION DIAGRAM | REF.: CON-BMP-TRA-070060 | CON RESPONSE REQUIRED
BMP-SOC-TRE-000065 | 2018-05-18 | COMMENTS TO UNIT 356 - MATERIAL SELECTION DIAGRAM | REF.: CON-BMP-TRA-070065 | CON RESPONSE REQUIRED
BMP-SOC-TRE-000066 | 2018-05-18 | COMMENTS TO UNIT 357 - MATERIAL SELECTION DIAGRAM | REF.: CON-BMP-TRA-070066 | CON RESPONSE REQUIRED
BMP-SOC-TRE-000068 | 2018-05-20 | COMMENTS TO UNIT 357 - PROCESS FLOW DIAGRAM | REF.: CON-BMP-TRA-070062 | CON RESPONSE REQUIRED
BMP-SOC-TRE-000069 | 2018-05-20 | COMMENTS TO UNIT 358 - PROCESS FLOW DIAGRAM | REF.: CON-BMP-TRA-070063 | CON RESPONSE REQUIRED
BMP-SOC-TRE-000070 | 2018-05-20 | COMMENTS TO UNIT 037 - MATERIAL SELECTION DIAGRAM | REF.: CON-BMP-TRA-070078 | CON RESPONSE REQUIRED
BMP-SOC-TRE-000071 | 2018-05-20 | COMMENTS TO UNIT 036 - MATERIAL SELECTION DIAGRAM | REF.: CON-BMP-TRA-070077 | CON RESPONSE REQUIRED
BMP-SOC-TRE-000072 | 2018-05-20 | COMMENTS TO UNIT 048 - MATERIAL SELECTION DIAGRAM | REF.: CON-BMP-TRA-070080 | CON RESPONSE REQUIRED
BMP-SOC-TRE-000073 | 2018-05-21 | COMMENTS TO 049 MATERIAL SELECTION DIAGRAM | REF.: CON-BMP-TRA-070081 | CON RESPONSE REQUIRED
BMP-SOC-TRE-000074 | 2018-05-21 | COMMENTS TO UNIT-044 - MATERIAL SELECTION DIAGRAM | REF.: CON-BMP-TRA-070079 | CON RESPONSE REQUIRED
BMP-SOC-TRE-000075 | 2018-05-21 | COMMENTS TO UNIT 356 - PROCESS FLOW DIAGRAM | REF.: CON-BMP-TRA-070061 | CON RESPONSE REQUIRED
BMP-SOC-TRE-000076 | 2018-05-21 | COMMENTS TO UNIT-372 - MATERIAL SELECTION DIAGRAM | REF.: CON-BMP-TRA-070068 | CON RESPONSE REQUIRED
BMP-SOC-TRE-000077 | 2018-05-23 | COMMENTS TO UNIT-372 - PROCESS PLOW DIAGRAM | REF.: CON-BMP-TRA-070064 | CON RESPONSE REQUIRED
BMP-SOC-TRE-000078 | 2018-05-23 | COMMENTS TO UNIT 098 DATASHHET FOR HYDROGEN PSA | REF.: CON-BMP-TRA-070075 | CON RESPONSE REQUIRED
BMP-SOC-TRE-000079 | 2018-05-23 | COMMENTS TO UNIT 099 DATASHHET FOR HYDROGEN PSA | REF.: CON-BMP-TRA-070076 | CON RESPONSE REQUIRED