## Sheet1
al
|  | TPIT Proj. N° | 076551C
|  | Project | BAPCO MODERNIZATION PROGRAM
|  | Client | BAPCO
Material Requisition | MR Description | Vendor | Tag | Document Code | Doc. Client Code | Doc. Description | RD Code | Rev. | Issue Type | Date | Trasmittal | Transmittal Date | Action | Expected Date | Response Date | Comments | Discipline
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0001 | B-8787-8790-20-1 | 018-F-INX-00001-001 | LIST OF VENDOR'S DOCUMENTS AND DWGS ALL ITEMS | A0001 | AX | 4 | 2018-12-18 | CON-BMP-VTRA-010159 | 2018-12-18 | FOR BAPCO REVIEW | 2019-01-03 | 2019-01-09 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000100 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0001 | B-8787-8790-20-4 | 018-F-GAD-40046-001 | DRAWING GENERAL NOTES OF FABRICATION ALL ITEMS | A2007 | 0X | 3 | 2019-05-02 | CON-BMP-VTRA-011351 | 2019-05-02 | FOR BAPCO REVIEW | 2019-05-17 | 2019-05-22 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000727 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0001 | B-8787-8790-22-1 | 018-F-PLD-40081-001 | TYPICAL STANDARD DETAILS FOR PLATFORM STAIR HANDRAIL AND LADDER ALL ITEMS | A2008 | BX | 2 | 2019-05-02 | CON-BMP-VTRA-011360 | 2019-05-02 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0001 | B-8787-8790-31-1 | 018-F-ITP-40001-001 | INSPECTION & TEST PLAN HEATER STEELWORKS PREFABRICATION ALL ITEMS | B1002 | 0X | 3 | 2019-05-07 | CON-BMP-VTRA-011460 | 2019-05-07 | FOR BAPCO REVIEW | 2019-05-21 | 2019-06-20 | 1-APPROVED BMP-ROC-VTRE-001007 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0001 | B-8787-8790-31-10 | 018-F-ITP-40003-001 | INSPECTION & TEST PLAN STATIC CASTINGS ALL ITEMS | B1002 | 0X | 3 | 2019-05-07 | CON-BMP-VTRA-011460 | 2019-05-07 | FOR BAPCO REVIEW | 2019-05-21 | 2019-06-20 | 1-APPROVED BMP-ROC-VTRE-001007 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0001 | B-8787-8790-31-11 | 018-F-ITP-40004-001 | INSPECTION & TEST PLAN BURNERS ALL ITEMS | B1002 | 0X | 3 | 2019-05-07 | CON-BMP-VTRA-011460 | 2019-05-07 | FOR BAPCO REVIEW | 2019-05-21 | 2019-06-20 | 1-APPROVED BMP-ROC-VTRE-001007 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0001 | B-8787-8790-31-12 | 018-F-ITP-40005-001 | INSPECTION & TEST PLAN LOOSE INSTRUMENTATION ALL ITEMS | B1002 | 0X | 3 | 2019-05-07 | CON-BMP-VTRA-011460 | 2019-05-07 | FOR BAPCO REVIEW | 2019-05-21 | 2019-06-20 | 1-APPROVED BMP-ROC-VTRE-001007 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0001 | B-8787-8790-31-13 | 018-F-ITP-40006-001 | INSPECTION & TEST PLAN CASTABLE INSTALL. & FIBRES INSTALL. ALL ITEMS | B1002 | 0X | 3 | 2019-05-07 | CON-BMP-VTRA-011460 | 2019-05-07 | FOR BAPCO REVIEW | 2019-05-21 | 2019-06-20 | 1-APPROVED BMP-ROC-VTRE-001007 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0001 | B-8787-8790-31-9 | 018-F-ITP-40002-001 | INSPECTION & TEST PLAN - 1RHCU FINNING OF TUBES ALL ITEMS | B1002 | 0X | 3 | 2019-04-16 | CON-BMP-VTRA-011190 | 2019-04-16 | FOR BAPCO REVIEW | 2019-04-30 | 2019-04-29 | 1-APPROVED BMP-ROC-VTRE-000614 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0001 | B-8787-8790-32-1 | 018-F-MCD-40001-001 | WELDING BOOK HEATERS STRUCTURES PREFABRICATION ALL ITEMS | B1304 | CX | 2 | 2019-05-17 | CON-BMP-VTRA-011672 | 2019-05-17 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0001 | B-8787-8790-32-6 | 018-F-MCD-40002-001 | WELDING BOOK FINNING OF TUBES ALL ITEMS | B1304 | 0X | 3 | 2019-06-13 | CON-BMP-VTRA-012196 | 2019-06-13 | FOR BAPCO REVIEW | 2019-06-28 | 2019-06-29 | 1-APPROVED BMP-ROC-VTRE-001080 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0001 | B-8787-8790-32-7 | 018-F-MCD-40003-001 | WELDING BOOK BURNERS ALL ITEMS | B1304 | AX | 1 | 2019-01-28 | CON-BMP-VTRA-010294 | 2019-01-28 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0001 | B-8787-8790-33-1 | 018-F-PRO-40003-001 | PROCEDURE - HEATER STEELWORKS TRIAL ASSEMBLING ALL ITEMS | B1103 | AX | 2 | 2019-04-10 | CON-BMP-VTRA-011096 | 2019-04-10 | FOR BAPCO REVIEW | 2019-04-24 | 2019-04-28 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000602 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0001 | B-8787-8790-33-10 | 018-F-PRO-40004-001 | PROCEDURE HYDROSTATIC TEST (COILS & MANIFOLDS) ALL ITEMS | B1103 | 0X | 3 | 2019-06-28 | CON-BMP-VTRA-012541 | 2019-06-28 | FOR BAPCO REVIEW | 2019-07-12 | 2019-07-11 | 1-APPROVED BMP-ROC-VTRE- 001297 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0001 | B-8787-8790-33-12 | 018-F-TSP-40003-001 | PROCEDURE 1RHCU - BURNERS PAINTING ALL ITEMS | A0106 | BX | 2 | 2019-06-20 | CON-BMP-VTRA-012314 | 2019-06-20 | FOR INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0001 | B-8787-8790-33-13 | 018-F-PRO-40001-001 | PROCEDURE REFRACTORY CASTABLE AND FIBRES INSTALLATION ALL ITEMS | A1201 | 0X | 3 | 2019-06-19 | CON-BMP-VTRA-012312 | 2019-06-19 | FOR BAPCO REVIEW | 2019-07-04 | 2019-07-10 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001272 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0001 | B-8787-8790-33-14 | 018-F-PRO-40006-001 | PROCEDURE TRACEABILITY & MARKING OF COMPONENTS AND/OR PRESSURE SYSTEMS ALL ITEMS | B1103 | 0X | 3 | 2019-06-28 | CON-BMP-VTRA-012541 | 2019-06-28 | FOR BAPCO REVIEW | 2019-07-12 | 2019-07-11 | 1-APPROVED BMP-ROC-VTRE- 001297 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0001 | B-8787-8790-33-15 | 018-F-SIN-40001-001 | PROCEDURE PACKING AND PRESERVATION ALL ITEMS | A5001 | 0X | 3 | 2019-06-19 | CON-BMP-VTRA-012310 | 2019-06-19 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0001 | B-8787-8790-33-2 | 018-F-TSP-40001-001 | PROCEDURE JOB PAINTING AND COLOUR SUMMARY TABLE ALL ITEMS | A1016 | BX | 2 | 2019-03-05 | CON-BMP-VTRA-010585 | 2019-03-05 | FOR BAPCO REVIEW | 2019-03-20 | 2019-03-14 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000299 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0001 | B-8787-8790-33-3 | 018-F-TSP-40002-001 | PROCEDURE 1RHCU - HEATERS STEELWORKS PAINTING ALL ITEMS | A0106 | BX | 2 | 2019-06-20 | CON-BMP-VTRA-012314 | 2019-06-20 | FOR INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0001 | B-8787-8790-33-4 | 018-F-PRO-40008-001 | PROCEDURE 1RHCU - GAMMA RAY EXAMINATION OF WELDS (COILS AND MANIFOLDS) ALL ITEMS | B1202 | 0X | 3 | 2019-05-08 | CON-BMP-VTRA-011470 | 2019-05-08 | FOR BAPCO REVIEW | 2019-05-22 | 2019-05-27 | 1-APPROVED BMP-ROC-VTRE-000798 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0001 | B-8787-8790-33-5 | 018-F-PRO-40009-001 | PROCEDURE 1RHCU DYE PENETRANT EXAMINATION OF WELDS (COILS AND MANIFOLDS) ALL ITEMS | B1202 | 0AX | 3 | 2019-05-07 | CON-BMP-VTRA-011458 | 2019-05-07 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0001 | B-8787-8790-33-6 | 018-F-PRO-40012-001 | PROCEDURE 1RHCU-POSITIVE MATERIAL IDENTIFICATION OF MATERIALS AND WELDS(COILS AND MANIFOLDS) ALL ITEMS | B1204 | 0X | 3 | 2019-07-05 | CON-BMP-VTRA-012685 | 2019-07-05 | FOR BAPCO REVIEW | 2019-07-19 |  |  | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0001 | B-8787-8790-33-7 | 018-F-PRO-40007-001 | PROCEDURE PWHT MATERIAL AND WELDS (COILS AND MANIFOLDS) ALL ITEMS | B1201 | 0X | 3 | 2019-07-05 | CON-BMP-VTRA-012684 | 2019-07-05 | FOR BAPCO REVIEW | 2019-07-19 |  |  | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0001 | B-8787-8790-33-8 | 018-F-PRO-40010-001 | PROCEDURE 1RHCU-HARDNESS TEST (COILS AND MANIFOLDS) ALL ITEMS | B1202 | 0X | 3 | 2019-07-02 | CON-BMP-VTRA-012621 | 2019-07-02 | FOR BAPCO REVIEW | 2019-07-17 |  |  | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0001 | B-8787-8790-33-9 | 018-F-PRO-40011-001 | PROCEDURE 1RHCU-FERRITE INSPECTION (COILS AND MANIFOLDS) ALL ITEMS | B1202 | 0X | 3 | 2019-07-02 | CON-BMP-VTRA-012621 | 2019-07-02 | FOR BAPCO REVIEW | 2019-07-17 |  |  | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0001 | B-8787-8790-80-1 | 018-F-MRS-40001-001 | REPORT 1RHCU HEATERS VENDOR MONTHLY PROGRESS REPORT ALL ITEMS (EX BAPCO N.018-FMRS-00001-001) | C1002 | GX | 3 | 2019-06-19 | CON-BMP-VTRA-012308 | 2019-06-19 | FOR BAPCO REVIEW | 2019-07-04 |  |  | CLASS 3
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0001 | B-8787-8790-80-2 | 018-F-INV-40001-001 | 1RHCU - UN-PRICED COPY OF MAIN SUBORDERS ALL ITEMS (EX BAPCO N.018-F-INV-00001-001) | C1005 | EX | 4 | 2019-05-15 | CON-BMP-VTRA-011587 | 2019-05-15 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0001 | B-8787-8790-80-3 | 018-F-PLN-00001-001 | JOB QUALITY ASSURANCE PLAN ALL ITEMS | B1001 | AX | 3 | 2018-12-12 | CON-BMP-VTRA-010147 | 2018-12-12 | FOR BAPCO REVIEW | 2018-12-27 | 2019-01-09 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000093 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0001 | B-8787-8790-80-4 | 018-F-SCH-40001-001 | 1RHCU HEATERS - ENGINEERING PROCUREMENT MANIFACT. & TEST SHCEDULE ALL ITEMS (EX BAPCO N. 018-F-SCH-00001-001) | C1001 | 0CX | 4 | 2019-06-19 | CON-BMP-VTRA-012309 | 2019-06-19 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0001 | B-8789-11-1 | 018-F-GAD-40176-001 | ATM COLUMN FEED FURNACE HEATER GENERAL ASSEMBLY - ELEVATION 1 018F0001 | A2001 | 0X | 3 | 2019-04-26 | CON-BMP-VTRA-011272 | 2019-04-26 | FOR BAPCO REVIEW | 2019-05-14 | 2019-05-17 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000696 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0001 | B-8789-11-1 SHEET 2 | 018-F-GAD-40176-002 | ATM COLUMN FEED FURNACE HEATER GENERAL ASSEMBLY - ELEVATION -2 018F0001 | A2001 | 0X | 3 | 2019-04-26 | CON-BMP-VTRA-011272 | 2019-04-26 | FOR BAPCO REVIEW | 2019-05-14 | 2019-05-17 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000696 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0001 | B-8789-11-2 SHEET 1 | 018-F-GAD-40278-001 | ATM COLUMN FEED FURNACE HEATER GENERAL ASSEMBLY PLANS 1 018F0001 | A2001 | 0AX | 3 | 2019-06-28 | CON-BMP-VTRA-012543 | 2019-06-28 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0001 | B-8789-11-2 SHEET 2 | 018-F-GAD-40278-002 | ATM COLUMN FEED FURNACE HEATER GENERAL ASSEMBLY PLANS 2 018F0001 | A2001 | 0X | 3 | 2019-04-26 | CON-BMP-VTRA-011272 | 2019-04-26 | FOR BAPCO REVIEW | 2019-05-14 | 2019-05-17 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000696 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0001 | B-8789-11-2 SHEET 3 | 018-F-GAD-40278-003 | ATM COLUMN FEED FURNACE HEATER GENERAL ASSEMBLY PLANS 3 018F0001 | A2001 | 0X | 3 | 2019-04-26 | CON-BMP-VTRA-011272 | 2019-04-26 | FOR BAPCO REVIEW | 2019-05-14 | 2019-05-17 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000696 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0001 | B-8789-11-2 SHEET 4 | 018-F-GAD-40278-004 | ATM COLUMN FEED FURNACE HEATER GENERAL ASSEMBLY PLANS 4 018F0001 | A2001 | 0AX | 3 | 2019-06-28 | CON-BMP-VTRA-012542 | 2019-06-28 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0001 | B-8789-12-1 SHEET 1 | 018-F-PED-40003-001 | HEATER GENERAL FOUNDATIONS AND LOADS 018F0001 (EX BAPCO N.018-F-PED-00003-001) | A2006 | 0X | 3 | 2019-04-08 | CON-BMP-VTRA-011052 | 2019-04-08 | FOR BAPCO REVIEW | 2019-04-23 | 2019-04-25 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000582 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0001 | B-8789-12-2 SHEET 1 | 018-F-PED-40008-001 | HEATER GENERAL FOUNDATIONS - DETAILS 018F0001 (EX BAPCO N.018-F-PED-00008-001) | A2006 | 0X | 3 | 2019-04-08 | CON-BMP-VTRA-011052 | 2019-04-08 | FOR BAPCO REVIEW | 2019-04-23 | 2019-04-25 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000582 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0001 | B-8789-13-1 SH.1 | 018-F-GAD-40123-001 | RADIANT COIL 018F0001 | A1103 | 0X | 3 | 2019-05-21 | CON-BMP-VTRA-011696 | 2019-05-21 | FOR BAPCO REVIEW | 2019-06-05 | 2019-06-06 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000886 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0001 | B-8789-13-1 SH.2 | 018-F-GAD-40123-002 | RADIANT COIL 018F0001 | A1103 | 0X | 3 | 2019-05-21 | CON-BMP-VTRA-011696 | 2019-05-21 | FOR BAPCO REVIEW | 2019-06-05 | 2019-06-06 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000886 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0001 | B-8789-13-2 SH.1 | 018-F-GAD-40279-001 | ATM COLUMN FEED FURNACE CONVECTION COIL 018F0001 | A1103 | 0X | 3 | 2019-05-21 | CON-BMP-VTRA-011696 | 2019-05-21 | FOR BAPCO REVIEW | 2019-06-05 | 2019-06-06 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000886 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0001 | B-8789-13-2 SH.2 | 018-F-GAD-40279-002 | ATM COLUMN FEED FURNACE CONVECTION COIL 018F0001 | A1103 | 0X | 3 | 2019-05-21 | CON-BMP-VTRA-011696 | 2019-05-21 | FOR BAPCO REVIEW | 2019-06-05 | 2019-06-06 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000886 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0001 | B-8789-13-3 SH.1 | 018-F-GAD-40280-001 | SSH CONVECTION COIL 018F0001 | A1103 | 0X | 3 | 2019-05-21 | CON-BMP-VTRA-011696 | 2019-05-21 | FOR BAPCO REVIEW | 2019-06-05 | 2019-06-06 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000886 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0001 | B-8789-13-3 SH.2 | 018-F-GAD-40280-002 | SSH CONVECTION COIL 018F0001 | A1103 | 0X | 3 | 2019-05-21 | CON-BMP-VTRA-011697 | 2019-05-21 | FOR BAPCO REVIEW | 2019-06-05 | 2019-06-06 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000887 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0001 | B-8789-13-3 SH.3 | 018-F-GAD-40280-003 | SSH CONVECTION COIL 018F0001 | A1103 | 0X | 3 | 2019-05-21 | CON-BMP-VTRA-011697 | 2019-05-21 | FOR BAPCO REVIEW | 2019-06-05 | 2019-06-06 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000887 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0001 | B-8789-14-1 SH.1 | 018-F-GAD-40124-001 | WELDING MAP RADIANT COIL 018F0001 | A1103 | BX | 2 | 2019-04-05 | CON-BMP-VTRA-011017 | 2019-04-05 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0001 | B-8789-14-2 SH.1 | 018-F-GAD-40285-001 | WELDING MAP CONVECTION COIL 018F0001 | A1103 | BX | 2 | 2019-04-05 | CON-BMP-VTRA-011017 | 2019-04-05 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0001 | B-8789-14-3 SH.1 | 018-F-GAD-40286-001 | WELDING MAP SSH CONVECTION COIL 018F0001 | A1103 | BX | 2 | 2019-04-05 | CON-BMP-VTRA-011017 | 2019-04-05 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0001 | B-8789-17-1 | 018-F-GAD-40117-001 | CASTING NOTES AND DETAILS 018F0001 | A1101 | 0X | 3 | 2019-04-08 | CON-BMP-VTRA-011039 | 2019-04-08 | FOR BAPCO REVIEW | 2019-04-23 | 2019-04-25 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000578 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0001 | B-8789-17-2 | 018-F-GAD-40171-001 | ATM COLUMN FEED FURNACE CASTING RADIANT SUPPORTS 018F0001 | A1101 | 0X | 3 | 2019-06-05 | CON-BMP-VTRA-011979 | 2019-06-05 | FOR BAPCO REVIEW | 2019-06-19 | 2019-06-29 | 5-RETAINED FOR INFORMATION BMP-ROC-VRE-001106 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0001 | B-8789-17-3 SH.1 | 018-F-GAD-40118-001 | INTERMEDIATE TUBE SHEETS CA-1 018F0001 | A1101 | 0X | 3 | 2019-04-08 | CON-BMP-VTRA-011039 | 2019-04-08 | FOR BAPCO REVIEW | 2019-04-23 | 2019-04-25 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000578 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0001 | B-8789-17-3 SH.2 | 018-F-GAD-40118-002 | INTERMEDIATE TUBE SHEETS CA-2 018F0001 | A1101 | 0X | 3 | 2019-04-08 | CON-BMP-VTRA-011039 | 2019-04-08 | FOR BAPCO REVIEW | 2019-04-23 | 2019-04-25 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000578 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0001 | B-8789-17-3 SH.3 | 018-F-GAD-40118-003 | INTERMEDIATE TUBE SHEETS CCA-3 018F0001 | A1101 | 0X | 3 | 2019-04-08 | CON-BMP-VTRA-011039 | 2019-04-08 | FOR BAPCO REVIEW | 2019-04-23 | 2019-04-25 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000578 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0001 | B-8789-17-3 SH.4 | 018-F-GAD-40118-004 | INTERMEDIATE TUBE SHEETS CA-4 018F0001 | A1101 | 0X | 3 | 2019-04-08 | CON-BMP-VTRA-011039 | 2019-04-08 | FOR BAPCO REVIEW | 2019-04-23 | 2019-04-25 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000578 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0001 | B-8789-19-1-7 | 018-F-INX-40008-001 | DATA SHEET UTILITIES CONSUMPTION LIST 018F0001/ 018F0003 | A4001 | AX | 2 | 2019-06-06 | CON-BMP-VTRA-012073 | 2019-06-06 | FOR BAPCO REVIEW | 2019-06-21 | 2019-07-01 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001127 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0001 | B-8789-19-3 | 018-F-MCD-40040-001 | INSTRUMENTATION SOFTWARE FREEZING PACKAGE 018F0001 | A3008 | AX | 2 | 2019-05-03 | CON-BMP-VTRA-011365 | 2019-05-03 | FOR BAPCO REVIEW | 2019-05-17 | 2019-05-25 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000760 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0001 | B-8789-21-1 | 018-F-GAD-40147-001 | FLOOR PANELS ASSEMBLY - 1 018F0001 | A1109 | 0X | 3 | 2019-04-10 | CON-BMP-VTRA-011100 | 2019-04-10 | FOR BAPCO REVIEW | 2019-04-25 | 2019-04-28 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000610 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0001 | B-8789-21-10 | 018-F-GAD-40159-001 | END TUBE SHEET CONVECTION I MODULE 018F0001 | A1109 | 0X | 3 | 2019-05-23 | CON-BMP-VTRA-011762 | 2019-05-23 | FOR BAPCO REVIEW | 2019-06-07 | 2019-06-16 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000930 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0001 | B-8789-21-11 | 018-F-GAD-40160-001 | CONVECTION II MODULE ASSEMBLY 018F0001 | A1109 | 0X | 3 | 2019-05-23 | CON-BMP-VTRA-011762 | 2019-05-23 | FOR BAPCO REVIEW | 2019-06-07 | 2019-06-16 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000930 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0001 | B-8789-21-12 | 018-F-GAD-40162-001 | END TUBE SHEET CONVECTION II MODULE 018F0001 | A1109 | 0X | 3 | 2019-05-23 | CON-BMP-VTRA-011762 | 2019-05-23 | FOR BAPCO REVIEW | 2019-06-07 | 2019-06-16 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000930 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0001 | B-8789-21-13 | 018-F-GAD-40163-001 | HEADER BOXES I MODULE ASSEMBLY 018F0001 | A1109 | 0X | 3 | 2019-05-23 | CON-BMP-VTRA-011762 | 2019-05-23 | FOR BAPCO REVIEW | 2019-06-07 | 2019-06-16 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000930 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0001 | B-8789-21-14 | 018-F-GAD-40164-001 | HEADER BOXES II MODULE ASSEMBLY 018F0001 | A1109 | 0X | 3 | 2019-05-23 | CON-BMP-VTRA-011762 | 2019-05-23 | FOR BAPCO REVIEW | 2019-06-07 | 2019-06-16 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000930 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0001 | B-8789-21-15 | 018-F-GAD-40165-001 | STEELSTRUCTURE FOR CONVECTION COILS AND MANIFOLDS SUPPORT: ASSEMBLY 018F0001 | A1109 | 0X | 3 | 2019-06-29 | CON-BMP-VTRA-012580 | 2019-06-29 | FOR BAPCO REVIEW | 2019-07-15 |  |  | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0001 | B-8789-21-16 | 018-F-GAD-40166-001 | ATM COLUMN FEED FOURNACE FLUE GAS DAMPER 018F0001 | A1109 | AX | 2 | 2019-06-05 | CON-BMP-VTRA-011993 | 2019-06-05 | FOR BAPCO REVIEW | 2019-06-19 |  |  | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0001 | B-8789-21-17 | 018-F-GAD-40167-001 | EXTERNAL STEELSTRUCTURE FOR SUPPORT FLUE GAS DUCT - 1 ATM COLUMN FEED FURNACE 018F0001 | A1109 | AX | 2 | 2019-05-03 | CON-BMP-VTRA-011370 | 2019-05-03 | FOR BAPCO REVIEW | 2019-05-17 | 2019-05-28 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000826 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0001 | B-8789-21-18 | 018-F-GAD-40168-001 | EXTERNAL STEELSTRUCTURE FOR SUPPORT FLUE GAS DUCT - 2 ATM COLUMN FEED FURNACE 018F0001 | A1109 | AX | 2 | 2019-05-03 | CON-BMP-VTRA-011370 | 2019-05-03 | FOR BAPCO REVIEW | 2019-05-17 | 2019-05-28 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000826 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0001 | B-8789-21-19 | 018-F-GAD-40169-001 | EXTERNAL STEELSTRUCTURE FOR SUPPORT FLUE GAS DUCT - 3 ATM COLUMN FEED FURNACE 018F0001 | A1109 | AX | 2 | 2019-05-03 | CON-BMP-VTRA-011370 | 2019-05-03 | FOR BAPCO REVIEW | 2019-05-17 | 2019-05-28 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000826 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0001 | B-8789-21-2 | 018-F-GAD-40148-001 | FLOOR PANLES ASSEMBLY - 2 018F0001 | A1109 | 0X | 3 | 2019-04-10 | CON-BMP-VTRA-011100 | 2019-04-10 | FOR BAPCO REVIEW | 2019-04-25 | 2019-04-28 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000610 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0001 | B-8789-21-20 | 018-F-GAD-40170-001 | BREECHING ASSEMBLY 018F0001 | A1109 | 0X | 3 | 2019-05-23 | CON-BMP-VTRA-011762 | 2019-05-23 | FOR BAPCO REVIEW | 2019-06-07 | 2019-06-16 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000930 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0001 | B-8789-21-21 | 018-F-GAD-40172-001 | FLUE GAS DUCT ASSEMBLY ATM COLUMN FEED FURNACE 018F0001 | A1109 | AX | 2 | 2019-05-03 | CON-BMP-VTRA-011370 | 2019-05-03 | FOR BAPCO REVIEW | 2019-05-17 | 2019-05-28 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000826 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0001 | B-8789-21-22 | 018-F-GAD-40174-001 | EXPANSION JOINT ASSEMBLY AND DETAILS ATM COLUMN FEED FURNACE 018F0001 | A1109 | AX | 2 | 2019-05-03 | CON-BMP-VTRA-011370 | 2019-05-03 | FOR BAPCO REVIEW | 2019-05-17 | 2019-05-28 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000826 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0001 | B-8789-21-23 | 018-F-GAD-40127-001 | ATM COLUMN FEED FURNACE FLUE GAS GUILLOTTINE FG-02 018F0001 | A1109 | BX | 2 | 2019-06-29 | CON-BMP-VTRA-012574 | 2019-06-29 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0001 | B-8789-21-3 | 018-F-GAD-40149-001 | RADIANT PANELS ASSEMBLY (LONGITUDINAL WALL) - 1 018F0001 | A1109 | 0X | 3 | 2019-04-10 | CON-BMP-VTRA-011100 | 2019-04-10 | FOR BAPCO REVIEW | 2019-04-25 | 2019-04-28 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000610 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0001 | B-8789-21-4 | 018-F-GAD-40150-001 | RADIANT PANELS ASSEMBLY (LONGITUDINAL WALL) - 2 018F0001 | A1109 | 0X | 3 | 2019-04-10 | CON-BMP-VTRA-011100 | 2019-04-10 | FOR BAPCO REVIEW | 2019-04-25 | 2019-04-28 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000610 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0001 | B-8789-21-5 | 018-F-GAD-40152-001 | RADIANT PANELS ASSEMBLY (LATERAL WALL) - 1 018F0001 | A1109 | 0X | 3 | 2019-04-10 | CON-BMP-VTRA-011100 | 2019-04-10 | FOR BAPCO REVIEW | 2019-04-25 | 2019-04-28 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000610 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0001 | B-8789-21-6 | 018-F-GAD-40153-001 | RADIANT PANELS SECTIONS (LATERAL WALL) 018F0001 | A1109 | 0X | 3 | 2019-04-10 | CON-BMP-VTRA-011100 | 2019-04-10 | FOR BAPCO REVIEW | 2019-04-25 | 2019-04-28 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000610 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0001 | B-8789-21-7 | 018-F-GAD-40155-001 | ARCH PANELS ASSEMBLY - 1 018F0001 | A1109 | 0X | 3 | 2019-04-10 | CON-BMP-VTRA-011100 | 2019-04-10 | FOR BAPCO REVIEW | 2019-04-25 | 2019-04-28 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000610 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0001 | B-8789-21-8 | 018-F-GAD-40156-001 | ARCH PANELS ASSEMBLY - 2 018F0001 | A1109 | 0X | 3 | 2019-04-10 | CON-BMP-VTRA-011100 | 2019-04-10 | FOR BAPCO REVIEW | 2019-04-25 | 2019-04-28 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000610 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0001 | B-8789-21-9 | 018-F-GAD-40157-001 | CONVECTION I MODULE ASSEMBLY 018F0001 | A1109 | 0X | 3 | 2019-05-23 | CON-BMP-VTRA-011762 | 2019-05-23 | FOR BAPCO REVIEW | 2019-06-07 | 2019-06-16 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000930 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0001 | B-8789-22-1 | 018-F-PLD-40034-001 | LOWER RADIANT PLATFORM ATM COLUMN FEED FURNACE 018F0001 | A2008 | 0AX | 3 | 2019-06-19 | CON-BMP-VTRA-012306 | 2019-06-19 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0001 | B-8789-22-10 | 018-F-PLD-40042-001 | STAIR ATM COLUMN FEED FURNACE 018F0001 | A2008 | 0AX | 3 | 2019-06-19 | CON-BMP-VTRA-012306 | 2019-06-19 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0001 | B-8789-22-2 | 018-F-PLD-40035-001 | INTERMEDIATE RADIANT PLATFORM 018F0001 | A2008 | 0X | 3 | 2019-05-02 | CON-BMP-VTRA-011347 | 2019-05-02 | FOR BAPCO REVIEW | 2019-05-16 | 2019-05-23 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000729 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0001 | B-8789-22-3 | 018-F-PLD-40036-001 | ARCH / CONVECTION PLATFORM ATM COLUMN FEED FURNACE 018F0001 | A2008 | 0AX | 3 | 2019-06-19 | CON-BMP-VTRA-012306 | 2019-06-19 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0001 | B-8789-22-4 | 018-F-PLD-40037-001 | BREECHING PLATFORM 018F0001 | A2008 | 0X | 3 | 2019-05-02 | CON-BMP-VTRA-011349 | 2019-05-02 | FOR BAPCO REVIEW | 2019-05-16 | 2019-05-23 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000725 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0001 | B-8789-22-5 | 018-F-PLD-40038-001 | BRFLUE GAS DUCT PLATFORM 018F0001 | A2008 | 0X | 3 | 2019-05-02 | CON-BMP-VTRA-011349 | 2019-05-02 | FOR BAPCO REVIEW | 2019-05-16 | 2019-05-23 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000725 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0001 | B-8789-22-7 | 018-F-PLD-40039-001 | ATM COLUMN FEED FURNACE 018F0001 VERTICAL LADDER RADIANT ZONE | A2008 | AX | 2 | 2019-06-29 | CON-BMP-VTRA-012569 | 2019-06-29 | FOR BAPCO REVIEW | 2019-07-15 |  |  | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0001 | B-8789-22-8 | 018-F-PLD-40040-001 | ATM COLUMN FEED FURNACE 018F0001 VERTICAL LADDER CONVECTION SECTION | A2008 | AX | 2 | 2019-06-29 | CON-BMP-VTRA-012569 | 2019-06-29 | FOR BAPCO REVIEW | 2019-07-15 |  |  | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0001 | B-8789-22-9 | 018-F-PLD-40041-001 | ATM COLUMN FEED FURNACE 018F0001 VERTICAL LADDER FOR DUCT | A2008 | AX | 2 | 2019-06-29 | CON-BMP-VTRA-012569 | 2019-06-29 | FOR BAPCO REVIEW | 2019-07-15 |  |  | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0001 | B-8789-23-1 | 018-F-PLD-40043-001 | GRATINGS FOR LOWER RADIANT PLATFORM 018F0001 | A2008 | 0AX | 3 | 2019-06-27 | CON-BMP-VTRA-012522 | 2019-06-27 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0001 | B-8789-23-2 | 018-F-PLD-40044-001 | GRATINGS FOR INTERMEDIATE RADIANT PLATFORM 018F0001 | A2008 | 0X | 3 | 2019-05-02 | CON-BMP-VTRA-011349 | 2019-05-02 | FOR BAPCO REVIEW | 2019-05-16 | 2019-05-23 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000725 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0001 | B-8789-23-3 | 018-F-PLD-40045-001 | GRATINGS FOR ARCH / CONVECTION PLATFORM ATM COLUMN FEED FURNACE 018F0001 | A2008 | 0AX | 3 | 2019-06-27 | CON-BMP-VTRA-012522 | 2019-06-27 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0001 | B-8789-23-4 | 018-F-PLD-40046-001 | GRATINGS FOR BREECHING PLATFORM 018F0001 | A2008 | 0X | 3 | 2019-05-02 | CON-BMP-VTRA-011349 | 2019-05-02 | FOR BAPCO REVIEW | 2019-05-16 | 2019-05-23 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000725 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0001 | B-8789-23-5 | 018-F-PLD-40047-001 | GRATINGS FOR BREECHING PLATFORM 018F0001 | A2008 | 0X | 3 | 2019-05-02 | CON-BMP-VTRA-011349 | 2019-05-02 | FOR BAPCO REVIEW | 2019-05-16 | 2019-05-23 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000725 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0001 | B-8789-24-1 | 018-F-GAD-40128-001 | ATM COLUMM FEED FURNACE 018F0001 ACCESS DOOR ON RTADIANT ZONE | A1109 | AX | 2 | 2019-05-23 | CON-BMP-VTRA-011765 | 2019-05-23 | FOR BAPCO REVIEW | 2019-06-07 | 2019-06-16 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000933 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0001 | B-8789-24-2 | 018-F-GAD-40129-001 | UNIT ATM COLUMN FEED FURNACE OBSERVATION DOOR FOR RADIANT (CAST IRON) 018F0001 | A1109 | 0X | 3 | 2019-05-23 | CON-BMP-VTRA-011751 | 2019-05-23 | FOR BAPCO REVIEW | 2019-06-07 | 2019-06-29 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001107 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0001 | B-8789-24-3 | 018-F-GAD-40130-001 | ATM COLUMM FEED FURNACE 018F0001 EXPLOSION DOOR | A1109 | AX | 2 | 2019-05-23 | CON-BMP-VTRA-011765 | 2019-05-23 | FOR BAPCO REVIEW | 2019-06-07 | 2019-06-16 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000933 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0001 | B-8789-24-4 | 018-F-GAD-40131-001 | UNIT ATM COLUMM FEED FURNACE 018F0001 INSPECTION DOOR FOR CONVECTION SECTION | A1109 | AX | 2 | 2019-05-30 | CON-BMP-VTRA-011865 | 2019-05-30 | FOR BAPCO REVIEW | 2019-06-14 | 2019-06-17 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000994 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0001 | B-8789-24-5 | 018-F-GAD-40132-001 | UNIT ATM COLUMM FEED FURNACE 018F0001 ACCESS DOOR FOR BREECHING | A1109 | AX | 2 | 2019-05-30 | CON-BMP-VTRA-011865 | 2019-05-30 | FOR BAPCO REVIEW | 2019-06-14 | 2019-06-17 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000994 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0001 | B-8789-24-6 | 018-F-GAD-40133-001 | UNIT ATM COLUMM FEED FURNACE 018F0001 ACCESS DOOR FOR FLUE GAS DUCT | A1109 | AX | 2 | 2019-05-30 | CON-BMP-VTRA-011865 | 2019-05-30 | FOR BAPCO REVIEW | 2019-06-14 | 2019-06-17 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000994 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0001 | B-8789-25-1 | 018-F-GAD-40134-001 | ATM COLUMN FEED FURNACE INSTRUMENT CONNECTIONS 018F0001 | A1109 | 0AX | 3 | 2019-06-29 | CON-BMP-VTRA-012582 | 2019-06-29 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0001 | B-8789-25-2 | 018-F-DLB-40003-001 | UNIT ATM COLUMN FEED FURNACE NAMEPLATE 018F0001 | A1112 | 0X | 3 | 2019-06-20 | CON-BMP-VTRA-012337 | 2019-06-20 | FOR BAPCO REVIEW | 2019-07-05 | 2019-07-10 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001260 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0001 | B-8789-25-3 | 018-F-GAD-40135-001 | EARTHING LUG GENERAL ARRANGEMENT 018F0001 | A1109 | AX | 2 | 2019-03-01 | CON-BMP-VTRA-010559 | 2019-03-01 | FOR BAPCO REVIEW | 2019-03-18 | 2019-03-18 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000336 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0001 | B-8789-25-4 | 018-F-GAD-40136-001 | ATM COLUMN FEED FURNACE FIRE PROOFING GENERAL ASSEMBLY018F0001 | A1109 | 0X | 3 | 2019-04-11 | CON-BMP-VTRA-011112 | 2019-04-11 | FOR BAPCO REVIEW | 2019-04-25 | 2019-04-28 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000608 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0001 | B-8789-25-5 | 018-F-PLD-40080-001 | ATM COLUMN FEED FURNACE 018F0001 SAFETY BAR | A2008 | AX | 2 | 2019-06-29 | CON-BMP-VTRA-012569 | 2019-06-29 | FOR BAPCO REVIEW | 2019-07-15 |  |  | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0001 | B-8789-26-1 | 018-F-GAD-40119-001 | UNIT ATM COLUMN FEED FURNACE 018F0001 GENERAL ARRANGEMENT FOR LINING | A1101 | 0X | 3 | 2019-06-05 | CON-BMP-VTRA-011989 | 2019-06-05 | FOR BAPCO REVIEW | 2019-06-19 | 2019-06-29 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001085 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0001 | B-8789-26-4 | 018-F-GAD-40122-001 | ANCHORS FOR REFRACTORY ATM COLUMN FEED FURNACE 018F0001 | A1101 | 0X | 3 | 2019-05-23 | CON-BMP-VTRA-011763 | 2019-05-23 | FOR BAPCO REVIEW | 2019-06-07 | 2019-06-17 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000961 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0001 | B-8789-28-1 | 018-F-DAT-40009-001 | DATA SHEET 018F0001 HEATER DATA SHEET | A1001 | 0AX | 2 | 2019-07-10 | CON-BMP-VTRA-012795 | 2019-07-10 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0001 | B-8789-28-2 | 018-F-DAT-40010-001 | DATA SHEET BURNER DATA SHEET WITH CAPACITY CURVES AND NOISE DATA SHEET 018F0001 | A0105 | AX | 2 | 2019-02-06 | CON-BMP-VTRA-011442 | 2019-05-06 | FOR BAPCO REVIEW | 2019-05-21 | 2019-06-08 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000891 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0001 | B-8789-29-1 | 018-F-CAL-40015-001 | CALCULATION HEATER MAIN STRUCTURAL CALCULATION 018F0001 | A2201 | 0X | 3 | 2019-05-09 | CON-BMP-VTRA-011500 | 2019-05-09 | FOR BAPCO REVIEW | 2019-05-24 | 2019-05-29 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000830 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0001 | B-8789-29-2 | 018-F-CAL-40013-001 | LIFTING CALCULATION 018F0001 | A2201 | 0X | 3 | 2019-06-20 | CON-BMP-VTRA-012313 | 2019-06-20 | FOR INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0001 | B-8789-29-3 | 018-F-CAL-40011-001 | DATA SHEET REFRACTORY CALCULATION 018F0001 | A1303 | 0X | 3 | 2019-06-20 | CON-BMP-VTRA-012336 | 2019-06-20 | FOR BAPCO REVIEW | 2019-07-05 | 2019-07-10 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001269 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0001 | B-8789-29-4 | 018-F-CAL-40012-001 | CALCULATION 018F0001 COIL MECHANICAL CALCULATION (EX BAPCO N.018-F-CAL-00012-001) | A1304 | 0X | 3 | 2019-04-26 | CON-BMP-VTRA-011269 | 2019-04-26 | FOR BAPCO REVIEW | 2019-05-14 | 2019-05-18 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000701 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0001 | B-8789-29-5 | 018-F-CAL-40014-001 | CALCULATION CASTING CALCULATION 018F0001 | A2201 | 0X | 3 | 2019-04-29 | CON-BMP-VTRA-011294 | 2019-04-29 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0001 | B-8789-31-5 | 018-F-ITP-40017-001 | INSPECTION & TEST PLAN RADIANT COILS PREFABRICATION 018F0001 | B1002 | 0X | 3 | 2019-05-07 | CON-BMP-VTRA-011460 | 2019-05-07 | FOR BAPCO REVIEW | 2019-05-21 | 2019-06-20 | 1-APPROVED BMP-ROC-VTRE-001007 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0001 | B-8789-31-6 | 018-F-ITP-40018-001 | INSPECTION & TEST PLAN CONVECTION COILS PREFABRICATION 018F0001 | B1002 | 0X | 3 | 2019-05-07 | CON-BMP-VTRA-011460 | 2019-05-07 | FOR BAPCO REVIEW | 2019-05-21 | 2019-06-20 | 1-APPROVED BMP-ROC-VTRE-001007 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0001 | B-8789-32-4 | 018-F-MCD-40051-001 | WELDING BOOK RADIANT AND CONVECTION COILS PREFABRICATION 018F0001 | B1304 | 0X | 3 | 2019-06-04 | CON-BMP-VTRA-011947 | 2019-06-04 | FOR BAPCO REVIEW | 2019-06-19 | 2019-06-15 | 1-APPROVED BMP-ROC-VTRE-000926 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0001 | B-8789-35-1 | 018-F-GAD-40144-001 | ATM COLUMN FEED FURNACE BURNER GENERAL ASSEMBLY AND DETAILS 018F0001 | A1109 | AX | 2 | 2019-05-03 | CON-BMP-VTRA-011379 | 2019-05-03 | FOR BAPCO REVIEW | 2019-05-17 | 2019-05-24 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000759 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0001 | B-8789-70-1 | 018-F-S3D-40003-001 | 3D EQUIPMENT MODEL 018F0001 | A2013 | BX | 4 | 2019-03-27 | CON-BMP-VTRA-010882 | 2019-03-27 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0002 | B-8788-AB-24-2 | 018-F-GAD-40079-001 | RECYCLE HYDROGEN OBSERVATION DOOR FOR RADIANT (CAST IRON) 018F0002 018F2002 | A1109 | 0X | 3 | 2019-05-23 | CON-BMP-VTRA-011751 | 2019-05-23 | FOR BAPCO REVIEW | 2019-06-07 | 2019-06-29 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001107 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0002 | B-8790-11-1 SHEET 2 | 018-F-GAD-40242-002 | VACUUM COLUMN FEED FURNACE HEATER GENERAL ASSEMBLY ELEVATION - 2 018F0002 | A2001 | 0X | 3 | 2019-04-26 | CON-BMP-VTRA-011272 | 2019-04-26 | FOR BAPCO REVIEW | 2019-05-14 | 2019-05-17 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000696 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0002 | B-8790-11-1 SHEET1 | 018-F-GAD-40242-001 | VACUUM COLUMN FEED FURNACE HEATER GENERAL ASSEMBLY ELEVATION -1 018F0002 | A2001 | 0X | 3 | 2019-04-26 | CON-BMP-VTRA-011272 | 2019-04-26 | FOR BAPCO REVIEW | 2019-05-14 | 2019-05-17 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000696 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0002 | B-8790-11-2 SHEET 1 | 018-F-GAD-40301-001 | VACUUM COLUMN FEED FURNACE HEATER GENERAL ASSEMBLY PLANS 1 018F0002 | A2001 | 0X | 3 | 2019-04-26 | CON-BMP-VTRA-011272 | 2019-04-26 | FOR BAPCO REVIEW | 2019-05-14 | 2019-05-17 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000696 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0002 | B-8790-11-2 SHEET 2 | 018-F-GAD-40301-002 | VACUUM COLUMN FEED FURNACE HEATER GENERAL ASEMBLY PLANS 2 018F0002 | A2001 | 0X | 3 | 2019-04-26 | CON-BMP-VTRA-011272 | 2019-04-26 | FOR BAPCO REVIEW | 2019-05-14 | 2019-05-17 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000696 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0002 | B-8790-11-2 SHEET 3 | 018-F-GAD-40301-003 | VACUUM COLUMN FEED FURNACE HEATER GENERAL ASSEMBLY PLANS 3 018F0002 | A2001 | 0X | 3 | 2019-04-26 | CON-BMP-VTRA-011272 | 2019-04-26 | FOR BAPCO REVIEW | 2019-05-14 | 2019-05-17 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000696 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0002 | B-8790-11-2 SHEET 4 | 018-F-GAD-40301-004 | VACUUM COLUMN FEED FURNACE HEATER GENERAL ASSEMBLY PLANS 4 018F0002 | A2001 | 0X | 3 | 2019-04-26 | CON-BMP-VTRA-011272 | 2019-04-26 | FOR BAPCO REVIEW | 2019-05-14 | 2019-05-17 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000696 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0002 | B-8790-11-2 SHEET 5 | 018-F-GAD-40301-005 | VACUUM COLUMN FEED FURNACE HEATER GENERAL ASSEMBLY PLANS 5 018F0002 | A2001 | 0AX | 3 | 2019-06-28 | CON-BMP-VTRA-012542 | 2019-06-28 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0002 | B-8790-11-2 SHEET 6 | 018-F-GAD-40301-006 | VACUUM COLUMN FEED FURNACE HEATER GENERAL ASSEMBLY PLANS 6 018F0002 | A2001 | 0X | 3 | 2019-04-26 | CON-BMP-VTRA-011272 | 2019-04-26 | FOR BAPCO REVIEW | 2019-05-14 | 2019-05-17 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000696 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0002 | B-8790-12-1 | 018-F-PED-40004-001 | GENERAL FOUNDATION AND LOAD 018F0002 (EX 018-F-PED-00004-001) | A2006 | 0X | 3 | 2019-04-08 | CON-BMP-VTRA-011052 | 2019-04-08 | FOR BAPCO REVIEW | 2019-04-23 | 2019-04-25 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000582 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0002 | B-8790-12-2 | 018-F-PED-40009-001 | GENERAL FOUNDATIONS DETAILS 018F0002 (EX BAPCO N.018-FPED- 00009-001) | A2006 | 0X | 3 | 2019-04-08 | CON-BMP-VTRA-011052 | 2019-04-08 | FOR BAPCO REVIEW | 2019-04-23 | 2019-04-25 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000582 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0002 | B-8790-13-1 SH.1 | 018-F-GAD-40180-001 | RADIANT COIL 018F0002 | A1103 | 0X | 2 | 2019-05-21 | CON-BMP-VTRA-011697 | 2019-05-21 | FOR BAPCO REVIEW | 2019-06-05 | 2019-06-06 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000887 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0002 | B-8790-13-1 SH.2 | 018-F-GAD-40180-002 | RADIANT COIL 018F0002 | A1103 | 0X | 3 | 2019-05-21 | CON-BMP-VTRA-011697 | 2019-05-21 | FOR BAPCO REVIEW | 2019-06-05 | 2019-06-06 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000887 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0002 | B-8790-13-1 SH.3 | 018-F-GAD-40180-003 | RADIANT COIL 018F0002 | A1103 | 0X | 3 | 2019-05-21 | CON-BMP-VTRA-011697 | 2019-05-21 | FOR BAPCO REVIEW | 2019-06-05 | 2019-06-06 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000887 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0002 | B-8790-13-1 SH.4 | 018-F-GAD-40180-004 | RADIANT COIL 018F0002 | A1103 | 0X | 3 | 2019-05-21 | CON-BMP-VTRA-011697 | 2019-05-21 | FOR BAPCO REVIEW | 2019-06-05 | 2019-06-06 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000887 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0002 | B-8790-13-1 SH.5 | 018-F-GAD-40180-005 | RADIANT COIL 018F0002 | A1103 | 0X | 3 | 2019-05-21 | CON-BMP-VTRA-011697 | 2019-05-21 | FOR BAPCO REVIEW | 2019-06-05 | 2019-06-06 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000887 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0002 | B-8790-13-1 SH.6 | 018-F-GAD-40180-006 | RADIANT COIL 018F0002 | A1103 | 0X | 3 | 2019-05-21 | CON-BMP-VTRA-011697 | 2019-05-21 | FOR BAPCO REVIEW | 2019-06-05 | 2019-06-06 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000887 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0002 | B-8790-13-2 SH.1 | 018-F-GAD-40302-001 | VACUUM COLUMN FEED CONVECTION COIL 018F0002 | A1103 | 0X | 2 | 2019-05-21 | CON-BMP-VTRA-011697 | 2019-05-21 | FOR BAPCO REVIEW | 2019-06-05 | 2019-06-06 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000887 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0002 | B-8790-13-2 SH.2 | 018-F-GAD-40302-002 | VACUUM COLUMN FEED CONVECTION COIL 018F0002 | A1103 | 0X | 2 | 2019-05-21 | CON-BMP-VTRA-011697 | 2019-05-21 | FOR BAPCO REVIEW | 2019-06-05 | 2019-06-06 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000887 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0002 | B-8790-13-2 SH.3 | 018-F-GAD-40302-003 | VACUUM COLUMN FEED CONVECTION COIL 018F0002 | A1103 | 0X | 2 | 2019-05-21 | CON-BMP-VTRA-011697 | 2019-05-21 | FOR BAPCO REVIEW | 2019-06-05 | 2019-06-06 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000887 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0002 | B-8790-13-3 SH.1 | 018-F-GAD-40303-001 | MP SSH CONVECTION COIL 018F0002 | A1103 | 0X | 2 | 2019-05-21 | CON-BMP-VTRA-011697 | 2019-05-21 | FOR BAPCO REVIEW | 2019-06-05 | 2019-06-06 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000887 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0002 | B-8790-13-3 SH.2 | 018-F-GAD-40303-002 | MP SSH CONVECTION COIL 018F0002 | A1103 | 0X | 3 | 2019-05-21 | CON-BMP-VTRA-011696 | 2019-05-21 | FOR BAPCO REVIEW | 2019-06-05 | 2019-06-06 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000886 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0002 | B-8790-13-3 SH.3 | 018-F-GAD-40303-003 | MP SSH CONVECTION COIL 018F0002 | A1103 | 0X | 3 | 2019-05-21 | CON-BMP-VTRA-011696 | 2019-05-21 | FOR BAPCO REVIEW | 2019-06-05 | 2019-06-06 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000886 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0002 | B-8790-13-4 SH.1 | 018-F-GAD-40304-001 | LP SSH CONVECTION COIL 018F0002 | A1103 | 0X | 3 | 2019-05-21 | CON-BMP-VTRA-011697 | 2019-05-21 | FOR BAPCO REVIEW | 2019-06-05 | 2019-06-06 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000887 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0002 | B-8790-13-4 SH.2 | 018-F-GAD-40304-002 | LP SSH CONVECTION COIL 018F0002 | A1103 | 0X | 3 | 2019-05-21 | CON-BMP-VTRA-011697 | 2019-05-21 | FOR BAPCO REVIEW | 2019-06-05 | 2019-06-06 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000887 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0002 | B-8790-14-1 | 018-F-GAD-40181-001 | WELDING MAP RADIANT COIL 018F0002 | A1103 | BX | 2 | 2019-04-05 | CON-BMP-VTRA-011017 | 2019-04-05 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0002 | B-8790-14-2 | 018-F-GAD-40305-001 | WELDING MAP CONVECTION COIL 018F0002 | A1103 | BX | 2 | 2019-04-05 | CON-BMP-VTRA-011017 | 2019-04-05 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0002 | B-8790-14-3 | 018-F-GAD-40306-001 | WELDING MAP WELDING MAP MP SSH CONVECTION COIL 018F0002 | A1103 | BX | 2 | 2019-04-05 | CON-BMP-VTRA-011017 | 2019-04-05 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0002 | B-8790-14-4 | 018-F-GAD-40307-001 | WELDING MAP WELDING MAP LP SSH CONVECTION COIL 018F0002 | A1103 | BX | 2 | 2019-04-05 | CON-BMP-VTRA-011017 | 2019-04-05 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0002 | B-8790-17-1 SH.1 | 018-F-GAD-40178-001 | CASTING NOTES AND DETAILS 018F0002 | A1101 | 0X | 3 | 2019-04-08 | CON-BMP-VTRA-011039 | 2019-04-08 | FOR BAPCO REVIEW | 2019-04-23 | 2019-04-25 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000578 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0002 | B-8790-17-2 SH.1 | 018-F-GAD-40308-001 | UNIT VACUUM COLUMN FEED FURNACE 018F0002 RADIANT CASTING SUPPORTS FOR TUBE DN 4 VACUUM COLUMN FEED FURNACE | A1101 | 0X | 3 | 2019-05-23 | CON-BMP-VTRA-011750 | 2019-05-23 | FOR BAPCO REVIEW | 2019-06-06 | 2019-06-16 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000935 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0002 | B-8790-17-2 SH.2 | 018-F-GAD-40308-002 | UNIT VACUUM COLUMN FEED FURNACE 018F0002 RADIANT CASTING SUPPORTS FOR TUBE DN 6 VACUUM COLUMN FEED FURNACE | A1101 | 0X | 3 | 2019-05-23 | CON-BMP-VTRA-011750 | 2019-05-23 | FOR BAPCO REVIEW | 2019-06-06 | 2019-06-16 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000935 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0002 | B-8790-17-2 SH.3 | 018-F-GAD-40308-003 | UNIT VACUUM COLUMN FEED FURNACE 018F0002 RADIANT CASTING SUPPORTS FOR TUBE DN 8 VACUUM COLUMN FEED FURNACE | A1101 | 0X | 3 | 2019-05-23 | CON-BMP-VTRA-011750 | 2019-05-23 | FOR BAPCO REVIEW | 2019-06-06 | 2019-06-16 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000935 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0002 | B-8790-17-3 | 018-F-GAD-40309-001 | RADIANT CASTING U-BOLTS FOR ARCH TUBE DN 4 VACUUM COLUMN FEED FURNACE 018F0002 | A1101 | 0X | 3 | 2019-05-23 | CON-BMP-VTRA-011763 | 2019-05-23 | FOR BAPCO REVIEW | 2019-06-07 | 2019-06-17 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000961 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0002 | B-8790-17-4 SH.1 | 018-F-GAD-40233-001 | INTERMEDIATE TUBE SHEETS CA-1 018F0002 | A1101 | 0X | 3 | 2019-04-08 | CON-BMP-VTRA-011039 | 2019-04-08 | FOR BAPCO REVIEW | 2019-04-23 | 2019-04-25 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000578 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0002 | B-8790-17-4 SH.2 | 018-F-GAD-40233-002 | INTERMEDIATE TUBE SHEETS CA-2 018F0002 | A1101 | 0X | 3 | 2019-04-08 | CON-BMP-VTRA-011039 | 2019-04-08 | FOR BAPCO REVIEW | 2019-04-23 | 2019-04-25 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000578 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0002 | B-8790-17-4 SH.3 | 018-F-GAD-40233-003 | INTERMEDIATE TUBE SHEETS CA-3 018F0002 | A1101 | 0X | 3 | 2019-04-08 | CON-BMP-VTRA-011039 | 2019-04-08 | FOR BAPCO REVIEW | 2019-04-23 | 2019-04-25 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000578 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0002 | B-8790-17-4 SH.4 | 018-F-GAD-40233-004 | INTERMEDIATE TUBE SHEETS CA-4 018F0002 | A1101 | 0X | 3 | 2019-04-08 | CON-BMP-VTRA-011039 | 2019-04-08 | FOR BAPCO REVIEW | 2019-04-23 | 2019-04-25 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000578 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0002 | B-8790-19-1-7 | 018-F-INX-40009-001 | DATA SHEET UTILITIES CONSUMPTION LIST 018F0002 | A4001 | AX | 2 | 2019-06-06 | CON-BMP-VTRA-012073 | 2019-06-06 | FOR BAPCO REVIEW | 2019-06-21 | 2019-07-01 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001127 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0002 | B-8790-19-3 | 018-F-MCD-40054-001 | INSTRUMENTATION SOFTWARE FREEZING PACKAGE 018F0002 | A3008 | AX | 2 | 2019-05-03 | CON-BMP-VTRA-011365 | 2019-05-03 | FOR BAPCO REVIEW | 2019-05-17 | 2019-05-25 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000760 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0002 | B-8790-21-1 | 018-F-GAD-40206-001 | FLOOR PANELS ASSEMBLY CELL A 018F0002 | A1109 | AX | 2 | 2019-03-06 | CON-BMP-VTRA-010610 | 2019-03-06 | FOR BAPCO REVIEW | 2019-03-21 | 2019-03-26 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000377 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0002 | B-8790-21-10 | 018-F-GAD-40217-001 | UNIT VACUUM FEED FURNACE 018F0002 UPPER FLOOR PANELS ASSEMBLY - 2 | A1109 | 0X | 2 | 2019-05-30 | CON-BMP-VTRA-011857 | 2019-05-30 | FOR BAPCO REVIEW | 2019-06-14 | 2019-06-16 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000938 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0002 | B-8790-21-11 | 018-F-GAD-40219-001 | ARCH PANELS ASSEMBLY - 1 PLAN VIEW VACUUM COLUMN FEED FURNACE 018F0002 | A1109 | AX | 2 | 2019-05-03 | CON-BMP-VTRA-011370 | 2019-05-03 | FOR BAPCO REVIEW | 2019-05-17 | 2019-05-28 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000826 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0002 | B-8790-21-12 | 018-F-GAD-40220-001 | ARCH PANELS ASSEMBLY - 2 SECTIONS VACUUM COLUMN FEED FURNACE 018F0002 | A1109 | AX | 2 | 2019-05-03 | CON-BMP-VTRA-011370 | 2019-05-03 | FOR BAPCO REVIEW | 2019-05-17 | 2019-05-28 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000826 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0002 | B-8790-21-13 | 018-F-GAD-40222-001 | CONVECTION I MODULE ASSEMBLY VACUUM COLUMN FEED FURNACE 018F0002 | A1109 | AX | 2 | 2019-05-03 | CON-BMP-VTRA-011370 | 2019-05-03 | FOR BAPCO REVIEW | 2019-05-17 | 2019-05-28 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000826 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0002 | B-8790-21-14 | 018-F-GAD-40224-001 | END TUBE SHEET CONVECTION I MODULE VACUUM COLUMN FEED FURNACE 018F0002 | A1109 | AX | 2 | 2019-05-03 | CON-BMP-VTRA-011370 | 2019-05-03 | FOR BAPCO REVIEW | 2019-05-17 | 2019-05-28 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000826 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0002 | B-8790-21-15 | 018-F-GAD-40225-001 | CONVECTION II MODULE ASSEMBLY VACUUM COLUMN FEED FURNACE 018F0002 | A1109 | AX | 2 | 2019-05-03 | CON-BMP-VTRA-011370 | 2019-05-03 | FOR BAPCO REVIEW | 2019-05-17 | 2019-05-28 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000826 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0002 | B-8790-21-16 | 018-F-GAD-40227-001 | END TUBE SHEET CONVECTION II MODULE VACUUM COLUMN FEED FURNACE 018F0002 | A1109 | AX | 2 | 2019-05-03 | CON-BMP-VTRA-011370 | 2019-05-03 | FOR BAPCO REVIEW | 2019-05-17 | 2019-05-28 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000826 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0002 | B-8790-21-17 | 018-F-GAD-40228-001 | VACUUM COLUMN FEED FURNACE STEEL STRUCTURE FOR RADIANT COIL SUPPORT 018F0002 | A1109 | 0X | 3 | 2019-06-29 | CON-BMP-VTRA-012580 | 2019-06-29 | FOR BAPCO REVIEW | 2019-07-15 |  |  | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0002 | B-8790-21-19 | 018-F-GAD-40230-001 | HEADER BOXES I MODULE ASSEMBLY AND DETAILS VACUUM COLUMN FEED FURNACE 018F0002 | A1109 | AX | 2 | 2019-05-03 | CON-BMP-VTRA-011370 | 2019-05-03 | FOR BAPCO REVIEW | 2019-05-17 | 2019-05-28 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000826 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0002 | B-8790-21-2 | 018-F-GAD-40207-001 | FLOOR PANELS DETAILS CELL A 018F0002 | A1109 | AX | 2 | 2019-03-06 | CON-BMP-VTRA-010610 | 2019-03-06 | FOR BAPCO REVIEW | 2019-03-21 | 2019-03-26 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000377 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0002 | B-8790-21-20 | 018-F-GAD-40231-001 | UNIT VACUUM COLUMN FEED FURNACE HEADER BOXES II MODULE ASSEMBLY AND DETAILS 018F0002 | A1109 | 0X | 3 | 2019-06-05 | CON-BMP-VTRA-011983 | 2019-06-05 | FOR BAPCO REVIEW | 2019-06-19 | 2019-06-29 | 5-RETAINED FOR INFORMATION CON-BMP-VTRA-011983 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0002 | B-8790-21-21 | 018-F-GAD-40232-001 | BREECHING ASSEMBLY VACUUM COLUMN FEED FURNACE 018F0002 | A1109 | AX | 2 | 2019-05-03 | CON-BMP-VTRA-011370 | 2019-05-03 | FOR BAPCO REVIEW | 2019-05-17 | 2019-05-28 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000826 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0002 | B-8790-21-22 | 018-F-GAD-40234-001 | VACUUM COLUMN FEED FURNACE FLUE GAS DUCT ASSEMBLY 018F0002 | A1109 | 0X | 3 | 2019-06-20 | CON-BMP-VTRA-012329 | 2019-06-20 | FOR BAPCO REVIEW | 2019-07-04 | 2019-07-10 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001266 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0002 | B-8790-21-24 | 018-F-GAD-40237-001 | VACUUM COLUMN FEED FURNACE EXPANSION JOINT 018F0002 | A1109 | AX | 2 | 2019-05-07 | CON-BMP-VTRA-011457 | 2019-05-07 | FOR BAPCO REVIEW | 2019-05-21 | 2019-05-26 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000787 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0002 | B-8790-21-25 | 018-F-GAD-40238-001 | VACUUM COLUMN FEED FURNACE FLUE GAS GUILLOTTINE FG-03 018F0002 | A1109 | BX | 2 | 2019-06-29 | CON-BMP-VTRA-012576 | 2019-06-29 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0002 | B-8790-21-27 | 018-F-GAD-40235-001 | RADIANT PANELS ASSEMBLY CELL B 018F0002 | A1109 | 0X | 3 | 2019-04-11 | CON-BMP-VTRA-011111 | 2019-04-11 | FOR BAPCO REVIEW | 2019-04-25 | 2019-04-28 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000609 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0002 | B-8790-21-28 | 018-F-GAD-40240-001 | RADIANT PANELS DETAILS CELL B 018F0002 | A1109 | AX | 2 | 2019-03-06 | CON-BMP-VTRA-010610 | 2019-03-06 | FOR BAPCO REVIEW | 2019-03-21 | 2019-03-26 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000377 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0002 | B-8790-21-29 | 018-F-GAD-40226-001 | VACUUM COLUMN FEED FOURNACE FLUE GAS DAMPER 018F0002 | A1109 | AX | 2 | 2019-06-05 | CON-BMP-VTRA-011993 | 2019-06-05 | FOR BAPCO REVIEW | 2019-06-19 |  |  | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0002 | B-8790-21-3 | 018-F-GAD-40208-001 | FLOOR PANELS ASSEMBLY CELL B 018F0002 | A1109 | AX | 2 | 2019-03-06 | CON-BMP-VTRA-010610 | 2019-03-06 | FOR BAPCO REVIEW | 2019-03-21 | 2019-03-26 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000377 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0002 | B-8790-21-4 | 018-F-GAD-40209-001 | FLOOR PANELS DETAILS CELL B 018F0002 | A1109 | AX | 2 | 2019-03-06 | CON-BMP-VTRA-010610 | 2019-03-06 | FOR BAPCO REVIEW | 2019-03-21 | 2019-03-26 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000377 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0002 | B-8790-21-5 | 018-F-GAD-40210-001 | RADIANT PANELS ASSEMBLY CELL A 018F0002 | A1109 | AX | 2 | 2019-03-06 | CON-BMP-VTRA-010610 | 2019-03-06 | FOR BAPCO REVIEW | 2019-03-21 | 2019-03-26 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000377 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0002 | B-8790-21-6 | 018-F-GAD-40211-001 | RADIANT PANELS ASSEMBLY CELL A VACUUM COLUMN FEED FURNACE 018F0002 | A1109 | 0X | 3 | 2019-05-02 | CON-BMP-VTRA-011348 | 2019-05-02 | FOR BAPCO REVIEW | 2019-05-16 | 2019-05-23 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000745 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0002 | B-8790-21-7 | 018-F-GAD-40412-001 | RADIANT PANELS DETAILS CELL A 018F0002 | A1109 | AX | 2 | 2019-03-06 | CON-BMP-VTRA-010610 | 2019-03-06 | FOR BAPCO REVIEW | 2019-03-21 | 2019-03-26 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000377 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0002 | B-8790-21-8 | 018-F-GAD-40213-001 | RADIANT PANELS ASSEMBLY CELL B 018F0002 | A1109 | AX | 2 | 2019-03-06 | CON-BMP-VTRA-010610 | 2019-03-06 | FOR BAPCO REVIEW | 2019-03-21 | 2019-03-26 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000377 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0002 | B-8790-21-9 | 018-F-GAD-40216-001 | UNIT VACUUM COLUMN FEED FURNACE 018F0002 TOP RADIANT PANELS ASSEMBLY - 1 - ASSEMBLY | A1109 | 0X | 3 | 2019-05-30 | CON-BMP-VTRA-011867 | 2019-05-30 | FOR BAPCO REVIEW | 2019-06-14 | 2019-06-17 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000956 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0002 | B-8790-22-1 | 018-F-PLD-40050-001 | VACUUM COLUMN FEED FURNACE LOWER RADIANT PLATFORM 018F0002 | A2008 | AX | 2 | 2019-06-11 | CON-BMP-VTRA-012146 | 2019-06-11 | FOR BAPCO REVIEW | 2019-06-25 | 2019-07-02 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001139 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0002 | B-8790-22-2 | 018-F-PLD-40051-001 | VACUUM COLUMN FEED FURNACE INTERMEDIATE RADIANT PLATFORM 018F0002 | A2008 | AX | 2 | 2019-06-05 | CON-BMP-VTRA-011984 | 2019-06-05 | FOR BAPCO REVIEW | 2019-06-19 | 2019-06-30 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001101 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0002 | B-8790-22-3 | 018-F-PLD-40052-001 | VACUUM COLUMN FEED FURNACE TOP RADIANT PLATFORM 018F0002 | A2008 | AX | 2 | 2019-06-05 | CON-BMP-VTRA-011984 | 2019-06-05 | FOR BAPCO REVIEW | 2019-06-19 | 2019-06-30 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001101 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0002 | B-8790-22-6 | 018-F-PLD-40055-001 | VACCUM COLUMN FEED FURNACE BREECHING PLATFORM AT EL.+16608 018F0002 | A2008 | AX | 2 | 2019-06-05 | CON-BMP-VTRA-011984 | 2019-06-05 | FOR BAPCO REVIEW | 2019-06-19 | 2019-06-30 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001101 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0002 | B-8790-22-7 | 018-F-PLD-40056-001 | VACUUM COLUMN FEED FURNACE FLUE GAS DUCT PLATFORM AT EL.+18270 018F0002 | A2008 | AX | 2 | 2019-06-05 | CON-BMP-VTRA-011984 | 2019-06-05 | FOR BAPCO REVIEW | 2019-06-19 | 2019-06-30 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001101 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0002 | B-8790-22-9 | 018-F-PLD-40057-001 | UNIT VACUUM COLUMN FEED FURNACE 018F0002 STAIR | A2008 | AX | 2 | 2019-05-31 | CON-BMP-VTRA-011869 | 2019-05-31 | FOR BAPCO REVIEW | 2019-06-14 | 2019-06-17 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000974 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0002 | B-8790-23-1 | 018-F-PLD-40062-001 | VACUUM COLUMN FEED FURNACE GRATING FOR LOWER RADIANT PLATFORM 018F0002 | A2008 | AX | 2 | 2019-06-05 | CON-BMP-VTRA-011984 | 2019-06-05 | FOR BAPCO REVIEW | 2019-06-19 | 2019-06-30 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001101 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0002 | B-8790-23-2 | 018-F-PLD-40063-001 | VACUUM COLUMN FEED FURNACE GRATING FOR INTERMEDIATE RADIANT PLATFORM 018F0002 | A2008 | AX | 2 | 2019-06-05 | CON-BMP-VTRA-011984 | 2019-06-05 | FOR BAPCO REVIEW | 2019-06-19 | 2019-06-30 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001101 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0002 | B-8790-23-3 | 018-F-PLD-40064-001 | VACUUM COLUMN FEED FURNACE GRATING FOR TOP RADIANT PLATFORM 018F0002 | A2008 | AX | 2 | 2019-06-05 | CON-BMP-VTRA-011984 | 2019-06-05 | FOR BAPCO REVIEW | 2019-06-19 | 2019-06-30 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001101 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0002 | B-8790-23-6 | 018-F-PLD-40067-001 | VACUUM COLUMN FEED FURNACE GRATING FOR BREECHING PLATFORM 018F0002 | A2008 | AX | 2 | 2019-06-05 | CON-BMP-VTRA-011984 | 2019-06-05 | FOR BAPCO REVIEW | 2019-06-19 | 2019-06-30 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001101 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0002 | B-8790-23-7 | 018-F-PLD-40068-001 | VACUUM COLUMN FEDD FURNACE GRATING FOR FLUE GAS DUCT PLATFORM 018F0002 | A2008 | AX | 2 | 2019-06-05 | CON-BMP-VTRA-011984 | 2019-06-05 | FOR BAPCO REVIEW | 2019-06-19 | 2019-06-30 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001101 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0002 | B-8790-24-1 | 018-F-GAD-40186-001 | UNIT VACUUM COLUMN FEED FURNACE 018F0002 ACCESS DOOR ON RADIANT ZONE | A1109 | AX | 2 | 2019-05-30 | CON-BMP-VTRA-011865 | 2019-05-30 | FOR BAPCO REVIEW | 2019-06-14 | 2019-06-17 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000994 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0002 | B-8790-24-2 | 018-F-GAD-40187-001 | VACUUM COLUMN FEED FURNACE OBSERVATION DOOR FOR RADIANT (CAST IRON) 018F0002 | A1109 | 0X | 3 | 2019-06-05 | CON-BMP-VTRA-011981 | 2019-06-05 | FOR BAPCO REVIEW | 2019-06-19 | 2019-06-29 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-011981 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0002 | B-8790-24-3 | 018-F-GAD-40188-001 | UNIT VACUUM COLUMN FEED FURNACE 018F0002 EXPLOSION DOOR | A1109 | AX | 2 | 2019-05-30 | CON-BMP-VTRA-011865 | 2019-05-30 | FOR BAPCO REVIEW | 2019-06-14 | 2019-06-17 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000994 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0002 | B-8790-24-4 | 018-F-GAD-40189-001 | UNIT VACUUM COLUMN FEED FURNACE 018F0002 INSPECTION DOOR FOR CONVECTION SECTION | A1109 | AX | 2 | 2019-05-30 | CON-BMP-VTRA-011865 | 2019-05-30 | FOR BAPCO REVIEW | 2019-06-14 | 2019-06-17 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000994 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0002 | B-8790-24-6 | 018-F-GAD-40191-001 | UNIT VACUUM COLUMN FEED FURNACE 018F0002 ACCESS DOOR FOR FLUE GAS DUCT | A1109 | AX | 2 | 2019-05-30 | CON-BMP-VTRA-011865 | 2019-05-30 | FOR BAPCO REVIEW | 2019-06-14 | 2019-06-17 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000994 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0002 | B-8790-25-1 | 018-F-GAD-40192-001 | VACUUM COLUMN FEED FURNACE INSTRUMENT CONNECTIONS 018F0002 | A1109 | 0AX | 3 | 2019-06-20 | CON-BMP-VTRA-012339 | 2019-06-20 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0002 | B-8790-25-2 | 018-F-DLB-40004-001 | UNIT VACUUM COLUMN FEED FURNACE NAMEPLATE 018F0002 | A1112 | 0X | 3 | 2019-06-20 | CON-BMP-VTRA-012337 | 2019-06-20 | FOR BAPCO REVIEW | 2019-07-05 | 2019-07-10 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001260 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0002 | B-8790-25-3 | 018-F-GAD-40193-001 | EARTHING LUGS GENERAL ARRANGEMENT VACUUM COLUMN FEED FURNACE 018F0002 | A1109 | 0X | 3 | 2019-06-20 | CON-BMP-VTRA-012329 | 2019-06-20 | FOR BAPCO REVIEW | 2019-07-04 | 2019-07-10 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001266 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0002 | B-8790-26-1 | 018-F-GAD-40179-001 | UNIT VACUUM COLUMN FEED FURNACE 018F0002 GENERAL ARRANGEMENT FOR LININ | A1101 | 0X | 3 | 2019-06-05 | CON-BMP-VTRA-011989 | 2019-06-05 | FOR BAPCO REVIEW | 2019-06-19 | 2019-06-29 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001085 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0002 | B-8790-26-2 | 018-F-GAD-40311-001 | GENERAL ARRANGEMENT FOR LINING 2 018F0002 | A1101 | 0X | 3 | 2019-06-12 | CON-BMP-VTRA-012171 | 2019-06-12 | FOR BAPCO REVIEW | 2019-06-25 | 2019-07-03 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001156 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0002 | B-8790-26-4 | 018-F-GAD-40313-001 | ANCHORS FOR REFRACTORY VACUUM COLUMN FEED FURNACE 018F0002 | A1101 | 0X | 3 | 2019-05-23 | CON-BMP-VTRA-011763 | 2019-05-23 | FOR BAPCO REVIEW | 2019-06-07 | 2019-06-17 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000961 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0002 | B-8790-28-1 | 018-F-DAT-40011-001 | DATA SHEET 018F0002 HEATER DATA SHEET | A1001 | 0AX | 2 | 2019-07-10 | CON-BMP-VTRA-012795 | 2019-07-10 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0002 | B-8790-28-2 | 018-F-DAT-40012-001 | DATA SSHEET - BURNER DATA SHEET WITH CAPACITY CURVES AND NOISE DATA SHEET 018F0002 | A0105 | AX | 2 | 2019-02-06 | CON-BMP-VTRA-011442 | 2019-05-06 | FOR BAPCO REVIEW | 2019-05-21 | 2019-06-08 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000891 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0002 | B-8790-29-1 | 018-F-CAL-40018-001 | CALCULATION HEATER MAIN STRUCTURAL CALCULATION 018F0002 | A2201 | 0X | 3 | 2019-05-09 | CON-BMP-VTRA-011500 | 2019-05-09 | FOR BAPCO REVIEW | 2019-05-24 | 2019-05-29 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000830 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0002 | B-8790-29-2 | 018-F-CAL-40019-001 | LIFTING CALCULATION 018F0002 | A2201 | 0X | 3 | 2019-06-20 | CON-BMP-VTRA-012313 | 2019-06-20 | FOR INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0002 | B-8790-29-3 | 018-F-CAL-40016-001 | DATA SHEET REFRACTORY CALCULATION 018F0002 | A1303 | 0X | 3 | 2019-06-20 | CON-BMP-VTRA-012336 | 2019-06-20 | FOR BAPCO REVIEW | 2019-07-05 | 2019-07-10 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001269 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0002 | B-8790-29-4 | 018-F-CAL-40017-001 | CALCULATION 018F0002 COIL MECHANICAL CALC. (EX BAPCO N.018-F-CAL-00017-001) | A1304 | 0X | 3 | 2019-04-26 | CON-BMP-VTRA-011269 | 2019-04-26 | FOR BAPCO REVIEW | 2019-05-14 | 2019-05-18 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000701 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0002 | B-8790-29-5 | 018-F-CAL-40020-001 | CALCULATION CASTING CALCULATION 018F0002 | A2201 | 0X | 3 | 2019-04-29 | CON-BMP-VTRA-011294 | 2019-04-29 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0002 | B-8790-31-7 | 018-F-ITP-40019-001 | INSPECTION & TEST PLAN RADIANT COILS PREFABRICATION 018F0002 | B1002 | 0X | 3 | 2019-05-07 | CON-BMP-VTRA-011460 | 2019-05-07 | FOR BAPCO REVIEW | 2019-05-21 | 2019-06-20 | 1-APPROVED BMP-ROC-VTRE-001007 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0002 | B-8790-31-8 | 018-F-ITP-40020-001 | INSPECTION & TEST PLAN CONVECTION COILS PREFABRICATION 018F0002 | B1002 | 0X | 3 | 2019-05-07 | CON-BMP-VTRA-011460 | 2019-05-07 | FOR BAPCO REVIEW | 2019-05-21 | 2019-06-20 | 1-APPROVED BMP-ROC-VTRE-001007 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0002 | B-8790-32-5 | 018-F-MCD-40065-001 | WELDING BOOK RADIANT & CONV. COILS PREFABRICATION 018F0002 | B1304 | 0X | 3 | 2019-06-04 | CON-BMP-VTRA-011947 | 2019-06-04 | FOR BAPCO REVIEW | 2019-06-19 | 2019-06-15 | 1-APPROVED BMP-ROC-VTRE-000926 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0002 | B-8790-35-1 | 018-F-GAD-40204-001 | VACUUM COLUMN FEED FURNACE BURNER GENERAL ASSEMBLY AND DETAILS 018F0002 | A1109 | AX | 2 | 2019-05-03 | CON-BMP-VTRA-011379 | 2019-05-03 | FOR BAPCO REVIEW | 2019-05-17 | 2019-05-24 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000759 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0002 | B-8790-70-1 | 018-F-S3D-40004-001 | 3D EQUIPMENT MODEL 018F0002 | A2013 | AX | 4 | 2019-03-27 | CON-BMP-VTRA-010883 | 2019-03-27 | FOR BAPCO REVIEW | 2019-04-10 | 2019-04-10 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000496 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0003 | B-8789-8790-11-1 SHEET 1 | 018-F-GAD-40257-001 | GROUNDED SELF-SUPPORTED STACK GENERAL ASS.LY ELEVATIONS 018F0003 | A2001 | 0X | 3 | 2019-04-26 | CON-BMP-VTRA-011272 | 2019-04-26 | FOR BAPCO REVIEW | 2019-05-14 | 2019-05-17 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000696 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0003 | B-8789-8790-11-2 | 018-F-GAD-40248-001 | GROUNDED SELF SUPPORTED STACK GENERAL ASS.LY PLANS 1 018F0003 | A2001 | 0X | 3 | 2019-04-26 | CON-BMP-VTRA-011272 | 2019-04-26 | FOR BAPCO REVIEW | 2019-05-14 | 2019-05-17 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000696 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0003 | B-8789-8790-11-2 SHEET 2 | 018-F-GAD-40248-002 | GROUNDED SELF-SUPPORTED STACK GENERAL ASS.LY PLANS-2 018F0003 | A2001 | 0AX | 3 | 2019-06-28 | CON-BMP-VTRA-012542 | 2019-06-28 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0003 | B-8789-8790-12-1 SHEET 1 | 018-F-PED-40005-001 | GROUND SELF-SUPPORTED STACK TEMPLATE FOR FOUNDATIONS 018F0003 | A2006 | 0X | 3 | 2019-04-11 | CON-BMP-VTRA-011110 | 2019-04-11 | FOR BAPCO REVIEW | 2019-04-25 | 2019-04-28 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000599 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0003 | B-8789-8790-21-1 | 018-F-GAD-40246-001 | STACK MODULES STEELWORK DRAWING 1 018F0003 | A1109 | 0X | 3 | 2019-05-30 | CON-BMP-VTRA-011863 | 2019-05-30 | FOR BAPCO REVIEW | 2019-06-14 | 2019-06-17 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000955 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0003 | B-8789-8790-21-10 | 018-F-GAD-40252-001 | EARTHING LUG GENERAL ARRANGEMENT 018F0003 | A1109 | 0X | 3 | 2019-04-10 | CON-BMP-VTRA-011099 | 2019-04-10 | FOR BAPCO REVIEW | 2019-04-25 | 2019-04-28 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000605 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0003 | B-8789-8790-21-2 | 018-F-GAD-40247-001 | STACK MODULES STEELWORK DRAWING 2 018F0003 | A1109 | 0X | 3 | 2019-05-30 | CON-BMP-VTRA-011863 | 2019-05-30 | FOR BAPCO REVIEW | 2019-06-14 | 2019-06-17 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000955 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0003 | B-8789-8790-22-1 | 018-F-PLD-40072-001 | STACK PLATFORMS 018F0003 | A2008 | 0AX | 3 | 2019-06-19 | CON-BMP-VTRA-012306 | 2019-06-19 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0003 | B-8789-8790-22-2 | 018-F-PLD-40071-001 | PLATFORMS TYPICAL DETAILS 018F0003 | A2008 | 0AX | 3 | 2019-06-19 | CON-BMP-VTRA-012306 | 2019-06-19 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0003 | B-8789-8790-22-3 | 018-F-PLD-40073-001 | UNIT GROUND SELF-SUPPORTED STACK 018F0003 VERTICAL LADDERS | A2008 | 0X | 2 | 2019-05-30 | CON-BMP-VTRA-011866 | 2019-05-30 | FOR BAPCO REVIEW | 2019-06-14 | 2019-06-15 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000937 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0003 | B-8789-8790-23-1 | 018-F-PLD-40074-001 | GROUND SELF-SUPPORTED STACK GRATINGS FOR STACK PLATFORMS 018F0003 | A2008 | 0X | 3 | 2019-06-19 | CON-BMP-VTRA-012307 | 2019-06-19 | FOR BAPCO REVIEW | 2019-07-04 | 2019-07-09 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001250 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0003 | B-8789-8790-24-1 | 018-F-GAD-40253-001 | GROUND SELF-SUPPORTED STACK ACCESS DOOR 018F0003 | A1109 | AX | 2 | 2019-05-07 | CON-BMP-VTRA-011456 | 2019-05-07 | FOR BAPCO REVIEW | 2019-05-21 | 2019-05-26 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000784 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0003 | B-8789-8790-25-1 | 018-F-PLD-40075-001 | UNIT GROUND SELF-SUPPORTED STACK 018F0003 SAFETY BAR | A2008 | 0X | 2 | 2019-05-30 | CON-BMP-VTRA-011866 | 2019-05-30 | FOR BAPCO REVIEW | 2019-06-14 | 2019-06-15 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000937 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0003 | B-8789-8790-25-2 | 018-F-PLD-40076-001 | UNIT GROUND SELF-SUPPORTED STACK 018F0003 LANDING SAFETY CAGES | A2008 | 0X | 2 | 2019-05-30 | CON-BMP-VTRA-011866 | 2019-05-30 | FOR BAPCO REVIEW | 2019-06-14 | 2019-06-15 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000937 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0003 | B-8789-8790-26-1 | 018-F-GAD-40243-001 | UNIT GROUND SELF-SUPPORTED STACK 018F0003 GENERAL ARRANGEMENT FOR LINING: STACK | A1101 | 0X | 3 | 2019-06-05 | CON-BMP-VTRA-011989 | 2019-06-05 | FOR BAPCO REVIEW | 2019-06-19 | 2019-06-29 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001085 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0003 | B-8789-8790-26-2 | 018-F-GAD-40250-001 | ANCHOR FOR REFRACTORY 018F0003 | A1101 | 0X | 3 | 2019-04-11 | CON-BMP-VTRA-011107 | 2019-04-11 | FOR BAPCO REVIEW | 2019-04-25 | 2019-04-28 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000600 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0003 | B-8789-8790-27-1 | 018-F-GAD-40255-001 | PACKING FOR TRANSPORT STACK MODULES GROUND SELF-SUPPORTED STACK 018F0003 | A1316 | AX | 2 | 2019-05-09 | CON-BMP-VTRA-011507 | 2019-05-09 | FOR BAPCO REVIEW | 2019-05-24 | 2019-05-27 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000802 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0003 | B-8789-8790-27-2 | 018-F-GAD-40256-001 | UNIT GROUND SELF-SUPPORTED STACK SPREADER BEAMS FOR STACK 018F0003 | A1316 | 0X | 3 | 2019-06-29 | CON-BMP-VTRA-012581 | 2019-06-29 | FOR BAPCO REVIEW | 2019-07-15 |  |  | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0003 | B-8789-8790-29-1 | 018-F-CAL-40022-001 | CALCULATION HEATER MAIN STRUCTURE CALCULATION 018F0003 | A2201 | 0X | 3 | 2019-05-09 | CON-BMP-VTRA-011500 | 2019-05-09 | FOR BAPCO REVIEW | 2019-05-24 | 2019-05-29 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000830 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0003 | B-8789-8790-29-2 | 018-F-CAL-40023-001 | LIFTING CALCULATION 018F0003 | A2201 | 0X | 3 | 2019-06-20 | CON-BMP-VTRA-012313 | 2019-06-20 | FOR INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F0003 | B-8789-8790-70-1 | 018-F-S3D-40005-001 | 3D EQUIPMENT MODEL 018F0003 | A2013 | BX | 4 | 2019-03-27 | CON-BMP-VTRA-010882 | 2019-03-27 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F1001 | B-8787 A/B-14-1 | 018-F-GAD-40006-001 | WELDING MAP RADIANT COIL CELL A AND CELL B 018F1001 018F2001 | A1103 | BX | 2 | 2019-04-05 | CON-BMP-VTRA-011017 | 2019-04-05 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F1001 | B-8787-14-5 | 018-F-GAD-40293-001 | WELDING MAP BFW HEATING 018F1001 018F2001 | A1103 | BX | 2 | 2019-04-05 | CON-BMP-VTRA-011017 | 2019-04-05 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F1001 | B-8787-A/B-14-2 | 018-F-GAD-40290-001 | WELDING MAP RADIANT COIL CELL B 018F1001 018F2001 | A1103 | 0X | V | 2019-04-05 | CON-BMP-VTRA-011018 | 2019-04-05 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F1001 | B-8787-A/B-14-3 | 018-F-GAD-40291-001 | WELDING MAP STEAM GENERATOR 018F1001 018F2001 | A1103 | BX | 2 | 2019-04-05 | CON-BMP-VTRA-011017 | 2019-04-05 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F1001 | B-8787-A/B-14-4 | 018-F-GAD-40292-001 | WELDING MAP STEAM SUPERHEATER 018F1001 018F2001 | A1103 | BX | 2 | 2019-04-05 | CON-BMP-VTRA-011017 | 2019-04-05 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F1001 | B-8787-AB-11-1 | 018-F-GAD-40069-001 | HEATER GENERAL ASSEMBLY - ELEVATION 1 REACTOR FEED FURNACE 018F1001 018F2001 | A2001 | 0AX | 3 | 2019-07-05 | CON-BMP-VTRA-012683 | 2019-07-05 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F1001 | B-8787-AB-11-1 SHEET 2 | 018-F-GAD-40069-002 | HEATER GENERAL ASSEMBLY ELEVATION 2 REACTOR FEED FURNACE 018F1001 018F2001 | A2001 | 0AX | 3 | 2019-06-27 | CON-BMP-VTRA-012521 | 2019-06-27 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F1001 | B-8787-AB-11-2 SHEET 1 | 018-F-GAD-40259-001 | HEATER GENERAL ASSEMBLY PLANS- 1 018F1001 / 018F2001 | A2001 | 0X | 3 | 2019-05-02 | CON-BMP-VTRA-011352 | 2019-05-02 | FOR BAPCO REVIEW | 2019-05-16 | 2019-05-23 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000721 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F1001 | B-8787-AB-11-2 SHEET 2 | 018-F-GAD-40259-002 | HEATER GENERAL ASSEMBLY - ELEVATION 2 REACTOR FEED FURNACE 018F1001 018F2001 | A2001 | 0AX | 3 | 2019-06-27 | CON-BMP-VTRA-012521 | 2019-06-27 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F1001 | B-8787-AB-11-2 SHEET 3 | 018-F-GAD-40259-003 | HEATER GENERAL ASSEMBLY - PLANS 3 REACTOR FEED FURNACE 018F1001 018F2001 | A2001 | 0AX | 3 | 2019-06-27 | CON-BMP-VTRA-012521 | 2019-06-27 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F1001 | B-8787-AB-11-2 SHEET 4 | 018-F-GAD-40259-004 | HEATER GENERAL ASSEMBLY PLANS 4 REACTOR FEED FURNACE 018F1001 018F2001 | A2001 | 0AX | 3 | 2019-06-27 | CON-BMP-VTRA-012521 | 2019-06-27 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F1001 | B-8787-AB-11-2 SHEET 5 | 018-F-GAD-40259-005 | HEATER GENERAL ASSEMBLY PLANS 5 REACTOR FEED FURNACE 018F1001 018F2001 | A2001 | 0AX | 3 | 2019-06-27 | CON-BMP-VTRA-012521 | 2019-06-27 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F1001 | B-8787-AB-11-2 SHEET 6 | 018-F-GAD-40259-006 | HEATER GENERAL ASSEMBLY - PLANS 6 018F1001 018F2001 | A2001 | 0X | 3 | 2019-05-02 | CON-BMP-VTRA-011352 | 2019-05-02 | FOR BAPCO REVIEW | 2019-05-16 | 2019-05-23 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000721 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F1001 | B-8787-AB-12-1 SHEET 1 | 018-F-PED-40001-001 | GENERAL FOUNDATIONS AND LOADS 1 018F1001 018F2001 (EX 018-FPED-00001-001) | A2006 | 0X | 3 | 2019-04-08 | CON-BMP-VTRA-011052 | 2019-04-08 | FOR BAPCO REVIEW | 2019-04-23 | 2019-04-25 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000582 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F1001 | B-8787-AB-12-1 SHEET 2 | 018-F-PED-40001-002 | GENERAL FOUNDATIONS AND LOADS 2 018F1001 018F2001 (EX BAPCO N.018-F-PED-00001-002) | A2006 | 0X | 3 | 2019-04-08 | CON-BMP-VTRA-011052 | 2019-04-08 | FOR BAPCO REVIEW | 2019-04-23 | 2019-04-25 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000582 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F1001 | B-8787-AB-12-2 | 018-F-PED-40010-001 | GENERAL FOUNDATIONS DETAILS 018F1001 018F2001 (EX BAPCO N.018-F-PED-00010-001) | A2006 | 0X | 3 | 2019-04-08 | CON-BMP-VTRA-011052 | 2019-04-08 | FOR BAPCO REVIEW | 2019-04-23 | 2019-04-25 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000582 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F1001 | B-8787-AB-13-2 SH.1 | 018-F-GAD-40260-001 | RADIANT COIL CELL B 018F1001 018F2001 | A1103 | 0X | V | 2019-03-20 | CON-BMP-VTRA-010802 | 2019-03-20 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F1001 | B-8787-AB-13-2 SH.2 | 018-F-GAD-40260-002 | RADIANT COIL CELL. B 018F1001 018F2001 | A1103 | 0X | V | 2019-03-20 | CON-BMP-VTRA-010802 | 2019-03-20 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F1001 | B-8787-AB-13-3 SH.1 | 018-F-GAD-40261-001 | STEAM GENERATOR CONVECTION COIL 018F1001 018F2001 | A1103 | 0X | 3 | 2019-05-21 | CON-BMP-VTRA-011696 | 2019-05-21 | FOR BAPCO REVIEW | 2019-06-05 | 2019-06-06 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000886 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F1001 | B-8787-AB-13-3 SH.2 | 018-F-GAD-40261-002 | STEAM GENERATOR CONVECTION COIL 018F1001 018F2001 | A1103 | 0X | 3 | 2019-05-21 | CON-BMP-VTRA-011696 | 2019-05-21 | FOR BAPCO REVIEW | 2019-06-05 | 2019-06-06 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000886 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F1001 | B-8787-AB-13-3 SH.3 | 018-F-GAD-40261-003 | STEAM GENERATOR CONVECTION COIL 018F1001 018F2001 | A1103 | 0X | 3 | 2019-05-21 | CON-BMP-VTRA-011696 | 2019-05-21 | FOR BAPCO REVIEW | 2019-06-05 | 2019-06-06 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000886 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F1001 | B-8787-AB-13-4 SH.1 | 018-F-GAD-40262-001 | STEAM SUPERHEATER CONVECTION COIL 018F1001 018F2001 | A1103 | 0X | 3 | 2019-05-21 | CON-BMP-VTRA-011696 | 2019-05-21 | FOR BAPCO REVIEW | 2019-06-05 | 2019-06-06 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000886 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F1001 | B-8787-AB-13-4 SH.2 | 018-F-GAD-40262-002 | STEAM SUPERHEATER CONVECTION COIL 018F1001 018F2001 | A1103 | 0X | 3 | 2019-05-21 | CON-BMP-VTRA-011696 | 2019-05-21 | FOR BAPCO REVIEW | 2019-06-05 | 2019-06-06 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000886 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F1001 | B-8787-AB-13-4 SH.3 | 018-F-GAD-40262-003 | STEAM SUPERHEATER CONVECTION COIL 018F1001 018F2001 | A1103 | 0X | 3 | 2019-05-21 | CON-BMP-VTRA-011696 | 2019-05-21 | FOR BAPCO REVIEW | 2019-06-05 | 2019-06-06 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000886 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F1001 | B-8787-AB-13-5 SH.1 | 018-F-GAD-40263-001 | BFW HEATING CONVECTION COIL 018F1001 018F2001 | A1103 | 0X | 3 | 2019-05-21 | CON-BMP-VTRA-011696 | 2019-05-21 | FOR BAPCO REVIEW | 2019-06-05 | 2019-06-06 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000886 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F1001 | B-8787-AB-13-5 SH.2 | 018-F-GAD-40263-002 | BFW HEATING CONVECTION COIL 018F1001 018F2001 | A1103 | 0X | 3 | 2019-05-21 | CON-BMP-VTRA-011696 | 2019-05-21 | FOR BAPCO REVIEW | 2019-06-05 | 2019-06-06 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000886 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F1001 | B-8787-AB-17-1 SH.1 | 018-F-GAD-40003-001 | CASTING NOTES AND DETAILS 018F1001 018F2001 | A1101 | 0X | 3 | 2019-04-05 | CON-BMP-VTRA-011015 | 2019-04-05 | FOR BAPCO REVIEW | 2019-04-22 | 2019-04-24 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000567 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F1001 | B-8787-AB-17-2 | 018-F-GAD-40294-001 | UNIT REACTOR FEED FURNACE 018F1001 018F2001 RADIANT CASTING SUPPORTS REACTOR FEED FURNACE | A1101 | 0X | 3 | 2019-05-23 | CON-BMP-VTRA-011750 | 2019-05-23 | FOR BAPCO REVIEW | 2019-06-06 | 2019-06-16 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000935 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F1001 | B-8787-AB-17-3 | 018-F-GAD-40295-001 | INTERMEDIATE TUBE SHEETS CA-1 018F1001 018F2001 | A1101 | 0X | 3 | 2019-04-05 | CON-BMP-VTRA-011015 | 2019-04-05 | FOR BAPCO REVIEW | 2019-04-22 | 2019-04-24 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000567 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F1001 | B-8787-AB-17-3 SH.2 | 018-F-GAD-40295-002 | INTERMEDIATE TUBE SHEETS CA-2 018F1001 018F2001 | A1101 | 0X | 3 | 2019-04-08 | CON-BMP-VTRA-011039 | 2019-04-08 | FOR BAPCO REVIEW | 2019-04-23 | 2019-04-25 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000578 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F1001 | B-8787-AB-17-3 SH.3 | 018-F-GAD-40295-003 | INTERMEDIATE TUBE SHEETS CA-3 018F1001 018F2001 | A1101 | 0X | 3 | 2019-04-08 | CON-BMP-VTRA-011039 | 2019-04-08 | FOR BAPCO REVIEW | 2019-04-23 | 2019-04-25 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000578 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F1001 | B-8787-AB-17-3 SH.4 | 018-F-GAD-40295-004 | INTERMEDIATE TUBE SHEETS CA-4 & CA-5 018F1001 018F2001 | A1101 | 0X | 3 | 2019-04-08 | CON-BMP-VTRA-011039 | 2019-04-08 | FOR BAPCO REVIEW | 2019-04-23 | 2019-04-25 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000578 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F1001 | B-8787-AB-19-1-7 | 018-F-INX-40006-001 | DATA SHEET UTILITIES CONSUMPTION LIST 018F1001/ 018F2001 | A4001 | AX | 2 | 2019-06-06 | CON-BMP-VTRA-012073 | 2019-06-06 | FOR BAPCO REVIEW | 2019-06-21 | 2019-07-01 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001127 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F1001 | B-8787-AB-19-3 | 018-F-MCD-40006-001 | INSTRUMENTATION SOFTWARE FREEZING PACKAGE 018F1001/ 018F2001 | A3008 | AX | 2 | 2019-05-03 | CON-BMP-VTRA-011365 | 2019-05-03 | FOR BAPCO REVIEW | 2019-05-17 | 2019-05-25 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000760 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F1001 | B-8787-AB-21-1 | 018-F-GAD-40031-001 | FLOOR PANELS ASSEMBLY CELL A-1 018F1001 018F2001 | A1109 | 0X | 3 | 2019-04-11 | CON-BMP-VTRA-011111 | 2019-04-11 | FOR BAPCO REVIEW | 2019-04-25 | 2019-04-28 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000609 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F1001 | B-8787-AB-21-10 | 018-F-GAD-40044-001 | ARCH PANELS ASSEMBLY 1 018F1001 018F2001 | A1109 | 0X | 3 | 2019-04-11 | CON-BMP-VTRA-011111 | 2019-04-11 | FOR BAPCO REVIEW | 2019-04-25 | 2019-04-28 | 2-RETAINED FOR INFORMATION BMP-ROC-VTRE-000609 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F1001 | B-8787-AB-21-11 | 018-F-GAD-40045-001 | ARCH PANELS SECTIONS 1 018F1001 018F2001 | A1109 | 0X | 3 | 2019-04-11 | CON-BMP-VTRA-011111 | 2019-04-11 | FOR BAPCO REVIEW | 2019-04-25 | 2019-04-28 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000609 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F1001 | B-8787-AB-21-12 | 018-F-GAD-40047-001 | TRANSICTION DUCT - ASSEMBLY 1 - 018F1001 018F2001 | A1109 | 0X | 3 | 2019-04-11 | CON-BMP-VTRA-011111 | 2019-04-11 | FOR BAPCO REVIEW | 2019-04-25 | 2019-04-28 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000609 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F1001 | B-8787-AB-21-13 | 018-F-GAD-40048-001 | TRANSICTION DUCT SECTIONS AND PLANS -1 - 018F1001 018F2001 | A1109 | 0X | 3 | 2019-04-11 | CON-BMP-VTRA-011111 | 2019-04-11 | FOR BAPCO REVIEW | 2019-04-25 | 2019-04-28 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000609 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F1001 | B-8787-AB-21-14 | 018-F-GAD-40050-001 | REACTOR FEED FURNACE STEEL STRUCTURE FOR RADIANTCOIL SUPPORT - 1 018F1001 018F2001 | A1109 | 0X | 3 | 2019-06-28 | CON-BMP-VTRA-012540 | 2019-06-28 | FOR BAPCO REVIEW | 2019-07-12 |  |  | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F1001 | B-8787-AB-21-16 | 018-F-GAD-40053-001 | REACTOR FEED FURNACE CONVECTION I¿ MODULE ASSEMBLY - 1 018F1001 018F2001 | A1109 | 0X | 3 | 2019-06-28 | CON-BMP-VTRA-012540 | 2019-06-28 | FOR BAPCO REVIEW | 2019-07-12 |  |  | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F1001 | B-8787-AB-21-17 | 018-F-GAD-40055-001 | REACTOR FEED FURNACE END TUBE SHEET CONVECTION I MODULE - 1 018F1001 018F2001 | A1109 | AX | 2 | 2019-05-09 | CON-BMP-VTRA-011508 | 2019-05-09 | FOR BAPCO REVIEW | 2019-05-24 | 2019-05-29 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000834 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F1001 | B-8787-AB-21-18 | 018-F-GAD-40056-001 | REACTOR FEED FURNACE CONVECTION II MODULE ASSEMBLY - 1 018F1001 018F2001 | A1109 | 0X | 3 | 2019-06-28 | CON-BMP-VTRA-012540 | 2019-06-28 | FOR BAPCO REVIEW | 2019-07-12 |  |  | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F1001 | B-8787-AB-21-19 | 018-F-GAD-40058-001 | REACTOR FEED FURNACE END TUBE SHEET CONVECTION II MODULE - 1 018F1001 018F2001 | A1109 | 0X | 2 | 2019-06-28 | CON-BMP-VTRA-012544 | 2019-06-28 | FOR BAPCO REVIEW | 2019-07-12 |  |  | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F1001 | B-8787-AB-21-2 | 018-F-GAD-40032-001 | FLOOR PANELS ASSEMBLY CELL A-2 018F1001 018F2001 | A1109 | 0X | 3 | 2019-04-11 | CON-BMP-VTRA-011111 | 2019-04-11 | FOR BAPCO REVIEW | 2019-04-25 | 2019-04-28 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000609 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F1001 | B-8787-AB-21-20 | 018-F-GAD-40059-001 | UNIT REACTOR FEED FURNACE 018F1001 018F2001 STEELSTRUCTURE FOR CONVECTION COIL- MANIFOLDS SUPPORTS | A1109 | AX | 2 | 2019-05-31 | CON-BMP-VTRA-011870 | 2019-05-31 | FOR BAPCO REVIEW | 2019-06-14 | 2019-06-17 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000981 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F1001 | B-8787-AB-21-21 | 018-F-GAD-40061-001 | REACTOR FEED FURNACE HEADER BOXES I MODULE ASSEMBLY AND DETAILS - 1 018F1001 018F2001 | A1109 | 0X | 3 | 2019-06-28 | CON-BMP-VTRA-012540 | 2019-06-28 | FOR BAPCO REVIEW | 2019-07-12 |  |  | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F1001 | B-8787-AB-21-22 | 018-F-GAD-40062-001 | REACTOR FEED FURNACE HEADER BOXES II MODULE ASSEMBLY AND DETAILS 018F1001 018F2001 | A1109 | 0X | 3 | 2019-06-28 | CON-BMP-VTRA-012540 | 2019-06-28 | FOR BAPCO REVIEW | 2019-07-12 |  |  | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F1001 | B-8787-AB-21-23 | 018-F-GAD-40063-001 | REACTOR FEED FURNACE BREECHING ASSEMBLY-1 018F1001 018F2001 | A1109 | 0X | 3 | 2019-06-28 | CON-BMP-VTRA-012549 | 2019-06-28 | FOR BAPCO REVIEW | 2019-07-12 |  |  | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F1001 | B-8787-AB-21-24 | 018-F-GAD-40065-001 | REACTOR FEED FURNACE TAKE OFFASSEMBLY-1 018F1001 018F2001 | A1109 | 0X | 3 | 2019-06-28 | CON-BMP-VTRA-012549 | 2019-06-28 | FOR BAPCO REVIEW | 2019-07-12 |  |  | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F1001 | B-8787-AB-21-27 | 018-F-GAD-40070-001 | UNIT REACTOR FEED FURNACE 018F1001/018F2001 STACK ASSEMBLY AND DETAILS - 1 | A2009 | BX | 2 | 2019-07-01 | CON-BMP-VTRA-012585 | 2019-07-01 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F1001 | B-8787-AB-21-3 | 018-F-GAD-40033-001 | FLOOR PANELS ASSEMBLY CELL B-1 018F1001 018F2001 | A1109 | 0X | 3 | 2019-04-11 | CON-BMP-VTRA-011111 | 2019-04-11 | FOR BAPCO REVIEW | 2019-04-25 | 2019-04-28 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000609 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F1001 | B-8787-AB-21-4 | 018-F-GAD-40034-001 | FLOOR PANELS ASSEMBLY CELL B-2 018F1001 018F2001 | A1109 | 0X | 3 | 2019-04-11 | CON-BMP-VTRA-011111 | 2019-04-11 | FOR BAPCO REVIEW | 2019-04-25 | 2019-04-28 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000609 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F1001 | B-8787-AB-21-5 | 018-F-GAD-40035-001 | RADIANT PANELS ASSEMBLY CELL A-1 018F1001 018F2001 | A1109 | 0X | 3 | 2019-04-11 | CON-BMP-VTRA-011111 | 2019-04-11 | FOR BAPCO REVIEW | 2019-04-25 | 2019-04-28 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000609 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F1001 | B-8787-AB-21-6 | 018-F-GAD-40036-001 | RADIANT PANELS ASSEMBLY CELL A-2 018F1001 018F2001 | A1109 | 0X | 3 | 2019-04-11 | CON-BMP-VTRA-011111 | 2019-04-11 | FOR BAPCO REVIEW | 2019-04-25 | 2019-04-28 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000609 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F1001 | B-8787-AB-21-7 | 018-F-GAD-40037-001 | RADIANT PANELS ASSEMBLY CELL B-1 018F1001 018F2001 | A1109 | 0X | 3 | 2019-04-11 | CON-BMP-VTRA-011111 | 2019-04-11 | FOR BAPCO REVIEW | 2019-04-25 | 2019-04-28 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000609 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F1001 | B-8787-AB-21-8 | 018-F-GAD-40038-001 | RADIANT PANELS ASSEMBLY CELL B-2 018F1001 018F2001 | A1109 | 0X | 3 | 2019-04-11 | CON-BMP-VTRA-011111 | 2019-04-11 | FOR BAPCO REVIEW | 2019-04-25 | 2019-04-28 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000609 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F1001 | B-8787-AB-21-9 | 018-F-GAD-40041-001 | COMMON FLUE GAS DUCT ASSEMBLY - 1 018F1001 018F2001 | A1109 | 0X | 3 | 2019-04-11 | CON-BMP-VTRA-011111 | 2019-04-11 | FOR BAPCO REVIEW | 2019-04-25 | 2019-04-28 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000609 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F1001 | B-8787-AB-22-1 | 018-F-PLD-40001-001 | REACTOR FEED FURNACE LOWER RADIANT PLATFORM AT EL.+3300 018F1001 018F2001 | A2008 | AX | 2 | 2019-05-13 | CON-BMP-VTRA-011543 | 2019-05-13 | FOR BAPCO REVIEW | 2019-05-28 | 2019-05-29 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000827 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F1001 | B-8787-AB-22-2 | 018-F-PLD-40002-001 | REACTOR FEED FURNACE INTERMEDIATE RADIANT PLATFORM AT EL.+7895 018F1001 018F2001 | A2008 | AX | 2 | 2019-05-13 | CON-BMP-VTRA-011543 | 2019-05-13 | FOR BAPCO REVIEW | 2019-05-28 | 2019-05-29 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000827 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F1001 | B-8787-AB-22-3 | 018-F-PLD-40003-001 | UNIT REACTOR FEED FURNACE 018F1001 018F2001 ARCH PLATFORM AT EL.+9130 AND EL.+12301 | A2008 | AX | 2 | 2019-05-31 | CON-BMP-VTRA-011869 | 2019-05-31 | FOR BAPCO REVIEW | 2019-06-14 | 2019-06-17 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000974 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F1001 | B-8787-AB-22-4 | 018-F-PLD-40004-001 | CONVECTION PLATFORM REACTOR FEED FURNACE 018F1001 018F2001 | A2008 | AX | 2 | 2019-06-25 | CON-BMP-VTRA-012419 | 2019-06-25 | FOR BAPCO REVIEW | 2019-07-09 | 2019-07-11 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001298 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F1001 | B-8787-AB-22-5 | 018-F-PLD-40005-001 | CONVECTION PLATFORM REACTOR FEED FURNACE 018F1001 018F2001 | A2008 | AX | 2 | 2019-06-25 | CON-BMP-VTRA-012419 | 2019-06-25 | FOR BAPCO REVIEW | 2019-07-09 | 2019-07-11 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001298 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F1001 | B-8787-AB-22-6 | 018-F-PLD-40006-001 | TAKE-OFF PLATFORM AT EL21766 REACTOR FEED FURNACE 018F1001 018F2001 | A2008 | AX | 2 | 2019-06-25 | CON-BMP-VTRA-012419 | 2019-06-25 | FOR BAPCO REVIEW | 2019-07-09 | 2019-07-11 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001298 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F1001 | B-8787-AB-22-7 | 018-F-PLD-40007-001 | UNIT REACTOR FEED FURNACE STACK PLATFORM 018F1001 018F2001 | A2008 | AX | 2 | 2019-06-29 | CON-BMP-VTRA-012569 | 2019-06-29 | FOR BAPCO REVIEW | 2019-07-15 |  |  | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F1001 | B-8787-AB-22-8 | 018-F-PLD-40008-001 | UNIT REACTOR FEED FURNACE STAIR 018F1001 018F2001 | A2008 | AX | 2 | 2019-06-29 | CON-BMP-VTRA-012569 | 2019-06-29 | FOR BAPCO REVIEW | 2019-07-15 |  |  | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F1001 | B-8787-AB-23-1 | 018-F-PLD-40013-001 | REACTOR FEED FURNACE GRATING FOR LOWER RADIANT PLATFORM 018F1001 | A2008 | AX | 2 | 2019-05-13 | CON-BMP-VTRA-011543 | 2019-05-13 | FOR BAPCO REVIEW | 2019-05-28 | 2019-05-29 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000827 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F1001 | B-8787-AB-23-2 | 018-F-PLD-40014-001 | REACTOR FEED FURNACE 018F1001 018F2001 GRATING FOR INTERMEDIATE RADIANT PLATFORM | A2008 | AX | 2 | 2019-05-13 | CON-BMP-VTRA-011543 | 2019-05-13 | FOR BAPCO REVIEW | 2019-05-28 | 2019-05-29 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000827 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F1001 | B-8787-AB-23-3 | 018-F-PLD-40015-001 | UNIT REACTOR FEED FURNACE 018F1001 018F2001 GRATING FOR ARCH PLATFORM | A2008 | AX | 2 | 2019-05-31 | CON-BMP-VTRA-011869 | 2019-05-31 | FOR BAPCO REVIEW | 2019-06-14 | 2019-06-17 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000974 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F1001 | B-8787-AB-23-4 | 018-F-PLD-40016-001 | GRATING FOR CONVECTION PLATFORM REACTOR FEED FURNACE 018F1001 018F2001 | A2008 | AX | 2 | 2019-06-25 | CON-BMP-VTRA-012419 | 2019-06-25 | FOR BAPCO REVIEW | 2019-07-09 | 2019-07-11 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001298 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F1001 | B-8787-AB-23-5 | 018-F-PLD-40017-001 | GRATING FOR CONVECTION PLATFORM REACTOR FEED FURNACE 018F1001 018F2001 | A2008 | AX | 2 | 2019-06-25 | CON-BMP-VTRA-012419 | 2019-06-25 | FOR BAPCO REVIEW | 2019-07-09 | 2019-07-11 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001298 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F1001 | B-8787-AB-23-6 | 018-F-PLD-40018-001 | GRATING FOR TAKE-OFF PLATFORM REACTOR FEED FURNACE 018F1001 018F2001 | A2008 | AX | 2 | 2019-06-26 | CON-BMP-VTRA-012510 | 2019-06-26 | FOR BAPCO REVIEW | 2019-07-11 |  |  | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F1001 | B-8787-AB-23-7 | 018-F-PLD-40019-001 | UNIT REACTOR FEED FURNACE GRATING FOR STACK PLATFORM 018F1001 018F2001 | A2008 | AX | 2 | 2019-06-29 | CON-BMP-VTRA-012569 | 2019-06-29 | FOR BAPCO REVIEW | 2019-07-15 |  |  | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F1001 | B-8787-AB-24-1 | 018-F-GAD-40011-001 | REACTOR FEED FURNACE 018F1001 018F2001 ACCESS DOOR ON RADIANT ZONE - 1 | A1109 | AX | 2 | 2019-05-23 | CON-BMP-VTRA-011765 | 2019-05-23 | FOR BAPCO REVIEW | 2019-06-07 | 2019-06-16 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000933 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F1001 | B-8787-AB-24-2 | 018-F-GAD-40012-001 | REACTOR FEED FURNACE OBSERVATION DOOR FOR RADIANT (CAST IRON) 018F1001 018F2001 | A1109 | 0X | 3 | 2019-05-23 | CON-BMP-VTRA-011751 | 2019-05-23 | FOR BAPCO REVIEW | 2019-06-07 | 2019-06-29 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001107 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F1001 | B-8787-AB-24-3 | 018-F-GAD-40013-001 | REACTOR FEED FURNACE 018F1001 018F2001 EXPLOSION DOOR - | A1109 | AX | 2 | 2019-05-23 | CON-BMP-VTRA-011765 | 2019-05-23 | FOR BAPCO REVIEW | 2019-06-07 | 2019-06-16 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000933 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F1001 | B-8787-AB-24-4 | 018-F-GAD-40014-001 | REACTOR FEED FURNACE 018F1001 018F2001 INSPECTION DOOR FOR CONVECTION SECTION - 1 | A1109 | AX | 2 | 2019-05-23 | CON-BMP-VTRA-011765 | 2019-05-23 | FOR BAPCO REVIEW | 2019-06-07 | 2019-06-16 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000933 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F1001 | B-8787-AB-24-5 | 018-F-GAD-40015-001 | REACTOR FEED FURNACE 018F1001 018F2001 ACCESS DOOR FOR BREECHING - 1 | A1109 | AX | 2 | 2019-05-23 | CON-BMP-VTRA-011765 | 2019-05-23 | FOR BAPCO REVIEW | 2019-06-07 | 2019-06-16 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000933 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F1001 | B-8787-AB-24-6 | 018-F-GAD-40016-001 | REACTOR FEED FURNACE 018F1001 018F2001 ACCESS DOOR DAMPER - 1 | A1109 | AX | 2 | 2019-05-23 | CON-BMP-VTRA-011765 | 2019-05-23 | FOR BAPCO REVIEW | 2019-06-07 | 2019-06-16 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000933 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F1001 | B-8787-AB-25-1 | 018-F-GAD-40017-001 | REACTOR FEED FURNACE INSTRUMENT CONNECTIONS 018F1001 018F2001 | A1109 | 0AX | 3 | 2019-06-28 | CON-BMP-VTRA-012548 | 2019-06-28 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F1001 | B-8787-AB-25-2 | 018-F-DLB-40001-001 | UNIT REACTOR FEED FURNACE NAMEPLATE 018F1001-018F2001 | A1112 | 0X | 3 | 2019-06-20 | CON-BMP-VTRA-012337 | 2019-06-20 | FOR BAPCO REVIEW | 2019-07-05 | 2019-07-10 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001260 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F1001 | B-8787-AB-25-3 | 018-F-GAD-40018-001 | EARTHING LUG GENERAL ARRANGEMENT 018F1001 018F2001 | A1109 | 0X | 3 | 2019-04-29 | CON-BMP-VTRA-011307 | 2019-04-29 | FOR BAPCO REVIEW | 2019-05-14 | 2019-05-23 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000744 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F1001 | B-8787-AB-25-4 | 018-F-GAD-40019-001 | REACTOR FEED FURNACE FIRE- PROOFING GENERAL ASSEMBLY018F1001 018F2001 | A1109 | 0X | 3 | 2019-04-11 | CON-BMP-VTRA-011112 | 2019-04-11 | FOR BAPCO REVIEW | 2019-04-25 | 2019-04-28 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000608 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F1001 | B-8787-AB-26-1 | 018-F-GAD-40004-001 | UNIT REACTOR FEED FURNACE 018F1001 018F2001 GENERAL ARRANGEMENT FOR LINING 1 | A1101 | 0X | 3 | 2019-06-05 | CON-BMP-VTRA-011989 | 2019-06-05 | FOR BAPCO REVIEW | 2019-06-19 | 2019-06-29 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001085 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F1001 | B-8787-AB-26-2 | 018-F-GAD-40264-001 | UNIT REACTOR FEED RUENACE 018F1001 018F2001 GENERAL ARRANGEMENT FOR LINING 2 | A1101 | 0X | 3 | 2019-06-05 | CON-BMP-VTRA-011989 | 2019-06-05 | FOR BAPCO REVIEW | 2019-06-19 | 2019-06-29 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001085 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F1001 | B-8787-AB-26-3 | 018-F-GAD-40296-001 | ANCHOR FOR REFRACTORY REACTOR FEED FURNACE 018F1001/2001 | A1101 | 0X | 3 | 2019-05-23 | CON-BMP-VTRA-011763 | 2019-05-23 | FOR BAPCO REVIEW | 2019-06-07 | 2019-06-17 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000961 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F1001 | B-8787-AB-27-7 | 018-F-GAD-40272-001 | UNIT REACTOR FEED FURNACE SPREADER BEAMS FOR CONVECTION TRANSICTION & STACK 018F1001 018F2001 | A1316 | AX | 2 | 2019-05-09 | CON-BMP-VTRA-012572 | 2019-06-29 | FOR BAPCO REVIEW | 2019-07-15 |  |  | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F1001 | B-8787-AB-28-1 | 018-F-DAT-40005-001 | DATA SHEET 018F1001 / 018F2001 HEATER DATA SHEET | A1001 | 0AX | 3 | 2019-07-10 | CON-BMP-VTRA-012794 | 2019-07-10 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F1001 | B-8787-AB-28-2 | 018-F-DAT-40006-001 | DTA SHEET - BURNER DATA SHEET WITH CAPACITY CURVES AND NOISE DATA SHEET 018F1001 018F2001 | A0105 | AX | 2 | 2019-05-06 | CON-BMP-VTRA-011437 | 2019-05-06 | FOR BAPCO REVIEW | 2019-05-21 | 2019-05-26 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000783 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F1001 | B-8787-AB-29-1 | 018-F-CAL-40005-001 | CALCULATION HEATER MAIN STRUCTURAL CALCULATION 018F1001/2001 | A2201 | 0X | 3 | 2019-06-20 | CON-BMP-VTRA-012331 | 2019-06-20 | FOR BAPCO REVIEW | 2019-07-04 | 2019-07-10 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001270 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F1001 | B-8787-AB-29-2 | 018-F-CAL-40003-001 | LIFTING CALCULATION 018F1001/018F2001 | A2201 | 0X | 3 | 2019-06-20 | CON-BMP-VTRA-012313 | 2019-06-20 | FOR INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F1001 | B-8787-AB-29-3 | 018-F-CAL-40001-001 | DATA SHEET REFRACTORY CALCULATION 018F1001 018F2001 | A1303 | 0X | 3 | 2019-06-20 | CON-BMP-VTRA-012336 | 2019-06-20 | FOR BAPCO REVIEW | 2019-07-05 | 2019-07-10 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001269 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F1001 | B-8787-AB-29-4 | 018-F-CAL-40002-001 | CALCULATION 018F1001 / 018F2001 MECHANICAL CALC. (EX BAPCO N.018-F-CAL-00002-001) | A1304 | 0X | 3 | 2019-04-26 | CON-BMP-VTRA-011269 | 2019-04-26 | FOR BAPCO REVIEW | 2019-05-14 | 2019-05-18 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000701 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F1001 | B-8787-AB-29-5 | 018-F-CAL-40004-001 | CALCULATION CASTING CALCULATION 018F1001 018F2001 | A2201 | 0X | 3 | 2019-04-29 | CON-BMP-VTRA-011294 | 2019-04-29 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F1001 | B-8787-AB-31-2 | 018-F-ITP-40014-001 | INSPECTION & TEST PLAN RADIANT COILS PREFABRICATION 018F1001 018F2001 | B1002 | 0X | 3 | 2019-05-07 | CON-BMP-VTRA-011460 | 2019-05-07 | FOR BAPCO REVIEW | 2019-05-21 | 2019-06-20 | 1-APPROVED BMP-ROC-VTRE-001007 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F1001 | B-8787-AB-31-3 | 018-F-ITP-40015-001 | INSPECTION & TEST PLAN CONVECTION COILS PREFABRICATION 018F1001 018F2001 | B1002 | 0X | 3 | 2019-05-07 | CON-BMP-VTRA-011460 | 2019-05-07 | FOR BAPCO REVIEW | 2019-05-21 | 2019-06-20 | 1-APPROVED BMP-ROC-VTRE-001007 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F1001 | B-8787-AB-32-2 | 018-F-MCD-40020-001 | WELDING BOOK RADIANT AND CONV. COILS PREFABRICATION 018F1001 018F2001 | B1304 | BX | 2 | 2019-03-29 | CON-BMP-VTRA-010906 | 2019-03-29 | FOR BAPCO REVIEW | 2019-04-15 | 2019-04-12 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000508 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F1001 | B-8787-AB-35-1 | 018-F-GAD-40029-001 | REACTOR FEED FURNACE BURNERS GENERAL ASSEMBLY AND DETAILS 018F1001 018F2001 | A1109 | AX | 2 | 2019-05-03 | CON-BMP-VTRA-011379 | 2019-05-03 | FOR BAPCO REVIEW | 2019-05-17 | 2019-05-24 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000759 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F1001 | B-8787-AB-70-1 | 018-F-S3D-40001-001 | 3D EQUIPMENT MODEL 018F1001/018F2001 | A2013 | BX | 4 | 2019-03-27 | CON-BMP-VTRA-010882 | 2019-03-27 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F1002 | B-8788-29-3 | 018-F-CAL-40006-001 | DATA SHEET REFRACTORY CALCULATION 018F1002 018F2002 | A1303 | 0X | 3 | 2019-06-20 | CON-BMP-VTRA-012336 | 2019-06-20 | FOR BAPCO REVIEW | 2019-07-05 | 2019-07-10 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001269 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F1002 | B-8788-A/B-14-1 SH.1 | 018-F-GAD-40074-001 | WELDING MAP RADIANT COIL 018F1002 018F2002 | A1103 | BX | 2 | 2019-04-05 | CON-BMP-VTRA-011017 | 2019-04-05 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F1002 | B-8788-A/B-14-1 SH.2 | 018-F-GAD-40074-002 | WELDING MAP RADIANT COIL 018F1002 018F2002 | A1103 | BX | 2 | 2019-04-05 | CON-BMP-VTRA-011017 | 2019-04-05 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F1002 | B-8788-A/B-25-1 | 018-F-GAD-40084-001 | RECICLE HYDROGEN FURNACE INSTRUMENT CONNECTIONS 018F1002 018F2002 | A1109 | 0AX | 3 | 2019-06-28 | CON-BMP-VTRA-012548 | 2019-06-28 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F1002 | B-8788-AB-11-1 | 018-F-GAD-40116-001 | RECYCLE HYDROGEN FURNACEHEATER GENERAL ASSEMBLY ELEVATION 018F1002 / 018F2002 | A2001 | 0AX | 2 | 2019-06-27 | CON-BMP-VTRA-012535 | 2019-06-27 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F1002 | B-8788-AB-11-2 SHEET 1 | 018-F-GAD-40275-001 | HEATER GENERAL ASSEMBLY PLANS 1 018F1002 018F2002 | A2001 | 0AX | 3 | 2019-06-28 | CON-BMP-VTRA-012542 | 2019-06-28 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F1002 | B-8788-AB-11-2 SHEET 2 | 018-F-GAD-40275-002 | HEATER GENERAL ASSEMBLY PLANS 2 018F1002 018F2002 | A2001 | 0AX | 3 | 2019-06-28 | CON-BMP-VTRA-012542 | 2019-06-28 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F1002 | B-8788-AB-12-1 | 018-F-PED-40002-001 | GENERAL FOUNDATIONS AND LOADS 018F1002 018F2002 (EX BAPCO N.018-F-PED-00002-001) | A2006 | 0X | 3 | 2019-04-08 | CON-BMP-VTRA-011052 | 2019-04-08 | FOR BAPCO REVIEW | 2019-04-23 | 2019-04-25 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000582 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F1002 | B-8788-AB-12-2 SHEET 1 | 018-F-PED-40007-001 | GENERAL FOUNDATION - DETAILS 1 018F1002 018F2002 (EX BAPCO N.018-F-PED-00007-001) | A2006 | 0X | 3 | 2019-04-08 | CON-BMP-VTRA-011052 | 2019-04-08 | FOR BAPCO REVIEW | 2019-04-23 | 2019-04-25 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000582 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F1002 | B-8788-AB-12-2 SHEET 2 | 018-F-PED-40007-002 | GENERAL FOUNDATION DETAILS -2 018F1002 018F2002 (EX BAPCO N.018-F-PED-00007-002) | A2006 | 0X | 3 | 2019-04-08 | CON-BMP-VTRA-011052 | 2019-04-08 | FOR BAPCO REVIEW | 2019-04-23 | 2019-04-25 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000582 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F1002 | B-8788-AB-13-1 SH.1 | 018-F-GAD-40073-001 | RADIANT COIL 018F1002 018F2002 | A1103 | 0X | 3 | 2019-05-21 | CON-BMP-VTRA-011696 | 2019-05-21 | FOR BAPCO REVIEW | 2019-06-05 | 2019-06-06 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000886 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F1002 | B-8788-AB-13-1 SH.2 | 018-F-GAD-40073-002 | RADIANT COIL 018F1002 018F2002 | A1103 | 0X | 3 | 2019-05-21 | CON-BMP-VTRA-011696 | 2019-05-21 | FOR BAPCO REVIEW | 2019-06-05 | 2019-06-06 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000886 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F1002 | B-8788-AB-13-1 SH.3 | 018-F-GAD-40073-003 | RADIANT COIL 018F1002 018F2002 | A1103 | 0X | 3 | 2019-05-21 | CON-BMP-VTRA-011696 | 2019-05-21 | FOR BAPCO REVIEW | 2019-06-05 | 2019-06-06 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000886 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F1002 | B-8788-AB-17-1 | 018-F-GAD-40071-001 | UNIT RECYCLE HYDROGEN FURNACE 018F1002 018F2002 RADIANT CASTING SUPPORTS RECYCLE HYDROGEN FURNACE | A1101 | 0X | 3 | 2019-05-23 | CON-BMP-VTRA-011750 | 2019-05-23 | FOR BAPCO REVIEW | 2019-06-06 | 2019-06-16 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000935 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F1002 | B-8788-AB-19-1-7 | 018-F-INX-40007-001 | DATA SHEET UTILITIES CONSUMPTION LIST 018F1002/ 018F2002 | A4001 | AX | 2 | 2019-06-06 | CON-BMP-VTRA-012073 | 2019-06-06 | FOR BAPCO REVIEW | 2019-06-21 | 2019-07-01 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001127 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F1002 | B-8788-AB-19-3 | 018-F-MCD-40023-001 | INSTRUMENTATION SOFTWARE FREEZING PACKAGE 018F1002/ 018F2002 | A3008 | AX | 2 | 2019-05-03 | CON-BMP-VTRA-011365 | 2019-05-03 | FOR BAPCO REVIEW | 2019-05-17 | 2019-05-25 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000760 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F1002 | B-8788-AB-21-1 | 018-F-GAD-40093-001 | FLOOR PANELS ASSEMBLY 1 018F1002/2002 | A1109 | 0X | 3 | 2019-04-10 | CON-BMP-VTRA-011101 | 2019-04-10 | FOR BAPCO REVIEW | 2019-04-25 | 2019-04-27 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000606 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F1002 | B-8788-AB-21-10 | 018-F-GAD-40103-001 | RECYCLE HYDROGEN FURNCACE EXPANSION JOINT 018F1002/2002 | A1109 | BX | 2 | 2019-06-28 | CON-BMP-VTRA-012546 | 2019-06-28 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F1002 | B-8788-AB-21-11-A | 018-F-GAD-40104-001 | RECYCLE HYDROGEN FURNACE GUILLOTTINE FG01 ASSEMBLY AND DET 018F1002 018F2002 | A1109 | BX | 2 | 2019-07-02 | CON-BMP-VTRA-012628 | 2019-07-03 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F1002 | B-8788-AB-21-12 | 018-F-GAD-40105-001 | RECYCLE HYFROGEN FURNACE COMMON DUCT ASSEMBLY 018F1002/2002 | A1109 | 0X | 3 | 2019-06-20 | CON-BMP-VTRA-012329 | 2019-06-20 | FOR BAPCO REVIEW | 2019-07-04 | 2019-07-10 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001266 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F1002 | B-8788-AB-21-13 | 018-F-GAD-40106-001 | RECYCLE HYDROGEN FURNACE COMMON DUCT SECTION AND PLANS 018F1002 018F2002 | A1109 | 0X | 3 | 2019-06-29 | CON-BMP-VTRA-012580 | 2019-06-29 | FOR BAPCO REVIEW | 2019-07-15 |  |  | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F1002 | B-8788-AB-21-14 | 018-F-GAD-40108-001 | RECYCLE HYDROGEN FURNACE STRUCTURE FOR SUPPORTS COMMON DUCT ASSEMBLY 018F1002 018F2002 | A1109 | 0X | 3 | 2019-06-29 | CON-BMP-VTRA-012580 | 2019-06-29 | FOR BAPCO REVIEW | 2019-07-15 |  |  | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F1002 | B-8788-AB-21-15 | 018-F-GAD-40110-001 | RECYCLE HYDROGEN FURNACE STEELSTRUCTURE FOR RADIANT COILS SUPPORT 018F1002 018F2002 | A1109 | BX | 2 | 2019-06-20 | CON-BMP-VTRA-012315 | 2019-06-20 | FOR INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F1002 | B-8788-AB-21-2 | 018-F-GAD-40094-001 | RECYCLE HYDROGEN FURNACE FLOOR PANELS ASSEMBLY 2 018F1002/2002 | A1109 | 0X | 3 | 2019-04-15 | CON-BMP-VTRA-011169 | 2019-04-15 | FOR BAPCO REVIEW | 2019-04-29 |  |  | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F1002 | B-8788-AB-21-3 | 018-F-GAD-40095-001 | RADIANT PANELS ASSEMBLY 1 018F1002/2002 | A1109 | 0AX | 3 | 2019-06-20 | CON-BMP-VTRA-012339 | 2019-06-20 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F1002 | B-8788-AB-21-4 | 018-F-GAD-40097-001 | RADIANT PANELS ASSEMBLY 2 018F1002/2002 | A1109 | 0X | 3 | 2019-04-10 | CON-BMP-VTRA-011100 | 2019-04-10 | FOR BAPCO REVIEW | 2019-04-25 | 2019-04-28 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000610 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F1002 | B-8788-AB-21-5 | 018-F-GAD-40098-001 | ARCH PANELS ASSEMBLY 018F1002/2002 | A1109 | 0AX | 3 | 2019-06-20 | CON-BMP-VTRA-012339 | 2019-06-20 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F1002 | B-8788-AB-21-6 | 018-F-GAD-40099-001 | ARCH PANELS SECTION 1 018F1002/2002 | A1109 | 0X | 3 | 2019-04-10 | CON-BMP-VTRA-011100 | 2019-04-10 | FOR BAPCO REVIEW | 2019-04-25 | 2019-04-28 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000610 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F1002 | B-8788-AB-21-7 | 018-F-GAD-40100-001 | ARCH PANELS SECTION 1 018F1002/2002 | A1109 | 0X | 3 | 2019-04-10 | CON-BMP-VTRA-011100 | 2019-04-10 | FOR BAPCO REVIEW | 2019-04-25 | 2019-04-28 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000610 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F1002 | B-8788-AB-21-8 | 018-F-GAD-40101-001 | RECYCLE HYDROGEN FURNACE FLUE GAS DUCT 018F1002 018F2002 | A1109 | 0X | 2 | 2019-06-29 | CON-BMP-VTRA-012573 | 2019-06-29 | FOR BAPCO REVIEW | 2019-07-15 |  |  | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F1002 | B-8788-AB-21-9 | 018-F-GAD-40102-001 | RECYCLE HYDROGEN FURNACE HV- 1080 FLUE GAS DAMPER 018F1002 018F2002 | A1109 | BX | 2 | 2019-06-29 | CON-BMP-VTRA-012576 | 2019-06-29 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F1002 | B-8788-AB-22-1 | 018-F-PLD-40022-001 | LOWER RADIANT PLATFORM 018F1002 018F2002 | A2008 | 0AX | 3 | 2019-06-19 | CON-BMP-VTRA-012306 | 2019-06-19 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F1002 | B-8788-AB-22-2 | 018-F-PLD-40023-001 | RECYCLE HYDROGEN FURNACE TOP RADIANT PLATFORM 018F1002 018F2002 | A2008 | 0AX | 3 | 2019-06-19 | CON-BMP-VTRA-012306 | 2019-06-19 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F1002 | B-8788-AB-22-3 | 018-F-PLD-40024-001 | ARCH RADIANT PLATFORM 018F1002 018F2002 | A2008 | 0AX | 3 | 2019-06-19 | CON-BMP-VTRA-012306 | 2019-06-19 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F1002 | B-8788-AB-22-4 | 018-F-PLD-40025-001 | UNIT RECYCLEN HYDROGEN FURNACE018F1002/018F2002 DAMPER PLATFORM | A2008 | BX | 2 | 2019-06-19 | CON-BMP-VTRA-012305 | 2019-06-19 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F1002 | B-8788-AB-22-5 | 018-F-PLD-40032-001 | RECYCLE HYDROGEN FURNACE PLATFORM TYPICAL DETAILS 018F1002 018F2002 | A2008 | 0X | 2 | 2019-06-26 | CON-BMP-VTRA-012508 | 2019-06-26 | FOR BAPCO REVIEW | 2019-07-11 |  |  | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F1002 | B-8788-AB-22-6 | 018-F-PLD-40077-001 | STAIR RECYCLE HYDROGEN FURNACE 018F1002 018F2002 | A2008 | 0X | 3 | 2019-06-29 | CON-BMP-VTRA-012579 | 2019-06-29 | FOR BAPCO REVIEW | 2019-07-15 |  |  | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F1002 | B-8788-AB-22-7 | 018-F-PLD-40026-001 | VERTICAL LADDERS FOR RADIANT ZONE RECYCLE HYDROGEN FURNACE 018F1002 018F2002 | A2008 | BX | 2 | 2019-06-26 | CON-BMP-VTRA-012506 | 2019-06-26 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F1002 | B-8788-AB-22-8 | 018-F-PLD-40027-001 | UNIT RECYCLE HYDROGEN FURNACE 018F1002/018F2002 VERTICAL LADDER FOR FLUE GAS DUCT | A2008 | BX | 2 | 2019-06-27 | CON-BMP-VTRA-012526 | 2019-06-27 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F1002 | B-8788-AB-23-1 | 018-F-PLD-40028-001 | GRATINGS FOR LOWER RADIANT PLATFORM RECYCLE HYDROGEN FURNACE 018F1002 018F2002 | A2008 | BX | 2 | 2019-06-27 | CON-BMP-VTRA-012526 | 2019-06-27 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F1002 | B-8788-AB-23-2 | 018-F-PLD-40029-001 | GRATINGS FOR TOP RADIANT PLATFORM RECYCLE HYDROGEN FURNACE 018F1002 018F2002 | A2008 | BX | 2 | 2019-06-27 | CON-BMP-VTRA-012526 | 2019-06-27 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F1002 | B-8788-AB-23-3 | 018-F-PLD-40030-001 | GRATINGS FOR ARCH PLATFORM RECYCLE HYDROGEN FURNACE 018F1002 018F2002 | A2008 | 0X | 3 | 2019-06-27 | CON-BMP-VTRA-012523 | 2019-06-27 | FOR BAPCO REVIEW | 2019-07-11 |  |  | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F1002 | B-8788-AB-23-4 | 018-F-PLD-40031-001 | UNIT RECYCLEN HYDROGEN FURNACE018F1002/018F2002 GRATING FOR DAMPER PLATFORM | A2008 | BX | 2 | 2019-06-27 | CON-BMP-VTRA-012526 | 2019-06-27 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F1002 | B-8788-AB-24-1 | 018-F-GAD-40078-001 | RECYCLE HYDROGEN FURNACE ACCESS DOOR ON RADIANT ZONE 018F1002/018F2002 | A1109 | AX | 2 | 2019-06-05 | CON-BMP-VTRA-011993 | 2019-06-05 | FOR BAPCO REVIEW | 2019-06-19 |  |  | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F1002 | B-8788-AB-24-3 | 018-F-GAD-40080-001 | RECYCLE HYDROGEN FURNACE EXPLOSION DOOR 018F1002/018F2002 | A1109 | AX | 2 | 2019-06-05 | CON-BMP-VTRA-011993 | 2019-06-05 | FOR BAPCO REVIEW | 2019-06-19 |  |  | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F1002 | B-8788-AB-24-4 | 018-F-GAD-40081-001 | RECYCLE HYDROGEN FURNACE TUBE REMOVAL DOOR 018F1002/018F2002 | A1109 | AX | 2 | 2019-06-05 | CON-BMP-VTRA-011993 | 2019-06-05 | FOR BAPCO REVIEW | 2019-06-19 |  |  | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F1002 | B-8788-AB-24-5 | 018-F-GAD-40082-001 | RECYCLE HYDROGEN FURNACE ACCESS DOOR FOR FLUE GAS DUCT AND DAMPER 018F1002 /018F2002 | A1109 | AX | 2 | 2019-06-05 | CON-BMP-VTRA-011993 | 2019-06-05 | FOR BAPCO REVIEW | 2019-06-19 |  |  | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F1002 | B-8788-AB-25-2 | 018-F-DLB-40002-001 | UNIT RECICLE HYDROGEN FURNACE NAMEPLATE 018F1002-018F2002 | A1112 | 0X | 2 | 2019-06-20 | CON-BMP-VTRA-012338 | 2019-06-20 | FOR BAPCO REVIEW | 2019-07-05 | 2019-07-10 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001259 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F1002 | B-8788-AB-25-3 | 018-F-GAD-40085-001 | EARTHING LUGS GENERAL ARRANGEMENT 018F1002/2002 | A1109 | 0X | 3 | 2019-04-29 | CON-BMP-VTRA-011307 | 2019-04-29 | FOR BAPCO REVIEW | 2019-05-14 | 2019-05-23 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000744 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F1002 | B-8788-AB-25-4 | 018-F-GAD-40086-001 | RECYCLE HYDROGEN FURNACE FIRE PROOFING GENERAL ASSEMBLY018F1002/2002 | A1109 | 0X | 3 | 2019-04-11 | CON-BMP-VTRA-011112 | 2019-04-11 | FOR BAPCO REVIEW | 2019-04-25 | 2019-04-28 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000608 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F1002 | B-8788-AB-25-5 | 018-F-PLD-40079-001 | RECYCLE HYDROGEN FURNACE SAFETY BAR 018F1002 018F2002 | A2008 | 0X | 3 | 2019-06-29 | CON-BMP-VTRA-012579 | 2019-06-29 | FOR BAPCO REVIEW | 2019-07-15 |  |  | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F1002 | B-8788-AB-25-6 | 018-F-PLD-40033-001 | LANDING SAFETY CAGES RECYCLE HYDROGEN FURNACE 018F1002 018F2002 | A2008 | BX | 2 | 2019-06-19 | CON-BMP-VTRA-012305 | 2019-06-19 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F1002 | B-8788-AB-26-1 | 018-F-GAD-40072-001 | UNIT RECYCLE HYDROGEN FURNACE 018F1002 018F2002 GENERAL ARRANGEMENT FOR LINING | A1101 | 0X | 3 | 2019-06-05 | CON-BMP-VTRA-011989 | 2019-06-05 | FOR BAPCO REVIEW | 2019-06-19 | 2019-06-29 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001085 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F1002 | B-8788-AB-26-2 | 018-F-GAD-40300-001 | ANCHOR FOR REFRACTORY RECYCLE HYDROGEN FURNACE 018F1002/2002 | A1101 | 0X | 3 | 2019-05-23 | CON-BMP-VTRA-011763 | 2019-05-23 | FOR BAPCO REVIEW | 2019-06-07 | 2019-06-17 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000961 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F1002 | B-8788-AB-28-1 | 018-F-DAT-40007-001 | DATA SHEET 018F1002 / 018F2002 HEATER DATA SHEET | A1001 | 0AX | 3 | 2019-07-10 | CON-BMP-VTRA-012794 | 2019-07-10 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F1002 | B-8788-AB-28-2 | 018-F-DAT-40008-001 | DATA SHEET - BURNER DATA SHEET WITH CAPACITY CURVES AND NOISE DATA SHEET 018F1002 018F2002 | A0105 | AX | 2 | 2019-02-06 | CON-BMP-VTRA-011442 | 2019-05-06 | FOR BAPCO REVIEW | 2019-05-21 | 2019-06-08 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000891 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F1002 | B-8788-AB-29-1 | 018-F-CAL-40010-001 | CALCULATION - HEATER MAIN STRUCTURAL CALCULATION 018F1002 018F2002 | A2201 | 0AX | 3 | 2019-06-19 | CON-BMP-VTRA-012311 | 2019-06-19 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F1002 | B-8788-AB-29-5 | 018-F-CAL-40009-001 | CALCULATION CASTING CALCULATION 018F1002 018F2002 | A2201 | 0X | 3 | 2019-04-29 | CON-BMP-VTRA-011294 | 2019-04-29 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F1002 | B-8788-AB-31-4 | 018-F-ITP-40016-001 | INSPECTION & TEST PLAN RADIANT COILS PREFABRICATION 018F0001 018F2002 | B1002 | 0X | 3 | 2019-05-07 | CON-BMP-VTRA-011460 | 2019-05-07 | FOR BAPCO REVIEW | 2019-05-21 | 2019-06-20 | 1-APPROVED BMP-ROC-VTRE-001007 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F1002 | B-8788-AB-32-3 | 018-F-MCD-40037-001 | WELDING BOOK RADIANT COILS PREFABRICATION 018F1002 018F2002 | B1304 | 0X | 3 | 2019-06-04 | CON-BMP-VTRA-011947 | 2019-06-04 | FOR BAPCO REVIEW | 2019-06-19 | 2019-06-15 | 1-APPROVED BMP-ROC-VTRE-000926 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F1002 | B-8788-AB-35-1 | 018-F-GAD-40091-001 | RECYCLE HYDROGEN FURNACE BURNER GENERAL ASSEMBLY AND DETAILS 018F1002 018F2002 | A1109 | AX | 2 | 2019-05-03 | CON-BMP-VTRA-011379 | 2019-05-03 | FOR BAPCO REVIEW | 2019-05-17 | 2019-05-24 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000759 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F1002 | B-8788-AB-70-1 | 018-F-S3D-40002-001 | 3D EQUIPMENT MODEL 018F1002/018F2002 | A2013 | BX | 4 | 2019-03-27 | CON-BMP-VTRA-010882 | 2019-03-27 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F2001 | B-8787-AB-13-1 SH.1 | 018-F-GAD-40005-001 | RADIANT COIL CELL. A AND CELL.B 018F1001 018F2001 | A1103 | 0X | 3 | 2019-05-21 | CON-BMP-VTRA-011696 | 2019-05-21 | FOR BAPCO REVIEW | 2019-06-05 | 2019-06-06 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000886 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F2001 | B-8787-AB-13-1 SH.2 | 018-F-GAD-40005-002 | RADIANT COIL CELL. A AND CELL.B 018F1001 018F2001 | A1103 | 0X | 3 | 2019-05-21 | CON-BMP-VTRA-011696 | 2019-05-21 | FOR BAPCO REVIEW | 2019-06-05 | 2019-06-06 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000886 | CLASS 2
076551C-000R-MR-0110-001 | MATERIAL REQUISITION 1 RHCU FIRED HEATERS | KIRCHNER ITALIA S.p.A. | 018F2002 | B-8788-AB-29-4 | 018-F-CAL-40007-001 | CALCULATION 018F1002 / 018F2002 COIL MECHANICAL CALC. (EX BAPCO N.018-F-CAL-00007- 001) | A1304 | 0X | 3 | 2019-04-26 | CON-BMP-VTRA-011269 | 2019-04-26 | FOR BAPCO REVIEW | 2019-05-14 | 2019-05-18 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000701 | CLASS 2
076551C-000R-MR-0110-003 | MATERIAL REQUISITION FOR 3HDU FIRED HEATER | KIRCHNER ITALIA S.p.A. | 021F0001 | B-8796-11-1 | 021-F-GAD-40052-001 | 021F0001 GENERAL ASSEMBLY ELEVATION (EX BAPCO N.021-F-GAD-00052-001) | A2001 | DX | 2 | 2019-05-06 | CON-BMP-VTRA-011436 | 2019-05-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0110-003 | MATERIAL REQUISITION FOR 3HDU FIRED HEATER | KIRCHNER ITALIA S.p.A. | 021F0001 | B-8796-11-2 | 021-F-GAD-40053-001 | 021F0001 GENERAL ASSEMBLY PLAN (EX BAPCO N. 021-F-GAD-00053-001) | A2001 | DX | 2 | 2019-05-06 | CON-BMP-VTRA-011436 | 2019-05-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0110-003 | MATERIAL REQUISITION FOR 3HDU FIRED HEATER | KIRCHNER ITALIA S.p.A. | 021F0001 | B-8796-11-3 | 021-F-GAD-40064-001 | COMBINED FEED HEATER GENERAL ARRANGEMENT FOR DAMPER MOVEMENT 021F0001 | A1109 | AX | 2 | 2019-05-06 | CON-BMP-VTRA-011439 | 2019-05-06 | FOR BAPCO REVIEW | 2019-05-21 | 2019-05-26 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000774 | CLASS 2
076551C-000R-MR-0110-003 | MATERIAL REQUISITION FOR 3HDU FIRED HEATER | KIRCHNER ITALIA S.p.A. | 021F0001 | B-8796-12-1 | 021-F-PED-40004-001 | 021F0001 GENERAL FOUNDATIONS AND LOADS (EX BAPCO N. 021-F-PED-00004-001) | A2006 | 1X | ASB | 2019-06-24 | CON-BMP-VTRA-012403 | 2019-06-24 | FOR BAPCO REVIEW | 2019-07-08 |  |  | CLASS 2
076551C-000R-MR-0110-003 | MATERIAL REQUISITION FOR 3HDU FIRED HEATER | KIRCHNER ITALIA S.p.A. | 021F0001 | B-8796-12-2 | 021-F-GAD-40015-001 | FOUNDATIONS DETAILS 021F0001 (EX BAPCO N. 021-F-GAD-00015-001) | A1101 | 0X | 3 | 2019-04-29 | CON-BMP-VTRA-011319 | 2019-04-29 | FOR BAPCO REVIEW | 2019-05-15 | 2019-05-23 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000737 | CLASS 2
076551C-000R-MR-0110-003 | MATERIAL REQUISITION FOR 3HDU FIRED HEATER | KIRCHNER ITALIA S.p.A. | 021F0001 | B-8796-12-3 | 021-F-PED-40005-001 | TEMPLATE FOUNDATION 021F0001 | A2006 | 0X | 2 | 2019-04-29 | CON-BMP-VTRA-011313 | 2019-04-29 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0110-003 | MATERIAL REQUISITION FOR 3HDU FIRED HEATER | KIRCHNER ITALIA S.p.A. | 021F0001 | B-8796-13-1 | 021-F-GAD-40011-001 | UNIT COMBINED FEED HEATER RADIANT COIL DRAWING 021F0001 (EX BAPCO N.021-F-GAD-00011- 001) | A1103 | 0AX | 3 | 2019-06-06 | CON-BMP-VTRA-012045 | 2019-06-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0110-003 | MATERIAL REQUISITION FOR 3HDU FIRED HEATER | KIRCHNER ITALIA S.p.A. | 021F0001 | B-8796-13-2 | 021-F-GAD-40012-001 | UNIT COMBINED FEED HEATER CONVECTION COIL DRAWING 021F0001 (EX BAPCO N.021-FGAD- 00012-001) | A1103 | 0AX | 3 | 2019-06-06 | CON-BMP-VTRA-012045 | 2019-06-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0110-003 | MATERIAL REQUISITION FOR 3HDU FIRED HEATER | KIRCHNER ITALIA S.p.A. | 021F0001 | B-8796-14-1 | 021-F-GAD-40013-001 | COMBINED FEED HEATER 021F0001 WELDING MAP RADIANT & CONVECTION COIL DRAWING 021F0001 | A1103 | 0X | 2 | 2019-04-29 | CON-BMP-VTRA-011317 | 2019-04-29 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0110-003 | MATERIAL REQUISITION FOR 3HDU FIRED HEATER | KIRCHNER ITALIA S.p.A. | 021F0001 | B-8796-17-1 | 021-F-GAD-40016-001 | CASTING SUPPORT FOR RADIANT COIL DRAWING 021F0001 (EX BAPCO N. 021-F-GAD-00016-001) | A1101 | 0AX | 3 | 2019-04-17 | CON-BMP-VTRA-011213 | 2019-04-17 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0110-003 | MATERIAL REQUISITION FOR 3HDU FIRED HEATER | KIRCHNER ITALIA S.p.A. | 021F0001 | B-8796-17-2 SH 1 OF 4 | 021-F-GAD-40060-001 | INTERMEDIATE TUBE SHEET FOR CONV. SECTION CA-01 021F0001 (EX BAPCO N. 021-F-GAD-00060- 001) | A1101 | 0X | 3 | 2019-02-14 | CON-BMP-VTRA-010425 | 2019-02-14 | FOR BAPCO REVIEW | 2019-02-28 | 2019-03-05 | 1-APPROVED BMP-ROC-VTRE-000252 | CLASS 2
076551C-000R-MR-0110-003 | MATERIAL REQUISITION FOR 3HDU FIRED HEATER | KIRCHNER ITALIA S.p.A. | 021F0001 | B-8796-17-2 SH 2 OF 4 | 021-F-GAD-40060-002 | INTERMEDIATE TUBE SHEET FOR CONV. SECTION CA-02 021F0001 (EX BAPCO N. 021-F-GAD-00060- 002) | A1101 | 0X | 3 | 2019-02-14 | CON-BMP-VTRA-010425 | 2019-02-14 | FOR BAPCO REVIEW | 2019-02-28 | 2019-03-05 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000252 | CLASS 2
076551C-000R-MR-0110-003 | MATERIAL REQUISITION FOR 3HDU FIRED HEATER | KIRCHNER ITALIA S.p.A. | 021F0001 | B-8796-17-2 SH 3 OF 4 | 021-F-GAD-40060-003 | INTERMEDIATE TUBE SHEET FOR CONV. SECTION CA-03 021F0001 (EX BAPCO N. 021-F-GAD-00060- 003) | A1101 | 0AX | 3 | 2019-03-19 | CON-BMP-VTRA-010761 | 2019-03-19 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0110-003 | MATERIAL REQUISITION FOR 3HDU FIRED HEATER | KIRCHNER ITALIA S.p.A. | 021F0001 | B-8796-17-2 SH 4 OF 4 | 021-F-GAD-40060-004 | INTERMEDIATE TUBE SHEET FOR CONV. SECTION CA-04 021F0001 (EX BAPCO N. 021-F-GAD-00060- 004) | A1101 | 0AX | 3 | 2019-03-19 | CON-BMP-VTRA-010761 | 2019-03-19 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0110-003 | MATERIAL REQUISITION FOR 3HDU FIRED HEATER | KIRCHNER ITALIA S.p.A. | 021F0001 | B-8796-17-2 SH. 5 OF 5 | 021-F-GAD-40060-005 | COMBINED FEED HEATER INTERMEDIATE TUBE SHEET FOR FUTURE ROW CONV. SECTION CA-18021F0001 | A1101 | 0X | 3 | 2019-05-06 | CON-BMP-VTRA-011419 | 2019-05-06 | FOR BAPCO INFORMATION |  | 2019-06-18 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000977 | CLASS 2
076551C-000R-MR-0110-003 | MATERIAL REQUISITION FOR 3HDU FIRED HEATER | KIRCHNER ITALIA S.p.A. | 021F0001 | B-8796-19-1 | 021-F-MCD-40001-001 | INSTRUMENTATION - INSTRUMENT HARDWARE PACKAGE 021F0001 | A3007 | AX | 2 | 2019-06-21 | CON-BMP-VTRA-012351 | 2019-06-21 | FOR BAPCO REVIEW | 2019-07-05 | 2019-07-10 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001276 | CLASS 2
076551C-000R-MR-0110-003 | MATERIAL REQUISITION FOR 3HDU FIRED HEATER | KIRCHNER ITALIA S.p.A. | 021F0001 | B-8796-19-1-7 | 021-F-INX-40003-001 | DATA SHEET 021F0001 UTILITIES CONSUMPTION LIST | A4001 | AX | 2 | 2019-05-31 | CON-BMP-VTRA-011907 | 2019-06-01 | FOR BAPCO REVIEW | 2019-06-17 | 2019-06-18 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000993 | CLASS 2
076551C-000R-MR-0110-003 | MATERIAL REQUISITION FOR 3HDU FIRED HEATER | KIRCHNER ITALIA S.p.A. | 021F0001 | B-8796-19-2 | 021-F-MCD-40002-001 | INSTRUMENTATION HARDWARE FREEZING PACKAGE 021F0001 | A3007 | AXX | 2 | 2019-06-24 | CON-BMP-VTRA-012412 | 2019-06-24 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0110-003 | MATERIAL REQUISITION FOR 3HDU FIRED HEATER | KIRCHNER ITALIA S.p.A. | 021F0001 | B-8796-19-3 | 021-F-MCD-40003-001 | INSTRUMNETATION SOFTWARE FREEZING PACKAGE 021F0001 | A3008 | BX | 2 | 2019-07-08 | CON-BMP-VTRA-012704 | 2019-07-08 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0110-003 | MATERIAL REQUISITION FOR 3HDU FIRED HEATER | KIRCHNER ITALIA S.p.A. | 021F0001 | B-8796-20-1 | 021-F-INX-00001-001 | LIST OF VENDOR DOCUMENT AND DRAWINGS 021F0001 | A0001 | BX | 4 | 2018-12-03 | CON-BMP-VTRA-010083 | 2018-12-03 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0110-003 | MATERIAL REQUISITION FOR 3HDU FIRED HEATER | KIRCHNER ITALIA S.p.A. | 021F0001 | B-8796-20-2 | 021-F-GAD-40017-001 | LIST OF MARKS 021F0001 | A1109 | AX | 2 | 2019-05-14 | CON-BMP-VTRA-011551 | 2019-05-14 | FOR BAPCO REVIEW | 2019-05-28 | 2019-05-27 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-0011551 | CLASS 2
076551C-000R-MR-0110-003 | MATERIAL REQUISITION FOR 3HDU FIRED HEATER | KIRCHNER ITALIA S.p.A. | 021F0001 | B-8796-20-3 | 021-F-GAD-40018-001 | LIST - LIST OF BOLTS 021F0001 | A1109 | AX | 2 | 2019-05-14 | CON-BMP-VTRA-011553 | 2019-05-14 | FOR BAPCO REVIEW | 2019-05-28 | 2019-05-28 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000813 | CLASS 2
076551C-000R-MR-0110-003 | MATERIAL REQUISITION FOR 3HDU FIRED HEATER | KIRCHNER ITALIA S.p.A. | 021F0001 | B-8796-20-4 | 021-F-GAD-40059-001 | GENERAL NOTES OF FABRICATION 021F0001 | A1109 | AX | 2 | 2019-03-08 | CON-BMP-VTRA-010645 | 2019-03-08 | FOR BAPCO REVIEW | 2019-03-25 | 2019-03-26 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000378 | CLASS 2
076551C-000R-MR-0110-003 | MATERIAL REQUISITION FOR 3HDU FIRED HEATER | KIRCHNER ITALIA S.p.A. | 021F0001 | B-8796-21-1 | 021-F-GAD-40019-001 | COMBINED FEED HEATER FLOOR PANELS ASSEMBLY 021F0001 | A1101 | 0AX | 3 | 2019-05-14 | CON-BMP-VTRA-011546 | 2019-05-14 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0110-003 | MATERIAL REQUISITION FOR 3HDU FIRED HEATER | KIRCHNER ITALIA S.p.A. | 021F0001 | B-8796-21-10 SH. 1 OF 2 | 021-F-GAD-40028-001 | CONVECTION SECTION END TUBE SHEET SIDE 0 021F0001 | A1101 | 0X | 3 | 2019-04-09 | CON-BMP-VTRA-011061 | 2019-04-09 | FOR BAPCO REVIEW | 2019-04-23 | 2019-04-25 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000585 | CLASS 2
076551C-000R-MR-0110-003 | MATERIAL REQUISITION FOR 3HDU FIRED HEATER | KIRCHNER ITALIA S.p.A. | 021F0001 | B-8796-21-10 SH.2 OF 2 | 021-F-GAD-40028-002 | CONVECTION SECTION END TUBE SHEET SIDE 0 021F0001 | A1101 | 0X | 3 | 2019-04-09 | CON-BMP-VTRA-011061 | 2019-04-09 | FOR BAPCO REVIEW | 2019-04-23 | 2019-04-25 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000585 | CLASS 2
076551C-000R-MR-0110-003 | MATERIAL REQUISITION FOR 3HDU FIRED HEATER | KIRCHNER ITALIA S.p.A. | 021F0001 | B-8796-21-11 | 021-F-GAD-40029-001 | CONVECTION SECTION INTERMEDIATE TUBE SHEET 021F0001 | A1101 | 0AX | 3 | 2019-04-17 | CON-BMP-VTRA-011213 | 2019-04-17 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0110-003 | MATERIAL REQUISITION FOR 3HDU FIRED HEATER | KIRCHNER ITALIA S.p.A. | 021F0001 | B-8796-21-12 | 021-F-GAD-40030-001 | HEADER BOXES ASSEMBLY 021F0001 | A1101 | 0X | 3 | 2019-04-09 | CON-BMP-VTRA-011061 | 2019-04-09 | FOR BAPCO REVIEW | 2019-04-23 | 2019-04-25 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000585 | CLASS 2
076551C-000R-MR-0110-003 | MATERIAL REQUISITION FOR 3HDU FIRED HEATER | KIRCHNER ITALIA S.p.A. | 021F0001 | B-8796-21-13 | 021-F-GAD-40031-001 | HEADER BOXES SECTIONS AND DETAILS 021F0001 | A1101 | 0X | 3 | 2019-04-09 | CON-BMP-VTRA-011061 | 2019-04-09 | FOR BAPCO REVIEW | 2019-04-23 | 2019-04-25 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000585 | CLASS 2
076551C-000R-MR-0110-003 | MATERIAL REQUISITION FOR 3HDU FIRED HEATER | KIRCHNER ITALIA S.p.A. | 021F0001 | B-8796-21-14 | 021-F-GAD-40032-001 | BREECHING ASSEMBLY COMBINED FEED HEATER 021F0001 | A1101 | 0AX | 3 | 2019-04-26 | CON-BMP-VTRA-011267 | 2019-04-26 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0110-003 | MATERIAL REQUISITION FOR 3HDU FIRED HEATER | KIRCHNER ITALIA S.p.A. | 021F0001 | B-8796-21-15 | 021-F-GAD-40033-001 | STACK ASSEMBLY 1 MODULE 021F0001 | A1101 | 0X | 3 | 2019-04-10 | CON-BMP-VTRA-011082 | 2019-04-10 | FOR BAPCO REVIEW | 2019-04-24 | 2019-04-25 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000574 | CLASS 2
076551C-000R-MR-0110-003 | MATERIAL REQUISITION FOR 3HDU FIRED HEATER | KIRCHNER ITALIA S.p.A. | 021F0001 | B-8796-21-16 | 021-F-GAD-40056-001 | COMBINED FEED HEATER STACK ASSEMBLY II MODULE 021F0001 | A2009 | 0AX | 3 | 2019-05-28 | CON-BMP-VTRA-011816 | 2019-05-29 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0110-003 | MATERIAL REQUISITION FOR 3HDU FIRED HEATER | KIRCHNER ITALIA S.p.A. | 021F0001 | B-8796-21-18 | 021-F-GAD-40002-001 | COMBINED FEED HEATER - DAMPER FOR STACK ASSEMBLY AND DETAILS 021F0001 | A1109 | CX | 2 | 2019-06-28 | CON-BMP-VTRA-012552 | 2019-06-28 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0110-003 | MATERIAL REQUISITION FOR 3HDU FIRED HEATER | KIRCHNER ITALIA S.p.A. | 021F0001 | B-8796-21-19 | 021-F-GAD-40057-001 | STRUCTURE FOR SUPPORT RADIANT COIL COMBINED FEED HEATER 021F0001 | A2007 | 0X | 3 | 2019-04-18 | CON-BMP-VTRA-011220 | 2019-04-18 | FOR BAPCO REVIEW | 2019-05-03 | 2019-05-15 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000684 | CLASS 2
076551C-000R-MR-0110-003 | MATERIAL REQUISITION FOR 3HDU FIRED HEATER | KIRCHNER ITALIA S.p.A. | 021F0001 | B-8796-21-2 | 021-F-GAD-40020-001 | FLOOR PANELS DETAILS 021F0001 | A1101 | 0X | 3 | 2019-03-16 | CON-BMP-VTRA-010709 | 2019-03-16 | FOR BAPCO REVIEW | 2019-04-01 | 2019-04-05 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000463 | CLASS 2
076551C-000R-MR-0110-003 | MATERIAL REQUISITION FOR 3HDU FIRED HEATER | KIRCHNER ITALIA S.p.A. | 021F0001 | B-8796-21-20 | 021-F-GAD-40058-001 | STRUCTURE FOR SUPPORT CONVECTION COIL 021F0001 | A2007 | AX | 2 | 2019-04-09 | CON-BMP-VTRA-011054 | 2019-04-09 | FOR BAPCO REVIEW | 2019-04-23 | 2019-04-25 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000586 | CLASS 2
076551C-000R-MR-0110-003 | MATERIAL REQUISITION FOR 3HDU FIRED HEATER | KIRCHNER ITALIA S.p.A. | 021F0001 | B-8796-21-3 | 021-F-GAD-40021-001 | RADIANT PANELS ASSEMBLY 021F0001 | A1101 | 0X | 3 | 2019-04-09 | CON-BMP-VTRA-011061 | 2019-04-09 | FOR BAPCO REVIEW | 2019-04-23 | 2019-04-25 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000585 | CLASS 2
076551C-000R-MR-0110-003 | MATERIAL REQUISITION FOR 3HDU FIRED HEATER | KIRCHNER ITALIA S.p.A. | 021F0001 | B-8796-21-4 | 021-F-GAD-40022-001 | RADIANT PANELS SECTIONS 021F0001 | A1101 | 0X | 3 | 2019-04-09 | CON-BMP-VTRA-011061 | 2019-04-09 | FOR BAPCO REVIEW | 2019-04-23 | 2019-04-25 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000585 | CLASS 2
076551C-000R-MR-0110-003 | MATERIAL REQUISITION FOR 3HDU FIRED HEATER | KIRCHNER ITALIA S.p.A. | 021F0001 | B-8796-21-5 | 021-F-GAD-40023-001 | RADIANT PANELS DETAILS 021F0001 | A1101 | 0X | 3 | 2019-04-09 | CON-BMP-VTRA-011061 | 2019-04-09 | FOR BAPCO REVIEW | 2019-04-23 | 2019-04-25 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-00585 | CLASS 2
076551C-000R-MR-0110-003 | MATERIAL REQUISITION FOR 3HDU FIRED HEATER | KIRCHNER ITALIA S.p.A. | 021F0001 | B-8796-21-6 | 021-F-GAD-40024-001 | ARCH PANELS ASSEMBLY 021F0001 | A1101 | 0X | 3 | 2019-04-10 | CON-BMP-VTRA-011082 | 2019-04-10 | FOR BAPCO REVIEW | 2019-04-24 | 2019-04-25 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000574 | CLASS 2
076551C-000R-MR-0110-003 | MATERIAL REQUISITION FOR 3HDU FIRED HEATER | KIRCHNER ITALIA S.p.A. | 021F0001 | B-8796-21-7 | 021-F-GAD-40025-001 | ARCH PANELS DETAILS 021F0001 | A1101 | 0X | 3 | 2019-04-10 | CON-BMP-VTRA-011082 | 2019-04-10 | FOR BAPCO REVIEW | 2019-04-24 | 2019-04-25 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000574 | CLASS 2
076551C-000R-MR-0110-003 | MATERIAL REQUISITION FOR 3HDU FIRED HEATER | KIRCHNER ITALIA S.p.A. | 021F0001 | B-8796-21-8 SH. 1 OF 2 | 021-F-GAD-40026-001 | CONVECTION SECTION PLAN & ELEVATION FROM 270 021F0001 | A1101 | 0X | 3 | 2019-04-09 | CON-BMP-VTRA-011061 | 2019-04-09 | FOR BAPCO REVIEW | 2019-04-23 | 2019-04-25 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000585 | CLASS 2
076551C-000R-MR-0110-003 | MATERIAL REQUISITION FOR 3HDU FIRED HEATER | KIRCHNER ITALIA S.p.A. | 021F0001 | B-8796-21-8 SH. 2 OF 2 | 021-F-GAD-40026-002 | CONVECTION SECTION LATERAL VIEW FROM 0 021F0001 | A1101 | 0X | 3 | 2019-04-09 | CON-BMP-VTRA-011061 | 2019-04-09 | FOR BAPCO REVIEW | 2019-04-23 | 2019-04-25 | 1-APPROVED BMP-ROC-VTRE-00585 | CLASS 2
076551C-000R-MR-0110-003 | MATERIAL REQUISITION FOR 3HDU FIRED HEATER | KIRCHNER ITALIA S.p.A. | 021F0001 | B-8796-21-9 SH. 1 OF 2 | 021-F-GAD-40027-001 | CONVECTION SECTION PLAN & ELEVATION FROM 90 021F0001 | A1101 | 0X | 3 | 2019-04-09 | CON-BMP-VTRA-011061 | 2019-04-09 | FOR BAPCO REVIEW | 2019-04-23 | 2019-04-25 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000585 | CLASS 2
076551C-000R-MR-0110-003 | MATERIAL REQUISITION FOR 3HDU FIRED HEATER | KIRCHNER ITALIA S.p.A. | 021F0001 | B-8796-21-9 SH. 2 OF 2 | 021-F-GAD-40027-002 | CONVECTION SECTION LATERAL VVIEW FROM 180 021F0001 | A1101 | 0X | 3 | 2019-04-09 | CON-BMP-VTRA-011061 | 2019-04-09 | FOR BAPCO REVIEW | 2019-04-23 | 2019-04-25 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000585 | CLASS 2
076551C-000R-MR-0110-003 | MATERIAL REQUISITION FOR 3HDU FIRED HEATER | KIRCHNER ITALIA S.p.A. | 021F0001 | B-8796-22-1 | 021-F-PLD-40001-001 | COMBINED FEED HEATER LOWER RADIANT PLATFORM DRAWING EL+3300 021F0001 | A2008 | 0X | 2 | 2019-04-29 | CON-BMP-VTRA-011314 | 2019-04-29 | FOR BAPCO REVIEW | 2019-05-15 | 2019-05-23 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000732 | CLASS 2
076551C-000R-MR-0110-003 | MATERIAL REQUISITION FOR 3HDU FIRED HEATER | KIRCHNER ITALIA S.p.A. | 021F0001 | B-8796-22-10 | 021-F-PLD-40010-001 | VERTICAL LADDERS FOR STACK 021F0001 | A2008 | 0X | 3 | 2019-05-14 | CON-BMP-VTRA-011572 | 2019-05-14 | FOR BAPCO REVIEW | 2019-05-29 | 2019-05-30 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000842 | CLASS 2
076551C-000R-MR-0110-003 | MATERIAL REQUISITION FOR 3HDU FIRED HEATER | KIRCHNER ITALIA S.p.A. | 021F0001 | B-8796-22-11 | 021-F-PLD-40019-001 | COMBINED FEED HEATER TYPICAL STANDARD DETAILS FOR PLATFORMS STAIRS HANDRAILS ANDLADDERS 021F0001 | A2008 | 0X | 3 | 2019-06-05 | CON-BMP-VTRA-011995 | 2019-06-05 | FOR BAPCO REVIEW | 2019-06-19 | 2019-06-30 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001099 | CLASS 2
076551C-000R-MR-0110-003 | MATERIAL REQUISITION FOR 3HDU FIRED HEATER | KIRCHNER ITALIA S.p.A. | 021F0001 | B-8796-22-2 | 021-F-PLD-40002-001 | COMBINED FEED HEATER INTERMEDIATE RADIANT PLATFORM DRAWING EL+6900 021F0001 | A2008 | 0X | 2 | 2019-04-29 | CON-BMP-VTRA-011314 | 2019-04-29 | FOR BAPCO REVIEW | 2019-05-15 | 2019-05-23 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000732 | CLASS 2
076551C-000R-MR-0110-003 | MATERIAL REQUISITION FOR 3HDU FIRED HEATER | KIRCHNER ITALIA S.p.A. | 021F0001 | B-8796-22-3 | 021-F-PLD-40003-001 | COMBINED FEED HEATER UPPER RADIANT PLATFORM DRAWING EL+10500 EL+11700 021F0001 | A2008 | 0X | 2 | 2019-04-29 | CON-BMP-VTRA-011314 | 2019-04-29 | FOR BAPCO REVIEW | 2019-05-15 | 2019-05-23 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000732 | CLASS 2
076551C-000R-MR-0110-003 | MATERIAL REQUISITION FOR 3HDU FIRED HEATER | KIRCHNER ITALIA S.p.A. | 021F0001 | B-8796-22-4 SH.1 OF 4 | 021-F-PLD-40004-001 | UNIT COMBINED FEED HEATER CONVECTION PLATFORM DRAWING - EL.+14200/14400 021F0001 | A2008 | 0AX | 3 | 2019-06-06 | CON-BMP-VTRA-012057 | 2019-06-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0110-003 | MATERIAL REQUISITION FOR 3HDU FIRED HEATER | KIRCHNER ITALIA S.p.A. | 021F0001 | B-8796-22-4 SH.2 OF 4 | 021-F-PLD-40004-002 | CONVECTION PLATFORM DRAWING EL+16673 021F0001 | A2008 | 0X | 2 | 2019-04-09 | CON-BMP-VTRA-011055 | 2019-04-09 | FOR BAPCO REVIEW | 2019-04-23 | 2019-04-25 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000587 | CLASS 2
076551C-000R-MR-0110-003 | MATERIAL REQUISITION FOR 3HDU FIRED HEATER | KIRCHNER ITALIA S.p.A. | 021F0001 | B-8796-22-4 SH.3 OF 4 | 021-F-PLD-40004-003 | COMBINED FEED HEATER CONVECTION PLATFORM DRAWIONG EL+18676 021F0001 | A2008 | 0X | 2 | 2019-04-29 | CON-BMP-VTRA-011311 | 2019-04-29 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0110-003 | MATERIAL REQUISITION FOR 3HDU FIRED HEATER | KIRCHNER ITALIA S.p.A. | 021F0001 | B-8796-22-4 SH.4 OF 4 | 021-F-PLD-40004-004 | COMBINED FEED HEATER CONVECTION PLATFORM DRAWING - EL+19804 021F0001 | A2008 | 0X | 3 | 2019-05-14 | CON-BMP-VTRA-011561 | 2019-05-14 | FOR BAPCO REVIEW | 2019-05-28 | 2019-05-28 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000824 | CLASS 2
076551C-000R-MR-0110-003 | MATERIAL REQUISITION FOR 3HDU FIRED HEATER | KIRCHNER ITALIA S.p.A. | 021F0001 | B-8796-22-5 | 021-F-PLD-40005-001 | COMBINED FEED HEATER BREECHING PLATFORM DRAWING EL+22714 021F0001 | A2008 | 0X | 3 | 2019-06-06 | CON-BMP-VTRA-012028 | 2019-06-06 | FOR BAPCO REVIEW | 2019-06-20 | 2019-06-30 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001103 | CLASS 2
076551C-000R-MR-0110-003 | MATERIAL REQUISITION FOR 3HDU FIRED HEATER | KIRCHNER ITALIA S.p.A. | 021F0001 | B-8796-22-6 | 021-F-PLD-40006-001 | 021F0001 UNIT COMBINED FEED HEATER - STACK PLATFORM DRAWING | A2008 | 0AX | 3 | 2019-06-06 | CON-BMP-VTRA-012057 | 2019-06-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0110-003 | MATERIAL REQUISITION FOR 3HDU FIRED HEATER | KIRCHNER ITALIA S.p.A. | 021F0001 | B-8796-22-7 | 021-F-PLD-40007-001 | COMBINED FEED HEATER STAIR ASSEMBLY 021F0001 | A2008 | 0AX | 3 | 2019-06-07 | CON-BMP-VTRA-012099 | 2019-06-07 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0110-003 | MATERIAL REQUISITION FOR 3HDU FIRED HEATER | KIRCHNER ITALIA S.p.A. | 021F0001 | B-8796-22-8 SH.1 OF 2 | 021-F-PLD-40008-001 | VERTICAL LADDERS FOR RADIANT ZONE 021F0001 | A2008 | 0X | 3 | 2019-05-14 | CON-BMP-VTRA-011572 | 2019-05-14 | FOR BAPCO REVIEW | 2019-05-29 | 2019-05-30 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000842 | CLASS 2
076551C-000R-MR-0110-003 | MATERIAL REQUISITION FOR 3HDU FIRED HEATER | KIRCHNER ITALIA S.p.A. | 021F0001 | B-8796-22-8 SH.2 OF 2 | 021-F-PLD-40008-002 | COMBINED FEED HEATER VERTICAL LADDERS FOR RADIANT ZONE 021F0001 | A2008 | 0X | 2 | 2019-04-29 | CON-BMP-VTRA-011311 | 2019-04-29 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0110-003 | MATERIAL REQUISITION FOR 3HDU FIRED HEATER | KIRCHNER ITALIA S.p.A. | 021F0001 | B-8796-22-9 SH.1 OF 2 | 021-F-PLD-40009-001 | VERTICAL LADDERS FOR CONVECTION ZONE 021F0001 | A2008 | 0X | 3 | 2019-04-26 | CON-BMP-VTRA-011274 | 2019-04-26 | FOR BAPCO REVIEW | 2019-05-14 | 2019-05-15 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000688 | CLASS 2
076551C-000R-MR-0110-003 | MATERIAL REQUISITION FOR 3HDU FIRED HEATER | KIRCHNER ITALIA S.p.A. | 021F0001 | B-8796-22-9 SH.2 OF 2 | 021-F-PLD-40009-002 | VERTICAL LADDERS FOR CONVECTION ZONE 021F0001 | A2008 | 0X | 3 | 2019-04-26 | CON-BMP-VTRA-011274 | 2019-04-26 | FOR BAPCO REVIEW | 2019-05-14 | 2019-05-15 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000688 | CLASS 2
076551C-000R-MR-0110-003 | MATERIAL REQUISITION FOR 3HDU FIRED HEATER | KIRCHNER ITALIA S.p.A. | 021F0001 | B-8796-23-1 | 021-F-PLD-40011-001 | COMBINED FEED HEATER 021F0001 LOWER RADIANT PLATFORM DRAWINGEL.+3300 - GRATINGS 021F0001 | A2008 | AX | 3 | 2019-05-13 | CON-BMP-VTRA-011544 | 2019-05-13 | FOR BAPCO REVIEW | 2019-05-28 | 2019-05-28 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000817 | CLASS 2
076551C-000R-MR-0110-003 | MATERIAL REQUISITION FOR 3HDU FIRED HEATER | KIRCHNER ITALIA S.p.A. | 021F0001 | B-8796-23-2 | 021-F-PLD-40012-001 | COMBINED FEED HEATER 021F0001 INTERMEDIATE RADIANT PLATFORM DRAWING EL.+6900-GRATINGS | A2008 | AX | 3 | 2019-05-13 | CON-BMP-VTRA-011544 | 2019-05-13 | FOR BAPCO REVIEW | 2019-05-28 | 2019-05-28 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000817 | CLASS 2
076551C-000R-MR-0110-003 | MATERIAL REQUISITION FOR 3HDU FIRED HEATER | KIRCHNER ITALIA S.p.A. | 021F0001 | B-8796-23-3 | 021-F-PLD-40013-001 | COMBINED FEED HEATER 021F0001 UPPER RADIANT PLATFORM DRAWING EL.+10500/11700-GRATINGS | A2008 | AX | 2 | 2019-05-14 | CON-BMP-VTRA-011554 | 2019-05-14 | FOR BAPCO REVIEW | 2019-05-28 | 2019-05-28 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000823 | CLASS 2
076551C-000R-MR-0110-003 | MATERIAL REQUISITION FOR 3HDU FIRED HEATER | KIRCHNER ITALIA S.p.A. | 021F0001 | B-8796-23-4 SH 4 OF 4 | 021-F-PLD-40014-004 | COMBINED FEED HEATER 021F0001 CONVECTION PLATFORM DRAWING EL.+19804-GRATINGS | A2008 | AX | 2 | 2019-05-14 | CON-BMP-VTRA-011554 | 2019-05-14 | FOR BAPCO REVIEW | 2019-05-28 | 2019-05-28 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000823 | CLASS 2
076551C-000R-MR-0110-003 | MATERIAL REQUISITION FOR 3HDU FIRED HEATER | KIRCHNER ITALIA S.p.A. | 021F0001 | B-8796-23-4 SH. 2 OF 4 | 021-F-PLD-40014-002 | COMBINED FEED HEATER CONVECTION PLATFORM DRAWING EL.16683 GRATINGS 021F0001 | A2008 | AX | 2 | 2019-03-08 | CON-BMP-VTRA-011257 | 2019-04-26 | FOR BAPCO REVIEW | 2019-05-10 | 2019-05-15 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000692 | CLASS 2
076551C-000R-MR-0110-003 | MATERIAL REQUISITION FOR 3HDU FIRED HEATER | KIRCHNER ITALIA S.p.A. | 021F0001 | B-8796-23-4 SH. 3 OF 4 | 021-F-PLD-40014-003 | COMBINED FEED HEATER 021F0001 CONVECTION PLATFORM DRAWING - EL. 18158 -GRATINGS | A2008 | AX | 2 | 2019-05-14 | CON-BMP-VTRA-011554 | 2019-05-14 | FOR BAPCO REVIEW | 2019-05-28 | 2019-05-28 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000823 | CLASS 2
076551C-000R-MR-0110-003 | MATERIAL REQUISITION FOR 3HDU FIRED HEATER | KIRCHNER ITALIA S.p.A. | 021F0001 | B-8796-23-4 SH.1 OF 4 | 021-F-PLD-40014-001 | COMBINED FEED HEATER 021F0001 CONVECTION PLATFORM DRAWING - EL.+14200/ 14400-GRATINGS | A2008 | AX | 2 | 2019-05-14 | CON-BMP-VTRA-011554 | 2019-05-14 | FOR BAPCO REVIEW | 2019-05-28 | 2019-05-28 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000823 | CLASS 2
076551C-000R-MR-0110-003 | MATERIAL REQUISITION FOR 3HDU FIRED HEATER | KIRCHNER ITALIA S.p.A. | 021F0001 | B-8796-23-5 | 021-F-PLD-40015-001 | COMBINED FEED HEATER BREECHING PLATFORM DRAWING EL.+22714 - GRATINGS 021F0001 | A2008 | AX | 2 | 2019-05-14 | CON-BMP-VTRA-011554 | 2019-05-14 | FOR BAPCO REVIEW | 2019-05-28 | 2019-05-28 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000823 | CLASS 2
076551C-000R-MR-0110-003 | MATERIAL REQUISITION FOR 3HDU FIRED HEATER | KIRCHNER ITALIA S.p.A. | 021F0001 | B-8796-23-6 | 021-F-PLD-40016-001 | STACK PLATFORM DRAWING - GRATINGS 021F0001 | A2008 | 0X | 3 | 2019-04-08 | CON-BMP-VTRA-011051 | 2019-04-08 | FOR BAPCO REVIEW | 2019-04-22 | 2019-04-28 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000597 | CLASS 2
076551C-000R-MR-0110-003 | MATERIAL REQUISITION FOR 3HDU FIRED HEATER | KIRCHNER ITALIA S.p.A. | 021F0001 | B-8796-24-1 | 021-F-GAD-40035-001 | COMBINED FEED HEATER ACCESS DOOR ON FLOOR 021F0001 | A1101 | BX | 2 | 2019-05-14 | CON-BMP-VTRA-011548 | 2019-05-14 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0110-003 | MATERIAL REQUISITION FOR 3HDU FIRED HEATER | KIRCHNER ITALIA S.p.A. | 021F0001 | B-8796-24-2 | 021-F-GAD-40036-001 | COMBINED FEED HEATER OBSERVATION DOOR ON FLOOR 021F0001 | A1101 | 0X | 3 | 2019-04-29 | CON-BMP-VTRA-011320 | 2019-04-29 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0110-003 | MATERIAL REQUISITION FOR 3HDU FIRED HEATER | KIRCHNER ITALIA S.p.A. | 021F0001 | B-8796-24-3 | 021-F-GAD-40037-001 | COMBINED FEED HEATER OBSERVATION DOOR FOR RADIANT (CAST IRON ) 021F0001 | A1101 | 0X | 3 | 2019-04-29 | CON-BMP-VTRA-011320 | 2019-04-29 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0110-003 | MATERIAL REQUISITION FOR 3HDU FIRED HEATER | KIRCHNER ITALIA S.p.A. | 021F0001 | B-8796-24-5 | 021-F-GAD-40039-001 | UNIT 021F0001 COMBINED FEED HEATER TUBE REMOVAL DOOR | A1101 | 0X | 3 | 2019-05-14 | CON-BMP-VTRA-011571 | 2019-05-14 | FOR BAPCO REVIEW | 2019-05-29 | 2019-05-30 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000841 | CLASS 2
076551C-000R-MR-0110-003 | MATERIAL REQUISITION FOR 3HDU FIRED HEATER | KIRCHNER ITALIA S.p.A. | 021F0001 | B-8796-24-6 | 021-F-GAD-40040-001 | INSPECTION DOOR FOR CONVECTIONSECTION 021F0001 | A1101 | BX | 2 | 2019-04-09 | CON-BMP-VTRA-011057 | 2019-04-09 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0110-003 | MATERIAL REQUISITION FOR 3HDU FIRED HEATER | KIRCHNER ITALIA S.p.A. | 021F0001 | B-8796-24-7 | 021-F-GAD-40041-001 | ACCESS DOOR ON BREECHING 021F0001 | A1101 | 0X | 3 | 2019-04-09 | CON-BMP-VTRA-011061 | 2019-04-09 | FOR BAPCO REVIEW | 2019-04-23 | 2019-04-25 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000585 | CLASS 2
076551C-000R-MR-0110-003 | MATERIAL REQUISITION FOR 3HDU FIRED HEATER | KIRCHNER ITALIA S.p.A. | 021F0001 | B-8796-24-8 | 021-F-GAD-40042-001 | ACCESS DOOR ON STACK 021F0001 | A1101 | BX | 2 | 2019-04-09 | CON-BMP-VTRA-011057 | 2019-04-09 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0110-003 | MATERIAL REQUISITION FOR 3HDU FIRED HEATER | KIRCHNER ITALIA S.p.A. | 021F0001 | B-8796-25-1 | 021-F-GAD-40043-001 | INSTRUMENT CONNECTIONS COMBINED FEED HEATER 021F0001 | A1101 | 0X | 3 | 2019-04-18 | CON-BMP-VTRA-011219 | 2019-04-18 | FOR BAPCO REVIEW | 2019-05-03 | 2019-05-09 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000644 | CLASS 2
076551C-000R-MR-0110-003 | MATERIAL REQUISITION FOR 3HDU FIRED HEATER | KIRCHNER ITALIA S.p.A. | 021F0001 | B-8796-25-2 | 021-F-DLB-40001-001 | COMBINED FEED HEATER NAME PLATE 021F0001 | A1112 | BX | 2 | 2019-06-25 | CON-BMP-VTRA-012417 | 2019-06-25 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0110-003 | MATERIAL REQUISITION FOR 3HDU FIRED HEATER | KIRCHNER ITALIA S.p.A. | 021F0001 | B-8796-25-3 | 021-F-PLD-40017-001 | COMBINED FEED HEATER SAFETY BAR 021F0001 | A2008 | 0X | 3 | 2019-05-14 | CON-BMP-VTRA-011561 | 2019-05-14 | FOR BAPCO REVIEW | 2019-05-28 |  |  | CLASS 2
076551C-000R-MR-0110-003 | MATERIAL REQUISITION FOR 3HDU FIRED HEATER | KIRCHNER ITALIA S.p.A. | 021F0001 | B-8796-25-4 | 021-F-PLD-40018-001 | UNIT COMBINED FEED HEATER 021F0001 LANDING SAFETY CAGES | A2008 | AX | 2 | 2019-06-05 | CON-BMP-VTRA-011994 | 2019-06-05 | FOR BAPCO REVIEW | 2019-06-19 | 2019-07-02 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001135 | CLASS 2
076551C-000R-MR-0110-003 | MATERIAL REQUISITION FOR 3HDU FIRED HEATER | KIRCHNER ITALIA S.p.A. | 021F0001 | B-8796-25-5 | 021-F-GAD-40044-001 | COMBINED FEED HEATER 021F0001 EARTH LUGS DISPOSITION | A1109 | 0X | 3 | 2019-05-28 | CON-BMP-VTRA-011817 | 2019-05-29 | FOR BAPCO REVIEW | 2019-06-12 | 2019-06-16 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000947 | CLASS 2
076551C-000R-MR-0110-003 | MATERIAL REQUISITION FOR 3HDU FIRED HEATER | KIRCHNER ITALIA S.p.A. | 021F0001 | B-8796-25-6 | 021-F-GAD-40065-001 | COMBINED FEED HEATER FIREPROOFING GENERAL ASSEMBLY 021F0001 | A1109 | 0X | 3 | 2019-06-05 | CON-BMP-VTRA-011982 | 2019-06-05 | FOR BAPCO REVIEW | 2019-06-19 | 2019-06-29 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001102 | CLASS 2
076551C-000R-MR-0110-003 | MATERIAL REQUISITION FOR 3HDU FIRED HEATER | KIRCHNER ITALIA S.p.A. | 021F0001 | B-8796-26-1 | 021-F-GAD-40045-001 | 021F0001 ANCHORS FOR REFRACTORY | A1101 | CX | 2 | 2019-04-17 | CON-BMP-VTRA-011212 | 2019-04-17 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0110-003 | MATERIAL REQUISITION FOR 3HDU FIRED HEATER | KIRCHNER ITALIA S.p.A. | 021F0001 | B-8796-26-2 | 021-F-GAD-40046-001 | ANCHORS DISPOSITION RADIANT ZONE 021F0001 | A1101 | 0X | 3 | 2019-05-14 | CON-BMP-VTRA-011558 | 2019-05-14 | FOR BAPCO REVIEW | 2019-05-28 | 2019-05-28 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000814 | CLASS 2
076551C-000R-MR-0110-003 | MATERIAL REQUISITION FOR 3HDU FIRED HEATER | KIRCHNER ITALIA S.p.A. | 021F0001 | B-8796-26-3 | 021-F-GAD-40047-001 | ANCHORS DISPOSITION ARCH 021F0001 | A1101 | 0X | 3 | 2019-05-14 | CON-BMP-VTRA-011558 | 2019-05-14 | FOR BAPCO REVIEW | 2019-05-28 | 2019-05-28 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000814 | CLASS 2
076551C-000R-MR-0110-003 | MATERIAL REQUISITION FOR 3HDU FIRED HEATER | KIRCHNER ITALIA S.p.A. | 021F0001 | B-8796-26-4 | 021-F-GAD-40048-001 | ANCHORS DISPOSITION CONVECTION ZONE 021F0001 | A1101 | 0X | 3 | 2019-05-14 | CON-BMP-VTRA-011558 | 2019-05-14 | FOR BAPCO REVIEW | 2019-05-28 | 2019-05-28 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000814 | CLASS 2
076551C-000R-MR-0110-003 | MATERIAL REQUISITION FOR 3HDU FIRED HEATER | KIRCHNER ITALIA S.p.A. | 021F0001 | B-8796-26-5 | 021-F-GAD-40049-001 | ANCHORS DISPOSITION BREECHING 021F0001 | A1101 | 0X | 3 | 2019-05-14 | CON-BMP-VTRA-011558 | 2019-05-14 | FOR BAPCO REVIEW | 2019-05-28 | 2019-05-28 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000814 | CLASS 2
076551C-000R-MR-0110-003 | MATERIAL REQUISITION FOR 3HDU FIRED HEATER | KIRCHNER ITALIA S.p.A. | 021F0001 | B-8796-26-6 | 021-F-GAD-40050-001 | ANCHORS DISPOSITION STACK 021F0001 | A1101 | 0X | 3 | 2019-05-14 | CON-BMP-VTRA-011558 | 2019-05-14 | FOR BAPCO REVIEW | 2019-05-28 | 2019-05-28 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000814 | CLASS 2
076551C-000R-MR-0110-003 | MATERIAL REQUISITION FOR 3HDU FIRED HEATER | KIRCHNER ITALIA S.p.A. | 021F0001 | B-8796-26-7 | 021-F-GAD-40003-001 | COMBINED FEED HEATER GENERAL ARRANGEMENT FOR REFRACTORY MATERIAL AND LINING 021F0001 | A1101 | BX | 2 | 2019-05-14 | CON-BMP-VTRA-011547 | 2019-05-14 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0110-003 | MATERIAL REQUISITION FOR 3HDU FIRED HEATER | KIRCHNER ITALIA S.p.A. | 021F0001 | B-8796-26-8 | 021-F-GAD-40063-001 | GENERAL ARRANGEMENT FOR REFRACTORY MATERIAL AND LINING - INSTALLATION DETAILS 021F0001 | A1101 | 0X | 3 | 2019-05-14 | CON-BMP-VTRA-011566 | 2019-05-14 | FOR BAPCO REVIEW | 2019-05-29 | 2019-05-30 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000840 | CLASS 2
076551C-000R-MR-0110-003 | MATERIAL REQUISITION FOR 3HDU FIRED HEATER | KIRCHNER ITALIA S.p.A. | 021F0001 | B-8796-27-9 | 021-F-GAD-40004-001 | COMBINED FEED HEATER EQUIPMENT FOR LIFTING (ROPE SHACKLES AND LIFTING SCHEME) 021F0001 | A1316 | AX | 4 | 2019-06-05 | CON-BMP-VTRA-011988 | 2019-06-05 | FOR BAPCO REVIEW | 2019-06-19 | 2019-07-08 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001225 | CLASS 2
076551C-000R-MR-0110-003 | MATERIAL REQUISITION FOR 3HDU FIRED HEATER | KIRCHNER ITALIA S.p.A. | 021F0001 | B-8796-28-1 | 021-F-DAT-40002-001 | 021F00001 HEATER DATA SHEET (EX BAPCO N.021-F-DAT-00002- 001) | A1001 | 0X | 3 | 2019-05-06 | CON-BMP-VTRA-011421 | 2019-05-06 | FOR BAPCO REVIEW | 2019-05-20 | 2019-05-26 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000778 | CLASS 2
076551C-000R-MR-0110-003 | MATERIAL REQUISITION FOR 3HDU FIRED HEATER | KIRCHNER ITALIA S.p.A. | 021F0001 | B-8796-28-2 | 021-F-DAT-40003-001 | DATA SHEET -BURNER DATA SHEET WITH CAPACITY CURVES AND NOISE DATA SHEET 021F0001 | A0105 | 0X | 3 | 2019-06-12 | CON-BMP-VTRA-012172 | 2019-06-12 | FOR BAPCO REVIEW | 2019-06-26 | 2019-07-03 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001158 | CLASS 2
076551C-000R-MR-0110-003 | MATERIAL REQUISITION FOR 3HDU FIRED HEATER | KIRCHNER ITALIA S.p.A. | 021F0001 | B-8796-29-1 | 021-F-CAL-40003-001 | MAIN STRUCTURAL CALCULATION 021F0001 | A2201 | 0X | 4 | 2019-04-09 | CON-BMP-VTRA-011056 | 2019-04-09 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-0110-003 | MATERIAL REQUISITION FOR 3HDU FIRED HEATER | KIRCHNER ITALIA S.p.A. | 021F0001 | B-8796-29-2 | 021-F-CAL-40002-001 | 021F0001 COIL MECHANICAL CALCULATION (EX BAPCO N.021-F-CAL-00002-001) | A1304 | 0X | 4 | 2019-03-16 | CON-BMP-VTRA-010707 | 2019-03-16 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0110-003 | MATERIAL REQUISITION FOR 3HDU FIRED HEATER | KIRCHNER ITALIA S.p.A. | 021F0001 | B-8796-29-3 | 021-F-CAL-40001-001 | COMBINED FEED HEATER REFRACTORY CALCULATION 021F0001 (EX BAPCO N.021-F-CAL-00001-001) | A1303 | 0AX | 3 | 2019-06-11 | CON-BMP-VTRA-012159 | 2019-06-11 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0110-003 | MATERIAL REQUISITION FOR 3HDU FIRED HEATER | KIRCHNER ITALIA S.p.A. | 021F0001 | B-8796-29-4 | 021-F-CAL-40004-001 | CASTING CALCULATION 021F0001 (EX BAPCO CODE N.021-F-CAL-40004-001) | A2201 | 0AX | 4 | 2019-03-19 | CON-BMP-VTRA-010764 | 2019-03-19 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0110-003 | MATERIAL REQUISITION FOR 3HDU FIRED HEATER | KIRCHNER ITALIA S.p.A. | 021F0001 | B-8796-31-1 | 021-F-ITP-40009-001 | ITP 021F00001-HEATER STEELWORKS PREFABRICATION (EX BAPCO N. 021-F-ITP-00009-001) | B1002 | 0X | 3 | 2019-04-29 | CON-BMP-VTRA-011302 | 2019-04-29 | FOR BAPCO REVIEW | 2019-05-14 | 2019-05-10 | 1-APPROVED BMP-ROC-VTRE-000655 | CLASS 2
076551C-000R-MR-0110-003 | MATERIAL REQUISITION FOR 3HDU FIRED HEATER | KIRCHNER ITALIA S.p.A. | 021F0001 | B-8796-31-2 | 021-F-ITP-40010-001 | ITP 021F0001 RADIANT COILS PREFABRICATION (EX BAPCO N.021-F-ITP-00010-001) | B1002 | 0AX | 3 | 2019-04-29 | CON-BMP-VTRA-011306 | 2019-04-29 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0110-003 | MATERIAL REQUISITION FOR 3HDU FIRED HEATER | KIRCHNER ITALIA S.p.A. | 021F0001 | B-8796-31-3 | 021-F-ITP-40011-001 | ITP 021F0001-CONVECTION COILS PREFABRICATION (EX BAPCO N.021-F-ITP-00011-001) | B1002 | 0AX | 3 | 2019-04-29 | CON-BMP-VTRA-011306 | 2019-04-29 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0110-003 | MATERIAL REQUISITION FOR 3HDU FIRED HEATER | KIRCHNER ITALIA S.p.A. | 021F0001 | B-8796-31-4 | 021-F-ITP-40012-001 | ITP 021F0001-FINNING OF TUBES (EX BAPCON.021-F-ITP-00012-001) | B1002 | 0XX | 3 | 2019-03-04 | CON-BMP-VTRA-010574 | 2019-03-05 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0110-003 | MATERIAL REQUISITION FOR 3HDU FIRED HEATER | KIRCHNER ITALIA S.p.A. | 021F0001 | B-8796-31-5 | 021-F-ITP-40013-001 | ITP 021F00001-STATIC CASTINGS (TUBE SHEETS AND SUPPORTS) (EX BAPCO N.021-F-PQP-00013-001) | B1002 | 0X | 3 | 2019-07-01 | CON-BMP-VTRA-012603 | 2019-07-01 | FOR BAPCO REVIEW | 2019-07-16 | 2019-07-11 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001285 | CLASS 2
076551C-000R-MR-0110-003 | MATERIAL REQUISITION FOR 3HDU FIRED HEATER | KIRCHNER ITALIA S.p.A. | 021F0001 | B-8796-31-6 | 021-F-ITP-40014-001 | COMBINED FEED HEATER INSPECTION AND TEST PLAN BURNERS 021F0001 (EX BAPCO N. 021-F-ITP-00014-001) | B1002 | 0X | 3 | 2019-06-06 | CON-BMP-VTRA-012050 | 2019-06-06 | FOR BAPCO REVIEW | 2019-06-20 | 2019-06-30 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001100 | CLASS 2
076551C-000R-MR-0110-003 | MATERIAL REQUISITION FOR 3HDU FIRED HEATER | KIRCHNER ITALIA S.p.A. | 021F0001 | B-8796-31-7 | 021-F-ITP-40015-001 | INSPECTION & TEST PLAN 021F0001 LOOSE INSTRUMENTATION (EX BAPCO N.021-F-ITP-00015-001) | B1002 | 0AX | 3 | 2019-05-06 | CON-BMP-VTRA-011416 | 2019-05-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0110-003 | MATERIAL REQUISITION FOR 3HDU FIRED HEATER | KIRCHNER ITALIA S.p.A. | 021F0001 | B-8796-31-8 | 021-F-ITP-40016-001 | ITP 021F0001-CASTABLE INSTALLATION (EX BAPCO N.021-F-ITP-00016-001)) | B1002 | 0X | 3 | 2019-04-29 | CON-BMP-VTRA-011302 | 2019-04-29 | FOR BAPCO REVIEW | 2019-05-14 | 2019-05-10 | 1-APPROVED BMP-ROC-VTRE-000655 | CLASS 2
076551C-000R-MR-0110-003 | MATERIAL REQUISITION FOR 3HDU FIRED HEATER | KIRCHNER ITALIA S.p.A. | 021F0001 | B-8796-32-1 | 021-F-MCD-40013-001 | WELDING BOOK HEATER STRUCTURES PREFABRICATION 021F0001 (EX BAPCO N.021-F-MCD-00013-001) | B1304 | 0X | 3 | 2019-06-14 | CON-BMP-VTRA-012206 | 2019-06-14 | FOR BAPCO REVIEW | 2019-06-28 | 2019-06-29 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001074 | CLASS 2
076551C-000R-MR-0110-003 | MATERIAL REQUISITION FOR 3HDU FIRED HEATER | KIRCHNER ITALIA S.p.A. | 021F0001 | B-8796-32-2 | 021-F-MCD-00014-001 | WELDING BOOK 21F0001-RADIANT AND CONVECTION COILS PREFABRICATION | B1304 | BX | 2 | 2019-03-26 | CON-BMP-VTRA-010861 | 2019-03-26 | FOR BAPCO REVIEW | 2019-04-10 | 2019-04-05 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000465 | CLASS 2
076551C-000R-MR-0110-003 | MATERIAL REQUISITION FOR 3HDU FIRED HEATER | KIRCHNER ITALIA S.p.A. | 021F0001 | B-8796-32-3 | 021-F-MCD-40015-001 | WELDING BOOK 021F0001 FINNING OF TUBES | B1304 | 0X | 3 | 2019-06-25 | CON-BMP-VTRA-012418 | 2019-06-25 | FOR BAPCO REVIEW |  | 2019-07-08 | 1-APPROVED BMP-ROC-VTRE-001192 | CLASS 2
076551C-000R-MR-0110-003 | MATERIAL REQUISITION FOR 3HDU FIRED HEATER | KIRCHNER ITALIA S.p.A. | 021F0001 | B-8796-32-4 | 021-F-MCD-40016-001 | WELDING BOOK 021F0001 - BURNERS | B1304 | AX | 2 | 2019-05-16 | CON-BMP-VTRA-011625 | 2019-05-16 | FOR BAPCO REVIEW | 2019-05-30 | 2019-05-20 | 4-NOT APPROVED BMP-ROC-VTRE-000712 | CLASS 2
076551C-000R-MR-0110-003 | MATERIAL REQUISITION FOR 3HDU FIRED HEATER | KIRCHNER ITALIA S.p.A. | 021F0001 | B-8796-33-1 | 021-F-PRO-40003-001 | PROCEDURE 021F0001-HEATERS STEELWORKS TRIAL ASSEMBLING (EX BAPCO N.021-F-PRO-00003-001) | B1103 | 0X | 3 | 2019-07-01 | CON-BMP-VTRA-012590 | 2019-07-01 | FOR BAPCO REVIEW | 2019-07-15 |  |  | CLASS 2
076551C-000R-MR-0110-003 | MATERIAL REQUISITION FOR 3HDU FIRED HEATER | KIRCHNER ITALIA S.p.A. | 021F0001 | B-8796-33-10 | 021-F-PRO-40005-001 | PROCEDURE BURNERS FIRING TEST 021F0001 | B1103 | BX | 2 | 2019-05-20 | CON-BMP-VTRA-011677 | 2019-05-21 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0110-003 | MATERIAL REQUISITION FOR 3HDU FIRED HEATER | KIRCHNER ITALIA S.p.A. | 021F0001 | B-8796-33-11 | 021-F-TSP-40003-001 | PROCEDURE BURNERS PAINTING 021F0001 | A0106 | 0X | 3 | 2019-06-25 | CON-BMP-VTRA-012414 | 2019-06-25 | FOR BAPCO REVIEW | 2019-07-09 | 2019-07-08 | 1-APPROVED BMP-ROC-VTRE-001194 | CLASS 2
076551C-000R-MR-0110-003 | MATERIAL REQUISITION FOR 3HDU FIRED HEATER | KIRCHNER ITALIA S.p.A. | 021F0001 | B-8796-33-12 | 021-F-PRO-40001-001 | PROCEDURE 021F0001-REFRACTORY CASTABLE AND FIBRES INSTALLATION (EX BAPCO N. 021-F-PRO-00001-001) | A1309 | 0AX | 3 | 2019-06-06 | CON-BMP-VTRA-012054 | 2019-06-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0110-003 | MATERIAL REQUISITION FOR 3HDU FIRED HEATER | KIRCHNER ITALIA S.p.A. | 021F0001 | B-8796-33-13 | 021-F-PRO-40006-001 | PROCEDURE 021F0001 TRACEABILITY AND MARKING OF COMPONENTS AND PRESSURE SYSTEMS (EX BAPCO N.021-F-PRO-00006-001) | B1103 | 0X | 3 | 2019-06-06 | CON-BMP-VTRA-012049 | 2019-06-06 | FOR BAPCO REVIEW | 2019-06-20 | 2019-06-17 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000959 | CLASS 2
076551C-000R-MR-0110-003 | MATERIAL REQUISITION FOR 3HDU FIRED HEATER | KIRCHNER ITALIA S.p.A. | 021F0001 | B-8796-33-14 | 021-F-SIN-40001-001 | PROCEDURE - PACKING AND PRESERVATION 021F0001 | A5001 | 0X | 3 | 2019-05-14 | CON-BMP-VTRA-011555 | 2019-05-14 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-0110-003 | MATERIAL REQUISITION FOR 3HDU FIRED HEATER | KIRCHNER ITALIA S.p.A. | 021F0001 | B-8796-33-2 | 021-F-TSP-40001-001 | PROCEDURE 21F0001-JOB PAINTING AND COLOUR SUMMARY TABLE (EX BAPCO N.021-F-TSP-00001-001) | A0106 | CXX | 2 | 2019-03-26 | CON-BMP-VTRA-010862 | 2019-03-26 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0110-003 | MATERIAL REQUISITION FOR 3HDU FIRED HEATER | KIRCHNER ITALIA S.p.A. | 021F0001 | B-8796-33-3 | 021-F-TSP-40002-001 | PROCEDURE HEATERS STEELWORKS PAINTING 021F0001 | A0106 | 0AX | 3 | 2019-06-25 | CON-BMP-VTRA-012413 | 2019-06-25 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0110-003 | MATERIAL REQUISITION FOR 3HDU FIRED HEATER | KIRCHNER ITALIA S.p.A. | 021F0001 | B-8796-33-4 | 021-F-PRO-40008-001 | PROCEDURE 21F0001- GAMMA RAY EXAMINATION OF WELDS (COILS) (EX BAPCO N. 021-F-PRO-00008-001) | B1202 | 0AX | 3 | 2019-03-25 | CON-BMP-VTRA-010853 | 2019-03-25 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0110-003 | MATERIAL REQUISITION FOR 3HDU FIRED HEATER | KIRCHNER ITALIA S.p.A. | 021F0001 | B-8796-33-5 | 021-F-PRO-40009-001 | PROCEDURE 21F0001-DYE PENETRANT EXAMINATION OF WELDS (COILS) (EX BAPCO N. 021-F-PRO-00009-001) | B1202 | 0AX | 3 | 2019-05-16 | CON-BMP-VTRA-011631 | 2019-05-16 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0110-003 | MATERIAL REQUISITION FOR 3HDU FIRED HEATER | KIRCHNER ITALIA S.p.A. | 021F0001 | B-8796-33-6 | 021-F-PRO-40011-001 | PROCEDURE POSITIVE MATERIAL IDENTIFICATION OF MATERIALS AND WELDS (COILS) 021F0001 (EX BAPCO N. 021-F-PRO-00011-001) | B1204 | 0AX | 3 | 2019-03-08 | CON-BMP-VTRA-010643 | 2019-03-08 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-0110-003 | MATERIAL REQUISITION FOR 3HDU FIRED HEATER | KIRCHNER ITALIA S.p.A. | 021F0001 | B-8796-33-7 | 021-F-PRO-40007-001 | PROCEDURE 21F0001 PWHT WELDS (COILS) (EX BAPCO N.021-F-PRO-00007-001) | B1201 | 0X | 4 | 2019-01-30 | CON-BMP-VTRA-010330 | 2019-01-30 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0110-003 | MATERIAL REQUISITION FOR 3HDU FIRED HEATER | KIRCHNER ITALIA S.p.A. | 021F0001 | B-8796-33-8 | 021-F-PRO-40010-001 | PROCEDURE 21F0001-FERRITE INSPECTION (COILS) (EX BAPCO N. 021-F-PRO-00010-001) | B1202 | 0X | 3 | 2019-03-08 | CON-BMP-VTRA-010647 | 2019-03-08 | FOR BAPCO REVIEW | 2019-03-25 | 2019-03-19 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000349 | CLASS 2
076551C-000R-MR-0110-003 | MATERIAL REQUISITION FOR 3HDU FIRED HEATER | KIRCHNER ITALIA S.p.A. | 021F0001 | B-8796-33-9 | 021-F-PRO-40004-001 | PROCEDURE 021F0001 HYDROSTATIC TEST (COILS) (EX BAPCO N. 021-F-PRO-00004-001) | B1103 | 0X | 3 | 2019-03-04 | CON-BMP-VTRA-010563 | 2019-03-04 | FOR BAPCO REVIEW | 2019-03-19 | 2019-03-13 | 1-APPROVED BMP-ROC-VTRE-00296 | CLASS 2
076551C-000R-MR-0110-003 | MATERIAL REQUISITION FOR 3HDU FIRED HEATER | KIRCHNER ITALIA S.p.A. | 021F0001 | B-8796-35-1 | 021-F-GAD-40055-001 | COMBINED FEED HEATER BURNER GENERAL ASSEMBLY 021F0001 | A1109 | 0X | 3 | 2019-07-05 | CON-BMP-VTRA-012681 | 2019-07-05 | FOR BAPCO REVIEW | 2019-07-19 |  |  | CLASS 2
076551C-000R-MR-0110-003 | MATERIAL REQUISITION FOR 3HDU FIRED HEATER | KIRCHNER ITALIA S.p.A. | 021F0001 | B-8796-35-2 | 021-F-GAD-40061-001 | COMBINED FEED HEATER PILOT GENERAL ASSEMBLY AND DETAILS 021F0001 | A1109 | 0X | 3 | 2019-07-01 | CON-BMP-VTRA-012589 | 2019-07-01 | FOR BAPCO REVIEW | 2019-07-15 |  |  | CLASS 2
076551C-000R-MR-0110-003 | MATERIAL REQUISITION FOR 3HDU FIRED HEATER | KIRCHNER ITALIA S.p.A. | 021F0001 | B-8796-35-3 | 021-F-DLB-40003-001 | COMBINED FEED HEATER BURNER NAME PLATE 021F0001 | A1112 | AX | 2 | 2019-06-05 | CON-BMP-VTRA-011986 | 2019-06-05 | FOR BAPCO REVIEW | 2019-06-19 | 2019-06-30 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001096 | CLASS 2
076551C-000R-MR-0110-003 | MATERIAL REQUISITION FOR 3HDU FIRED HEATER | KIRCHNER ITALIA S.p.A. | 021F0001 | B-8796-70-1 | 021-F-S3D-40001-001 | DRAWING 021F0001-3D EQUIPMENT MODEL | A2013 | BX | 4 | 2019-06-06 | CON-BMP-VTRA-012053 | 2019-06-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0110-003 | MATERIAL REQUISITION FOR 3HDU FIRED HEATER | KIRCHNER ITALIA S.p.A. | 021F0001 | B-8796-70-2 | 021-F-PLN-00001-001 | QA DOCUMENT 021F0001 - JOB QUALITY ASSURANCE PLAN | B1001 | AX | 4 | 2018-11-15 | CON-BMP-VTRA-010052 | 2018-11-15 | FOR BAPCO REVIEW | 2018-11-30 | 2018-11-29 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000045 | CLASS 2
076551C-000R-MR-0110-003 | MATERIAL REQUISITION FOR 3HDU FIRED HEATER | KIRCHNER ITALIA S.p.A. | 021F0001 | B-8796-70-3 | 021-F-SCH-40001-001 | OTHER - ENGINEERING PROCUREMENT MANUFACTURING SCHEDULE 021F0001 (EX 021-F-SCH-00001-001) | C1001 | 0EX | 4 | 2019-06-28 | CON-BMP-VTRA-012555 | 2019-06-28 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-0110-003 | MATERIAL REQUISITION FOR 3HDU FIRED HEATER | KIRCHNER ITALIA S.p.A. | 021F0001 | B-8796-80-1 | 021-F-MRS-40001-001 | VENDOR MONTHLY PROGRESS REPORT 021F0001 | C1002 | 0EX | 4 | 2019-06-28 | CON-BMP-VTRA-012553 | 2019-06-28 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-0110-003 | MATERIAL REQUISITION FOR 3HDU FIRED HEATER | KIRCHNER ITALIA S.p.A. | 021F0001 | B-8796-80-2 | 021-F-INV-40001-001 | UNPRICED COPY OF MAIN SUBORDERS 021F0001 (EX BAPCO N.021-F-INV-00001-001) | C1005 | EX | 4 | 2019-05-16 | CON-BMP-VTRA-011628 | 2019-05-16 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-0110-003 | MATERIAL REQUISITION FOR 3HDU FIRED HEATER | KIRCHNER ITALIA S.p.A. | 021F0001 | B8796-27-7 | 021-F-GAD-40051-001 | COMBINED FEED HEATER SPREADED BEAM FOR STACK 021F0001 | A1101 | 0X | 3 | 2019-06-06 | CON-BMP-VTRA-012048 | 2019-06-06 | FOR BAPCO REVIEW | 2019-06-20 |  |  | CLASS 2
076551C-000R-MR-0180-001 | MATERIAL REQUISITION FOR REFINERY SOUTH FLARE PACKAGE | THERMOENGINEERING Srl | 082F0001 | CF-M31-100 | 082-F-PID-40001-001 | P&I DIAGRAM 082F0001 | A0103 | AX | 2 | 2019-05-21 | CON-BMP-VTRA-011699 | 2019-05-21 | FOR BAPCO REVIEW | 2019-06-05 | 2019-06-10 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000896 | CLASS 2
076551C-000R-MR-0180-001 | MATERIAL REQUISITION FOR REFINERY SOUTH FLARE PACKAGE | THERMOENGINEERING Srl | 082F0001 | CF-M31-101 | 082-F-GAD-40001-001 | GENERAL LAYOUT 082F0001 | A2001 | AX | 2 | 2019-05-15 | CON-BMP-VTRA-011598 | 2019-05-15 | FOR BAPCO REVIEW | 2019-05-29 | 2019-05-28 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000816 | CLASS 2
076551C-000R-MR-0180-001 | MATERIAL REQUISITION FOR REFINERY SOUTH FLARE PACKAGE | THERMOENGINEERING Srl | 082F0001 | CF-M31-11 | 082-F-INX-40001-001 | LIST OF VENDOR'S DOCUMENTS AND DRAWINGS 082F0001 | A0001 | BX | 2 | 2019-06-26 | CON-BMP-VTRA-012492 | 2019-06-26 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0180-001 | MATERIAL REQUISITION FOR REFINERY SOUTH FLARE PACKAGE | THERMOENGINEERING Srl | 082F0001 | CF-M31-12 | 082-F-SCH-40001-001 | FABRICATION PROGRAM FOR REFINERY SOUTH FLARE PACKAGE ITEM 082F0001 | C1001 | BX | 4 | 2019-06-26 | CON-BMP-VTRA-012494 | 2019-06-26 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-0180-001 | MATERIAL REQUISITION FOR REFINERY SOUTH FLARE PACKAGE | THERMOENGINEERING Srl | 082F0001 | CF-M31-130 | 082-F-PED-40001-001 | FOUNDATION LOADING DIAGRAM 082F0001 | A2006 | AX | 2 | 2019-05-15 | CON-BMP-VTRA-011597 | 2019-05-15 | FOR BAPCO REVIEW | 2019-05-29 | 2019-05-27 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000800 | CLASS 2
076551C-000R-MR-0180-001 | MATERIAL REQUISITION FOR REFINERY SOUTH FLARE PACKAGE | THERMOENGINEERING Srl | 082F0001 | CF-M31-406 | 082-F-DAT-40002-001 | ELEVATED FLARE DATASHEET 082F0001 | A1001 | AX | 2 | 2019-05-15 | CON-BMP-VTRA-011603 | 2019-05-15 | FOR BAPCO REVIEW | 2019-05-29 | 2019-06-11 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000901 | CLASS 2
076551C-000R-MR-0180-001 | MATERIAL REQUISITION FOR REFINERY SOUTH FLARE PACKAGE | THERMOENGINEERING Srl | 082F0001 | CF-M31-431 | 082-F-CAL-40001-001 | ELEVATED FLARE RADIATION CALCULATION 082F0001 | A1301 | AX | 2 | 2019-05-10 | CON-BMP-VTRA-011594 | 2019-05-15 | FOR BAPCO REVIEW | 2019-05-29 | 2019-06-11 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000904 | CLASS 2
076551C-000R-MR-0180-001 | MATERIAL REQUISITION FOR REFINERY SOUTH FLARE PACKAGE | THERMOENGINEERING Srl | 082F0001 | CF-M31-433 | 082-F-CAL-40002-001 | POLLUTTANTS DISPERSION CALCULATION 082F0001 | A1301 | AX | 2 | 2019-05-10 | CON-BMP-VTRA-011594 | 2019-05-15 | FOR BAPCO REVIEW | 2019-05-29 | 2019-06-11 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000904 | CLASS 2
076551C-000R-MR-0180-001 | MATERIAL REQUISITION FOR REFINERY SOUTH FLARE PACKAGE | THERMOENGINEERING Srl | 082F0001 | CF-M31-434 | 082-F-DAT-40003-001 | EQUIPMENT NOISE DATASHEET REFINERY SOUTH FLARE PACKAGE 082F0001 | A0105 | AX | 2 | 2019-05-15 | CON-BMP-VTRA-011593 | 2019-05-15 | FOR BAPCO REVIEW | 2019-05-29 | 2019-05-28 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000815 | CLASS 2
076551C-000R-MR-0180-001 | MATERIAL REQUISITION FOR REFINERY SOUTH FLARE PACKAGE | THERMOENGINEERING Srl | 082F0001 | CF-M31-600 | 082-F-RPT-40001-001 | UTILITY CONSUMPTION 082F0001 | A1014 | AX | 2 | 2019-05-15 | CON-BMP-VTRA-011596 | 2019-05-15 | FOR BAPCO REVIEW | 2019-05-29 | 2019-05-28 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000818 | CLASS 2
076551C-000R-MR-0180-001 | MATERIAL REQUISITION FOR REFINERY SOUTH FLARE PACKAGE | THERMOENGINEERING Srl | 082F0001 | CF-M31-PR | 082-F-MRS-40001-001 | MONTHLY PROGRESS REPORT 082F0001 | C1002 | AX | 4 | 2019-06-26 | CON-BMP-VTRA-012493 | 2019-06-26 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-0180-001 | MATERIAL REQUISITION FOR REFINERY SOUTH FLARE PACKAGE | THERMOENGINEERING Srl | 082TIP0001 | CF-M31-110 | 082-F-GAD-40002-001 | FLARE TIP GENERAL DRAWING 082TIP0001 | A1109 | AX | 2 | 2019-05-15 | CON-BMP-VTRA-011601 | 2019-05-15 | FOR BAPCO REVIEW | 2019-05-29 | 2019-05-28 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000820 | CLASS 2
076551C-000R-MR-0180-002 | MATERIAL REQUISITION FOR REFRIGERATED LPG STORAGE FLARE PACKAGES | ZEECO INC | 051F0001A | 38707-3012 | 051-F-INX-40002-001 | LIST OF VENDOR'S DOCUMENTS ANDDWGS | A0001 | AX | 1 | 2019-07-10 | CON-BMP-VTRA-012796 | 2019-07-10 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0180-002 | MATERIAL REQUISITION FOR REFRIGERATED LPG STORAGE FLARE PACKAGES | ZEECO INC | 051U0001A | 38707-1090 | 051-F-CAL-40002-001 | STRUCTURAL STEEL CALCULATIONS FOR 051U0001A/B | A2203 | AX | 2 | 2019-05-31 | CON-BMP-VTRA-011903 | 2019-05-31 | FOR BAPCO REVIEW | 2019-06-17 | 2019-06-15 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000923 | CLASS 2
076551C-000R-MR-0180-002 | MATERIAL REQUISITION FOR REFRIGERATED LPG STORAGE FLARE PACKAGES | ZEECO INC | 051U0001A | 38707-1150 | 051-F-CAL-40003-001 | REFRIGERATED LPG STORAGE FLARE051U0001A /B RADIATION CALCULATION | A1301 | AX | 1 | 2019-06-12 | CON-BMP-VTRA-012163 | 2019-06-12 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0180-002 | MATERIAL REQUISITION FOR REFRIGERATED LPG STORAGE FLARE PACKAGES | ZEECO INC | 051U0001A | 38707-2010 | 051-F-MCD-40001-001 | INSTRUMENT DATA SHEETS 051U0001A/B | A3006 | AX | 1 | 2019-06-07 | CON-BMP-VTRA-012103 | 2019-06-07 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0180-002 | MATERIAL REQUISITION FOR REFRIGERATED LPG STORAGE FLARE PACKAGES | ZEECO INC | 051U0001A | 38707-2013 | 051-F-DAT-40006-001 | NOISE DATA SHEET 051U0001A/B | A0105 | AX | 1 | 2019-05-30 | CON-BMP-VTRA-011864 | 2019-05-30 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0180-002 | MATERIAL REQUISITION FOR REFRIGERATED LPG STORAGE FLARE PACKAGES | ZEECO INC | 051U0001A | 38707-2020 | 051-F-MCD-40002-001 | DATA SHEETS FOR MANUAL VALVES SWING VALVES AND STRAINERS FOR051U0001A/B FLARE PACKAGES | A3006 | AX | 2 | 2019-06-11 | CON-BMP-VTRA-012162 | 2019-06-11 | FOR BAPCO REVIEW | 2019-06-26 |  |  | CLASS 2
076551C-000R-MR-0180-002 | MATERIAL REQUISITION FOR REFRIGERATED LPG STORAGE FLARE PACKAGES | ZEECO INC | 051U0001A | 38707-2030 | 051-F-DAT-40003-001 | DATA SHEETS FOR REFRIGERATED LPG STORAGE FLARE PACKAGES 051U0001A/B | A1001 | AX | 2 | 2019-06-11 | CON-BMP-VTRA-012161 | 2019-06-11 | FOR BAPCO REVIEW | 2019-06-26 |  |  | CLASS 2
076551C-000R-MR-0180-002 | MATERIAL REQUISITION FOR REFRIGERATED LPG STORAGE FLARE PACKAGES | ZEECO INC | 051U0001A | 38707-4010 | 051-F-SCH-40001-001 | ZEECO FABRICATION AND PRODUCTION SCHEDULE 051U0001A/B | C1001 | AX | 2 | 2019-06-29 | CON-BMP-VTRA-012575 | 2019-06-29 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-0180-002 | MATERIAL REQUISITION FOR REFRIGERATED LPG STORAGE FLARE PACKAGES | ZEECO INC | 051U0001A | 38707-7050 | 051-F-RPT-40001-001 | UTILITY CONSUMPTION LIST FOR REFRIGERATED LPG STORAGE PACKAGE 051U0001A/B | A1014 | AX | 2 | 2019-06-11 | CON-BMP-VTRA-012160 | 2019-06-11 | FOR BAPCO REVIEW | 2019-06-26 | 2019-06-24 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001019 | CLASS 2
076551C-000R-MR-0180-002 | MATERIAL REQUISITION FOR REFRIGERATED LPG STORAGE FLARE PACKAGES | ZEECO INC | 051U0001A | SD-8526 | 051-F-GAD-40002-001 | GUY WIRE SUPPORTED FLARE STACK SYSTEM GENERAL ARRANGEMENT 051U0001A/B | A2001 | AX | 2 | 2019-05-31 | CON-BMP-VTRA-011901 | 2019-05-31 | FOR BAPCO REVIEW | 2019-06-17 | 2019-06-16 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000949 | CLASS 2
076551C-000R-MR-0180-002 | MATERIAL REQUISITION FOR REFRIGERATED LPG STORAGE FLARE PACKAGES | ZEECO INC | 051U0001A | SD-8527 | 051-F-GAD-40003-001 | GUY WIRE SUPPORTED FLARE STACK SYSTEM FOUNDATION LOADING DATA 051U0001A /B | A2006 | AX | 2 | 2019-05-31 | CON-BMP-VTRA-011900 | 2019-05-31 | FOR BAPCO REVIEW | 2019-06-17 | 2019-06-11 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000899 | CLASS 2
076551C-000R-MR-0180-002 | MATERIAL REQUISITION FOR REFRIGERATED LPG STORAGE FLARE PACKAGES | ZEECO INC | 051U0001A | SD-8585 | 051-F-GAD-40008-001 | AFTA-28-60 FLARE TIP ASSEMBLY 051U0001A/B | A1112 | AX | 2 | 2019-06-06 | CON-BMP-VTRA-012076 | 2019-06-06 | FOR BAPCO REVIEW | 2019-06-21 | 2019-06-22 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001013 | CLASS 2
076551C-000R-MR-0180-002 | MATERIAL REQUISITION FOR REFRIGERATED LPG STORAGE FLARE PACKAGES | ZEECO INC | 051U0001A | WD-0798 | 051-F-MCD-40004-001 | LOCAL CONTROL PANEL ASSEMBLY AND SCHEMATIC ELEVATED FLARE 051U0001A/B | A1109 | AX | 2 | 2019-06-25 | CON-BMP-VTRA-012438 | 2019-06-25 | FOR BAPCO REVIEW | 2019-07-09 |  |  | CLASS 2
076551C-000R-MR-0180-002 | MATERIAL REQUISITION FOR REFRIGERATED LPG STORAGE FLARE PACKAGES | ZEECO INC | 051U0001A | YA-3353 | 051-F-PID-40001-001 | PIPING AND INSTRUMENT DIAGRAM ELEVATED FLARE 051U0001A/B | A0103 | AX | 2 | 2019-05-31 | CON-BMP-VTRA-011906 | 2019-05-31 | FOR BAPCO REVIEW | 2019-06-17 | 2019-06-18 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001001 | CLASS 2
076551C-000R-MR-0411-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V REACTORS AND INTERNALS | BELLELI ENERGY CPE SrL | 018C1001R | DL-18106-00-001 | 000-C-INX-60001-001 | LIST OF VENDOR'S DOCUMENTS AND DRAWINGS ALL ITEMS | A0001 | AX | 2 | 2018-10-19 | CON-BMP-VTRA-010002 | 2018-10-19 | FOR BAPCO REVIEW | 2018-11-07 | 2018-11-05 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000003 | CLASS 2
076551C-000R-MR-0411-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V REACTORS AND INTERNALS | BELLELI ENERGY CPE SrL | 018C1001R | DWG-18106-01-18 | 018-C-DLB-40008-001 | TRAIN 1 1ST REACTOR 018C1001R NAMEPLATE (EX BAPCO N.018-C-DLB-00008-001) | A1112 | 0X | 3 | 2019-03-21 | CON-BMP-VTRA-010817 | 2019-03-21 | FOR BAPCO REVIEW | 2019-04-04 | 2019-04-06 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000469 | CLASS 2
076551C-000R-MR-0411-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V REACTORS AND INTERNALS | BELLELI ENERGY CPE SrL | 018C1001R | DWG-18106.01-01 | 018-C-GAD-40094-001 | TRAIN 1 1ST REACTOR 018C1001R GENERAL ASSEMBLY 1/2 (EX BAPCO N.018-C-GAD-00094-001) | A1103 | 0AX | 2 | 2019-05-31 | CON-BMP-VTRA-011898 | 2019-05-31 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0411-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V REACTORS AND INTERNALS | BELLELI ENERGY CPE SrL | 018C1001R | DWG-18106.01-03 | 018-C-GAD-40095-001 | 1ST REACTOR 018C1001R 018C2001R BODY DETAILS (EX BAPCO DOC N. 018-C-GAD-00095-001) | A1109 | 0X | 2 | 2019-06-04 | CON-BMP-VTRA-011949 | 2019-06-04 | FOR BAPCO REVIEW | 2019-06-19 | 2019-06-26 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001041 | CLASS 2
076551C-000R-MR-0411-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V REACTORS AND INTERNALS | BELLELI ENERGY CPE SrL | 018C1001R | DWG-18106.01-04 | 018-C-GAD-40096-001 | TRAIN 1 1ST REACTOR 018C1001R NOZZLE DETAILS 1/3 (EX BAPCO N.018-C-GAD-00096-001) | A1109 | 0AX | 2 | 2019-05-31 | CON-BMP-VTRA-011904 | 2019-05-31 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0411-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V REACTORS AND INTERNALS | BELLELI ENERGY CPE SrL | 018C1001R | DWG-18106.01-05 | 018-C-GAD-40096-002 | TRAIN 1 1 ST REACTOR 018C1001R NOZZLE DETAILS 2/3 (EX BAPCO N.018-C-GAD-00096-002) | A1109 | 0AX | 2 | 2019-05-31 | CON-BMP-VTRA-011904 | 2019-05-31 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0411-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V REACTORS AND INTERNALS | BELLELI ENERGY CPE SrL | 018C1001R | DWG-18106.01-06 | 018-C-GAD-40096-003 | TRAIN 1 1ST REACTOR 018C-1001R NOZZLE DETAILS 3/3 (EX BAPCO N.018-C-GAD-00096-003) | A1109 | 0AX | 2 | 2019-05-31 | CON-BMP-VTRA-011904 | 2019-05-31 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0411-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V REACTORS AND INTERNALS | BELLELI ENERGY CPE SrL | 018C1001R | DWG-18106.01-07 | 018-C-GAD-40097-001 | INTERNAL DETAILS 1/12 DISTRIBUTOR PLATE 1/3 018C1001R | A1109 | 0X | 2 | 2019-06-04 | CON-BMP-VTRA-011949 | 2019-06-04 | FOR BAPCO REVIEW | 2019-06-19 | 2019-06-26 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001041 | CLASS 2
076551C-000R-MR-0411-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V REACTORS AND INTERNALS | BELLELI ENERGY CPE SrL | 018C1001R | DWG-18106.01-08 | 018-C-GAD-40097-002 | INTERNALS DETAILS 2/12 DISTRIBUTOR PLATE 2/3 018C1001R | A1109 | 0X | 2 | 2019-06-04 | CON-BMP-VTRA-011949 | 2019-06-04 | FOR BAPCO REVIEW | 2019-06-19 | 2019-06-26 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001041 | CLASS 2
076551C-000R-MR-0411-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V REACTORS AND INTERNALS | BELLELI ENERGY CPE SrL | 018C1001R | DWG-18106.01-09 | 018-C-GAD-40097-003 | INTERNALS DETAILS 3/12 DISTRIBUTOR PLATE 3/3 018C1001R | A1109 | 0X | 3 | 2019-06-04 | CON-BMP-VTRA-011957 | 2019-06-04 | FOR BAPCO REVIEW | 2019-06-19 | 2019-06-26 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001048 | CLASS 2
076551C-000R-MR-0411-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V REACTORS AND INTERNALS | BELLELI ENERGY CPE SrL | 018C1001R | DWG-18106.01-10 | 018-C-GAD-40097-004 | INTERNAL DETAIL 4/12 (NOZZLE 12 & DISTRIBUTOR RING 1/2) 018C1001R | A1109 | AX | 2 | 2019-05-31 | CON-BMP-VTRA-011902 | 2019-05-31 | FOR BAPCO REVIEW | 2019-06-17 | 2019-06-18 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000975 | CLASS 2
076551C-000R-MR-0411-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V REACTORS AND INTERNALS | BELLELI ENERGY CPE SrL | 018C1001R | DWG-18106.01-11 | 018-C-GAD-40097-005 | TRAIN 1 1ST REACTOR INTERNAL DETAILS 5/12 (NOZZLE 12 & DISTRIBUTOR RING 2/2) 018C1001R | A1109 | AX | 2 | 2019-05-31 | CON-BMP-VTRA-011889 | 2019-05-31 | FOR BAPCO REVIEW | 2019-06-17 | 2019-06-18 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000980 | CLASS 2
076551C-000R-MR-0411-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V REACTORS AND INTERNALS | BELLELI ENERGY CPE SrL | 018C1001R | DWG-18106.01-12 | 018-C-GAD-40097-006 | TRAIN 1 1ST REACTOR INTERNAL DETAILS 6/12 (SUCTION PIPE BOTTOM) 018C1001R | A1109 | AX | 2 | 2019-05-31 | CON-BMP-VTRA-011889 | 2019-05-31 | FOR BAPCO REVIEW | 2019-06-17 | 2019-06-18 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000980 | CLASS 2
076551C-000R-MR-0411-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V REACTORS AND INTERNALS | BELLELI ENERGY CPE SrL | 018C1001R | DWG-18106.01-13 | 018-C-GAD-40097-007 | TRAIN 1 1ST REACTOR INTERNALS DETAILS 7/12 (INTERNAL PIPES BOTTOM 1/2) 018C1001R | A1109 | AX | 2 | 2019-05-31 | CON-BMP-VTRA-011889 | 2019-05-31 | FOR BAPCO REVIEW | 2019-06-17 | 2019-06-18 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000980 | CLASS 2
076551C-000R-MR-0411-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V REACTORS AND INTERNALS | BELLELI ENERGY CPE SrL | 018C1001R | DWG-18106.01-14 | 018-C-GAD-40097-008 | INTERNALS DETAILS 8/12 (INTERNAL PIPES BOTTOM 2/2) 018C1001R | A1109 | AX | 2 | 2019-05-31 | CON-BMP-VTRA-011902 | 2019-05-31 | FOR BAPCO REVIEW | 2019-06-17 | 2019-06-18 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000975 | CLASS 2
076551C-000R-MR-0411-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V REACTORS AND INTERNALS | BELLELI ENERGY CPE SrL | 018C1001R | DWG-18106.01-15 | 018-C-GAD-40098-001 | TRAIN 1ST REACTOR 018C1001R EXTERNALS DETAILS 1-3 | A1109 | AX | 2 | 2019-05-31 | CON-BMP-VTRA-011889 | 2019-05-31 | FOR BAPCO REVIEW | 2019-06-17 | 2019-06-18 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000980 | CLASS 2
076551C-000R-MR-0411-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V REACTORS AND INTERNALS | BELLELI ENERGY CPE SrL | 018C1001R | DWG-18106.01-16 | 018-C-GAD-40098-002 | TRAIN 1 1ST REACTOR 018C1001R EXTERNAL DETAILS 2-3 | A1109 | AX | 2 | 2019-05-31 | CON-BMP-VTRA-011902 | 2019-05-31 | FOR BAPCO REVIEW | 2019-06-17 | 2019-06-18 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000975 | CLASS 2
076551C-000R-MR-0411-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V REACTORS AND INTERNALS | BELLELI ENERGY CPE SrL | 018C1001R | DWG-18106.01-23 | 018-C-DLB-40007-001 | 1ST REACTOR 018C1001R TEMPLATE DRAWING (EX BAPCO N. 018-C-DLB-00007-001) | A2010 | 0X | 3 | 2019-03-05 | CON-BMP-VTRA-010580 | 2019-03-05 | FOR BAPCO REVIEW | 2019-03-19 | 2019-03-18 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000333 | CLASS 2
076551C-000R-MR-0411-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V REACTORS AND INTERNALS | BELLELI ENERGY CPE SrL | 018C1001R | DWG-18106.01-24 | 018-C-GAD-40097-009 | TRAIN 1 1ST REACTOR 018C1001R INTERNALS DETAILS 9-12 (SUCTION PIPE TOP 1-2) | A1109 | AX | 2 | 2019-05-31 | CON-BMP-VTRA-011889 | 2019-05-31 | FOR BAPCO REVIEW | 2019-06-17 | 2019-06-18 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000980 | CLASS 2
076551C-000R-MR-0411-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V REACTORS AND INTERNALS | BELLELI ENERGY CPE SrL | 018C1001R | DWG-18106.01-25 | 018-C-GAD-40097-010 | TRAIN 1 1ST REACTOR 018C1001R INTERNALS DETAILS 10-12 (SUCTION PIPE TOP 2-2) | A1109 | AX | 2 | 2019-05-31 | CON-BMP-VTRA-011889 | 2019-05-31 | FOR BAPCO REVIEW | 2019-06-17 | 2019-06-18 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000980 | CLASS 2
076551C-000R-MR-0411-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V REACTORS AND INTERNALS | BELLELI ENERGY CPE SrL | 018C1001R | DWG-18106.01-26 | 018-C-GAD-40097-011 | TRAIN 1 1ST REACTOR 018C1001R INTERNALS DETAILS 11-12 (INTERNAL PIPES TOP) | A1109 | AX | 2 | 2019-05-31 | CON-BMP-VTRA-011889 | 2019-05-31 | FOR BAPCO REVIEW | 2019-06-17 | 2019-06-18 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000980 | CLASS 2
076551C-000R-MR-0411-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V REACTORS AND INTERNALS | BELLELI ENERGY CPE SrL | 018C1001R | DWG-18106.01-27 | 018-C-GAD-40097-012 | TRAIN 1 1ST REACTOR INTERNALS DETAILS 12-12 (REMOVABLE SPLIT COVER AND INSPECTION TOOLS) 018C1001R | A1109 | AX | 2 | 2019-05-31 | CON-BMP-VTRA-011889 | 2019-05-31 | FOR BAPCO REVIEW | 2019-06-17 | 2019-06-18 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000980 | CLASS 2
076551C-000R-MR-0411-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V REACTORS AND INTERNALS | BELLELI ENERGY CPE SrL | 018C1001R | FEA-18106.01-1 | 018-C-CAL-40015-001 | 1ST REACTOR (TRAIN 1) STRENGHT ANALYSIS 018C1001R | A1003 | 0X | 4 | 2019-07-01 | CON-BMP-VTRA-012601 | 2019-07-01 | FOR BAPCO REVIEW | 2019-07-16 |  |  | CLASS 2
076551C-000R-MR-0411-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V REACTORS AND INTERNALS | BELLELI ENERGY CPE SrL | 018C1001R | FEA-18106.01-2 | 018-C-CAL-40016-001 | FATIGUE / CREEP ANALYSIS ACCORDING TO CODE CASE 2605-2 - 1ST REACTOR - TRAIN 1 - ITEM 018C1001R | A1003 | 0X | 4 | 2019-07-01 | CON-BMP-VTRA-012591 | 2019-07-01 | FOR BAPCO REVIEW | 2019-07-15 |  |  | CLASS 2
076551C-000R-MR-0411-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V REACTORS AND INTERNALS | BELLELI ENERGY CPE SrL | 018C1001R | GP-18106-00-001 | 000-C-SCH-40001-001 | GENERAL PLANNING ALL ITEMS (EX BAPCO N. 000-C-SCH-60001-001) | C1001 | 0X | 4 | 2019-05-31 | CON-BMP-VTRA-011874 | 2019-05-31 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-0411-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V REACTORS AND INTERNALS | BELLELI ENERGY CPE SrL | 018C1001R | MCR-18106.01 | 018-C-CAL-40013-001 | TRAIN 1 1ST REACTOR 018C1001R MECHANICAL CALCULATION REPORT (EX BAPCO N.018-C-CAL-00013-001) | A1003 | 0AX | 2 | 2019-05-30 | CON-BMP-VTRA-011852 | 2019-05-30 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0411-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V REACTORS AND INTERNALS | BELLELI ENERGY CPE SrL | 018C1001R | MPO-18-106-00-001 | 000-C-INV-40001-001 | UNPRICED COPY OF MAIN SUBORDERDS ALL ITEMS (EX BAPCO N.000-C-INV-60001-001) | C1005 | 0AX | 4 | 2019-05-31 | CON-BMP-VTRA-011868 | 2019-05-31 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0411-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V REACTORS AND INTERNALS | BELLELI ENERGY CPE SrL | 018C1001R | MPR-18106-00-001 | 000-C-MRS-40001-001 | MONTHLY PROGRESS REPORT ALL ITEMS (EX BAPCO N.000-C-MRS- 60001-001) | C1002 | 0AX | 4 | 2019-06-06 | CON-BMP-VTRA-012082 | 2019-06-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-0411-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V REACTORS AND INTERNALS | BELLELI ENERGY CPE SrL | 018C1001R | MPS-18106-RM-16532018 | 000-C-PQP-40008-001 | MANUFACTURING PROCESS SPECIFICATION RING MILL ALL ITEMS | B1001 | 0X | 3 | 2019-05-29 | CON-BMP-VTRA-011830 | 2019-05-29 | FOR BAPCO REVIEW | 2019-06-13 | 2019-06-09 | 1-APPROVED BMP-ROC-VTRE-000893 | CLASS 2
076551C-000R-MR-0411-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V REACTORS AND INTERNALS | BELLELI ENERGY CPE SrL | 018C1001R | NDT-18106-FDB | 000-C-PRO-40053-001 | NDT PROCEDURES FORGIA DI BOLLATE 018C1001R 018C2001R 018C1002R 018C2002R 021C0001R | B1202 | 0X | 3 | 2019-06-17 | CON-BMP-VTRA-012235 | 2019-06-17 | FOR BAPCO REVIEW | 2019-07-01 | 2019-06-29 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001083 | CLASS 2
076551C-000R-MR-0411-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V REACTORS AND INTERNALS | BELLELI ENERGY CPE SrL | 018C1001R | NDT-18106-FM-2352019 | 018-C-PRO-40030-001 | NDT PROCEDURES FORGE MONCHIERI 018C1001R/2001R 018C1002R/2002R | B1202 | AX | 2 | 2019-05-29 | CON-BMP-VTRA-011834 | 2019-05-29 | FOR BAPCO REVIEW | 2019-06-13 | 2019-06-10 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000897 | CLASS 2
076551C-000R-MR-0411-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V REACTORS AND INTERNALS | BELLELI ENERGY CPE SrL | 018C1001R | NDT-18106-FV | 000-C-PRO-40009-001 | NDT PROCEDURES - FORGIATURA VIENNA ALL ITEMS (EX BAPCO DOC N. 000-C-PRO-60009-001) | B1202 | 0X | 3 | 2019-06-18 | CON-BMP-VTRA-012277 | 2019-06-18 | FOR BAPCO REVIEW | 2019-07-03 | 2019-06-30 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001119 | CLASS 2
076551C-000R-MR-0411-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V REACTORS AND INTERNALS | BELLELI ENERGY CPE SrL | 018C1001R | NDT-18106-RM-16532018 | 000-C-PRO-40040-001 | NDT PROCEDURES RING MILL ALL ITEMS | B1202 | 0X | 4 | 2019-06-18 | CON-BMP-VTRA-012274 | 2019-06-18 | FOR BAPCO REVIEW | 2019-07-02 | 2019-06-30 | 1-APPROVED BMP-ROC-VTRE-001119 | CLASS 2
076551C-000R-MR-0411-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V REACTORS AND INTERNALS | BELLELI ENERGY CPE SrL | 018C1001R | NDT-18106-SF-13732018 | 000-C-PRO-40027-001 | NDT PROCEDURES - SPECIAL FLANGES ALL ITEMS (EX BAPCO N. 000-C-PRO-60027-001) | B1202 | 0X | 3 | 2019-06-17 | CON-BMP-VTRA-012236 | 2019-06-17 | FOR BAPCO REVIEW | 2019-07-01 | 2019-06-29 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001065 | CLASS 2
076551C-000R-MR-0411-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V REACTORS AND INTERNALS | BELLELI ENERGY CPE SrL | 018C1001R | PC-18106-01-001 | 018-C-PQP-40009-001 | FABRICATION INSPECTION AND TEST PLAN FIRST REACTOR 018C1001R (EX BAPCO N. 018-C-PQP-00009-001) | B1002 | 0X | 2 | 2019-06-06 | CON-BMP-VTRA-012030 | 2019-06-06 | FOR BAPCO REVIEW | 2019-06-20 | 2019-06-17 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000962 | CLASS 2
076551C-000R-MR-0411-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V REACTORS AND INTERNALS | BELLELI ENERGY CPE SrL | 018C1001R | QCP-18106-FDB | 000-C-PQP-40011-001 | QUALITY CONTROL PLAN FORGIA DI BOLLATE ALL ITEMS | B1002 | 0X | 4 | 2019-06-20 | CON-BMP-VTRA-012326 | 2019-06-20 | FOR BAPCO REVIEW | 2019-07-04 | 2019-07-04 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001165 | CLASS 2
076551C-000R-MR-0411-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V REACTORS AND INTERNALS | BELLELI ENERGY CPE SrL | 018C1001R | QCP-18106-FM-2352019 | 018-C-PQP-40060-001 | QUALITY CONTROL PLAN FORGE MONCHIERI 018C1001R/2001R 018C1002R/2002R | B1002 | AX | 4 | 2019-06-14 | CON-BMP-VTRA-012216 | 2019-06-14 | FOR BAPCO REVIEW | 2019-06-28 | 2019-06-29 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001086 | CLASS 2
076551C-000R-MR-0411-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V REACTORS AND INTERNALS | BELLELI ENERGY CPE SrL | 018C1001R | QCP-18106-FV | 000-C-PQP-40004-001 | QUALITY CONTROL PLAN - FORGIATURA VIENNA ALL ITEMS (EX BAPCO N.000-C-PLN-60002-001) | B1002 | 0X | 4 | 2019-06-19 | CON-BMP-VTRA-012284 | 2019-06-19 | FOR BAPCO REVIEW | 2019-07-03 | 2019-07-01 | 2-REVIEWED WITH MINOR COMMENTS BMP-RPC-VTRE-001123 | CLASS 2
076551C-000R-MR-0411-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V REACTORS AND INTERNALS | BELLELI ENERGY CPE SrL | 018C1001R | QCP-18106-RM-16532018 | 018-C-PQP-40103-001 | QUALITY CONTROL PLAN RING MILL ALL ITEMS (EX BAPCO DOC N. 000-C-PQP-40006-001) | B1001 | 0X | 4 | 2019-06-13 | CON-BMP-VTRA-012195 | 2019-06-13 | FOR BAPCO REVIEW | 2019-06-28 | 2019-06-29 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001077 | CLASS 2
076551C-000R-MR-0411-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V REACTORS AND INTERNALS | BELLELI ENERGY CPE SrL | 018C1001R | QCP-18106-SF-13732018 | 021-C-PQP-40030-001 | QUALITY CONTROL PLAN - SPECIAL FLANGES ALL ITEMS (EX BAPCO N. 000-C-PQP-40003-001) | B1001 | 0X | 4 | 2019-06-06 | CON-BMP-VTRA-012080 | 2019-06-06 | FOR BAPCO REVIEW | 2019-06-21 | 2019-06-19 | 1-APPROVED BMP-ROC-VTRE-001003 | CLASS 2
076551C-000R-MR-0411-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V REACTORS AND INTERNALS | BELLELI ENERGY CPE SrL | 018C1001R | QP-18106-00-001 | 000-C-PQP-40001-001 | PROJECT QUALITY PLAN ALL ITEMS (EX BAPCO N.000-C-PLN-60001- 001) | B1001 | 0X | 4 | 2019-06-04 | CON-BMP-VTRA-011969 | 2019-06-04 | FOR BAPCO REVIEW | 2019-06-19 | 2019-06-15 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000927 | CLASS 2
076551C-000R-MR-0411-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V REACTORS AND INTERNALS | BELLELI ENERGY CPE SrL | 018C1001R | RFS-18106-00-001 | 000-C-MRS-40002-001 | REACTORS FABRICATION SCHEDULE ALL ITEMS (EX BAPCO N.000-C-MRS-60002-001) | C1002 | 0AX | 4 | 2019-06-06 | CON-BMP-VTRA-012082 | 2019-06-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-0411-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V REACTORS AND INTERNALS | BELLELI ENERGY CPE SrL | 018C1001R | SA-18106-00-100 | 000-C-TSP-40002-001 | PROCURAMENT SPECIFICATION FOR 2.25CR 1MO 0.25V - FILLER METAL ALL ITEMS (EX BAPCO N. 000-C-TSP-60002-001) | B1203 | 0X | 4 | 2019-05-29 | CON-BMP-VTRA-011827 | 2019-05-29 | FOR BAPCO REVIEW | 2019-06-12 | 2019-06-16 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000939 | CLASS 2
076551C-000R-MR-0411-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V REACTORS AND INTERNALS | BELLELI ENERGY CPE SrL | 018C1001R | SA-18162-00-001 | 018-C-TSP-40013-001 | SPEC. THE SUPPLY PLATES SA 542M TYPE D CLASS 4A 018C1001R 018C2001R 018C1002R 018C2002R (EX BAPCO N.018-C-TSP-00013-001) | B1203 | 0X | 4 | 2019-05-30 | CON-BMP-VTRA-011855 | 2019-05-30 | FOR BAPCO REVIEW | 2019-06-14 | 2019-06-17 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000978 | CLASS 2
076551C-000R-MR-0411-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V REACTORS AND INTERNALS | BELLELI ENERGY CPE SrL | 018C1001R | SA-18162-00-003 | 000-C-TSP-40001-001 | SPEC. FOR THE SUPPLY OF FORGINGS IN ALLOY STEEL ASME SA 336M GRADE F22V ALL ITEMS (EX BAPCO N.000-C-TSP-60001-001) | B1203 | 0X | 4 | 2019-05-30 | CON-BMP-VTRA-011855 | 2019-05-30 | FOR BAPCO REVIEW | 2019-06-14 | 2019-06-17 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000978 | CLASS 2
076551C-000R-MR-0411-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V REACTORS AND INTERNALS | BELLELI ENERGY CPE SrL | 018C1001R | SA-18162-00-004 | 018-C-TSP-40024-001 | SPECIFICATION FOR THE SUPPLY OF FORGINGS IN SA 182M GRADE F347 018C1001R/1002R/2001R/2002R | B1203 | 0X | 4 | 2019-06-20 | CON-BMP-VTRA-012324 | 2019-06-20 | FOR BAPCO REVIEW | 2019-07-04 | 2019-07-11 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001287 | CLASS 2
076551C-000R-MR-0411-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V REACTORS AND INTERNALS | BELLELI ENERGY CPE SrL | 018C1001R | SA-18162-00-007 | 018-C-TSP-40025-001 | SPECIFICATION FOR THE SUPPLY OF FORGINGS IN SA 965M GRADE F347 018C1001R/1002R/2001R/2002R | B1203 | 0X | 4 | 2019-06-20 | CON-BMP-VTRA-012324 | 2019-06-20 | FOR BAPCO REVIEW | 2019-07-04 | 2019-07-11 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001287 | CLASS 2
076551C-000R-MR-0411-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V REACTORS AND INTERNALS | BELLELI ENERGY CPE SrL | 018C1001R | SCR-18106.01 | 018-C-CAL-40014-001 | TRAIN 1 1ST REACTOR 018C1001R STRUCTURAL CALCULATION REPORT (EX BAPCO N.018-C-CAL-00014-001) | A1003 | 0AX | 2 | 2019-05-30 | CON-BMP-VTRA-011852 | 2019-05-30 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0411-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V REACTORS AND INTERNALS | BELLELI ENERGY CPE SrL | 018C1001R | SF-18106-00-001 | 000-C-PRO-40007-001 | ISR AND POSTWELD HEAT TREATMENT PROCEDURE ALL ITEMS (EX BAPCO N. 000-C-PRO-60007-001) | B1201 | CX | 2 | 2019-04-15 | CON-BMP-VTRA-011171 | 2019-04-15 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0411-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V REACTORS AND INTERNALS | BELLELI ENERGY CPE SrL | 018C1001R | SF-18106-00-002 | 000-C-PRO-40011-001 | PRODUCTION WELD TEST COUPONS PROCEDURE ALL ITEMS (EX BAPCO N. 000-C-PRO-60011-001) | B1201 | BX | 3 | 2019-01-15 | CON-BMP-VTRA-010226 | 2019-01-15 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0411-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V REACTORS AND INTERNALS | BELLELI ENERGY CPE SrL | 018C1001R | SF-18106-00-003 | 000-C-PRO-40016-001 | FORMING PROCEDURE ALL ITEMS (EX BAPCO N.000-C-PRO-60016-001) | B1201 | 0AX | 3 | 2019-06-21 | CON-BMP-VTRA-012354 | 2019-06-21 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0411-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V REACTORS AND INTERNALS | BELLELI ENERGY CPE SrL | 018C1001R | SI-18106-00-001 | 000-C-PRO-40001-001 | RADIOGRPHIC EXAMINATION PROCEDURE ALL ITEMS (EX BAPCO N.000-C-PRO-60001-001) | B1202 | 0X | 3 | 2019-04-04 | CON-BMP-VTRA-010996 | 2019-04-04 | FOR BAPCO REVIEW | 2019-04-18 | 2019-04-16 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000530 | CLASS 2
076551C-000R-MR-0411-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V REACTORS AND INTERNALS | BELLELI ENERGY CPE SrL | 018C1001R | SI-18106-00-002 | 000-C-PRO-40002-001 | MANUAL ULTRASONIC EXAMINATION PROCEDURE ALL ITEMS (EX BAPCO N.000-C-PRO-60002-001) | B1202 | 0X | 3 | 2019-04-04 | CON-BMP-VTRA-010996 | 2019-04-04 | FOR BAPCO REVIEW | 2019-04-18 | 2019-04-16 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000530 | CLASS 2
076551C-000R-MR-0411-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V REACTORS AND INTERNALS | BELLELI ENERGY CPE SrL | 018C1001R | SI-18106-00-003 | 000-C-PRO-40003-001 | MAGNETIC PARTICLE EXAMINATION PROCEDURE ALL ITEMS (EX BAPCO N.000-C-PRO-60003-001) | B1202 | 0X | 3 | 2019-04-04 | CON-BMP-VTRA-010996 | 2019-04-04 | FOR BAPCO REVIEW | 2019-04-18 | 2019-04-16 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000530 | CLASS 2
076551C-000R-MR-0411-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V REACTORS AND INTERNALS | BELLELI ENERGY CPE SrL | 018C1001R | SI-18106-00-004 | 000-C-PRO-40004-001 | LIQUID PENETRANT EXAMINATION PROCEDURE ALL ITEMS (EX BAPCO N.000-C-PRO-60004-001) | B1202 | 0X | 3 | 2019-04-04 | CON-BMP-VTRA-010996 | 2019-04-04 | FOR BAPCO REVIEW | 2019-04-18 | 2019-04-16 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000530 | CLASS 2
076551C-000R-MR-0411-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V REACTORS AND INTERNALS | BELLELI ENERGY CPE SrL | 018C1001R | SI-18106-00-005 | 000-C-PRO-40005-001 | POSITIVE MATERIAL IDENTIFICATION PROCEDURE ALL ITEMS (EX BAPCO N. 000-C-PRO- 60005-001) | B1202 | 0X | 3 | 2019-04-04 | CON-BMP-VTRA-010999 | 2019-04-04 | FOR BAPCO REVIEW | 2019-04-18 | 2019-04-16 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000529 | CLASS 2
076551C-000R-MR-0411-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V REACTORS AND INTERNALS | BELLELI ENERGY CPE SrL | 018C1001R | SI-18106-00-006 | 000-C-PRO-40006-001 | MECHANIZED ULTRASONIC EXAMINATION PROCEDURE ALL ITEMS (EX BAPCO N.000-C-PRO- 60006-001) | B1202 | BX | 2 | 2019-01-16 | CON-BMP-VTRA-010227 | 2019-01-16 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0411-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V REACTORS AND INTERNALS | BELLELI ENERGY CPE SrL | 018C1001R | SI-18106-00-007 | 000-C-PRO-40013-001 | HARDNESS TEST VERIFICATION PROCEDURE ALL ITEMS (EX BAPCO N. 000-C-PRO-60013-001) | B1202 | 0X | 3 | 2019-04-04 | CON-BMP-VTRA-010999 | 2019-04-04 | FOR BAPCO REVIEW | 2019-04-18 | 2019-04-16 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000529 | CLASS 2
076551C-000R-MR-0411-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V REACTORS AND INTERNALS | BELLELI ENERGY CPE SrL | 018C1001R | SI-18106-00-008 | 000-C-PRO-40010-001 | VISUAL & DIMENSIONAL CHECK PROCEDURE ALL ITEMS (EX BAPCO N.000-C-PRO-60010-001) | B1202 | 0X | 3 | 2019-04-04 | CON-BMP-VTRA-010996 | 2019-04-04 | FOR BAPCO REVIEW | 2019-04-18 | 2019-04-16 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000530 | CLASS 2
076551C-000R-MR-0411-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V REACTORS AND INTERNALS | BELLELI ENERGY CPE SrL | 018C1001R | SI-18106-00-009 | 000-C-PRO-40015-001 | ULTRASONIC THICKNESS VERIFICATION ALL ITEMS | B1202 | AX | 2 | 2019-01-11 | CON-BMP-VTRA-010207 | 2019-01-11 | FOR BAPCO REVIEW | 2019-01-28 | 2019-01-21 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000127 | CLASS 2
076551C-000R-MR-0411-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V REACTORS AND INTERNALS | BELLELI ENERGY CPE SrL | 018C1001R | SS-18106-01-001 | 018-C-MCD-00015-001 | WELDING BOOK 018C1001R | B1304 | AX | 2 | 2018-10-23 | CON-BMP-VTRA-010015 | 2018-10-23 | FOR BAPCO REVIEW | 2018-11-09 | 2018-11-07 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000016_5-RETAINED FOR INFORMATION BMP-ROC-VTRE-00029_DTD.13/11/2018 | CLASS 2
076551C-000R-MR-0411-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V REACTORS AND INTERNALS | BELLELI ENERGY CPE SrL | 018C1002R | DWG-18106-02-18 | 018-C-DLB-40009-001 | TRAIN 1 2ND REACTOR 018C1002R NAMEPLATE (EX BAPCO N.018-C-DLB-00009-001) | A1112 | 0X | 3 | 2019-03-21 | CON-BMP-VTRA-010817 | 2019-03-21 | FOR BAPCO REVIEW | 2019-04-04 | 2019-04-06 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000469 | CLASS 2
076551C-000R-MR-0411-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V REACTORS AND INTERNALS | BELLELI ENERGY CPE SrL | 018C1002R | DWG-18106.01-02 | 018-C-GAD-40094-002 | TRAIN 1 1ST REACTOR 018C1001R GENERAL ASSEMBLY 2/2 (EX BAPCO N.018-C-GAD-00094-002) | A1103 | 0AX | 2 | 2019-05-31 | CON-BMP-VTRA-011899 | 2019-05-31 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0411-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V REACTORS AND INTERNALS | BELLELI ENERGY CPE SrL | 018C1002R | DWG-18106.02-01 | 018-C-GAD-40101-001 | TRAIN 1 2ND REACTOR 018C1002R GENERAL ASSEMBLY 1/2 (EX BAPCO N.018-C-GAD-00101-001) | A1103 | 0AX | 2 | 2019-05-31 | CON-BMP-VTRA-011898 | 2019-05-31 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0411-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V REACTORS AND INTERNALS | BELLELI ENERGY CPE SrL | 018C1002R | DWG-18106.02-02 | 018-C-GAD-40101-002 | TRAIN 1 2ND REACTOR 018C1002R GENERAL ASSEMBLY 2/2 (EX BAPCO N.018-C-GAD-00101-002) | A1103 | 0AX | 2 | 2019-05-31 | CON-BMP-VTRA-011898 | 2019-05-31 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0411-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V REACTORS AND INTERNALS | BELLELI ENERGY CPE SrL | 018C1002R | DWG-18106.02-04 | 018-C-GAD-40102-001 | TRAIN 1 2ND REACTOR 018C1002R NOZZLE DETAILS 1/3 (EX BAPCO N.018-C-GAD-00102-001) | A1109 | 0AX | 2 | 2019-05-31 | CON-BMP-VTRA-011904 | 2019-05-31 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0411-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V REACTORS AND INTERNALS | BELLELI ENERGY CPE SrL | 018C1002R | DWG-18106.02-05 | 018-C-GAD-40102-002 | TRAIN 1 2ND REACTOR 018C1002R NOZZLE DETAILS 2/3 (EX BAPCO N.018-C-GAD-00102-002) | A1109 | 0AX | 2 | 2019-05-31 | CON-BMP-VTRA-011904 | 2019-05-31 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0411-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V REACTORS AND INTERNALS | BELLELI ENERGY CPE SrL | 018C1002R | DWG-18106.02-06 | 018-C-GAD-40102-003 | TRAIN 1 2 REACTOR 018C1002R NOZZLE DETAILS 3/3 (EX BAPCO N.018-C-GAD-00102-003) | A1109 | 0AX | 2 | 2019-05-31 | CON-BMP-VTRA-011904 | 2019-05-31 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0411-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V REACTORS AND INTERNALS | BELLELI ENERGY CPE SrL | 018C1002R | DWG-18106.02-07 | 018-C-GAD-40104-001 | TRAIN 1 2ND REACTOR INTERNALS DETAILS DISTRIBUTOR PLATE 018C1002R | A1109 | AX | 2 | 2019-05-31 | CON-BMP-VTRA-011889 | 2019-05-31 | FOR BAPCO REVIEW | 2019-06-17 | 2019-06-18 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000980 | CLASS 2
076551C-000R-MR-0411-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V REACTORS AND INTERNALS | BELLELI ENERGY CPE SrL | 018C1002R | DWG-18106.02-08 | 018-C-GAD-40104-002 | TRAIN 1 2ND REACTOR INTERNALS DETAILS DISTRIBUTOR PLATE 018C1002R | A1109 | AX | 2 | 2019-05-31 | CON-BMP-VTRA-011889 | 2019-05-31 | FOR BAPCO REVIEW | 2019-06-17 | 2019-06-18 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000980 | CLASS 2
076551C-000R-MR-0411-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V REACTORS AND INTERNALS | BELLELI ENERGY CPE SrL | 018C1002R | DWG-18106.02-09 | 018-C-GAD-40104-003 | TRAIN 1 2ND REACTOR INTERNALS DETAILS DISTRIBUTOR PLATE 018C1002R | A1109 | AX | 2 | 2019-05-31 | CON-BMP-VTRA-011889 | 2019-05-31 | FOR BAPCO REVIEW | 2019-06-17 | 2019-06-18 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000980 | CLASS 2
076551C-000R-MR-0411-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V REACTORS AND INTERNALS | BELLELI ENERGY CPE SrL | 018C1002R | DWG-18106.02-23 | 018-C-DLB-40010-001 | 2ND REACTOR 018C1002R TEMPLATE DRAWING (EX BAPCO N. 018-C-DLB-00010-001) | A2010 | 0X | 3 | 2019-03-05 | CON-BMP-VTRA-010580 | 2019-03-05 | FOR BAPCO REVIEW | 2019-03-19 | 2019-03-18 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000333 | CLASS 2
076551C-000R-MR-0411-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V REACTORS AND INTERNALS | BELLELI ENERGY CPE SrL | 018C1002R | FEA-18106.02-1 | 018-C-CAL-40019-001 | 2ND REACTOR (TRAIN 1) STRENGHT ANALYSIS 018C1002R | A1003 | 0X | 4 | 2019-07-01 | CON-BMP-VTRA-012601 | 2019-07-01 | FOR BAPCO REVIEW | 2019-07-16 |  |  | CLASS 2
076551C-000R-MR-0411-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V REACTORS AND INTERNALS | BELLELI ENERGY CPE SrL | 018C1002R | FEA-18106.02-2 | 018-C-CAL-40020-001 | FATIGUE / CREEP ANALYSIS ACCORDING TO CODE CASE 2605-2 - 2ND REACTOR - TRAIN 1 - ITEM 018C1002R | A1003 | 0X | 4 | 2019-07-01 | CON-BMP-VTRA-012591 | 2019-07-01 | FOR BAPCO REVIEW | 2019-07-15 |  |  | CLASS 2
076551C-000R-MR-0411-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V REACTORS AND INTERNALS | BELLELI ENERGY CPE SrL | 018C1002R | MCR-18106.02 | 018-C-CAL-40017-001 | TRAIN 1 2ND REACTOR 018C1002R MECHANICAL CALCULATION REPORT (EX BAPCO N.018-C-CAL-00017-001) | A1003 | 0AX | 2 | 2019-05-30 | CON-BMP-VTRA-011852 | 2019-05-30 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0411-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V REACTORS AND INTERNALS | BELLELI ENERGY CPE SrL | 018C1002R | PC-18106-02-001 | 018-C-PQP-40011-001 | FABRICATION INSPECTION AND TEST PLAN SECOND REACTOR 018C1002R (EX BAPCO N. 018-C-PQP-00011-001) | B1002 | 0X | 2 | 2019-06-06 | CON-BMP-VTRA-012030 | 2019-06-06 | FOR BAPCO REVIEW | 2019-06-20 | 2019-06-17 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000962 | CLASS 2
076551C-000R-MR-0411-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V REACTORS AND INTERNALS | BELLELI ENERGY CPE SrL | 018C1002R | SCR-18106.02 | 018-C-CAL-40018-001 | TRAIN 1 2ND REACTOR 018C1002R STRUCTURAL CALCULATION REPORT (EX BAPCO N.018-C-CAL-00018-001) | A1003 | 0AX | 2 | 2019-05-30 | CON-BMP-VTRA-011852 | 2019-05-30 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0411-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V REACTORS AND INTERNALS | BELLELI ENERGY CPE SrL | 018C1002R | SS-18106-02-001 | 018-C-MCD-00016-001 | WELDING BOOK 018C1002R | B1304 | AX | 2 | 2018-10-23 | CON-BMP-VTRA-010015 | 2018-10-23 | FOR BAPCO REVIEW | 2018-11-09 | 2018-11-07 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000016_5-RETAINED FOR INFORMATION BMP-ROC-VTRE-00029_DTD.13/11/2018 | CLASS 2
076551C-000R-MR-0411-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V REACTORS AND INTERNALS | BELLELI ENERGY CPE SrL | 018C2001R | DWG-18106.01-01A | 018-C-GAD-40110-001 | TRAIN 2 1ST REACTOR 018C2001R GENERAL ASSEMBLY 1/2 | A1103 | 0AX | 2 | 2019-05-31 | CON-BMP-VTRA-011898 | 2019-05-31 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0411-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V REACTORS AND INTERNALS | BELLELI ENERGY CPE SrL | 018C2001R | DWG-18106.01-02A | 018-C-GAD-40110-002 | TRAIN 2 1ST REACTOR 018C2001R GENERAL ASSEMBLY 2/2 | A1103 | 0AX | 2 | 2019-05-31 | CON-BMP-VTRA-011898 | 2019-05-31 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0411-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V REACTORS AND INTERNALS | BELLELI ENERGY CPE SrL | 018C2001R | DWG-18106.01-03A | 018-C-GAD-40111-001 | TRAIN 2 1ST REACTOR BODY DETAILS 018C2001R | A1109 | 0X | 2 | 2019-05-31 | CON-BMP-VTRA-011871 | 2019-05-31 | FOR BAPCO REVIEW | 2019-06-14 | 2019-06-18 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000973 | CLASS 2
076551C-000R-MR-0411-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V REACTORS AND INTERNALS | BELLELI ENERGY CPE SrL | 018C2001R | DWG-18106.01-04A | 018-C-GAD-40112-001 | TRAIN 2 1ST REACTOR 018C2001R NOZZLE DETAILS 1/3 (EX BAPCO N.018-C-GAD-00112-001) | A1109 | 0AX | 2 | 2019-05-31 | CON-BMP-VTRA-011904 | 2019-05-31 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0411-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V REACTORS AND INTERNALS | BELLELI ENERGY CPE SrL | 018C2001R | DWG-18106.01-05A | 018-C-GAD-40112-002 | TRAIN 2 1ST REACTOR 018C2001R NOZZLE DETAILS 2/3 (EX BAPCO N.018-C-GAD-00112-002) | A1109 | 0AX | 2 | 2019-06-01 | CON-BMP-VTRA-011910 | 2019-06-01 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0411-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V REACTORS AND INTERNALS | BELLELI ENERGY CPE SrL | 018C2001R | DWG-18106.01-06A | 018-C-GAD-40112-003 | TRAIN 2 1ST REACTOR 018C2001R NOZZLE DETAILS 3/3 (EX BAPCO N.018-C-GAD-00112-003) | A1109 | 0AX | 2 | 2019-05-31 | CON-BMP-VTRA-011904 | 2019-05-31 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0411-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V REACTORS AND INTERNALS | BELLELI ENERGY CPE SrL | 018C2001R | DWG-18106.01-07A | 018-C-GAD-40113-001 | TRAIN 2 1ST REACTOR INTERNALS DETAILS DISTRIBUTOR PLATE 018C2001R | A1109 | AX | 2 | 2019-05-31 | CON-BMP-VTRA-011889 | 2019-05-31 | FOR BAPCO REVIEW | 2019-06-17 | 2019-06-18 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000980 | CLASS 2
076551C-000R-MR-0411-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V REACTORS AND INTERNALS | BELLELI ENERGY CPE SrL | 018C2001R | DWG-18106.01-08A | 018-C-GAD-40113-002 | TRAIN 2 1ST REACTOR INTERNALS DETAILS DISTRIBUTOR PLATE 018C2001R | A1109 | AX | 2 | 2019-05-31 | CON-BMP-VTRA-011889 | 2019-05-31 | FOR BAPCO REVIEW | 2019-06-17 | 2019-06-18 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000980 | CLASS 2
076551C-000R-MR-0411-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V REACTORS AND INTERNALS | BELLELI ENERGY CPE SrL | 018C2001R | DWG-18106.01-09A | 018-C-GAD-40113-003 | TRAIN 2 1ST REACTOR INTERNALS DETAILS DISTRIBUTOR PLATE 018C2001R | A1109 | AX | 2 | 2018-05-31 | CON-BMP-VTRA-011883 | 2019-05-31 | FOR BAPCO REVIEW | 2019-06-17 | 2019-06-18 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000984 | CLASS 2
076551C-000R-MR-0411-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V REACTORS AND INTERNALS | BELLELI ENERGY CPE SrL | 018C2001R | DWG-18106.01-15A | 018-C-GAD-40114-001 | TRAIN 2 1ST REACTOR 018C2001R EXTERNAL DETAILS 1-3 | A1109 | AX | 2 | 2019-05-31 | CON-BMP-VTRA-011889 | 2019-05-31 | FOR BAPCO REVIEW | 2019-06-17 | 2019-06-18 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000980 | CLASS 2
076551C-000R-MR-0411-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V REACTORS AND INTERNALS | BELLELI ENERGY CPE SrL | 018C2001R | DWG-18106.01-16A | 018-C-GAD-40114-002 | TRAIN 2 1ST REACTOR 018C2001R EXTERNAL DETAILS 2-3 | A1109 | AX | 2 | 2019-05-31 | CON-BMP-VTRA-011889 | 2019-05-31 | FOR BAPCO REVIEW | 2019-06-17 | 2019-06-18 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000980 | CLASS 2
076551C-000R-MR-0411-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V REACTORS AND INTERNALS | BELLELI ENERGY CPE SrL | 018C2001R | DWG-18106.01-18A | 018-C-DLB-40011-001 | TRAIN 2 1ST REACTOR 018C2001R NAMEPLATE (EX BAPCO N.018-C-DLB-00011-001) | A1112 | 0X | 3 | 2019-03-21 | CON-BMP-VTRA-010817 | 2019-03-21 | FOR BAPCO REVIEW | 2019-04-04 | 2019-04-06 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000469 | CLASS 2
076551C-000R-MR-0411-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V REACTORS AND INTERNALS | BELLELI ENERGY CPE SrL | 018C2001R | DWG-18106.01-23A | 018-C-DLB-40012-001 | TRAIN 2 1ST REACTOR 018C2001R TEMPLATE DRAWING (EX BAPCO N.018-C-DLB-00012-001) | A2010 | BX | 3 | 2019-03-20 | CON-BMP-VTRA-010788 | 2019-03-20 | FOR BAPCO REVIEW | 2019-04-04 | 2019-04-04 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000448 | CLASS 2
076551C-000R-MR-0411-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V REACTORS AND INTERNALS | BELLELI ENERGY CPE SrL | 018C2001R | DWG-18106.02-03 | 018-C-GAD-40103-001 | 2ND REACTOR 018C2001R 018C2002R BODY DETAILS (EX BAPCO DOC N. 018-C-GAD-00103-001) | A1109 | 0X | 2 | 2019-06-04 | CON-BMP-VTRA-011949 | 2019-06-04 | FOR BAPCO REVIEW | 2019-06-19 | 2019-06-26 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001041 | CLASS 2
076551C-000R-MR-0411-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V REACTORS AND INTERNALS | BELLELI ENERGY CPE SrL | 018C2001R | FEA-18106.01-1A | 018-C-CAL-40023-001 | 1ST REACTOR (TRAIN 2) STRENGHT ANALYSIS 018C2001R | A1003 | 0X | 4 | 2019-07-01 | CON-BMP-VTRA-012601 | 2019-07-01 | FOR BAPCO REVIEW | 2019-07-16 |  |  | CLASS 2
076551C-000R-MR-0411-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V REACTORS AND INTERNALS | BELLELI ENERGY CPE SrL | 018C2001R | FEA-18106.01-2A | 018-C-CAL-40024-001 | FATIGUE / CREEP ANALYSIS ACCORDING TO CODE CASE 2605-2 - 1ST REACTOR - TRAIN 2 - ITEM 018C2001R | A1003 | 0X | 4 | 2019-07-01 | CON-BMP-VTRA-012591 | 2019-07-01 | FOR BAPCO REVIEW | 2019-07-15 |  |  | CLASS 2
076551C-000R-MR-0411-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V REACTORS AND INTERNALS | BELLELI ENERGY CPE SrL | 018C2001R | PC-18106-01-001A | 018-C-PQP-40010-001 | FABRICATION INSPECTION AND TEST PLAN FIRST REACTOR 018C2001R (EX BAPCO N. EX 018- C-ITP-00009-001) | B1002 | 0X | 2 | 2019-06-06 | CON-BMP-VTRA-012030 | 2019-06-06 | FOR BAPCO REVIEW | 2019-06-20 | 2019-06-17 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000962 | CLASS 2
076551C-000R-MR-0411-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V REACTORS AND INTERNALS | BELLELI ENERGY CPE SrL | 018C2001R | SS-18106-01-001A | 018-C-MCD-00018-001 | WELDING BOOK 018C2001R | B1304 | AX | 2 | 2018-10-23 | CON-BMP-VTRA-010015 | 2018-10-23 | FOR BAPCO REVIEW | 2018-11-09 | 2018-11-07 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000016_5-RETAINED FOR INFORMATION BMP-ROC-VTRE-00029_DTD.13/11/2018 | CLASS 2
076551C-000R-MR-0411-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V REACTORS AND INTERNALS | BELLELI ENERGY CPE SrL | 018C2002R | DWG-18106.02-01A | 018-C-GAD-40117-001 | TRAIN 2 2ND REACTOR 018C2002R GENERAL ASSEMBLY 1/2 | A1103 | 0AX | 2 | 2019-05-31 | CON-BMP-VTRA-011898 | 2019-05-31 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0411-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V REACTORS AND INTERNALS | BELLELI ENERGY CPE SrL | 018C2002R | DWG-18106.02-02A | 018-C-GAD-40117-002 | TRAIN 2 2ND REACTOR 018C2002R GENERAL ASSEMBLY 2/2 | A1103 | 0X | 2 | 2019-06-18 | CON-BMP-VTRA-012278 | 2019-06-18 | FOR BAPCO REVIEW | 2019-07-03 | 2019-07-09 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001242 | CLASS 2
076551C-000R-MR-0411-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V REACTORS AND INTERNALS | BELLELI ENERGY CPE SrL | 018C2002R | DWG-18106.02-03A | 018-C-GAD-40118-001 | TRAIN 2 2ND REACTOR BODY DETAILS 018C2002R | A1109 | 0X | 2 | 2019-05-31 | CON-BMP-VTRA-011871 | 2019-05-31 | FOR BAPCO REVIEW | 2019-06-14 | 2019-06-18 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000973 | CLASS 2
076551C-000R-MR-0411-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V REACTORS AND INTERNALS | BELLELI ENERGY CPE SrL | 018C2002R | DWG-18106.02-04A | 018-C-GAD-40119-001 | TRAIN 2 2ND REACTOR 018C2002R NOZZLE DETAILS 1/3 (EX BAPCO N.018-C-GAD-00119-001) | A1109 | 0AX | 2 | 2019-05-31 | CON-BMP-VTRA-011904 | 2019-05-31 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0411-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V REACTORS AND INTERNALS | BELLELI ENERGY CPE SrL | 018C2002R | DWG-18106.02-05A | 018-C-GAD-40119-002 | TRAIN 2 2ND REACTOR 018C2002R NOZZLE DETAILS 2/3 (EX BAPCO N.018-C-GAD-00119-002) | A1109 | 0AX | 2 | 2019-05-31 | CON-BMP-VTRA-011904 | 2019-05-31 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0411-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V REACTORS AND INTERNALS | BELLELI ENERGY CPE SrL | 018C2002R | DWG-18106.02-06A | 018-C-GAD-40119-003 | TRAIN 2 2ND REACTOR 0182002R NOZZLE DETAILS 3/3 (EX BAPCO N.018-C-GAD-00119-003) | A1109 | 0AX | 2 | 2019-05-31 | CON-BMP-VTRA-011904 | 2019-05-31 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0411-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V REACTORS AND INTERNALS | BELLELI ENERGY CPE SrL | 018C2002R | DWG-18106.02-07A | 018-C-GAD-40120-001 | TRAIN 2 2ND REACTOR INTERNALS DETAILS DISTRIBUTOR PLATE 018C2002R | A1109 | AX | 2 | 2019-05-31 | CON-BMP-VTRA-011889 | 2019-05-31 | FOR BAPCO REVIEW | 2019-06-17 | 2019-06-18 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000980 | CLASS 2
076551C-000R-MR-0411-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V REACTORS AND INTERNALS | BELLELI ENERGY CPE SrL | 018C2002R | DWG-18106.02-08A | 018-C-GAD-40120-002 | TRAIN 2 2ND REACTOR INTERNALS DETAILS DISTRIBUTOR PLATE 018C2002R | A1109 | AX | 2 | 2019-05-31 | CON-BMP-VTRA-011889 | 2019-05-31 | FOR BAPCO REVIEW | 2019-06-17 | 2019-06-18 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000980 | CLASS 2
076551C-000R-MR-0411-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V REACTORS AND INTERNALS | BELLELI ENERGY CPE SrL | 018C2002R | DWG-18106.02-09A | 018-C-GAD-40120-003 | TRAIN 2 2ND REACTOR INTERNALS DETAILS DISTRIBUTOR PLATE 018C2002R | A1109 | AX | 2 | 2019-05-31 | CON-BMP-VTRA-011889 | 2019-05-31 | FOR BAPCO REVIEW | 2019-06-17 | 2019-06-18 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000980 | CLASS 2
076551C-000R-MR-0411-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V REACTORS AND INTERNALS | BELLELI ENERGY CPE SrL | 018C2002R | DWG-18106.02-18A | 018-C-DLB-40013-001 | TRAIN 2 2ND REACTOR 018C2002R NAMEPLATE (EX BAPCO N.018-C-DLB-00013-001) | A1112 | 0X | 3 | 2019-03-21 | CON-BMP-VTRA-010817 | 2019-03-21 | FOR BAPCO REVIEW | 2019-04-04 | 2019-04-06 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000469 | CLASS 2
076551C-000R-MR-0411-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V REACTORS AND INTERNALS | BELLELI ENERGY CPE SrL | 018C2002R | DWG-18106.02-23A | 018-C-DLB-00014-001 | TRAIN 2 2ND REACTOR 018C2002R TEMPLATE DRAWING | A2010 | AX | 1 | 2018-12-10 | CON-BMP-VTRA-010135 | 2018-12-10 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0411-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V REACTORS AND INTERNALS | BELLELI ENERGY CPE SrL | 018C2002R | FEA-18106.02-1A | 018-C-CAL-40027-001 | 2ND REACTOR (TRAIN 2) STRENGHT ANALYSIS 018C2002R | A1003 | 0X | 4 | 2019-07-01 | CON-BMP-VTRA-012601 | 2019-07-01 | FOR BAPCO REVIEW | 2019-07-16 |  |  | CLASS 2
076551C-000R-MR-0411-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V REACTORS AND INTERNALS | BELLELI ENERGY CPE SrL | 018C2002R | FEA-18106.02-2A | 018-C-CAL-40028-001 | FATIGUE / CREEP ANALYSIS ACCORDING TO CODE CASE 2605-2 - 2ND REACTOR - TRAIN 2 - ITEM 018C2002R | A1003 | 0X | 4 | 2019-07-01 | CON-BMP-VTRA-012591 | 2019-07-01 | FOR BAPCO REVIEW | 2019-07-15 |  |  | CLASS 2
076551C-000R-MR-0411-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V REACTORS AND INTERNALS | BELLELI ENERGY CPE SrL | 018C2002R | MCR-18106.02A | 018-C-CAL-40025-001 | TRAIN 2 2ND REACTOR MECHANICAL CALCULATION REPORT 018C2002R | A1003 | AX | 2 | 2019-05-30 | CON-BMP-VTRA-011848 | 2019-05-30 | FOR BAPCO REVIEW | 2019-06-14 | 2019-07-08 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001227 | CLASS 2
076551C-000R-MR-0411-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V REACTORS AND INTERNALS | BELLELI ENERGY CPE SrL | 018C2002R | PC-18106-02-001A | 018-C-PQP-40012-001 | FABRICATION INSPECTION AND TEST PLAN SECOND REACTOR 018C2002R (EX BAPCO N. 018-C-ITP- 00010-001) | B1002 | 0X | 2 | 2019-06-06 | CON-BMP-VTRA-012030 | 2019-06-06 | FOR BAPCO REVIEW | 2019-06-20 | 2019-06-17 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000962 | CLASS 2
076551C-000R-MR-0411-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V REACTORS AND INTERNALS | BELLELI ENERGY CPE SrL | 018C2002R | SS-18106-02-001A | 018-C-MCD-00020-001 | WELDING BOOK 018C2002R | B1304 | AX | 2 | 2018-10-23 | CON-BMP-VTRA-010015 | 2018-10-23 | FOR BAPCO REVIEW | 2018-11-09 | 2018-11-07 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000016_5-RETAINED FOR INFORMATION BMP-ROC-VTRE-00029_DTD.13/11/2018 | CLASS 2
076551C-000R-MR-0411-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V REACTORS AND INTERNALS | BELLELI ENERGY CPE SrL | 021C0001R | DWG-18106.03-01 | 021-C-GAD-40026-001 | REACTOR 021C0001R GENERAL ASSEMBLY 1/2 (EX BAPCO N.021- C-GAD-00026-001) | A1103 | 0AX | 2 | 2019-05-31 | CON-BMP-VTRA-011898 | 2019-05-31 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0411-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V REACTORS AND INTERNALS | BELLELI ENERGY CPE SrL | 021C0001R | DWG-18106.03-02 | 021-C-GAD-40026-002 | REACTOR 021C0001R GENERAL ASSEMBLY 2/2 (EX BAPCO N.021- C-GAD-00026-002) | A1103 | 0AX | 2 | 2019-05-31 | CON-BMP-VTRA-011898 | 2019-05-31 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0411-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V REACTORS AND INTERNALS | BELLELI ENERGY CPE SrL | 021C0001R | DWG-18106.03-03 | 021-C-GAD-40027-001 | REACTOR 021C0001R BODY DETAILS (EX BAPCO N. 021-C-GAD-00027-001) | A1109 | 0AX | 3 | 2019-05-31 | CON-BMP-VTRA-011878 | 2019-05-31 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0411-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V REACTORS AND INTERNALS | BELLELI ENERGY CPE SrL | 021C0001R | DWG-18106.03-04 | 021-C-GAD-40028-001 | REACTOR 021C0001R NOZZLE DETAILS 1/2 (EX BAPCO N.021-C-GAD-00028-001) | A1109 | 0AX | 3 | 2019-05-31 | CON-BMP-VTRA-011878 | 2019-05-31 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0411-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V REACTORS AND INTERNALS | BELLELI ENERGY CPE SrL | 021C0001R | DWG-18106.03-05 | 021-C-GAD-40028-002 | REACTOR 021C0001R NOZZLE DATEILS 2/2 (EX BAPCO N.021-C-GAD-00028-002) | A1109 | 0X | 2 | 2019-03-05 | CON-BMP-VTRA-010578 | 2019-03-05 | FOR BAPCO REVIEW | 2019-03-19 | 2019-03-24 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000368 | CLASS 2
076551C-000R-MR-0411-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V REACTORS AND INTERNALS | BELLELI ENERGY CPE SrL | 021C0001R | DWG-18106.03-06 | 021-C-GAD-40029-001 | REACTOR INTERNAL DETAIL 1/10 021C0001R | A1109 | 0AX | 3 | 2019-05-31 | CON-BMP-VTRA-011878 | 2019-05-31 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0411-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V REACTORS AND INTERNALS | BELLELI ENERGY CPE SrL | 021C0001R | DWG-18106.03-16 | 021-C-GAD-40030-001 | REACTOR EXTERNAL DETAILS 1/2 021C0001R | A1109 | 0AX | 3 | 2019-05-31 | CON-BMP-VTRA-011878 | 2019-05-31 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0411-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V REACTORS AND INTERNALS | BELLELI ENERGY CPE SrL | 021C0001R | DWG-18106.03-17 | 021-C-GAD-40030-002 | REACTOR EXTERNAL DETAILS 2/2 021C0001R | A1109 | 0X | 3 | 2019-05-31 | CON-BMP-VTRA-011879 | 2019-05-31 | FOR BAPCO REVIEW | 2019-06-14 | 2019-06-17 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000988 | CLASS 2
076551C-000R-MR-0411-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V REACTORS AND INTERNALS | BELLELI ENERGY CPE SrL | 021C0001R | DWG-18106.03-18 | 021-C-GAD-40031-001 | REACTOR DEVELOPMENT DRAWING 021C0001R | A1109 | 0X | 3 | 2019-05-31 | CON-BMP-VTRA-011879 | 2019-05-31 | FOR BAPCO REVIEW | 2019-06-14 | 2019-06-17 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000988 | CLASS 2
076551C-000R-MR-0411-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V REACTORS AND INTERNALS | BELLELI ENERGY CPE SrL | 021C0001R | DWG-18106.03-19 | 021-C-DLB-40001-001 | REACTOR 021C0001R NAMEPLATE DRAWING(EX BAPCO N.021-C-DLB- 00001-001) | A1112 | 0AX | 3 | 2019-06-13 | CON-BMP-VTRA-012188 | 2019-06-13 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0411-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V REACTORS AND INTERNALS | BELLELI ENERGY CPE SrL | 021C0001R | DWG-18106.03-24 | 021-C-DLB-00002-001 | REACTOR 021C0001R TEMPLATE DRAWING | A2010 | BX | 1 | 2018-12-10 | CON-BMP-VTRA-010135 | 2018-12-10 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0411-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V REACTORS AND INTERNALS | BELLELI ENERGY CPE SrL | 021C0001R | FEA-18106.03-1 | 021-C-CAL-40003-001 | REACTOR UOP STRENGHT ANALYSIS 021C0001R | A1003 | 0X | 4 | 2019-07-01 | CON-BMP-VTRA-012602 | 2019-07-01 | FOR BAPCO REVIEW | 2019-07-16 |  |  | CLASS 2
076551C-000R-MR-0411-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V REACTORS AND INTERNALS | BELLELI ENERGY CPE SrL | 021C0001R | FEA-18106.03-2 | 021-C-CAL-40004-001 | UOP REACTOR FATIGUE CREEP ANALYSIS ACCORDING TO CODE CASE 2605-2 021C0001R | A1003 | 0X | 4 | 2019-07-01 | CON-BMP-VTRA-012602 | 2019-07-01 | FOR BAPCO REVIEW | 2019-07-16 |  |  | CLASS 2
076551C-000R-MR-0411-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V REACTORS AND INTERNALS | BELLELI ENERGY CPE SrL | 021C0001R | MCR-18106.03 | 021-C-CAL-40001-001 | REACTOR 021C0001R MECHANICAL CALCULATION REPORT (EX BAPCO N.021-C-CAL-00001-001) | A1003 | 0XX | 4 | 2019-04-19 | CON-BMP-VTRA-011233 | 2019-04-23 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0411-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V REACTORS AND INTERNALS | BELLELI ENERGY CPE SrL | 021C0001R | PC-18106-03-001 | 021-C-PQP-40001-001 | FABRICATION INSPECTION AND TEST PLAN REACTOR 021C0001R (EX BAPCO N. 021-C-PQP-00001- 001) | B1002 | 0X | 3 | 2019-06-06 | CON-BMP-VTRA-012029 | 2019-06-06 | FOR BAPCO REVIEW | 2019-06-20 | 2019-06-17 | 1-APPROVED BMP-ROC-VTRE-000963 | CLASS 2
076551C-000R-MR-0411-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V REACTORS AND INTERNALS | BELLELI ENERGY CPE SrL | 021C0001R | SA-18162-00-001A | 021-C-TSP-40003-001 | SPEC. THE SUPPLY OF PLATES IN ALLOY STEEL ASME SA 542M TYPE D CLASS 4A 021C0001R (EX BAPCO N. 021-C-TSP-00003-001) | B1203 | 0X | 4 | 2019-05-30 | CON-BMP-VTRA-011855 | 2019-05-30 | FOR BAPCO REVIEW | 2019-06-14 | 2019-06-17 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000978 | CLASS 2
076551C-000R-MR-0411-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V REACTORS AND INTERNALS | BELLELI ENERGY CPE SrL | 021C0001R | SA-18162-00-002 | 021-C-TSP-40004-001 | SPEC. THE SUPPLY OF PLATES IN ALLOY STEEL ASME SA 542M TYPE D CLASS 4A 021C0001R (EX BAPCO N.021-C-TSP-00004-001) | B1203 | 0X | 4 | 2019-05-30 | CON-BMP-VTRA-011855 | 2019-05-30 | FOR BAPCO REVIEW | 2019-06-14 | 2019-06-17 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000978 | CLASS 2
076551C-000R-MR-0411-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V REACTORS AND INTERNALS | BELLELI ENERGY CPE SrL | 021C0001R | SCR-18106.03 | 021-C-CAL-40002-001 | REACTOR 021C0001R STRUCTURAL CALCULATION REPORT (EX BAPCO N.021-C-CAL-00002-001) | A1003 | 0AX | 4 | 2019-05-29 | CON-BMP-VTRA-011826 | 2019-05-29 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0411-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V REACTORS AND INTERNALS | BELLELI ENERGY CPE SrL | 021C0001R | SS-18106-03-001 | 021-C-MCD-00002-001 | WELDING BOOK 021C1001R | B1304 | AX | 2 | 2018-10-23 | CON-BMP-VTRA-010016 | 2018-10-23 | FOR BAPCO REVIEW | 2018-11-09 | 2018-11-06 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000015_5-RETAINED FOR INFORMATION BMP-ROC-VTRE-00030 DTD.12/11/2018 | CLASS 2
076551C-000R-MR-0511-001 | MATERIAL REQUISITION FOR LARGE COLUMNS | DOOSAN MECATEC | 018C0001 | 18C0070-01-01 | 018-C-GAD-40272-001 | ATMOSPHERIC COLUMN GENERAL ASSEMBLY (1) 018C0001 | A1103 | BX | 2 | 2019-05-02 | CON-BMP-VTRA-011345 | 2019-05-02 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0511-001 | MATERIAL REQUISITION FOR LARGE COLUMNS | DOOSAN MECATEC | 018C0001 | 18C0070-01-02 | 018-C-GAD-40272-002 | ATMOSPHERIC COLUMN GENERAL ASSEMBLY (2) 018C0001 | A1103 | BX | 2 | 2019-05-02 | CON-BMP-VTRA-011345 | 2019-05-02 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0511-001 | MATERIAL REQUISITION FOR LARGE COLUMNS | DOOSAN MECATEC | 018C0001 | 18C0070-01-03 | 018-C-GAD-40273-001 | ATMOSPHERIC COLUMN BODY DETAIL (1) 018C0001 | A1109 | BX | 2 | 2019-05-03 | CON-BMP-VTRA-011362 | 2019-05-03 | FOR BAPCO REVIEW | 2019-05-17 | 2019-05-24 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000758 | CLASS 2
076551C-000R-MR-0511-001 | MATERIAL REQUISITION FOR LARGE COLUMNS | DOOSAN MECATEC | 018C0001 | 18C0070-01-04 | 018-C-GAD-40273-002 | ATMOSPHERIC COLUMN BODY DETAIL (2) 018C0001 | A1109 | BX | 2 | 2019-05-02 | CON-BMP-VTRA-011340 | 2019-05-02 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0511-001 | MATERIAL REQUISITION FOR LARGE COLUMNS | DOOSAN MECATEC | 018C0001 | 18C0070-01-05 | 018-C-GAD-40273-003 | ATMOSHERIC COLUMN BODY DETAIL (3) 018C0001 | A1109 | BX | 2 | 2019-05-02 | CON-BMP-VTRA-011340 | 2019-05-02 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0511-001 | MATERIAL REQUISITION FOR LARGE COLUMNS | DOOSAN MECATEC | 018C0001 | 18C0070-01-06 | 018-C-GAD-40274-001 | ATMOSPHERIC COLUMN - MANHOLE DETAIL (1) 018C0001 | A1109 | BX | 2 | 2019-05-02 | CON-BMP-VTRA-011340 | 2019-05-02 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0511-001 | MATERIAL REQUISITION FOR LARGE COLUMNS | DOOSAN MECATEC | 018C0001 | 18C0070-01-07 | 018-C-GAD-40274-002 | ATMOSPHERIC COLUMN - MANHOLE DETAIL (2) 018C0001 | A1109 | BX | 2 | 2019-05-02 | CON-BMP-VTRA-011340 | 2019-05-02 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0511-001 | MATERIAL REQUISITION FOR LARGE COLUMNS | DOOSAN MECATEC | 018C0001 | 18C0070-01-08 | 018-C-GAD-40275-001 | ATMOSPHERIC COLUMN - NOZZLE DETAIL (1) 018C0001 | A1109 | BX | 2 | 2019-05-02 | CON-BMP-VTRA-011340 | 2019-05-02 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0511-001 | MATERIAL REQUISITION FOR LARGE COLUMNS | DOOSAN MECATEC | 018C0001 | 18C0070-01-09 | 018-C-GAD-40275-002 | ATMOSPHERIC COLUMN - NOZZLE DETAIL (2) 018C0001 | A1109 | BX | 2 | 2019-05-31 | CON-BMP-VTRA-011872 | 2019-05-31 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0511-001 | MATERIAL REQUISITION FOR LARGE COLUMNS | DOOSAN MECATEC | 018C0001 | 18C0070-01-10 | 018-C-GAD-40275-003 | ATMOSPHERIC COLUMN - NOZZLE DETAIL (3) 018C0001 | A1109 | BX | 2 | 2019-05-02 | CON-BMP-VTRA-011340 | 2019-05-02 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0511-001 | MATERIAL REQUISITION FOR LARGE COLUMNS | DOOSAN MECATEC | 018C0001 | 18C0070-01-11 | 018-C-GAD-40275-004 | ATMOSPHERIC COLUMN - NOZZLE DETAIL (4) 018C0001 | A1109 | BX | 2 | 2019-05-02 | CON-BMP-VTRA-011340 | 2019-05-02 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0511-001 | MATERIAL REQUISITION FOR LARGE COLUMNS | DOOSAN MECATEC | 018C0001 | 18C0070-01-12 | 018-C-GAD-40275-005 | ATMOSPHERIC COLUMN - NOZZLE DETAIL (5) 018C0001 | A1109 | BX | 2 | 2019-05-02 | CON-BMP-VTRA-011340 | 2019-05-02 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0511-001 | MATERIAL REQUISITION FOR LARGE COLUMNS | DOOSAN MECATEC | 018C0001 | 18C0070-01-13 | 018-C-GAD-40275-006 | ATMOSPHERIC COLUMN -NOZZLE DETAIL (6) 018C0001 | A1109 | BX | 2 | 2019-05-02 | CON-BMP-VTRA-011340 | 2019-05-02 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0511-001 | MATERIAL REQUISITION FOR LARGE COLUMNS | DOOSAN MECATEC | 018C0001 | 18C0070-01-14 | 018-C-GAD-40275-007 | ATMOSPHERIC COLUMN - NOZZLE DETAIL (7) 018C0001 | A1109 | BX | 2 | 2019-05-02 | CON-BMP-VTRA-011340 | 2019-05-02 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0511-001 | MATERIAL REQUISITION FOR LARGE COLUMNS | DOOSAN MECATEC | 018C0001 | 18C0070-01-15 | 018-C-GAD-40275-008 | ATMOSPHERIC COLUMN -NOZZLE DETAIL (8) 018C0001 | A1109 | BX | 2 | 2019-05-02 | CON-BMP-VTRA-011340 | 2019-05-02 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0511-001 | MATERIAL REQUISITION FOR LARGE COLUMNS | DOOSAN MECATEC | 018C0001 | 18C0070-01-16 | 018-C-GAD-40275-009 | ATMOSPHERIC COLUMN - NOZZLE DETAIL (9) 018C0001 | A1109 | BX | 2 | 2019-05-02 | CON-BMP-VTRA-011340 | 2019-05-02 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0511-001 | MATERIAL REQUISITION FOR LARGE COLUMNS | DOOSAN MECATEC | 018C0001 | 18C0070-01-20 | 018-C-GAD-40276-001 | 018C0001 ATMOSPHERIC COLUMN INTERNAL SUPPORT DETAIL (1) | A1110 | AX | 2 | 2019-05-31 | CON-BMP-VTRA-011873 | 2019-05-31 | FOR BAPCO REVIEW | 2019-06-14 | 2019-06-18 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000969 | CLASS 2
076551C-000R-MR-0511-001 | MATERIAL REQUISITION FOR LARGE COLUMNS | DOOSAN MECATEC | 018C0001 | 18C0070-01-30 | 018-C-PLD-40001-001 | ATMOSPHERIC COLUMN INSUL.&FIREPROOF CLIP DETAIL(1) 018C0001 | A1105 | AX | 2 | 2019-06-25 | CON-BMP-VTRA-012425 | 2019-06-25 | FOR BAPCO REVIEW | 2019-07-09 |  |  | CLASS 2
076551C-000R-MR-0511-001 | MATERIAL REQUISITION FOR LARGE COLUMNS | DOOSAN MECATEC | 018C0001 | 18C0070-01-33 | 018-C-DLB-40021-001 | ATMOSPHERIC COLUMN TEMPLATE DETAIL 018C0001 | A2010 | BX | 2 | 2019-05-02 | CON-BMP-VTRA-011343 | 2019-05-02 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0511-001 | MATERIAL REQUISITION FOR LARGE COLUMNS | DOOSAN MECATEC | 018C0001 | 18C0070-CAL-01 | 018-C-CAL-40055-001 | ATMOSPHERIC COLUMN STRENGTH CALCULATION FOR 018C0001 | A1003 | BX | 2 | 2019-05-02 | CON-BMP-VTRA-011341 | 2019-05-02 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0511-001 | MATERIAL REQUISITION FOR LARGE COLUMNS | DOOSAN MECATEC | 018C0001 | 18C0070-FQCP | 018-C-PQP-40016-001 | FABRICATION AND QUALITY CONTROL PLAN ALL ITEMS | B1002 | AX | 1 | 2019-01-14 | CON-BMP-VTRA-010214 | 2019-01-14 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0511-001 | MATERIAL REQUISITION FOR LARGE COLUMNS | DOOSAN MECATEC | 018C0001 | 18C0070-FQCP-01 | 018-C-PQP-40044-001 | FABRICATION AND QUALITY CONTROL PLAN FOR 018C0001 | B1002 | BX | 2 | 2019-05-31 | CON-BMP-VTRA-011884 | 2019-05-31 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0511-001 | MATERIAL REQUISITION FOR LARGE COLUMNS | DOOSAN MECATEC | 018C0001 | 18C0070-MPR | 018-C-MRS-40003-001 | MONTHLY PROGRESS REPORT ALL ITEMS | C1002 | AX | 4 | 2019-05-20 | CON-BMP-VTRA-011676 | 2019-05-21 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-0511-001 | MATERIAL REQUISITION FOR LARGE COLUMNS | DOOSAN MECATEC | 018C0001 | 18C0070-NDE | 018-C-PRO-40027-001 | NDE PROCEDURE ALL ITEMS | B1202 | BX | 2 | 2019-04-04 | CON-BMP-VTRA-011007 | 2019-04-04 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0511-001 | MATERIAL REQUISITION FOR LARGE COLUMNS | DOOSAN MECATEC | 018C0001 | 18C0070-PWHT | 018-C-PRO-40025-001 | PWHT PROCEDURE ALL ITEMS | B1201 | AXX | 2 | 2019-04-15 | CON-BMP-VTRA-011172 | 2019-04-15 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0511-001 | MATERIAL REQUISITION FOR LARGE COLUMNS | DOOSAN MECATEC | 018C0001 | 18C0070-SCH | 018-C-SCH-40003-001 | MASTER SCHEDULE ALL ITEMS | C1001 | AX | 2 | 2019-03-20 | CON-BMP-VTRA-010772 | 2019-03-20 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-0511-001 | MATERIAL REQUISITION FOR LARGE COLUMNS | DOOSAN MECATEC | 018C0001 | 18C0070-UPO | 018-C-INV-40003-001 | UNPRICED COPY OF MAIN SUBORDERS ALL ITEMS | C1005 | AXX | 2 | 2019-04-16 | CON-BMP-VTRA-011201 | 2019-04-16 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0511-001 | MATERIAL REQUISITION FOR LARGE COLUMNS | DOOSAN MECATEC | 018C0001 | 18C0070-VDDL | 018-C-INX-40014-001 | LIST OF VENDOR'S DOCUMENTS AND DRAWINGS ALL ITEMS | A0001 | AXX | 2 | 2019-04-26 | CON-BMP-VTRA-011263 | 2019-04-26 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0511-001 | MATERIAL REQUISITION FOR LARGE COLUMNS | DOOSAN MECATEC | 018C0001 | 18C0070-WPS | 018-C-MCD-40070-001 | WELDING BOOK (WPS/PQR) 018C0001 (EX BAPCO N.018-C-MCD-40033-001) | B1304 | BX | 2 | 2019-03-20 | CON-BMP-VTRA-010797 | 2019-03-20 | FOR BAPCO REVIEW | 2019-04-04 | 2019-03-31 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000430 | CLASS 2
076551C-000R-MR-0511-001 | MATERIAL REQUISITION FOR LARGE COLUMNS | DOOSAN MECATEC | 018C0003 | 18C0070-02-01 | 018-C-GAD-40280-001 | VACUUM COLUMN GENERAL ASSEMBLY (1) 018C0003 | A1103 | BX | 2 | 2019-05-29 | CON-BMP-VTRA-011825 | 2019-05-29 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0511-001 | MATERIAL REQUISITION FOR LARGE COLUMNS | DOOSAN MECATEC | 018C0003 | 18C0070-02-02 | 018-C-GAD-40280-002 | VACUUM COLUMN GENERAL ASSEMBLY (2) 018C0003 | A1103 | BX | 2 | 2019-05-29 | CON-BMP-VTRA-011825 | 2019-05-29 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0511-001 | MATERIAL REQUISITION FOR LARGE COLUMNS | DOOSAN MECATEC | 018C0003 | 18C0070-02-03 | 018-C-GAD-40281-001 | VACUUM COLUMN BODY DETAIL (1) 018C0003 | A1109 | BX | 2 | 2019-04-26 | CON-BMP-VTRA-011265 | 2019-04-26 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0511-001 | MATERIAL REQUISITION FOR LARGE COLUMNS | DOOSAN MECATEC | 018C0003 | 18C0070-02-04 | 018-C-GAD-40281-002 | VACUUM COLUMN BODY DETAIL (2) 018C0003 | A1109 | BX | 2 | 2019-04-26 | CON-BMP-VTRA-011265 | 2019-04-26 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0511-001 | MATERIAL REQUISITION FOR LARGE COLUMNS | DOOSAN MECATEC | 018C0003 | 18C0070-02-05 | 018-C-GAD-40281-003 | VACUUM COLUMN BODY DETAIL (3) 018C0003 | A1109 | BX | 2 | 2019-04-26 | CON-BMP-VTRA-011265 | 2019-04-26 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0511-001 | MATERIAL REQUISITION FOR LARGE COLUMNS | DOOSAN MECATEC | 018C0003 | 18C0070-02-06 | 018-C-GAD-40282-001 | VACUUM COLUMN - MANHOLE DETAIL (1) 018C0003 | A1109 | BX | 2 | 2019-04-26 | CON-BMP-VTRA-011265 | 2019-04-26 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0511-001 | MATERIAL REQUISITION FOR LARGE COLUMNS | DOOSAN MECATEC | 018C0003 | 18C0070-02-07 | 018-C-GAD-40282-002 | VACUUM COLUMN - MANHOLE DETAIL (2) 018C0003 | A1109 | BX | 2 | 2019-05-03 | CON-BMP-VTRA-011386 | 2019-05-03 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0511-001 | MATERIAL REQUISITION FOR LARGE COLUMNS | DOOSAN MECATEC | 018C0003 | 18C0070-02-08 | 018-C-GAD-40282-003 | VACUUM COLUMN - MANHOLE DETAIL (3) 018C0003 | A1109 | BX | 2 | 2019-04-26 | CON-BMP-VTRA-011265 | 2019-04-26 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0511-001 | MATERIAL REQUISITION FOR LARGE COLUMNS | DOOSAN MECATEC | 018C0003 | 18C0070-02-08A | 018-C-GAD-40282-004 | VACUUM COLUMN - MANHOLE DETAIL (4) 018C0003 | A1109 | BX | 2 | 2019-04-26 | CON-BMP-VTRA-011265 | 2019-04-26 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0511-001 | MATERIAL REQUISITION FOR LARGE COLUMNS | DOOSAN MECATEC | 018C0003 | 18C0070-02-08B | 018-C-GAD-40282-005 | VACUUM COLUMN - MANHOLE DETAIL (5) 018C0003 | A1109 | BX | 2 | 2019-04-26 | CON-BMP-VTRA-011265 | 2019-04-26 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0511-001 | MATERIAL REQUISITION FOR LARGE COLUMNS | DOOSAN MECATEC | 018C0003 | 18C0070-02-09 | 018-C-GAD-40283-001 | VACUUM COLUMN - NOZZLE DETAIL (1) 018C0003 | A1109 | BX | 2 | 2019-04-26 | CON-BMP-VTRA-011265 | 2019-04-26 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0511-001 | MATERIAL REQUISITION FOR LARGE COLUMNS | DOOSAN MECATEC | 018C0003 | 18C0070-02-10 | 018-C-GAD-40283-002 | VACUUM COLUMN - NOZZLE DETAIL (2) 018C0003 | A1109 | BX | 2 | 2019-04-26 | CON-BMP-VTRA-011265 | 2019-04-26 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0511-001 | MATERIAL REQUISITION FOR LARGE COLUMNS | DOOSAN MECATEC | 018C0003 | 18C0070-02-11 | 018-C-GAD-40283-003 | VACUUM COLUMN - NOZZLE DETAIL (3) 018C0003 | A1109 | BX | 2 | 2019-04-26 | CON-BMP-VTRA-011265 | 2019-04-26 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0511-001 | MATERIAL REQUISITION FOR LARGE COLUMNS | DOOSAN MECATEC | 018C0003 | 18C0070-02-12 | 018-C-GAD-40283-004 | VACUUM COLUMN - NOZZLE DETAIL (4) 018C0003 | A1109 | BX | 2 | 2019-04-26 | CON-BMP-VTRA-011265 | 2019-04-26 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0511-001 | MATERIAL REQUISITION FOR LARGE COLUMNS | DOOSAN MECATEC | 018C0003 | 18C0070-02-13 | 018-C-GAD-40283-005 | VACUUM COLUMN - NOZZLE DETAIL (5) 018C0003 | A1109 | BX | 2 | 2019-04-26 | CON-BMP-VTRA-011265 | 2019-04-26 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0511-001 | MATERIAL REQUISITION FOR LARGE COLUMNS | DOOSAN MECATEC | 018C0003 | 18C0070-02-14 | 018-C-GAD-40283-006 | VACUUM COLUMN - NOZZLE DETAIL (6) 018C0003 | A1109 | BX | 2 | 2019-04-26 | CON-BMP-VTRA-011265 | 2019-04-26 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0511-001 | MATERIAL REQUISITION FOR LARGE COLUMNS | DOOSAN MECATEC | 018C0003 | 18C0070-02-15 | 018-C-GAD-40283-007 | VACUUM COLUMN - NOZZLE DETAIL (7) 018C0003 | A1109 | BX | 2 | 2019-04-26 | CON-BMP-VTRA-011265 | 2019-04-26 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0511-001 | MATERIAL REQUISITION FOR LARGE COLUMNS | DOOSAN MECATEC | 018C0003 | 18C0070-02-16 | 018-C-GAD-40283-008 | VACUUM COLUMN - NOZZLE DETAIL (8) 018C0003 | A1109 | BX | 2 | 2019-04-26 | CON-BMP-VTRA-011265 | 2019-04-26 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0511-001 | MATERIAL REQUISITION FOR LARGE COLUMNS | DOOSAN MECATEC | 018C0003 | 18C0070-02-17 | 018-C-GAD-40283-009 | VACUUM COLUMN - NOZZLE DETAIL (9) 018C0003 | A1109 | BX | 2 | 2019-04-26 | CON-BMP-VTRA-011265 | 2019-04-26 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0511-001 | MATERIAL REQUISITION FOR LARGE COLUMNS | DOOSAN MECATEC | 018C0003 | 18C0070-02-18 | 018-C-GAD-40283-010 | VACUUM COLUMN - NOZZLE DETAIL (10) 018C0003 | A1109 | BX | 2 | 2019-04-26 | CON-BMP-VTRA-011265 | 2019-04-26 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0511-001 | MATERIAL REQUISITION FOR LARGE COLUMNS | DOOSAN MECATEC | 018C0003 | 18C0070-02-19 | 018-C-GAD-40283-011 | VACUUM COLUMN - NOZZLE DETAIL (11) 018C0003 | A1109 | BX | 2 | 2019-04-26 | CON-BMP-VTRA-011265 | 2019-04-26 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0511-001 | MATERIAL REQUISITION FOR LARGE COLUMNS | DOOSAN MECATEC | 018C0003 | 18C0070-02-20 | 018-C-GAD-40283-012 | VACUUM COLUMN - NOZZLE DETAIL (12) 018C0003 | A1109 | BX | 2 | 2019-04-26 | CON-BMP-VTRA-011265 | 2019-04-26 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0511-001 | MATERIAL REQUISITION FOR LARGE COLUMNS | DOOSAN MECATEC | 018C0003 | 18C0070-02-21 | 018-C-GAD-40284-001 | VACUUM COLUMN INTERNAL SUPPORT DETAIL(1) 018C0003 | A1110 | AX | 2 | 2019-05-31 | CON-BMP-VTRA-011873 | 2019-05-31 | FOR BAPCO REVIEW | 2019-06-14 | 2019-06-18 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000969 | CLASS 2
076551C-000R-MR-0511-001 | MATERIAL REQUISITION FOR LARGE COLUMNS | DOOSAN MECATEC | 018C0003 | 18C0070-02-30 | 018-C-GAD-40284-010 | VACUUM COLUMN INTERNAL SUPPORTDETAIL(10) 018C0003 | A1110 | AX | 2 | 2019-05-31 | CON-BMP-VTRA-011891 | 2019-05-31 | FOR BAPCO REVIEW | 2019-06-17 | 2019-06-18 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000971 | CLASS 2
076551C-000R-MR-0511-001 | MATERIAL REQUISITION FOR LARGE COLUMNS | DOOSAN MECATEC | 018C0003 | 18C0070-02-31 | 018-C-PLD-40004-001 | VACUUM COLUMN INSUL.&FIREPROOFCLIP DETAIL(1) 018C0003 | A1105 | AX | 2 | 2019-05-27 | CON-BMP-VTRA-011815 | 2019-05-27 | FOR BAPCO REVIEW | 2019-06-11 | 2019-06-16 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000942 | CLASS 2
076551C-000R-MR-0511-001 | MATERIAL REQUISITION FOR LARGE COLUMNS | DOOSAN MECATEC | 018C0003 | 18C0070-02-32 | 018-C-PLD-40007-002 | VACUUM COLUMN INSUL.&FIREPROOFCLIP DETAIL(2) 018C0003 | A1105 | AX | 2 | 2019-05-27 | CON-BMP-VTRA-011815 | 2019-05-27 | FOR BAPCO REVIEW | 2019-06-11 | 2019-06-16 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000942 | CLASS 2
076551C-000R-MR-0511-001 | MATERIAL REQUISITION FOR LARGE COLUMNS | DOOSAN MECATEC | 018C0003 | 18C0070-02-34 | 018-C-DLB-40023-001 | VACUUM COLUMN TEMPLATE DETAIL 018C0003 | A2010 | BX | 2 | 2019-04-26 | CON-BMP-VTRA-011264 | 2019-04-26 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0511-001 | MATERIAL REQUISITION FOR LARGE COLUMNS | DOOSAN MECATEC | 018C0003 | 18C0070-03-10 | 018-C-GAD-40290-001 | TRAIN 1 HP AMINE ABSORBER & WASH COLUMN INTERNAL SUPPORT DETAIL(1) 018C0003 | A1110 | AX | 2 | 2019-05-07 | CON-BMP-VTRA-011459 | 2019-05-07 | FOR BAPCO REVIEW | 2019-05-22 | 2019-05-26 | 3-REVIEWED WITH COMMENTS BMP-ROC-VTRE-000791 | CLASS 2
076551C-000R-MR-0511-001 | MATERIAL REQUISITION FOR LARGE COLUMNS | DOOSAN MECATEC | 018C0003 | 18C0070-CAL-02 | 018-C-CAL-40056-001 | VACUUM COLUMN STRENGTH CALCULATION FOR 018C0003 | A1003 | BX | 2 | 2019-05-02 | CON-BMP-VTRA-011341 | 2019-05-02 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0511-001 | MATERIAL REQUISITION FOR LARGE COLUMNS | DOOSAN MECATEC | 018C0003 | 18C0070-FQCP-02 | 018-C-PQP-40045-001 | FABRICATION AND QUALITY CONTROL PLAN FOR 018C0003 | B1002 | BX | 2 | 2019-05-31 | CON-BMP-VTRA-011884 | 2019-05-31 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0511-001 | MATERIAL REQUISITION FOR LARGE COLUMNS | DOOSAN MECATEC | 018C0003 | 18C0070-WPS-02 | 018-C-MCD-40071-001 | WELDING BOOK (WPS/PQR) FOR 018C0003 | B1304 | AXX | 2 | 2019-04-16 | CON-BMP-VTRA-011191 | 2019-04-16 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0511-001 | MATERIAL REQUISITION FOR LARGE COLUMNS | DOOSAN MECATEC | 018C1003 | 18C0070-03-01 | 018-C-GAD-40288-001 | TRAIN 1 HP AMINE ABSORBER & WASH COLUMN GENERAL ASSEMBLY (1) 018C1003 | A1103 | BX | 2 | 2019-05-29 | CON-BMP-VTRA-011825 | 2019-05-29 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0511-001 | MATERIAL REQUISITION FOR LARGE COLUMNS | DOOSAN MECATEC | 018C1003 | 18C0070-03-02 | 018-C-GAD-40288-002 | TRAIN 1 HP AMINE ABSORBER & WASH COLUMN GENERAL ASSEMBLY (2) 018C1003 | A1103 | BX | 2 | 2019-05-29 | CON-BMP-VTRA-011825 | 2019-05-29 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0511-001 | MATERIAL REQUISITION FOR LARGE COLUMNS | DOOSAN MECATEC | 018C1003 | 18C0070-03-03 | 018-C-GAD-40296-001 | TRAIN 1 HP AMINE ABSORBER & WASH COLUMN BODY DETAIL 018C1003 | A1109 | BX | 2 | 2019-05-03 | CON-BMP-VTRA-011386 | 2019-05-03 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0511-001 | MATERIAL REQUISITION FOR LARGE COLUMNS | DOOSAN MECATEC | 018C1003 | 18C0070-03-04 | 018-C-GAD-40297-001 | VATRAIN 1 HP AMINE ABSORBER & WASH COLUMN - MANHOLE DETAIL 018C1003 | A1109 | BX | 2 | 2019-05-03 | CON-BMP-VTRA-011386 | 2019-05-03 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0511-001 | MATERIAL REQUISITION FOR LARGE COLUMNS | DOOSAN MECATEC | 018C1003 | 18C0070-03-05 | 018-C-GAD-40289-001 | TRAIN 1 HP AMINE ABSORBER & WASH COLUMN - NOZZLE DETAIL (1) 018C1003 | A1109 | BX | 2 | 2019-05-03 | CON-BMP-VTRA-011386 | 2019-05-03 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0511-001 | MATERIAL REQUISITION FOR LARGE COLUMNS | DOOSAN MECATEC | 018C1003 | 18C0070-03-06 | 018-C-GAD-40289-002 | TRAIN 1 HP AMINE ABSORBER & WASH COLUMN - NOZZLE DETAIL (2) 018C1003 | A1109 | BX | 2 | 2019-05-03 | CON-BMP-VTRA-011386 | 2019-05-03 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0511-001 | MATERIAL REQUISITION FOR LARGE COLUMNS | DOOSAN MECATEC | 018C1003 | 18C0070-03-07 | 018-C-GAD-40289-003 | TRAIN 1 HP AMINE ABSORBER & WASH COLUMN - NOZZLE DETAIL (3) 018C1003 | A1109 | BX | 2 | 2019-05-03 | CON-BMP-VTRA-011386 | 2019-05-03 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0511-001 | MATERIAL REQUISITION FOR LARGE COLUMNS | DOOSAN MECATEC | 018C1003 | 18C0070-03-08 | 018-C-GAD-40289-004 | TRAIN 1 HP AMINE ABSORBER & WASH COLUMN - NOZZLE DETAIL (4) 018C1003 | A1109 | BX | 2 | 2019-05-03 | CON-BMP-VTRA-011386 | 2019-05-03 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0511-001 | MATERIAL REQUISITION FOR LARGE COLUMNS | DOOSAN MECATEC | 018C1003 | 18C0070-03-09 | 018-C-GAD-40289-005 | TRAIN 1 HP AMINE ABSORBER & WASH COLUMN - NOZZLE DETAIL (5) 018C1003 | A1109 | BX | 2 | 2019-05-03 | CON-BMP-VTRA-011386 | 2019-05-03 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0511-001 | MATERIAL REQUISITION FOR LARGE COLUMNS | DOOSAN MECATEC | 018C1003 | 18C0070-03-11 | 018-C-GAD-40290-002 | TRAIN 1 HP AMINE ABSORBER & WASH COLUMN INTERNAL SUPPORT DETAIL(2)018C1003 | A1110 | AX | 2 | 2019-05-07 | CON-BMP-VTRA-011459 | 2019-05-07 | FOR BAPCO REVIEW | 2019-05-22 | 2019-05-26 | 3-REVIEWED WITH COMMENTS BMP-ROC-VTRE-000791 | CLASS 2
076551C-000R-MR-0511-001 | MATERIAL REQUISITION FOR LARGE COLUMNS | DOOSAN MECATEC | 018C1003 | 18C0070-03-12 | 018-C-GAD-40290-003 | 018C1003 TRAIN 1 HP AMINE ABSORBER & WASH COLUMN INTERNAL SUPPORT DETAIL(3) | A1110 | AX | 2 | 2019-05-07 | CON-BMP-VTRA-011459 | 2019-05-07 | FOR BAPCO REVIEW | 2019-05-22 | 2019-05-26 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000791 | CLASS 2
076551C-000R-MR-0511-001 | MATERIAL REQUISITION FOR LARGE COLUMNS | DOOSAN MECATEC | 018C1003 | 18C0070-03-13 | 018-C-GAD-40290-004 | TRAIN 1 HP AMINE ABSORBER & WASH COLUMN INTERNAL SUPPORT DETAIL(4) 018C1003 | A1110 | AX | 2 | 2019-05-07 | CON-BMP-VTRA-011459 | 2019-05-07 | FOR BAPCO REVIEW | 2019-05-22 | 2019-05-26 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000791 | CLASS 2
076551C-000R-MR-0511-001 | MATERIAL REQUISITION FOR LARGE COLUMNS | DOOSAN MECATEC | 018C1003 | 18C0070-03-14 | 018-C-PLD-40007-001 | TRAIN 1 HP AMINE ABSORBER & WASH COLUMN INSUL.&FIREPROOF CLIP DETAIL(1) 018C1003 | A1105 | AX | 2 | 2019-05-27 | CON-BMP-VTRA-011815 | 2019-05-27 | FOR BAPCO REVIEW | 2019-06-11 | 2019-06-16 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000942 | CLASS 2
076551C-000R-MR-0511-001 | MATERIAL REQUISITION FOR LARGE COLUMNS | DOOSAN MECATEC | 018C1003 | 18C0070-03-17 | 018-C-DLB-40025-001 | TRAIN 1 HP AMINE ABSORBER & WASH COLUMN TEMPLATE DETAIL 018C1003 | A2010 | BX | 2 | 2019-05-03 | CON-BMP-VTRA-011382 | 2019-05-03 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0511-001 | MATERIAL REQUISITION FOR LARGE COLUMNS | DOOSAN MECATEC | 018C1003 | 18C0070-CAL-03 | 018-C-CAL-40057-001 | STRENGTH CALCULATION FOR 018C1003 | A1003 | BX | 2 | 2019-05-03 | CON-BMP-VTRA-011381 | 2019-05-03 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0511-001 | MATERIAL REQUISITION FOR LARGE COLUMNS | DOOSAN MECATEC | 018C1003 | 18C0070-FQCP-03 | 018-C-PQP-40046-001 | FABRICATION AND QUALITY CONTROL PLAN FOR 018C1003 | B1002 | BX | 2 | 2019-05-31 | CON-BMP-VTRA-011884 | 2019-05-31 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0511-001 | MATERIAL REQUISITION FOR LARGE COLUMNS | DOOSAN MECATEC | 018C1003 | 18C0070-WPS-03 | 018-C-MCD-40072-001 | WELDING BOOK (WPS/PQR) FOR 018C1003 | B1304 | AXX | 2 | 2019-04-16 | CON-BMP-VTRA-011191 | 2019-04-16 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0511-001 | MATERIAL REQUISITION FOR LARGE COLUMNS | DOOSAN MECATEC | 018C2003 | 18C0070-04-01 | 018-C-GAD-40291-001 | TRAIN 2 HP AMINE ABSORBER & WASH COLUMN GENERAL ASSEMBLY (1) 018C2003 | A1103 | BX | 2 | 2019-05-29 | CON-BMP-VTRA-011825 | 2019-05-29 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0511-001 | MATERIAL REQUISITION FOR LARGE COLUMNS | DOOSAN MECATEC | 018C2003 | 18C0070-04-02 | 018-C-GAD-40291-002 | TRAIN 2 HP AMINE ABSORBER & WASH COLUMN GENERAL ASSEMBLY (2) 018C2003 | A1103 | BX | 2 | 2019-05-29 | CON-BMP-VTRA-011825 | 2019-05-29 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0511-001 | MATERIAL REQUISITION FOR LARGE COLUMNS | DOOSAN MECATEC | 018C2003 | 18C0070-04-03 | 018-C-GAD-40302-001 | TRAIN 2 HP AMINE ABSORBER & WASH COLUMN BODY DETAIL 018C2003 | A1109 | BX | 2 | 2019-05-03 | CON-BMP-VTRA-011386 | 2019-05-03 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0511-001 | MATERIAL REQUISITION FOR LARGE COLUMNS | DOOSAN MECATEC | 018C2003 | 18C0070-04-04 | 018-C-GAD-40303-001 | TRAIN 2 HP AMINE ABSORBER & WASH COLUMN - MANHOLE DETAIL 018C2003 | A1109 | BX | 2 | 2019-05-03 | CON-BMP-VTRA-011386 | 2019-05-03 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0511-001 | MATERIAL REQUISITION FOR LARGE COLUMNS | DOOSAN MECATEC | 018C2003 | 18C0070-04-05 | 018-C-GAD-40292-001 | TRAIN 2 HP AMINE ABSORBER & WASH COLUMN - NOZZLE DETAIL (1) 018C2003 | A1109 | BX | 2 | 2019-05-03 | CON-BMP-VTRA-011386 | 2019-05-03 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0511-001 | MATERIAL REQUISITION FOR LARGE COLUMNS | DOOSAN MECATEC | 018C2003 | 18C0070-04-06 | 018-C-GAD-40292-002 | TRAIN 2 HP AMINE ABSORBER & WASH COLUMN - NOZZLE DETAIL (2) 018C2003 | A1109 | BX | 2 | 2019-05-03 | CON-BMP-VTRA-011386 | 2019-05-03 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0511-001 | MATERIAL REQUISITION FOR LARGE COLUMNS | DOOSAN MECATEC | 018C2003 | 18C0070-04-07 | 018-C-GAD-40292-003 | TRAIN 2 HP AMINE ABSORBER & WASH COLUMN -NOZZLE DETAIL (3) 018C2003 | A1109 | BX | 2 | 2019-05-03 | CON-BMP-VTRA-011386 | 2019-05-03 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0511-001 | MATERIAL REQUISITION FOR LARGE COLUMNS | DOOSAN MECATEC | 018C2003 | 18C0070-04-08 | 018-C-GAD-40292-004 | TRAIN 2 HP AMINE ABSORBER & WASH COLUMN - NOZZLE DETAIL (4) 018C2003 | A1109 | BX | 2 | 2019-05-03 | CON-BMP-VTRA-011386 | 2019-05-03 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0511-001 | MATERIAL REQUISITION FOR LARGE COLUMNS | DOOSAN MECATEC | 018C2003 | 18C0070-04-09 | 018-C-GAD-40292-005 | TRAIN 2 HP AMINE ABSORBER & WASH COLUMN - NOZZLE DETAIL (5) 018C2003 | A1109 | BX | 2 | 2019-05-03 | CON-BMP-VTRA-011386 | 2019-05-03 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0511-001 | MATERIAL REQUISITION FOR LARGE COLUMNS | DOOSAN MECATEC | 018C2003 | 18C0070-04-10 | 018-C-GAD-40293-001 | TRAIN 2 HP AMINE ABSORBER & WASH COLUMN INTERNAL SUPPORT DETAIL(1) 018C2003 | A1110 | AX | 2 | 2019-05-10 | CON-BMP-VTRA-011515 | 2019-05-10 | FOR BAPCO REVIEW | 2019-05-24 | 2019-05-27 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000807 | CLASS 2
076551C-000R-MR-0511-001 | MATERIAL REQUISITION FOR LARGE COLUMNS | DOOSAN MECATEC | 018C2003 | 18C0070-04-11 | 018-C-GAD-40293-002 | TRAIN 2 HP AMINE ABSORBER & WASH COLUMN INTERNAL SUPPORT DETAIL(2) 018C2003 | A1110 | AX | 2 | 2019-05-10 | CON-BMP-VTRA-011515 | 2019-05-10 | FOR BAPCO REVIEW | 2019-05-24 | 2019-05-27 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000807 | CLASS 2
076551C-000R-MR-0511-001 | MATERIAL REQUISITION FOR LARGE COLUMNS | DOOSAN MECATEC | 018C2003 | 18C0070-04-12 | 018-C-GAD-40293-003 | TRAIN 2 HP AMINE ABSORBER & WASH COLUMN INTERNAL SUPPORT DETAIL(3) 018C2003 | A1110 | AX | 2 | 2019-05-10 | CON-BMP-VTRA-011515 | 2019-05-10 | FOR BAPCO REVIEW | 2019-05-24 | 2019-05-27 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000807 | CLASS 2
076551C-000R-MR-0511-001 | MATERIAL REQUISITION FOR LARGE COLUMNS | DOOSAN MECATEC | 018C2003 | 18C0070-04-13 | 018-C-GAD-40293-004 | TRAIN 2 HP AMINE ABSORBER & WASH COLUMN INTERNAL SUPPORT DETAIL(4) 018C2003 | A1110 | AX | 2 | 2019-05-10 | CON-BMP-VTRA-011515 | 2019-05-10 | FOR BAPCO REVIEW | 2019-05-24 | 2019-05-27 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000807 | CLASS 2
076551C-000R-MR-0511-001 | MATERIAL REQUISITION FOR LARGE COLUMNS | DOOSAN MECATEC | 018C2003 | 18C0070-04-14 | 018-C-PLD-40010-001 | TRAIN 2HP AMINE ABSORBER E WASH COLUMN INSUL E FIREPROOF CLIP DETAIL(1) 018C2003 | A1105 | AX | 2 | 2019-07-10 | CON-BMP-VTRA-012797 | 2019-07-10 | FOR BAPCO REVIEW | 2019-07-25 |  |  | CLASS 2
076551C-000R-MR-0511-001 | MATERIAL REQUISITION FOR LARGE COLUMNS | DOOSAN MECATEC | 018C2003 | 18C0070-04-17 | 018-C-DLB-40027-001 | TRAIN 2 HP AMINE ABSORBER & WASH COLUMN TEMPLATE DETAIL 018C2003 | A2010 | BX | 2 | 2019-05-03 | CON-BMP-VTRA-011382 | 2019-05-03 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0511-001 | MATERIAL REQUISITION FOR LARGE COLUMNS | DOOSAN MECATEC | 018C2003 | 18C0070-CAL-04 | 018-C-CAL-40058-001 | STRENGTH CALCULATION FOR 018C2003 | A1003 | BX | 2 | 2019-05-03 | CON-BMP-VTRA-011381 | 2019-05-03 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0511-001 | MATERIAL REQUISITION FOR LARGE COLUMNS | DOOSAN MECATEC | 018C2003 | 18C0070-FQCP-04 | 018-C-PQP-40047-001 | FABRICATION AND QUALITY CONTROL PLAN FOR 018C2003 | B1002 | BX | 2 | 2019-05-31 | CON-BMP-VTRA-011875 | 2019-05-31 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0511-001 | MATERIAL REQUISITION FOR LARGE COLUMNS | DOOSAN MECATEC | 018C2003 | 18C0070-WPS-04 | 018-C-MCD-40073-001 | WELDING BOOK (WPS/PQR) FOR 018C2003 | B1304 | AXX | 2 | 2019-04-16 | CON-BMP-VTRA-011191 | 2019-04-16 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0511-002 | MATERIAL REQUISITION FOR COLUMNS | GS GLOBAL CORP_MR-0511 | 018C0002 | RACO053-COM-004 | 000-C-MCD-40009-001 | WPS & PQR WITH WELD MAP ALL ITEMS | B1304 | 0X | V | 2019-03-18 | CON-BMP-VTRA-010729 | 2019-03-18 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0511-002 | MATERIAL REQUISITION FOR COLUMNS | GS GLOBAL CORP_MR-0511 | 018C0002 | RBCO053-01-001 | 018-C-CAL-40059-001 | STRENGTH CALCULATION FOR 018C0002 | A1003 | BX | 2 | 2019-05-21 | CON-BMP-VTRA-011687 | 2019-05-21 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0511-002 | MATERIAL REQUISITION FOR COLUMNS | GS GLOBAL CORP_MR-0511 | 018C0002 | RBCO053-01-A01,A02 | 018-C-GAD-40308-001 | DIESEL STRIPPER - GENERAL ASSEMBLY 018C0002 | A1103 | BX | 2 | 2019-05-21 | CON-BMP-VTRA-011689 | 2019-05-21 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0511-002 | MATERIAL REQUISITION FOR COLUMNS | GS GLOBAL CORP_MR-0511 | 018C0002 | RBCO053-01-B011 | 018-C-GAD-40309-001 | DIESEL STRIPPER - BODY DETAIL 018C0002 | A1109 | BX | 2 | 2019-05-21 | CON-BMP-VTRA-011685 | 2019-05-21 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0511-002 | MATERIAL REQUISITION FOR COLUMNS | GS GLOBAL CORP_MR-0511 | 018C0002 | RBCO053-01-D01 | 018-C-GAD-40310-001 | DIESEL STRIPPER DETAIL OF MANWAY 018C0002 | A1109 | BX | 2 | 2019-05-21 | CON-BMP-VTRA-011685 | 2019-05-21 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0511-002 | MATERIAL REQUISITION FOR COLUMNS | GS GLOBAL CORP_MR-0511 | 018C0002 | RBCO053-01-E01 | 018-C-GAD-40311-001 | DIESEL STRIPPER DETAIL OF NOZZLE (1 TO 3) 018C0002 | A1109 | BX | 2 | 2019-05-21 | CON-BMP-VTRA-011685 | 2019-05-21 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0511-002 | MATERIAL REQUISITION FOR COLUMNS | GS GLOBAL CORP_MR-0511 | 018C0002 | RBCO053-01-G01-G02 | 018-C-GAD-40312-001 | DIESEL STRIPPER DETAIL OF INTERNAL SUPPORT 1-2 018C0002 | A1110 | BX | 2 | 2019-05-21 | CON-BMP-VTRA-011690 | 2019-05-21 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0511-002 | MATERIAL REQUISITION FOR COLUMNS | GS GLOBAL CORP_MR-0511 | 018C0002 | RBCO053-01-H01 | 018-C-PLD-40015-001 | DIESEL STRIPPER DETAIL OF INS. & FIREPROOFING SUPPORT CLIP 018C0002 | A1105 | BX | 2 | 2019-05-27 | CON-BMP-VTRA-011814 | 2019-05-27 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0511-002 | MATERIAL REQUISITION FOR COLUMNS | GS GLOBAL CORP_MR-0511 | 018C0002 | RBCO053-01-H02 | 018-C-GAD-40327-001 | DIESEL STRIPPER DETAIL OF TOP DAVIT 018C0002 | A1109 | AX | 2 | 2019-05-21 | CON-BMP-VTRA-011682 | 2019-05-21 | FOR BAPCO REVIEW | 2019-06-05 | 2019-06-06 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000889 | CLASS 2
076551C-000R-MR-0511-002 | MATERIAL REQUISITION FOR COLUMNS | GS GLOBAL CORP_MR-0511 | 018C0002 | RBCO053-01-I01 | 018-C-DLB-40029-001 | DIESEL STRIEPPER - TEMPLATE & GAUGE PLATE DETAIL 018C0002 | A2010 | BX | 2 | 2019-05-21 | CON-BMP-VTRA-011692 | 2019-05-21 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0511-002 | MATERIAL REQUISITION FOR COLUMNS | GS GLOBAL CORP_MR-0511 | 018C0002 | RBCO053-01-J01-J02 | 018-C-PLD-40016-001 | DIESEL STRIPPER PIPE SUPPORT CLIP DETAIL 018C0002 | A1105 | AX | 2 | 2019-07-08 | CON-BMP-VTRA-012740 | 2019-07-08 | FOR BAPCO REVIEW | 2019-07-23 |  |  | CLASS 2
076551C-000R-MR-0511-002 | MATERIAL REQUISITION FOR COLUMNS | GS GLOBAL CORP_MR-0511 | 018C0002 | RBCO053-01-L01 | 018-C-DLB-40030-001 | DIESEL STRIPPER - NAMEPLATE DETAIL 018C0002 | A1112 | BXX | 2 | 2019-05-31 | CON-BMP-VTRA-011894 | 2019-05-31 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0511-002 | MATERIAL REQUISITION FOR COLUMNS | GS GLOBAL CORP_MR-0511 | 018C0002 | RBCO053-01-N01 | 018-C-GAD-40324-001 | DIESEL STRIPPER DETAIL OF PACKING SKETCH 018C0002 | A1109 | AX | 2 | 2019-03-08 | CON-BMP-VTRA-010636 | 2019-03-08 | FOR BAPCO REVIEW | 2019-03-25 | 2019-03-26 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000384 | CLASS 2
076551C-000R-MR-0511-002 | MATERIAL REQUISITION FOR COLUMNS | GS GLOBAL CORP_MR-0511 | 018C0002 | RBCO053-COM-001 | 000-C-INX-40006-001 | LIST OF VENDOR'S DOCUMENTS AND DWGS ALL ITEMS | A0001 | CX | 4 | 2019-05-08 | CON-BMP-VTRA-011473 | 2019-05-08 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0511-002 | MATERIAL REQUISITION FOR COLUMNS | GS GLOBAL CORP_MR-0511 | 018C0002 | RBCO053-COM-003 | 000-C-PRO-40028-001 | PWHT PROCEDURE FOR COLUMNS ALL ITEMS | B1201 | BX | 2 | 2019-04-29 | CON-BMP-VTRA-011304 | 2019-04-29 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0511-002 | MATERIAL REQUISITION FOR COLUMNS | GS GLOBAL CORP_MR-0511 | 018C0002 | RBCO053-COM-005 | 000-C-MCD-40010-001 | QUALIFIED WELDER LIST ALL ITEMS | B1304 | 0X | 3 | 2019-04-09 | CON-BMP-VTRA-011062 | 2019-04-09 | FOR BAPCO REVIEW | 2019-04-23 | 2019-04-21 | 1-APPROVED BMP-ROC-VTRE-000542 | CLASS 2
076551C-000R-MR-0511-002 | MATERIAL REQUISITION FOR COLUMNS | GS GLOBAL CORP_MR-0511 | 018C0002 | RBCO053-COM-006 | 000-C-MCD-40011-001 | WELDING CONSUMABLE CONTROL PROCEDURE FOR COLUMNS ALL ITEMS | B1304 | 0X | 2 | 2019-05-02 | CON-BMP-VTRA-011359 | 2019-05-02 | FOR BAPCO REVIEW | 2019-05-17 | 2019-05-13 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000667 | CLASS 2
076551C-000R-MR-0511-002 | MATERIAL REQUISITION FOR COLUMNS | GS GLOBAL CORP_MR-0511 | 018C0002 | RBCO053-COM-007 | 000-C-MCD-40012-001 | WELDING REPAIR TEST PROCEDURE FOR COLUMNS ALL ITEMS | B1304 | CX | 3 | 2019-05-02 | CON-BMP-VTRA-011357 | 2019-05-02 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0511-002 | MATERIAL REQUISITION FOR COLUMNS | GS GLOBAL CORP_MR-0511 | 018C0002 | RBCO053-COM-009 | 000-C-TSP-40003-001 | SURFACE PREPARATION & PAINTING (COATING) PROCEDURE FOR COLUMNS ALL ITEMS | A0106 | 0XX | 2 | 2019-07-05 | CON-BMP-VTRA-012682 | 2019-07-05 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0511-002 | MATERIAL REQUISITION FOR COLUMNS | GS GLOBAL CORP_MR-0511 | 018C0002 | RBCO053-COM-010 | 000-C-PQP-40005-001 | FABRICATION AND QUALITY CONTROL PLAN FOR COLUMNS ALL ITEMS | B1002 | 0X | V | 2019-03-20 | CON-BMP-VTRA-010803 | 2019-03-20 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0511-002 | MATERIAL REQUISITION FOR COLUMNS | GS GLOBAL CORP_MR-0511 | 018C0002 | RBCO053-COM-011 | 000-C-PLN-40005-001 | JOB ASSURANCE QUALITY PLAN ALL ITEMS | B1001 | AX | 2 | 2019-01-18 | CON-BMP-VTRA-010251 | 2019-01-18 | FOR BAPCO REVIEW | 2019-02-04 | 2019-01-27 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000132 | CLASS 2
076551C-000R-MR-0511-002 | MATERIAL REQUISITION FOR COLUMNS | GS GLOBAL CORP_MR-0511 | 018C0002 | RBCO053-COM-012 | 000-C-PRO-40030-001 | NDE PROCEDURE FOR COLUMNS ALL ITEMS | B1202 | BX | 2 | 2019-05-27 | CON-BMP-VTRA-011812 | 2019-05-27 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0511-002 | MATERIAL REQUISITION FOR COLUMNS | GS GLOBAL CORP_MR-0511 | 018C0002 | RBCO053-COM-013 | 000-C-PRO-40031-001 | HARDNESS TEST PROCEDURE FOR COLUMNS ALL ITEMS | B1103 | AX | 2 | 2019-04-09 | CON-BMP-VTRA-011058 | 2019-04-09 | FOR BAPCO REVIEW | 2019-04-23 | 2019-04-21 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000544 | CLASS 2
076551C-000R-MR-0511-002 | MATERIAL REQUISITION FOR COLUMNS | GS GLOBAL CORP_MR-0511 | 018C0002 | RBCO053-COM-014 | 000-C-PRO-40032-001 | PMI PROCEDURE FOR COLUMNS ALL ITEMS | B1103 | AXX | 2 | 2019-05-07 | CON-BMP-VTRA-011461 | 2019-05-07 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0511-002 | MATERIAL REQUISITION FOR COLUMNS | GS GLOBAL CORP_MR-0511 | 018C0002 | RBCO053-COM-018 | 000-C-TSP-40004-001 | MATERIAL SPECIFICATION FOR MAIN SUB-ORDERS FOR COLUMNS ALL ITEMS | B1203 | BX | 2 | 2019-05-23 | CON-BMP-VTRA-011770 | 2019-05-23 | FOR BAPCO REVIEW | 2019-06-07 | 2019-06-16 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000934 | CLASS 2
076551C-000R-MR-0511-002 | MATERIAL REQUISITION FOR COLUMNS | GS GLOBAL CORP_MR-0511 | 018C0002 | RBCO053-COM-019 | 000-C-PRO-40062-001 | IGC TEST PROCEDURE FORCOLUMNS 018C0002/4/5 021C0002/3/4 021V0005 023C0001 | B1103 | AX | 2 | 2019-05-23 | CON-BMP-VTRA-011767 | 2019-05-23 | FOR BAPCO REVIEW | 2019-06-07 | 2019-06-05 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000882 | CLASS 2
076551C-000R-MR-0511-002 | MATERIAL REQUISITION FOR COLUMNS | GS GLOBAL CORP_MR-0511 | 018C0002 | RBCO053-COM-021 | 000-C-PRO-40034-001 | FERRITE TEST PROCEDURE FOR COLUMNS ALL ITEMS | B1103 | AX | 2 | 2019-04-09 | CON-BMP-VTRA-011058 | 2019-04-09 | FOR BAPCO REVIEW | 2019-04-23 | 2019-04-21 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000544 | CLASS 2
076551C-000R-MR-0511-002 | MATERIAL REQUISITION FOR COLUMNS | GS GLOBAL CORP_MR-0511 | 018C0002 | RBCO053-COM-022 | 000-C-SCH-40004-001 | ENGINEERING PROCUREMENT MANUFACTURING & TEST SCHEDULE ALL ITEMS | C1001 | AX | 2 | 2019-03-05 | CON-BMP-VTRA-010598 | 2019-03-05 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-0511-002 | MATERIAL REQUISITION FOR COLUMNS | GS GLOBAL CORP_MR-0511 | 018C0002 | RBCO053-COM-023 | 000-C-MRS-40005-001 | MONTHLY PROGRESS REPORT FOR COLUMN ALL ITEMS | C1002 | FX | 2 | 2019-07-08 | CON-BMP-VTRA-012739 | 2019-07-08 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-0511-002 | MATERIAL REQUISITION FOR COLUMNS | GS GLOBAL CORP_MR-0511 | 018C0002 | RBCO053-COM-024 | 000-C-INV-40004-001 | UNPRICED COPY OF MAIN SUBORDERS ALL ITEMS | C1005 | AXX | 2 | 2019-04-09 | CON-BMP-VTRA-011059 | 2019-04-09 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0511-002 | MATERIAL REQUISITION FOR COLUMNS | GS GLOBAL CORP_MR-0511 | 018C0002 | RBCO053-COM-033 | 018-C-PQP-40048-001 | FABRICATION AND QUALITY CONTROL PLAN 018C0002 | B1002 | BX | 2 | 2019-06-10 | CON-BMP-VTRA-012105 | 2019-06-10 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0511-002 | MATERIAL REQUISITION FOR COLUMNS | GS GLOBAL CORP_MR-0511 | 018C0002 | RBCO053-COM-041 | 018-C-MCD-40074-001 | WPS & PQR WITH WELD MAP FOR COLUMNS 018C0002 | B1304 | 0X | 2 | 2019-05-02 | CON-BMP-VTRA-011359 | 2019-05-02 | FOR BAPCO REVIEW | 2019-05-17 | 2019-05-13 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000667 | CLASS 2
076551C-000R-MR-0511-002 | MATERIAL REQUISITION FOR COLUMNS | GS GLOBAL CORP_MR-0511 | 018C0004 | RBCO053-02-001 | 018-C-CAL-40060-001 | STRENGTH CALCULATION FOR 018C0004 | A1003 | BX | 2 | 2019-05-24 | CON-BMP-VTRA-011774 | 2019-05-24 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0511-002 | MATERIAL REQUISITION FOR COLUMNS | GS GLOBAL CORP_MR-0511 | 018C0004 | RBCO053-02-A01,02 | 018-C-GAD-40313-001 | VACUUM GAS SCRUBBER - GENERAL ASSEMBLY 018C0004 | A1103 | BX | 2 | 2019-06-26 | CON-BMP-VTRA-012470 | 2019-06-26 | FOR BAPCO REVIEW | 2019-07-10 |  |  | CLASS 2
076551C-000R-MR-0511-002 | MATERIAL REQUISITION FOR COLUMNS | GS GLOBAL CORP_MR-0511 | 018C0004 | RBCO053-02-B01 | 018-C-GAD-40314-001 | VACUUM GAS SCRUBBER - BODY DETAIL 018C0004 | A1109 | BX | 2 | 2019-05-24 | CON-BMP-VTRA-011778 | 2019-05-24 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0511-002 | MATERIAL REQUISITION FOR COLUMNS | GS GLOBAL CORP_MR-0511 | 018C0004 | RBCO053-02-D01 | 018-C-GAD-40315-001 | VACUUM GAS SCRUBBER DETAIL OF MANWAY 018C0004 | A1109 | BX | 2 | 2019-05-24 | CON-BMP-VTRA-011778 | 2019-05-24 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0511-002 | MATERIAL REQUISITION FOR COLUMNS | GS GLOBAL CORP_MR-0511 | 018C0004 | RBCO053-02-E01 | 018-C-GAD-40316-001 | VACUUM GAS SCRUBBER DETAIL OF NOZZLE (1 TO 3) 018C0004 | A1109 | BX | 2 | 2019-05-24 | CON-BMP-VTRA-011778 | 2019-05-24 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0511-002 | MATERIAL REQUISITION FOR COLUMNS | GS GLOBAL CORP_MR-0511 | 018C0004 | RBCO053-02-G01 | 018-C-GAD-40317-001 | VACUUM GAS SCRUBBER DETAIL OF INTERNAL SUPPORT 018C0004 | A1110 | BX | 2 | 2019-05-24 | CON-BMP-VTRA-011776 | 2019-05-24 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0511-002 | MATERIAL REQUISITION FOR COLUMNS | GS GLOBAL CORP_MR-0511 | 018C0004 | RBCO053-02-G03-04 | 018-C-GAD-40318-001 | VACUUM GAS SCRUBBER DETAIL OF DEMISTER 018C0004 | A1110 | AX | 2 | 2019-05-24 | CON-BMP-VTRA-011773 | 2019-05-24 | FOR BAPCO REVIEW | 2019-06-07 | 2019-06-16 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000929 | CLASS 2
076551C-000R-MR-0511-002 | MATERIAL REQUISITION FOR COLUMNS | GS GLOBAL CORP_MR-0511 | 018C0004 | RBCO053-02-H01 | 018-C-PLD-40018-001 | VACUUM GAS SCRUBBER DETAIL OF FIREPROOFING SUPPORT CLIP 018C0004 | A1105 | BX | 2 | 2019-05-27 | CON-BMP-VTRA-011814 | 2019-05-27 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0511-002 | MATERIAL REQUISITION FOR COLUMNS | GS GLOBAL CORP_MR-0511 | 018C0004 | RBCO053-02-I01 | 018-C-DLB-40031-001 | VACUUM GAS SCRUBBER - TEMPLATE & GAUGE PLATE DETAIL 018C0004 | A2010 | BX | 2 | 2019-05-23 | CON-BMP-VTRA-011771 | 2019-05-23 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0511-002 | MATERIAL REQUISITION FOR COLUMNS | GS GLOBAL CORP_MR-0511 | 018C0004 | RBCO053-02-L01 | 018-C-DLB-40032-001 | VACUUM GAS SCRUBBER - NAMEPLATE DETAIL 018C0004 | A1112 | BX | 2 | 2019-05-24 | CON-BMP-VTRA-011777 | 2019-05-24 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0511-002 | MATERIAL REQUISITION FOR COLUMNS | GS GLOBAL CORP_MR-0511 | 018C0004 | RBCO053-02-N01 | 018-C-GAD-40325-001 | VACUUM GAS SCRUBBER DETAIL OF PACKING SKETCH 018C0004 | A1109 | AX | 2 | 2019-03-08 | CON-BMP-VTRA-010636 | 2019-03-08 | FOR BAPCO REVIEW | 2019-03-25 | 2019-03-26 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000384 | CLASS 2
076551C-000R-MR-0511-002 | MATERIAL REQUISITION FOR COLUMNS | GS GLOBAL CORP_MR-0511 | 018C0004 | RBCO053-COM-004 | 018-C-MCD-40050-001 | WPS & PQR WITH WELD MAP 018C0004 | B1304 | BX | 2 | 2019-05-21 | CON-BMP-VTRA-011684 | 2019-05-21 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0511-002 | MATERIAL REQUISITION FOR COLUMNS | GS GLOBAL CORP_MR-0511 | 018C0004 | RBCO053-COM-034 | 018-C-MCD-40051-001 | WPS & PQR WITH WELD MAP FOR COLUMNS 018C0005 | B1304 | 0X | 2 | 2019-05-02 | CON-BMP-VTRA-011359 | 2019-05-02 | FOR BAPCO REVIEW | 2019-05-17 | 2019-05-13 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000667 | CLASS 2
076551C-000R-MR-0511-002 | MATERIAL REQUISITION FOR COLUMNS | GS GLOBAL CORP_MR-0511 | 018C0004 | RBCO053-COM-040 | 018-C-PQP-40033-001 | FABRICATION AND QUALITY CONTROL PLAN 018C0004 | B1002 | BX | 2 | 2019-06-10 | CON-BMP-VTRA-012105 | 2019-06-10 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0511-002 | MATERIAL REQUISITION FOR COLUMNS | GS GLOBAL CORP_MR-0511 | 018C0005 | RBCO053-03-001 | 018-C-CAL-40061-001 | STRENGTH CALCULATION FOR 018C0005 | A1003 | BX | 2 | 2019-05-21 | CON-BMP-VTRA-011687 | 2019-05-21 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0511-002 | MATERIAL REQUISITION FOR COLUMNS | GS GLOBAL CORP_MR-0511 | 018C0005 | RBCO053-03-A01,A02 | 018-C-GAD-40319-001 | HVGO STRIPPER - GENERAL ASSEMBLY 018C0005 | A1103 | BX | 2 | 2019-05-21 | CON-BMP-VTRA-011689 | 2019-05-21 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0511-002 | MATERIAL REQUISITION FOR COLUMNS | GS GLOBAL CORP_MR-0511 | 018C0005 | RBCO053-03-B01 | 018-C-GAD-40320-001 | HVGO STRIPPER - BODY DETAIL 018C0005 | A1109 | BX | 2 | 2019-05-21 | CON-BMP-VTRA-011685 | 2019-05-21 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0511-002 | MATERIAL REQUISITION FOR COLUMNS | GS GLOBAL CORP_MR-0511 | 018C0005 | RBCO053-03-D01 | 018-C-GAD-40321-001 | HVGO STRIPPER DETAIL OF MANWAY 018C0005 | A1109 | BX | 2 | 2019-05-21 | CON-BMP-VTRA-011685 | 2019-05-21 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0511-002 | MATERIAL REQUISITION FOR COLUMNS | GS GLOBAL CORP_MR-0511 | 018C0005 | RBCO053-03-E01 | 018-C-GAD-40322-001 | HVGO STRIPPER DETAIL OF NOZZLE(1 TO 3) 018C0005 | A1109 | BX | 2 | 2019-05-21 | CON-BMP-VTRA-011685 | 2019-05-21 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0511-002 | MATERIAL REQUISITION FOR COLUMNS | GS GLOBAL CORP_MR-0511 | 018C0005 | RBCO053-03-G01 | 018-C-GAD-40323-001 | HVGO STRIPPER DETAIL OF INTERNAL SUPPORT 018C0005 | A1110 | BX | 2 | 2019-05-21 | CON-BMP-VTRA-011690 | 2019-05-21 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0511-002 | MATERIAL REQUISITION FOR COLUMNS | GS GLOBAL CORP_MR-0511 | 018C0005 | RBCO053-03-H01 | 018-C-PLD-40021-001 | HVGO STRIPPER DETAIL OF INS. & FIREPROOFING SUPPORT CLIP 018C0005 | A1105 | BX | 2 | 2019-05-27 | CON-BMP-VTRA-011814 | 2019-05-27 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0511-002 | MATERIAL REQUISITION FOR COLUMNS | GS GLOBAL CORP_MR-0511 | 018C0005 | RBCO053-03-H02 | 018-C-GAD-40331-001 | HVGO STRIPPER DETAIL OF TOP DAVIT 018C0005 | A1109 | AX | 2 | 2019-05-21 | CON-BMP-VTRA-011682 | 2019-05-21 | FOR BAPCO REVIEW | 2019-06-05 | 2019-06-06 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000889 | CLASS 2
076551C-000R-MR-0511-002 | MATERIAL REQUISITION FOR COLUMNS | GS GLOBAL CORP_MR-0511 | 018C0005 | RBCO053-03-I01 | 018-C-DLB-40033-001 | HVGO STRIPPER - TEMPLATE & GAUGE PLATE DETAIL 018C0005 | A2010 | BX | 2 | 2019-05-21 | CON-BMP-VTRA-011692 | 2019-05-21 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0511-002 | MATERIAL REQUISITION FOR COLUMNS | GS GLOBAL CORP_MR-0511 | 018C0005 | RBCO053-03-J01-J02 | 018-C-PLD-40289-001 | HVGO STRIPPER PIPE SUPPORT CLIP DETAIL 018C0005 | A1105 | AX | 2 | 2019-07-08 | CON-BMP-VTRA-012740 | 2019-07-08 | FOR BAPCO REVIEW | 2019-07-23 |  |  | CLASS 2
076551C-000R-MR-0511-002 | MATERIAL REQUISITION FOR COLUMNS | GS GLOBAL CORP_MR-0511 | 018C0005 | RBCO053-03-L01 | 018-C-DLB-40034-001 | HVGO STRIPPER - NAMEPLATE DETAIL 018C0005 | A1112 | BX | 2 | 2019-05-21 | CON-BMP-VTRA-011688 | 2019-05-21 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0511-002 | MATERIAL REQUISITION FOR COLUMNS | GS GLOBAL CORP_MR-0511 | 018C0005 | RBCO053-03-N01 | 018-C-GAD-40326-001 | HVGO STRIPPER DETAIL OF PACKING SKETCH 018C0005 | A1109 | AX | 2 | 2019-03-08 | CON-BMP-VTRA-010636 | 2019-03-08 | FOR BAPCO REVIEW | 2019-03-25 | 2019-03-26 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000384 | CLASS 2
076551C-000R-MR-0511-002 | MATERIAL REQUISITION FOR COLUMNS | GS GLOBAL CORP_MR-0511 | 018C0005 | RBCO053-COM-027 | 018-C-PQP-40034-001 | FABRICATION AND QUALITY CONTROL PLAN 018C0005 | B1002 | BX | 2 | 2019-06-10 | CON-BMP-VTRA-012105 | 2019-06-10 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0511-002 | MATERIAL REQUISITION FOR COLUMNS | GS GLOBAL CORP_MR-0511 | 021C0002 | RBCO053-05-001 | 021-C-CAL-40012-001 | STRENGTH CALCULATION FOR 021C0002 / 021V0005 | A1003 | BX | 2 | 2019-05-31 | CON-BMP-VTRA-011887 | 2019-05-31 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0511-002 | MATERIAL REQUISITION FOR COLUMNS | GS GLOBAL CORP_MR-0511 | 021C0002 | RBCO053-05-002 | 021-C-CAL-40066-001 | OFFGAS AMINE ABSORBER - GENERAL ASSEMBLY 023C0001 | A1103 | AX | 2 | 2019-05-31 | CON-BMP-VTRA-011885 | 2019-05-31 | FOR BAPCO REVIEW | 2019-06-17 | 2019-06-18 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000970 | CLASS 2
076551C-000R-MR-0511-002 | MATERIAL REQUISITION FOR COLUMNS | GS GLOBAL CORP_MR-0511 | 021C0002 | RBCO053-05-A01-02 | 021-C-GAD-40060-001 | HIGH PRESSURE ABSORBER KO DRUM - GENERAL ASSEMBLY 021C0002 / 021V0005 | A1103 | BXX | 2 | 2019-05-31 | CON-BMP-VTRA-011890 | 2019-05-31 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0511-002 | MATERIAL REQUISITION FOR COLUMNS | GS GLOBAL CORP_MR-0511 | 021C0002 | RBCO053-05-B01 | 021-C-GAD-40061-001 | HIGH PRESSURE ABSORBER KO DRUM- BODY DETAIL 021C0002 / 021V0005 | A1109 | BX | 2 | 2019-05-31 | CON-BMP-VTRA-011876 | 2019-05-31 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0511-002 | MATERIAL REQUISITION FOR COLUMNS | GS GLOBAL CORP_MR-0511 | 021C0002 | RBCO053-05-D01 | 021-C-GAD-40062-001 | HIGJ PRESSURE ABSORBER KO DRUMDETAIL OF MANWAY (1 TO 2) 021C0002 021V0005 | A1109 | BX | 2 | 2019-05-31 | CON-BMP-VTRA-011876 | 2019-05-31 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0511-002 | MATERIAL REQUISITION FOR COLUMNS | GS GLOBAL CORP_MR-0511 | 021C0002 | RBCO053-05-E01 | 021-C-GAD-40063-001 | HIGH PRESSURE ABSORBER KO DRUMDETAIL OF NOZZLE (1 TO 5) 021C0002 021V0005 | A1109 | BX | 2 | 2019-05-31 | CON-BMP-VTRA-011876 | 2019-05-31 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0511-002 | MATERIAL REQUISITION FOR COLUMNS | GS GLOBAL CORP_MR-0511 | 021C0002 | RBCO053-05-G01-G02 | 021-C-GAD-40065-001 | HIGH PRESSURE ABSORBER HIGH PRESSURE ABSORBER KO DRUM DETAIL OF INTERNAL SUPPORT 1-2 021C0002 021V0005 | A1110 | BX | 2 | 2019-05-31 | CON-BMP-VTRA-011880 | 2019-05-31 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0511-002 | MATERIAL REQUISITION FOR COLUMNS | GS GLOBAL CORP_MR-0511 | 021C0002 | RBCO053-05-G05-06 | 021-C-GAD-40066-001 | HIGH PRESSURE ABSORBER KO DRUM DETAIL OF MIST ELIMINATOR 1/2 021C0002 021V0005 | A1110 | AX | 2 | 2019-05-31 | CON-BMP-VTRA-011881 | 2019-05-31 | FOR BAPCO REVIEW | 2019-06-14 | 2019-06-17 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000996 | CLASS 2
076551C-000R-MR-0511-002 | MATERIAL REQUISITION FOR COLUMNS | GS GLOBAL CORP_MR-0511 | 021C0002 | RBCO053-05-H01 | 021-C-PLD-40004-001 | HIGH PRESSURE ABSORBER HIGH PRESSURE ABSORBER KO DRUM DETAIL OF INS. & FIREPROOFING SUPPORT CLIP 021C0002 021V0005 | A1105 | BX | 2 | 2019-07-08 | CON-BMP-VTRA-012743 | 2019-07-08 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0511-002 | MATERIAL REQUISITION FOR COLUMNS | GS GLOBAL CORP_MR-0511 | 021C0002 | RBCO053-05-H02 | 021-C-GAD-40064-001 | HIGH PRESSURE ABSORBER /HIGH PRESSURE ABSORBER KO DRUM DETAIL OF TOP DAVIT 021C0002 021V0005 | A1109 | AX | 2 | 2019-05-31 | CON-BMP-VTRA-011877 | 2019-05-31 | FOR BAPCO REVIEW | 2019-06-14 | 2019-06-18 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000976 | CLASS 2
076551C-000R-MR-0511-002 | MATERIAL REQUISITION FOR COLUMNS | GS GLOBAL CORP_MR-0511 | 021C0002 | RBCO053-05-I01 | 021-C-DLB-40005-001 | HIGH PRESSURE ABSORBER KO DRUM TEMPLATE & GAUGE PLATE DETAIL 021C0002 021V0005 | A2010 | BX | 2 | 2019-05-31 | CON-BMP-VTRA-011896 | 2019-05-31 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0511-002 | MATERIAL REQUISITION FOR COLUMNS | GS GLOBAL CORP_MR-0511 | 021C0002 | RBCO053-05-J01-J02 | 021-C-PLD-40005-001 | HIGH PRESSURE ABSORBER/HIGH PRESSURE ABSORBER KO DRUM PIPE SUPPORT CLIP DTEAIL 021C0002 021V0005 | A1105 | AX | 2 | 2019-07-08 | CON-BMP-VTRA-012741 | 2019-07-08 | FOR BAPCO REVIEW | 2019-07-23 |  |  | CLASS 2
076551C-000R-MR-0511-002 | MATERIAL REQUISITION FOR COLUMNS | GS GLOBAL CORP_MR-0511 | 021C0002 | RBCO053-05-L01 | 021-C-DLB-40006-001 | HIGH PRESSURE ABSORBER KO DRUM - NAMEPLATE DETAIL 021C0002 / 021V0005 | A1112 | BX | 2 | 2019-05-31 | CON-BMP-VTRA-011895 | 2019-05-31 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0511-002 | MATERIAL REQUISITION FOR COLUMNS | GS GLOBAL CORP_MR-0511 | 021C0002 | RBCO053-05-N01 | 021-C-GAD-40067-001 | HIGH PRESSURE ABSORBER HIGH PRESSURE ABSORBER KO DRUM DETAIL OF PACKING SKETCH 021C0002 021V0005 | A1109 | AX | 2 | 2019-03-08 | CON-BMP-VTRA-010636 | 2019-03-08 | FOR BAPCO REVIEW | 2019-03-25 | 2019-03-26 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000384 | CLASS 2
076551C-000R-MR-0511-002 | MATERIAL REQUISITION FOR COLUMNS | GS GLOBAL CORP_MR-0511 | 021C0002 | RBCO053-COM-030 | 021-C-PQP-40009-001 | FABRICATION AND QUALITY CONTROL PLAN 021C0002 021V0005 | B1002 | BX | 2 | 2019-06-10 | CON-BMP-VTRA-012106 | 2019-06-10 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0511-002 | MATERIAL REQUISITION FOR COLUMNS | GS GLOBAL CORP_MR-0511 | 021C0002 | RBCO053-COM-037 | 021-C-MCD-40009-001 | WPS & PQR WITH WELD MAP FOR COLUMNS 021C0002 021V0005 | B1304 | 0X | 2 | 2019-05-02 | CON-BMP-VTRA-011359 | 2019-05-02 | FOR BAPCO REVIEW | 2019-05-17 | 2019-05-13 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000667 | CLASS 2
076551C-000R-MR-0511-002 | MATERIAL REQUISITION FOR COLUMNS | GS GLOBAL CORP_MR-0511 | 021C0003 | RBCO053-04-001 | 021-C-CAL-40011-001 | STRENGTH CALCULATION FOR 021C0003 | A1003 | BX | 2 | 2019-05-27 | CON-BMP-VTRA-011808 | 2019-05-27 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0511-002 | MATERIAL REQUISITION FOR COLUMNS | GS GLOBAL CORP_MR-0511 | 021C0003 | RBCO053-04-A01,02 | 021-C-GAD-40052-001 | STRIPPER - GENERAL ASSEMBLY 021C0003 | A1103 | BX | 2 | 2019-05-29 | CON-BMP-VTRA-011829 | 2019-05-29 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0511-002 | MATERIAL REQUISITION FOR COLUMNS | GS GLOBAL CORP_MR-0511 | 021C0003 | RBCO053-04-B01,02 | 021-C-GAD-40053-001 | STRIPPER - BODY DETAIL 021C0003 | A1109 | BX | 2 | 2019-05-27 | CON-BMP-VTRA-011813 | 2019-05-27 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0511-002 | MATERIAL REQUISITION FOR COLUMNS | GS GLOBAL CORP_MR-0511 | 021C0003 | RBCO053-04-D01 | 021-C-GAD-40054-001 | STRIPPER DETAIL OF MANWAY (1 TO 3) 021C0003 | A1109 | BX | 2 | 2019-05-27 | CON-BMP-VTRA-011813 | 2019-05-27 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0511-002 | MATERIAL REQUISITION FOR COLUMNS | GS GLOBAL CORP_MR-0511 | 021C0003 | RBCO053-04-E01 | 021-C-GAD-40055-001 | STRIPPER DETAIL OF NOZZLE (1 TO 5) 021C0003 | A1109 | BX | 2 | 2019-05-27 | CON-BMP-VTRA-011813 | 2019-05-27 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0511-002 | MATERIAL REQUISITION FOR COLUMNS | GS GLOBAL CORP_MR-0511 | 021C0003 | RBCO053-04-G01-G05 | 021-C-GAD-40057-001 | STRIPPER DETAIL OF INTERNAL SUPPORT 1-5 021C0003 | A1110 | BX | 2 | 2019-05-27 | CON-BMP-VTRA-011809 | 2019-05-27 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0511-002 | MATERIAL REQUISITION FOR COLUMNS | GS GLOBAL CORP_MR-0511 | 021C0003 | RBCO053-04-H01 | 021-C-PLD-40001-001 | STRIPPER DETAIL OF INS AND FIREPROOFING SUPPORT CLIP 021C0003 | A1105 | BX | 2 | 2019-05-27 | CON-BMP-VTRA-011814 | 2019-05-27 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0511-002 | MATERIAL REQUISITION FOR COLUMNS | GS GLOBAL CORP_MR-0511 | 021C0003 | RBCO053-04-H02 | 021-C-GAD-40056-001 | STRIPPER DETAIL OF TOP DAVIT 021C0003 | A1109 | AX | 2 | 2019-05-27 | CON-BMP-VTRA-011807 | 2019-05-27 | FOR BAPCO REVIEW | 2019-06-11 | 2019-06-16 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000944 | CLASS 2
076551C-000R-MR-0511-002 | MATERIAL REQUISITION FOR COLUMNS | GS GLOBAL CORP_MR-0511 | 021C0003 | RBCO053-04-I01 | 021-C-DLB-40003-001 | STRIPPER - TEMPLATE & GAUGE PLATE DETAIL 021C0003 | A2010 | BX | 2 | 2019-05-27 | CON-BMP-VTRA-011810 | 2019-05-27 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0511-002 | MATERIAL REQUISITION FOR COLUMNS | GS GLOBAL CORP_MR-0511 | 021C0003 | RBCO053-04-J01-J02-J03 | 021-C-PLD-40002-001 | STRIPPER PIPE SUPPORT CLIP DETAIL 021C0003 | A1105 | AX | 2 | 2019-07-08 | CON-BMP-VTRA-012741 | 2019-07-08 | FOR BAPCO REVIEW | 2019-07-23 |  |  | CLASS 2
076551C-000R-MR-0511-002 | MATERIAL REQUISITION FOR COLUMNS | GS GLOBAL CORP_MR-0511 | 021C0003 | RBCO053-04-L01 | 021-C-DLB-40004-001 | STRIPPER - NAMEPLATE DETAIL 021C0003 | A1112 | BX | 2 | 2019-05-27 | CON-BMP-VTRA-011811 | 2019-05-27 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0511-002 | MATERIAL REQUISITION FOR COLUMNS | GS GLOBAL CORP_MR-0511 | 021C0003 | RBCO053-04-N01 | 021-C-GAD-40058-001 | STRIPPER DETAIL OF PACKING SKETCH 021C0003 | A1109 | AX | 2 | 2019-03-08 | CON-BMP-VTRA-010636 | 2019-03-08 | FOR BAPCO REVIEW | 2019-03-25 | 2019-03-26 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000384 | CLASS 2
076551C-000R-MR-0511-002 | MATERIAL REQUISITION FOR COLUMNS | GS GLOBAL CORP_MR-0511 | 021C0003 | RBCO053-COM-028 | 021-C-PQP-40007-001 | FABRICATION AND QUALITY CONTROL PLAN 021C0003 | B1002 | BX | 2 | 2019-06-10 | CON-BMP-VTRA-012106 | 2019-06-10 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0511-002 | MATERIAL REQUISITION FOR COLUMNS | GS GLOBAL CORP_MR-0511 | 021C0003 | RBCO053-COM-035 | 021-C-MCD-40007-001 | WPS & PQR WITH WELD MAP FOR COLUMNS 021C0003 | B1304 | 0X | 2 | 2019-05-02 | CON-BMP-VTRA-011359 | 2019-05-02 | FOR BAPCO REVIEW | 2019-05-17 | 2019-05-13 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000667 | CLASS 2
076551C-000R-MR-0511-002 | MATERIAL REQUISITION FOR COLUMNS | GS GLOBAL CORP_MR-0511 | 021C0004 | RBCO053-02-002 | 018-C-CAL-40269-001 | STRENGTH CALCULATION FOR DEMISTER 018C0004 | A1003 | AX | 2 | 2019-05-23 | CON-BMP-VTRA-011768 | 2019-05-23 | FOR BAPCO REVIEW | 2019-06-07 | 2019-06-16 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000931 | CLASS 2
076551C-000R-MR-0511-002 | MATERIAL REQUISITION FOR COLUMNS | GS GLOBAL CORP_MR-0511 | 021C0004 | RBCO053-06-001 | 021-C-CAL-40013-001 | STRENGTH CALCULATION FOR 021C0004 | A1003 | BX | 2 | 2019-05-15 | CON-BMP-VTRA-011611 | 2019-05-15 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0511-002 | MATERIAL REQUISITION FOR COLUMNS | GS GLOBAL CORP_MR-0511 | 021C0004 | RBCO053-06-A01,02 | 021-C-GAD-40069-001 | VACUUM DRIER - GENERAL ASSEMBLY 021C0004 | A1103 | BX | 2 | 2019-05-15 | CON-BMP-VTRA-011612 | 2019-05-15 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0511-002 | MATERIAL REQUISITION FOR COLUMNS | GS GLOBAL CORP_MR-0511 | 021C0004 | RBCO053-06-B01 | 021-C-GAD-40070-001 | VACUUM DRIER - BODY DETAIL 021C0004 | A1109 | BX | 2 | 2019-05-15 | CON-BMP-VTRA-011604 | 2019-05-15 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0511-002 | MATERIAL REQUISITION FOR COLUMNS | GS GLOBAL CORP_MR-0511 | 021C0004 | RBCO053-06-D01 | 021-C-GAD-40071-001 | VACUUM DRIER DETAIL OF MANWAY 021C0004 | A1109 | BX | 2 | 2019-05-15 | CON-BMP-VTRA-011604 | 2019-05-15 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0511-002 | MATERIAL REQUISITION FOR COLUMNS | GS GLOBAL CORP_MR-0511 | 021C0004 | RBCO053-06-E01 | 021-C-GAD-40072-001 | VACUUM DRIER DETAIL OF NOZZLE (1 TO 2) 021C0004 | A1109 | BX | 2 | 2019-05-15 | CON-BMP-VTRA-011604 | 2019-05-15 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0511-002 | MATERIAL REQUISITION FOR COLUMNS | GS GLOBAL CORP_MR-0511 | 021C0004 | RBCO053-06-G01 | 021-C-GAD-40074-001 | VACUUM DRIER DETAIL OF INTERNAL SUPPORT 021C0004 | A1110 | BX | 2 | 2019-05-15 | CON-BMP-VTRA-011615 | 2019-05-15 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0511-002 | MATERIAL REQUISITION FOR COLUMNS | GS GLOBAL CORP_MR-0511 | 021C0004 | RBCO053-06-H01 | 021-C-PLD-40007-001 | VACUUM DRIER DETAIL OF INS AND FIREPROOFING SUPPORT CLIP 021C0004 | A1105 | BX | 2 | 2019-05-27 | CON-BMP-VTRA-011814 | 2019-05-27 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0511-002 | MATERIAL REQUISITION FOR COLUMNS | GS GLOBAL CORP_MR-0511 | 021C0004 | RBCO053-06-H02 | 021-C-GAD-40073-001 | VACUUM DRIER DETAIL OF TOP DAVIT 021C0004 | A1109 | AX | 2 | 2019-05-15 | CON-BMP-VTRA-011614 | 2019-05-15 | FOR BAPCO REVIEW | 2019-05-30 | 2019-05-28 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000848 | CLASS 2
076551C-000R-MR-0511-002 | MATERIAL REQUISITION FOR COLUMNS | GS GLOBAL CORP_MR-0511 | 021C0004 | RBCO053-06-I01 | 021-C-DLB-40007-001 | VACUUM DRIER - TEMPLATE & GAUGE PLATE DETAIL 021C0004 | A2010 | BX | 2 | 2019-05-15 | CON-BMP-VTRA-011605 | 2019-05-15 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0511-002 | MATERIAL REQUISITION FOR COLUMNS | GS GLOBAL CORP_MR-0511 | 021C0004 | RBCO053-06-J01 | 021-C-PLD-40008-001 | VACUUM DRIER PIPE SUPPORT CLIP DETAIL 021C0004 | A1105 | AX | 2 | 2019-07-08 | CON-BMP-VTRA-012741 | 2019-07-08 | FOR BAPCO REVIEW | 2019-07-23 |  |  | CLASS 2
076551C-000R-MR-0511-002 | MATERIAL REQUISITION FOR COLUMNS | GS GLOBAL CORP_MR-0511 | 021C0004 | RBCO053-06-L01 | 021-C-DLB-40008-001 | VACUUM DRIER NAMEPLATE DETAIL 021C0004 | A1112 | BX | 2 | 2019-05-15 | CON-BMP-VTRA-011608 | 2019-05-15 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0511-002 | MATERIAL REQUISITION FOR COLUMNS | GS GLOBAL CORP_MR-0511 | 021C0004 | RBCO053-06-N01 | 021-C-GAD-40075-001 | VACUUM DRIER DETAIL OF PACKING SKETCH 021C0004 | A1109 | AX | 2 | 2019-03-08 | CON-BMP-VTRA-010636 | 2019-03-08 | FOR BAPCO REVIEW | 2019-03-25 | 2019-03-26 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000384 | CLASS 2
076551C-000R-MR-0511-002 | MATERIAL REQUISITION FOR COLUMNS | GS GLOBAL CORP_MR-0511 | 021C0004 | RBCO053-COM-029 | 021-C-PQP-40008-001 | FABRICATION AND QUALITY CONTROL PLAN 021C0004 | B1002 | BX | 2 | 2019-06-10 | CON-BMP-VTRA-012106 | 2019-06-10 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0511-002 | MATERIAL REQUISITION FOR COLUMNS | GS GLOBAL CORP_MR-0511 | 021C0004 | RBCO053-COM-036 | 021-C-MCD-40008-001 | WPS & PQR WITH WELD MAP FOR COLUMNS 021C0004 | B1304 | 0X | 2 | 2019-05-02 | CON-BMP-VTRA-011359 | 2019-05-02 | FOR BAPCO REVIEW | 2019-05-17 | 2019-05-13 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000667 | CLASS 2
076551C-000R-MR-0511-002 | MATERIAL REQUISITION FOR COLUMNS | GS GLOBAL CORP_MR-0511 | 023C0001 | RBCO053-07-001 | 023-C-CAL-40003-001 | STRENGTH CALCULATION FOR 023C0001 | A1003 | BX | 2 | 2019-05-31 | CON-BMP-VTRA-011887 | 2019-05-31 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0511-002 | MATERIAL REQUISITION FOR COLUMNS | GS GLOBAL CORP_MR-0511 | 023C0001 | RBCO053-07-A01-02 | 023-C-GAD-40011-001 | OFFGAS AMINE ABSORBER - GENERAL ASSEMBLY 023C0001 | A1103 | BX | 2 | 2019-05-31 | CON-BMP-VTRA-011882 | 2019-05-31 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0511-002 | MATERIAL REQUISITION FOR COLUMNS | GS GLOBAL CORP_MR-0511 | 023C0001 | RBCO053-07-B01 | 023-C-GAD-40012-001 | OFFGAS AMINE ABSORBER - BODY DETAIL 023C0001 | A1109 | BX | 2 | 2019-05-31 | CON-BMP-VTRA-011876 | 2019-05-31 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0511-002 | MATERIAL REQUISITION FOR COLUMNS | GS GLOBAL CORP_MR-0511 | 023C0001 | RBCO053-07-D01 | 023-C-GAD-40013-001 | OFFGAS AMINE ABSORBER DETAIL OF MANWAY 023C0001 | A1109 | BX | 2 | 2019-05-31 | CON-BMP-VTRA-011876 | 2019-05-31 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0511-002 | MATERIAL REQUISITION FOR COLUMNS | GS GLOBAL CORP_MR-0511 | 023C0001 | RBCO053-07-E01 | 023-C-GAD-40014-001 | OFFGAS AMINE ABSOREBER DETAIL OF NOZZLE (1 TO 2) 023C0001 | A1109 | BX | 2 | 2019-05-31 | CON-BMP-VTRA-011876 | 2019-05-31 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0511-002 | MATERIAL REQUISITION FOR COLUMNS | GS GLOBAL CORP_MR-0511 | 023C0001 | RBCO053-07-G01-G02 | 023-C-GAD-40016-001 | OFF GAS AMINE ABSORBER DETAIL OF INTERNAL SUPPORT 1-2 023C0001 | A1110 | BX | 2 | 2019-05-31 | CON-BMP-VTRA-011880 | 2019-05-31 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0511-002 | MATERIAL REQUISITION FOR COLUMNS | GS GLOBAL CORP_MR-0511 | 023C0001 | RBCO053-07-H01 | 023-C-PLD-40001-001 | OFF GAS AMINE ABSORBER DETAIL OF FIREPROOFING SUPPORT CLIP 023C0001 | A1105 | BX | 2 | 2019-07-08 | CON-BMP-VTRA-012744 | 2019-07-08 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0511-002 | MATERIAL REQUISITION FOR COLUMNS | GS GLOBAL CORP_MR-0511 | 023C0001 | RBCO053-07-H02 | 023-C-GAD-40115-001 | OFF GAS AMINE ABSORBER DETAIL OF TOP DAVIT 023C0001 | A1109 | AX | 2 | 2019-05-31 | CON-BMP-VTRA-011877 | 2019-05-31 | FOR BAPCO REVIEW | 2019-06-14 | 2019-06-18 | 3-REVIEWED WITH COMMENTS BMP-ROC-VTRE-000976 | CLASS 2
076551C-000R-MR-0511-002 | MATERIAL REQUISITION FOR COLUMNS | GS GLOBAL CORP_MR-0511 | 023C0001 | RBCO053-07-I01 | 023-C-DLB-40001-001 | OFFGAS AMINE ABSORBER - TEMPLATE & GAUGE PLATE DETAIL 023C0001 | A2010 | BX | 2 | 2019-05-31 | CON-BMP-VTRA-011896 | 2019-05-31 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0511-002 | MATERIAL REQUISITION FOR COLUMNS | GS GLOBAL CORP_MR-0511 | 023C0001 | RBCO053-07-J01-J02-J03 | 023-C-PLD-40002-001 | OFFGAS AMINE ABSORBER PIPE SUPPORT CLIP DETAIL 023C0001 | A1105 | AX | 2 | 2019-07-08 | CON-BMP-VTRA-012745 | 2019-07-08 | FOR BAPCO REVIEW | 2019-07-23 |  |  | CLASS 2
076551C-000R-MR-0511-002 | MATERIAL REQUISITION FOR COLUMNS | GS GLOBAL CORP_MR-0511 | 023C0001 | RBCO053-07-L01 | 023-C-DLB-40002-001 | OFFGAS AMINE ABSORBER - NAMEPLATE DETAIL 023C0001 | A1112 | BX | 2 | 2019-05-31 | CON-BMP-VTRA-011895 | 2019-05-31 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0511-002 | MATERIAL REQUISITION FOR COLUMNS | GS GLOBAL CORP_MR-0511 | 023C0001 | RBCO053-07-N01 | 023-C-GAD-40017-001 | OFF GAS AMINE ABSORBER DETAIL OF PACKING SKETCH 023C0001 | A1109 | AX | 2 | 2019-03-08 | CON-BMP-VTRA-010636 | 2019-03-08 | FOR BAPCO REVIEW | 2019-03-25 | 2019-03-26 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000384 | CLASS 2
076551C-000R-MR-0511-002 | MATERIAL REQUISITION FOR COLUMNS | GS GLOBAL CORP_MR-0511 | 023C0001 | RBCO053-COM-032 | 023-C-PQP-40002-001 | FABRICATION AND QUALITY CONTROL PLAN 023C0001 | B1002 | BX | 2 | 2019-06-10 | CON-BMP-VTRA-012107 | 2019-06-10 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0511-002 | MATERIAL REQUISITION FOR COLUMNS | GS GLOBAL CORP_MR-0511 | 023C0001 | RBCO053-COM-039 | 023-C-MCD-40001-001 | WPS & PQR WITH WELD MAP FOR COLUMNS 023C0001 | B1304 | 0X | 2 | 2019-05-02 | CON-BMP-VTRA-011359 | 2019-05-02 | FOR BAPCO REVIEW | 2019-05-17 | 2019-05-13 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000667 | CLASS 2
076551C-000R-MR-0570-001 | MATERIAL REQUISITION FOR TRAYS AND INTERNALS FOR LARGE COLUMNS | SULZER INDIA PRIVATE LIMITED | 018-C0003-I | 9052132-002-071 | 018-C-GAD-40214-001 | LTS SPARGER TUBE -ID 5000MM FOR 018C0003 - VACUUM COLUMN | A1111 | AX | 2 | 2019-05-10 | CON-BMP-VTRA-011518 | 2019-05-10 | FOR BAPCO REVIEW | 2019-05-24 | 2019-05-30 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000837 | CLASS 2
076551C-000R-MR-0570-001 | MATERIAL REQUISITION FOR TRAYS AND INTERNALS FOR LARGE COLUMNS | SULZER INDIA PRIVATE LIMITED | 018-C0003-I | 9052132-002-073 | 018-C-GAD-40215-001 | LTS SPARGER TUBE -ID 5000MM FOR 018C0003 - VACUUM COLUMN | A1111 | AX | 2 | 2019-05-10 | CON-BMP-VTRA-011518 | 2019-05-10 | FOR BAPCO REVIEW | 2019-05-24 | 2019-05-30 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000837 | CLASS 2
076551C-000R-MR-0570-001 | MATERIAL REQUISITION FOR TRAYS AND INTERNALS FOR LARGE COLUMNS | SULZER INDIA PRIVATE LIMITED | 018-C0003-I | 9052132-002-079 | 018-C-GAD-40178-001 | GENERAL ARRANGEMENT OF 018C0003 (EX BAPCO N.018-C-GAD-00178-001) | A2001 | CX | 2 | 2019-04-09 | CON-BMP-VTRA-011064 | 2019-04-09 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0570-001 | MATERIAL REQUISITION FOR TRAYS AND INTERNALS FOR LARGE COLUMNS | SULZER INDIA PRIVATE LIMITED | 018-C0003-I | 9052132-002-080 | 018-C-GAD-40179-001 | GENERAL ATTACHMENT DRAWING OF 018C0003 | A1110 | BX | 2 | 2019-04-09 | CON-BMP-VTRA-011065 | 2019-04-09 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0570-001 | MATERIAL REQUISITION FOR TRAYS AND INTERNALS FOR LARGE COLUMNS | SULZER INDIA PRIVATE LIMITED | 018-C0003-I | 9052132_DTP | 018-C-PRO-40019-001 | TESTING PROCEDURE (DISTRIBUTOR) ALL ITEMS (EX BAPCO N.018-C-PRO-00019-001) | B1103 | BX | 2 | 2019-03-20 | CON-BMP-VTRA-010777 | 2019-03-20 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0570-001 | MATERIAL REQUISITION FOR TRAYS AND INTERNALS FOR LARGE COLUMNS | SULZER INDIA PRIVATE LIMITED | 018-C0003-I | 9052132_HCAL_018C0003 | 018-C-CAL-40044-001 | HYDRAULIC CALCULATION OF 018C0003 (EX BAPCO N. 018-CCAL- 00044-001) | A1003 | DX | 2 | 2019-05-24 | CON-BMP-VTRA-011775 | 2019-05-24 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0570-001 | MATERIAL REQUISITION FOR TRAYS AND INTERNALS FOR LARGE COLUMNS | SULZER INDIA PRIVATE LIMITED | 018-C0003-I | 9052132_ITP_2 | 018-C-PQP-40018-001 | QUALITY CONTROL PLAN (ITP) OF 018C0003 | B1002 | 0X | 3 | 2019-06-20 | CON-BMP-VTRA-012332 | 2019-06-20 | FOR BAPCO REVIEW | 2019-07-04 | 2019-07-04 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001159 | CLASS 2
076551C-000R-MR-0570-001 | MATERIAL REQUISITION FOR TRAYS AND INTERNALS FOR LARGE COLUMNS | SULZER INDIA PRIVATE LIMITED | 018-C0003-I | 9052132_MCAL_018C0003 | 018-C-CAL-40043-001 | MECHANICAL CALCULATION OF 018C0003 | A1003 | AX | 2 | 2019-02-04 | CON-BMP-VTRA-010345 | 2019-02-04 | FOR BAPCO REVIEW | 2019-02-19 | 2019-02-25 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000224 | CLASS 2
076551C-000R-MR-0570-001 | MATERIAL REQUISITION FOR TRAYS AND INTERNALS FOR LARGE COLUMNS | SULZER INDIA PRIVATE LIMITED | 018-C0003-I | 9052132_MPR | 018-C-MRS-40002-001 | MONTHLY PROGRESS REPORT ALL ITEMS (EX BAPCO DOC N. 018-C-MRS-00002-001) | C1002 | DX | 2 | 2019-05-07 | CON-BMP-VTRA-011464 | 2019-05-07 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0570-001 | MATERIAL REQUISITION FOR TRAYS AND INTERNALS FOR LARGE COLUMNS | SULZER INDIA PRIVATE LIMITED | 018-C0003-I | 9052132_MSMM | 018-C-TSP-40023-001 | MATERIAL SPECIFICATION FOR MAIN SUB-ORDERS ALL ITEMS | B1203 | AX | 2 | 2018-12-10 | CON-BMP-VTRA-010542 | 2019-02-28 | FOR BAPCO REVIEW | 2019-03-15 | 2019-03-17 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000330 | CLASS 2
076551C-000R-MR-0570-001 | MATERIAL REQUISITION FOR TRAYS AND INTERNALS FOR LARGE COLUMNS | SULZER INDIA PRIVATE LIMITED | 018-C0003-I | 9052132_NDT | 018-C-PRO-40023-001 | NDT PROCEDURE ALL ITEMS (EX BAPCO N.018-C-PRO-00023-001) | B1202 | CX | 3 | 2019-03-12 | CON-BMP-VTRA-010655 | 2019-03-12 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0570-001 | MATERIAL REQUISITION FOR TRAYS AND INTERNALS FOR LARGE COLUMNS | SULZER INDIA PRIVATE LIMITED | 018-C0003-I | 9052132_PMI | 018-C-PRO-40020-001 | TESTING PROCEDURE (POSITIVE MATERIAL IDENTIFICATION) ALL ITEMS (EX BAPCO N.018-C-PRO-00020-001) | B1103 | CX | 2 | 2019-05-02 | CON-BMP-VTRA-011361 | 2019-05-02 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0570-001 | MATERIAL REQUISITION FOR TRAYS AND INTERNALS FOR LARGE COLUMNS | SULZER INDIA PRIVATE LIMITED | 018-C0003-I | 9052132_PP | 018-C-PRO-40022-001 | TESTING PROCEDURE (PICKLING AND PASSIVATION) ALL ITEMS | B1103 | AX | 2 | 2019-03-07 | CON-BMP-VTRA-010617 | 2019-03-07 | FOR BAPCO REVIEW | 2019-03-22 | 2019-03-17 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000320 | CLASS 2
076551C-000R-MR-0570-001 | MATERIAL REQUISITION FOR TRAYS AND INTERNALS FOR LARGE COLUMNS | SULZER INDIA PRIVATE LIMITED | 018-C0003-I | 9052132_PS | 018-C-SCH-40002-001 | ENGINEERING PROCUREMENT MANUFACTURING & TEST SCHEDULE ALL ITEMS (EX BAPCO DOC. N. 018-C-SCH-00002-001) | C1001 | DX | 2 | 2019-05-07 | CON-BMP-VTRA-011462 | 2019-05-07 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-0570-001 | MATERIAL REQUISITION FOR TRAYS AND INTERNALS FOR LARGE COLUMNS | SULZER INDIA PRIVATE LIMITED | 018-C0003-I | 9052132_UPO | 018-C-INV-40002-001 | UNPRICED COPY OF MAIN SUB ORDERS ALL ITEMS | C1005 | AX | 4 | 2019-02-28 | CON-BMP-VTRA-010544 | 2019-02-28 | FOR BAPCO REVIEW | 2019-03-15 | 2019-03-17 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000328 | CLASS 2
076551C-000R-MR-0570-001 | MATERIAL REQUISITION FOR TRAYS AND INTERNALS FOR LARGE COLUMNS | SULZER INDIA PRIVATE LIMITED | 018-C0003-I | 9052132_VDRL | 018-C-INX-40012-001 | LIST OF VENDOR'S DOCUMENTS ANDDRAWINGS ALL ITEMS | A0001 | AX | 4 | 2018-12-05 | CON-BMP-VTRA-010614 | 2019-03-07 | FOR BAPCO REVIEW | 2019-03-22 | 2019-03-26 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000381 | CLASS 2
076551C-000R-MR-0570-001 | MATERIAL REQUISITION FOR TRAYS AND INTERNALS FOR LARGE COLUMNS | SULZER INDIA PRIVATE LIMITED | 018-C0003-I | 9052132_WPS | 018-C-MCD-40027-001 | WPS & PQR ALL ITEMS (EX BAPCO N.018-C-MCD-00027-001) | B1304 | CX | 3 | 2019-05-03 | CON-BMP-VTRA-011363 | 2019-05-03 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0570-001 | MATERIAL REQUISITION FOR TRAYS AND INTERNALS FOR LARGE COLUMNS | SULZER INDIA PRIVATE LIMITED | 018C0001-I | 9052132-001-002 | 018-C-GAD-40173-001 | 2-PASS ODD RV1 TRAYS #35 U/I 43 ID:5200 018C0001-I | A1111 | AX | 2 | 2019-06-28 | CON-BMP-VTRA-012554 | 2019-06-28 | FOR BAPCO REVIEW | 2019-07-12 |  |  | CLASS 2
076551C-000R-MR-0570-001 | MATERIAL REQUISITION FOR TRAYS AND INTERNALS FOR LARGE COLUMNS | SULZER INDIA PRIVATE LIMITED | 018C0001-I | 9052132-001-003 | 018-C-GAD-40261-001 | 2-PASS EVEN RV1 TRAYS #34 U/I 42 ID:5200 FOR C19C0004 - ATMOSPHERIC COLUMN 018C0001-I | A1111 | AX | 2 | 2019-06-28 | CON-BMP-VTRA-012554 | 2019-06-28 | FOR BAPCO REVIEW | 2019-07-12 |  |  | CLASS 2
076551C-000R-MR-0570-001 | MATERIAL REQUISITION FOR TRAYS AND INTERNALS FOR LARGE COLUMNS | SULZER INDIA PRIVATE LIMITED | 018C0001-I | 9052132-001-009 | 018-C-GAD-40159-001 | DISTRIBUTOR PIPE AT NOZZLE 10 FOR 018C0001-I ATMOSPHERIC COLUMN | A1111 | AX | 2 | 2019-04-09 | CON-BMP-VTRA-011550 | 2019-05-14 | FOR BAPCO REVIEW | 2019-05-28 | 2019-05-30 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000839 | CLASS 2
076551C-000R-MR-0570-001 | MATERIAL REQUISITION FOR TRAYS AND INTERNALS FOR LARGE COLUMNS | SULZER INDIA PRIVATE LIMITED | 018C0001-I | 9052132-001-011 | 018-C-GAD-40160-001 | DISTRIBUTOR PIPE AT NOZZLE 24 A/B FOR 018C0001 ATMOSPHERIC COLUM 018C0001-I | A1111 | AX | 2 | 2019-04-09 | CON-BMP-VTRA-011550 | 2019-05-14 | FOR BAPCO REVIEW | 2019-05-28 | 2019-05-30 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000839 | CLASS 2
076551C-000R-MR-0570-001 | MATERIAL REQUISITION FOR TRAYS AND INTERNALS FOR LARGE COLUMNS | SULZER INDIA PRIVATE LIMITED | 018C0001-I | 9052132-001-023 | 018-C-GAD-40163-001 | WASH DISTRIBUTOR PIPE AT NOZZLE 26 FOR 018C0001 ATMOSPHERIC COLUM 018C0001-I | A1111 | AX | 2 | 2019-04-09 | CON-BMP-VTRA-011550 | 2019-05-14 | FOR BAPCO REVIEW | 2019-05-28 | 2019-05-30 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000839 | CLASS 2
076551C-000R-MR-0570-001 | MATERIAL REQUISITION FOR TRAYS AND INTERNALS FOR LARGE COLUMNS | SULZER INDIA PRIVATE LIMITED | 018C0001-I | 9052132-001-045 | 018-C-GAD-40167-001 | STEAM DISTRIBUTOR PIPE AT NOZZLE 29 FOR 018C0001 ATMOSPHERIC COLUM 018C0001-I | A1111 | AX | 2 | 2019-04-09 | CON-BMP-VTRA-011550 | 2019-05-14 | FOR BAPCO REVIEW | 2019-05-28 | 2019-05-30 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000839 | CLASS 2
076551C-000R-MR-0570-001 | MATERIAL REQUISITION FOR TRAYS AND INTERNALS FOR LARGE COLUMNS | SULZER INDIA PRIVATE LIMITED | 018C0001-I | 9052132-001-047 | 018-C-GAD-40168-001 | QUENCH DISTRIBUTOR PIPE AT NOZZLE 28 FOR 018C0001 ATMOSPHERIC COLUMN 018C0001-I | A1111 | AX | 2 | 2019-04-09 | CON-BMP-VTRA-011550 | 2019-05-14 | FOR BAPCO REVIEW | 2019-05-28 | 2019-05-30 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000839 | CLASS 2
076551C-000R-MR-0570-001 | MATERIAL REQUISITION FOR TRAYS AND INTERNALS FOR LARGE COLUMNS | SULZER INDIA PRIVATE LIMITED | 018C0001-I | 9052132-001-057 | 018-C-GAD-40156-001 | GENERAL ARRANGEMENT OF 018C0001 (EX BAPCO N.018-C-GAD-00156-001) | A2001 | BX | 2 | 2019-02-04 | CON-BMP-VTRA-010343 | 2019-02-04 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0570-001 | MATERIAL REQUISITION FOR TRAYS AND INTERNALS FOR LARGE COLUMNS | SULZER INDIA PRIVATE LIMITED | 018C0001-I | 9052132-001-058 | 018-C-GAD-40157-001 | GENERAL ATTACHMENT DRAWING OF 018C0001 | A1110 | AXX | 2 | 2019-03-29 | CON-BMP-VTRA-010909 | 2019-03-29 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0570-001 | MATERIAL REQUISITION FOR TRAYS AND INTERNALS FOR LARGE COLUMNS | SULZER INDIA PRIVATE LIMITED | 018C0001-I | 9052132_HCAL_018C0001 | 018-C-CAL-40042-001 | HYDRAULIC CALCULATION OF 018C0001 (EX BAPCO N. 018-CCAL- 00042-001) | A1003 | DX | 2 | 2019-05-24 | CON-BMP-VTRA-011775 | 2019-05-24 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0570-001 | MATERIAL REQUISITION FOR TRAYS AND INTERNALS FOR LARGE COLUMNS | SULZER INDIA PRIVATE LIMITED | 018C0001-I | 9052132_ITP | 018-C-PQP-40017-001 | QUALITY CONTROL PLAN (ITP) 018C0001 (EX DOC.EX DOC. 018- C-PQP-00015-001) | B1002 | 0X | 3 | 2019-06-20 | CON-BMP-VTRA-012332 | 2019-06-20 | FOR BAPCO REVIEW | 2019-07-04 | 2019-07-04 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001159 | CLASS 2
076551C-000R-MR-0570-001 | MATERIAL REQUISITION FOR TRAYS AND INTERNALS FOR LARGE COLUMNS | SULZER INDIA PRIVATE LIMITED | 018C0001-I | 9052132_MCAL_018C0001 | 018-C-CAL-40041-001 | MECHANICAL CALCULATION OF 018C0001 | A1003 | AX | 2 | 2019-02-04 | CON-BMP-VTRA-010345 | 2019-02-04 | FOR BAPCO REVIEW | 2019-02-19 | 2019-02-25 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000224 | CLASS 2
076551C-000R-MR-0570-001 | MATERIAL REQUISITION FOR TRAYS AND INTERNALS FOR LARGE COLUMNS | SULZER INDIA PRIVATE LIMITED | 018C1003-I | 9052132-003-001 | 018-C-GAD-40221-001 | VKR2F DISTRIBUTOR -ID 2100MM TRAIN 1 HP AMINE 018C1003-I | A1111 | AX | 2 | 2019-06-17 | CON-BMP-VTRA-012258 | 2019-06-17 | FOR BAPCO REVIEW | 2019-07-02 | 2019-07-09 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001240 | CLASS 2
076551C-000R-MR-0570-001 | MATERIAL REQUISITION FOR TRAYS AND INTERNALS FOR LARGE COLUMNS | SULZER INDIA PRIVATE LIMITED | 018C1003-I | 9052132-003-003 | 018-C-GAD-40222-001 | SKHW CHIMNEY TRAY -ID 2100MM FOR TRAIN 1 HP AMINE ABSORBER AND WASH COLUMN 018C1003-I | A1111 | AX | 2 | 2019-02-04 | CON-BMP-VTRA-012021 | 2019-06-05 | FOR BAPCO REVIEW | 2019-06-20 | 2019-06-30 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001115 | CLASS 2
076551C-000R-MR-0570-001 | MATERIAL REQUISITION FOR TRAYS AND INTERNALS FOR LARGE COLUMNS | SULZER INDIA PRIVATE LIMITED | 018C1003-I | 9052132-003-005 | 018-C-GAD-40223-001 | GIS VAPOR INJECTION PLATE -ID 2100MM 018C1003-I | A1111 | AX | 2 | 2019-06-17 | CON-BMP-VTRA-012258 | 2019-06-17 | FOR BAPCO REVIEW | 2019-07-02 | 2019-07-09 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001240 | CLASS 2
076551C-000R-MR-0570-001 | MATERIAL REQUISITION FOR TRAYS AND INTERNALS FOR LARGE COLUMNS | SULZER INDIA PRIVATE LIMITED | 018C1003-I | 9052132-003-007 | 018-C-GAD-40224-001 | RPB BED LIMITER -ID 2100MM TRAIN 1 HP AMINE ABSORBER AND WA 018C1003-I | A1111 | AX | 2 | 2019-06-17 | CON-BMP-VTRA-012258 | 2019-06-17 | FOR BAPCO REVIEW | 2019-07-02 | 2019-07-09 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001240 | CLASS 2
076551C-000R-MR-0570-001 | MATERIAL REQUISITION FOR TRAYS AND INTERNALS FOR LARGE COLUMNS | SULZER INDIA PRIVATE LIMITED | 018C1003-I | 9052132-003-009 | 018-C-GAD-40225-001 | LTS SPARGER TUBE -ID 2100MM FOR 018C1003 - TRAIN 1 HP AMINE ABSORBER & WASH COLUMN | A1111 | AX | 2 | 2019-05-10 | CON-BMP-VTRA-011518 | 2019-05-10 | FOR BAPCO REVIEW | 2019-05-24 | 2019-05-30 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000837 | CLASS 2
076551C-000R-MR-0570-001 | MATERIAL REQUISITION FOR TRAYS AND INTERNALS FOR LARGE COLUMNS | SULZER INDIA PRIVATE LIMITED | 018C1003-I | 9052132-003-012 | 018-C-GAD-40227-001 | 2-PASS ODD RV1TRAYS #1 U/I 9 ID:2100 TRAIN 1 HP AMINE ABSORBER AND WASH COLUMN 018C1003-I | A1111 | AX | 2 | 2019-02-04 | CON-BMP-VTRA-012021 | 2019-06-05 | FOR BAPCO REVIEW | 2019-06-20 | 2019-06-30 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001115 | CLASS 2
076551C-000R-MR-0570-001 | MATERIAL REQUISITION FOR TRAYS AND INTERNALS FOR LARGE COLUMNS | SULZER INDIA PRIVATE LIMITED | 018C1003-I | 9052132-003-013 | 018-C-GAD-40269-001 | 2-PASS EVEN RV1 TRAYS #2 U/I 8ID:2100 TRAIN 1 HP AMINE ABSORBER AND WASH COLUMN 018C1003-I | A1111 | AX | 2 | 2019-02-04 | CON-BMP-VTRA-012021 | 2019-06-05 | FOR BAPCO REVIEW | 2019-06-20 | 2019-06-30 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001115 | CLASS 2
076551C-000R-MR-0570-001 | MATERIAL REQUISITION FOR TRAYS AND INTERNALS FOR LARGE COLUMNS | SULZER INDIA PRIVATE LIMITED | 018C1003-I | 9052132-003-017 | 018-C-GAD-40226-001 | FEED INLET DISTRIBUTOR AT NOZZLE N12 FOR 018C1003 - TRAIN 1 HP AMINE ABSORBER & WASH COLUMN | A1111 | AX | 2 | 2019-05-10 | CON-BMP-VTRA-011518 | 2019-05-10 | FOR BAPCO REVIEW | 2019-05-24 | 2019-05-30 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000837 | CLASS 2
076551C-000R-MR-0570-001 | MATERIAL REQUISITION FOR TRAYS AND INTERNALS FOR LARGE COLUMNS | SULZER INDIA PRIVATE LIMITED | 018C1003-I | 9052132-003-019 | 018-C-GAD-40219-001 | GENERAL ARRANGEMENT OF 018C1003 (EX BAPCO N.018-C-GAD-00219-001) | A2001 | CX | 2 | 2019-03-29 | CON-BMP-VTRA-010911 | 2019-03-29 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0570-001 | MATERIAL REQUISITION FOR TRAYS AND INTERNALS FOR LARGE COLUMNS | SULZER INDIA PRIVATE LIMITED | 018C1003-I | 9052132-003-020 | 018-C-GAD-40220-001 | GENERAL ATTACHMENT DRAWING OF 018C1003 | A1110 | CX | 2 | 2019-04-09 | CON-BMP-VTRA-011065 | 2019-04-09 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0570-001 | MATERIAL REQUISITION FOR TRAYS AND INTERNALS FOR LARGE COLUMNS | SULZER INDIA PRIVATE LIMITED | 018C1003-I | 9052132_HCAL_018C1003 | 018-C-CAL-40046-001 | HYDRAULIC CALCULATION OF 018C1003 (EX BAPCO N. 018-CCAL- 00046-001) | A1003 | DX | 2 | 2019-05-24 | CON-BMP-VTRA-011775 | 2019-05-24 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0570-001 | MATERIAL REQUISITION FOR TRAYS AND INTERNALS FOR LARGE COLUMNS | SULZER INDIA PRIVATE LIMITED | 018C1003-I | 9052132_ITP_3 | 018-C-PQP-40019-001 | QUALITY CONTROL PLAN (ITP) OF 018C1003 | B1002 | 0X | 3 | 2019-06-20 | CON-BMP-VTRA-012332 | 2019-06-20 | FOR BAPCO REVIEW | 2019-07-04 | 2019-07-04 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001159 | CLASS 2
076551C-000R-MR-0570-001 | MATERIAL REQUISITION FOR TRAYS AND INTERNALS FOR LARGE COLUMNS | SULZER INDIA PRIVATE LIMITED | 018C1003-I | 9052132_MCAL_018C1003 | 018-C-CAL-40045-001 | MECHANICAL CALCULATION OF 018C0003 | A1003 | AX | 2 | 2019-02-04 | CON-BMP-VTRA-010345 | 2019-02-04 | FOR BAPCO REVIEW | 2019-02-19 | 2019-02-25 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000224 | CLASS 2
076551C-000R-MR-0570-001 | MATERIAL REQUISITION FOR TRAYS AND INTERNALS FOR LARGE COLUMNS | SULZER INDIA PRIVATE LIMITED | 018C2003-I | 9052132-004-001 | 018-C-GAD-40230-001 | VKR2F DISTRIBUTOR -ID 2100MM TRAIN 2 HP AMINE 018C2003-I | A1111 | AX | 2 | 2019-06-17 | CON-BMP-VTRA-012258 | 2019-06-17 | FOR BAPCO REVIEW | 2019-07-02 | 2019-07-09 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001240 | CLASS 2
076551C-000R-MR-0570-001 | MATERIAL REQUISITION FOR TRAYS AND INTERNALS FOR LARGE COLUMNS | SULZER INDIA PRIVATE LIMITED | 018C2003-I | 9052132-004-003 | 018-C-GAD-40231-001 | SKHW CHIMNEY TRAY -ID 2100MM TRAIN 2 HP AMINE ABSORBER AND WASH COLUMN 018C2003-I | A1111 | AX | 2 | 2019-02-04 | CON-BMP-VTRA-012021 | 2019-06-05 | FOR BAPCO REVIEW | 2019-06-20 | 2019-06-30 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001115 | CLASS 2
076551C-000R-MR-0570-001 | MATERIAL REQUISITION FOR TRAYS AND INTERNALS FOR LARGE COLUMNS | SULZER INDIA PRIVATE LIMITED | 018C2003-I | 9052132-004-005 | 018-C-GAD-40232-001 | GIS VAPOR INJECTION PLATE -ID 2100MM TRAIN 2 HP AMINE ABSORBER AND WASH COLUMN 018C2003-I | A1111 | AX | 2 | 2019-06-17 | CON-BMP-VTRA-012258 | 2019-06-17 | FOR BAPCO REVIEW | 2019-07-02 | 2019-07-09 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001240 | CLASS 2
076551C-000R-MR-0570-001 | MATERIAL REQUISITION FOR TRAYS AND INTERNALS FOR LARGE COLUMNS | SULZER INDIA PRIVATE LIMITED | 018C2003-I | 9052132-004-007 | 018-C-GAD-40233-001 | RPB BED LIMITER -ID 2100MM TRAIN 2 HP AMINE ABSORBER AND WASH COLUMN 018C2003-I | A1111 | AX | 2 | 2019-06-17 | CON-BMP-VTRA-012258 | 2019-06-17 | FOR BAPCO REVIEW | 2019-07-02 | 2019-07-09 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001240 | CLASS 2
076551C-000R-MR-0570-001 | MATERIAL REQUISITION FOR TRAYS AND INTERNALS FOR LARGE COLUMNS | SULZER INDIA PRIVATE LIMITED | 018C2003-I | 9052132-004-009 | 018-C-GAD-40234-001 | LTS SPARGER TUBE -ID 2100MM FOR 018C2003 - TRAIN 2 HP AMINE ABSORBER & WASH COLUMN | A1111 | AX | 2 | 2019-05-10 | CON-BMP-VTRA-011518 | 2019-05-10 | FOR BAPCO REVIEW | 2019-05-24 | 2019-05-30 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000837 | CLASS 2
076551C-000R-MR-0570-001 | MATERIAL REQUISITION FOR TRAYS AND INTERNALS FOR LARGE COLUMNS | SULZER INDIA PRIVATE LIMITED | 018C2003-I | 9052132-004-012 | 018-C-GAD-40236-001 | 2-PASS ODD RV1 TRAYS #1 U/I 9 ID:2100 TRAIN 2 HP ABSORNBER AND WASH COLUMN 018C2003-I | A1111 | AX | 2 | 2019-02-04 | CON-BMP-VTRA-012021 | 2019-06-05 | FOR BAPCO REVIEW | 2019-06-20 | 2019-06-30 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001115 | CLASS 2
076551C-000R-MR-0570-001 | MATERIAL REQUISITION FOR TRAYS AND INTERNALS FOR LARGE COLUMNS | SULZER INDIA PRIVATE LIMITED | 018C2003-I | 9052132-004-013 | 018-C-GAD-40270-001 | 2-PASS EVEN RV1 TRAYS #2 U/I 8ID:2100 TRAIN 2 HP ABSORBER AND WASH COLUMN 018C2003-I | A1111 | AX | 2 | 2019-02-04 | CON-BMP-VTRA-012021 | 2019-06-05 | FOR BAPCO REVIEW | 2019-06-20 | 2019-06-30 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001115 | CLASS 2
076551C-000R-MR-0570-001 | MATERIAL REQUISITION FOR TRAYS AND INTERNALS FOR LARGE COLUMNS | SULZER INDIA PRIVATE LIMITED | 018C2003-I | 9052132-004-017 | 018-C-GAD-40235-001 | FEED INLET DISTRIBUTOR AT NOZZLE N12 FOR 018C2003- TRAIN 2 HP AMINE ABSORBER & WASH COLUMN | A1111 | AX | 2 | 2019-05-10 | CON-BMP-VTRA-011518 | 2019-05-10 | FOR BAPCO REVIEW | 2019-05-24 | 2019-05-30 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000837 | CLASS 2
076551C-000R-MR-0570-001 | MATERIAL REQUISITION FOR TRAYS AND INTERNALS FOR LARGE COLUMNS | SULZER INDIA PRIVATE LIMITED | 018C2003-I | 9052132-004-019 | 018-C-GAD-40228-001 | GENERAL ARRANGEMENT OF 018C2003 (EX BAPCO N.018-C-GAD-00228-001) | A2001 | CX | 2 | 2019-03-29 | CON-BMP-VTRA-010911 | 2019-03-29 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0570-001 | MATERIAL REQUISITION FOR TRAYS AND INTERNALS FOR LARGE COLUMNS | SULZER INDIA PRIVATE LIMITED | 018C2003-I | 9052132-004-020 | 018-C-GAD-40229-001 | GENERAL ATTACHMENT DRAWING OF 018C2003 | A1110 | CX | 2 | 2019-04-09 | CON-BMP-VTRA-011065 | 2019-04-09 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0570-001 | MATERIAL REQUISITION FOR TRAYS AND INTERNALS FOR LARGE COLUMNS | SULZER INDIA PRIVATE LIMITED | 018C2003-I | 9052132_HCAL_018C2003 | 018-C-CAL-40048-001 | HYDRAULIC CALCULATION OF 018C2003 (EX BAPCO N. 018-CCAL- 00048-001) | A1003 | DX | 2 | 2019-05-24 | CON-BMP-VTRA-011775 | 2019-05-24 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0570-001 | MATERIAL REQUISITION FOR TRAYS AND INTERNALS FOR LARGE COLUMNS | SULZER INDIA PRIVATE LIMITED | 018C2003-I | 9052132_ITP_4 | 018-C-PQP-40020-001 | QUALITY CONTROL PLAN (ITP) OF 018C2003 | B1002 | 0X | 3 | 2019-06-20 | CON-BMP-VTRA-012332 | 2019-06-20 | FOR BAPCO REVIEW | 2019-07-04 | 2019-07-04 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001159 | CLASS 2
076551C-000R-MR-0570-001 | MATERIAL REQUISITION FOR TRAYS AND INTERNALS FOR LARGE COLUMNS | SULZER INDIA PRIVATE LIMITED | 018C2003-I | 9052132_MCAL_018C2003 | 018-C-CAL-40047-001 | MECHANICAL CALCULATION OF 018C2003 | A1003 | AX | 2 | 2019-02-04 | CON-BMP-VTRA-010345 | 2019-02-04 | FOR BAPCO REVIEW | 2019-02-19 | 2019-02-25 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000224 | CLASS 2
076551C-000R-MR-0570-002 | MATERIAL REQUISITION FOR TRAYS AND INTERNALS FOR COLUMNS | SULZER INDIA PRIVATE LIMITED | 018-C0004-I | 9053210-003-001 | 018-C-GAD-40250-001 | VKG DISTRIBUTOR -ID 610MM 018- C0004-I | A1111 | BX | 2 | 2019-07-02 | CON-BMP-VTRA-012629 | 2019-07-03 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0570-002 | MATERIAL REQUISITION FOR TRAYS AND INTERNALS FOR COLUMNS | SULZER INDIA PRIVATE LIMITED | 018-C0004-I | 9053210-003-003 | 018-C-GAD-40251-001 | EMS VAPOR INJECTION PLATE -ID 610MM 018-C0004-I | A1111 | BX | 2 | 2019-07-02 | CON-BMP-VTRA-012629 | 2019-07-03 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0570-002 | MATERIAL REQUISITION FOR TRAYS AND INTERNALS FOR COLUMNS | SULZER INDIA PRIVATE LIMITED | 018-C0004-I | 9053210-003-005 | 018-C-GAD-40252-001 | RPB BED LIMITER -ID 610MM 018-C0004-I | A1111 | BX | 2 | 2019-07-01 | CON-BMP-VTRA-012586 | 2019-07-01 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0570-002 | MATERIAL REQUISITION FOR TRAYS AND INTERNALS FOR COLUMNS | SULZER INDIA PRIVATE LIMITED | 018-C0004-I | 9053210-003-007 | 018-C-GAD-40253-001 | VSI COLLECTOR/DISTR. -ID 610MM 018-C0004-I | A1111 | BX | 2 | 2019-07-01 | CON-BMP-VTRA-012586 | 2019-07-01 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0570-002 | MATERIAL REQUISITION FOR TRAYS AND INTERNALS FOR COLUMNS | SULZER INDIA PRIVATE LIMITED | 018-C0004-I | 9053210-003-021 | 018-C-GAD-40248-001 | GENERAL ARRANGEMENT OF 018C0004 (EX BAPCO N.018-C-GAD-00248-001) | A2001 | DX | 2 | 2019-07-08 | CON-BMP-VTRA-012714 | 2019-07-08 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0570-002 | MATERIAL REQUISITION FOR TRAYS AND INTERNALS FOR COLUMNS | SULZER INDIA PRIVATE LIMITED | 018-C0004-I | 9053210-003-022 | 018-C-GAD-40249-001 | GENERAL ATTACHMENT DRAWING OF 018C0004 | A1110 | CX | 2 | 2019-06-29 | CON-BMP-VTRA-012583 | 2019-06-29 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0570-002 | MATERIAL REQUISITION FOR TRAYS AND INTERNALS FOR COLUMNS | SULZER INDIA PRIVATE LIMITED | 018-C0004-I | 9053210_DTP | 000-C-PRO-40022-001 | TESTING PROCEDURE (DISTRIBUTOR) ALL ITEMS (EX BAPCO N.000-C-PRO-60022-001) | B1103 | BX | 2 | 2019-03-20 | CON-BMP-VTRA-010780 | 2019-03-20 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0570-002 | MATERIAL REQUISITION FOR TRAYS AND INTERNALS FOR COLUMNS | SULZER INDIA PRIVATE LIMITED | 018-C0004-I | 9053210_HCAL_018C0004 | 018-C-CAL-40054-001 | HYDRAULIC CALCULATION OF 018C0004 (EX BAPCO N.018-CCAL- 00054-001) | A1003 | CX | 2 | 2019-05-15 | CON-BMP-VTRA-011609 | 2019-05-15 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0570-002 | MATERIAL REQUISITION FOR TRAYS AND INTERNALS FOR COLUMNS | SULZER INDIA PRIVATE LIMITED | 018-C0004-I | 9053210_ITP_3 | 018-C-PQP-40023-001 | QUALITY CONTROL PLAN (ITP) OF 018C0004 | B1002 | 0X | 3 | 2019-06-20 | CON-BMP-VTRA-012333 | 2019-06-20 | FOR BAPCO REVIEW | 2019-07-05 | 2019-07-10 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001247 | CLASS 2
076551C-000R-MR-0570-002 | MATERIAL REQUISITION FOR TRAYS AND INTERNALS FOR COLUMNS | SULZER INDIA PRIVATE LIMITED | 018-C0004-I | 9053210_MCAL_018C0004 | 018-C-CAL-40053-001 | MECHANICAL CALCULATION OF 018C0004 | A1003 | DX | 2 | 2019-06-29 | CON-BMP-VTRA-012577 | 2019-06-29 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0570-002 | MATERIAL REQUISITION FOR TRAYS AND INTERNALS FOR COLUMNS | SULZER INDIA PRIVATE LIMITED | 018-C0004-I | 9053210_MPR | 000-C-MRS-40004-001 | MONTHLY PROGRESS REPORT ALL ITEMS (EX BAPCO N.000-C-MRS- 60004-001) | C1002 | DX | 2 | 2019-05-21 | CON-BMP-VTRA-011681 | 2019-05-21 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0570-002 | MATERIAL REQUISITION FOR TRAYS AND INTERNALS FOR COLUMNS | SULZER INDIA PRIVATE LIMITED | 018-C0004-I | 9053210_MSMM | 000-C-TSP-40005-001 | MATERIAL SPECIFICATION FOR MAIN SUB-ORDERS ALL ITEMS | B1203 | AXX | 2 | 2019-04-12 | CON-BMP-VTRA-011146 | 2019-04-12 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0570-002 | MATERIAL REQUISITION FOR TRAYS AND INTERNALS FOR COLUMNS | SULZER INDIA PRIVATE LIMITED | 018-C0004-I | 9053210_NDT | 000-C-PRO-40026-001 | NDT PROCEDURE ALL ITEMS (EX BAPCO N.000-C-PRO-60026-001) | B1202 | 0AX | 3 | 2019-06-04 | CON-BMP-VTRA-011959 | 2019-06-04 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0570-002 | MATERIAL REQUISITION FOR TRAYS AND INTERNALS FOR COLUMNS | SULZER INDIA PRIVATE LIMITED | 018-C0004-I | 9053210_PMI | 000-C-PRO-40023-001 | TESTING PROCEDURE (POSITIVE MATERIAL IDENTIFICATION) ALL ITEMS (EX BAPCO N.000-C-PRO- 60023-001) | B1103 | CX | 2 | 2019-05-03 | CON-BMP-VTRA-011372 | 2019-05-03 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0570-002 | MATERIAL REQUISITION FOR TRAYS AND INTERNALS FOR COLUMNS | SULZER INDIA PRIVATE LIMITED | 018-C0004-I | 9053210_PP | 000-C-PRO-40025-001 | TESTING PROCEDURE (PICKLING AND PASSIVATION) ALL ITEMS | B1103 | AX | 2 | 2019-09-08 | CON-BMP-VTRA-010620 | 2019-03-08 | FOR BAPCO REVIEW | 2019-03-22 | 2019-03-19 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000341 | CLASS 2
076551C-000R-MR-0570-002 | MATERIAL REQUISITION FOR TRAYS AND INTERNALS FOR COLUMNS | SULZER INDIA PRIVATE LIMITED | 018-C0004-I | 9053210_PS | 000-C-SCH-40003-001 | ENGINEERING PROCUREMENT MANUFACTURING & TEST SCHEDULE ALL ITEMS (EX BAPCO N.000-C-SCH-60003-001) | C1001 | DX | 2 | 2019-05-21 | CON-BMP-VTRA-011683 | 2019-05-21 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-0570-002 | MATERIAL REQUISITION FOR TRAYS AND INTERNALS FOR COLUMNS | SULZER INDIA PRIVATE LIMITED | 018-C0004-I | 9053210_UOP | 000-C-INV-40003-001 | UNPRICED COPY OF MAIN SUB ORDERS ALL ITEMS | C1005 | BX | 4 | 2019-05-08 | CON-BMP-VTRA-011474 | 2019-05-08 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0570-002 | MATERIAL REQUISITION FOR TRAYS AND INTERNALS FOR COLUMNS | SULZER INDIA PRIVATE LIMITED | 018-C0004-I | 9053210_VDRL | 000-C-INX-40004-001 | LIST OF VENDOR'S DOCUMENTS AND DRAWINGS ALL ITEMS | A0001 | BX | 2 | 2019-05-10 | CON-BMP-VTRA-011519 | 2019-05-10 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0570-002 | MATERIAL REQUISITION FOR TRAYS AND INTERNALS FOR COLUMNS | SULZER INDIA PRIVATE LIMITED | 018-C0004-I | 9053210_WPS | 000-C-MCD-40007-001 | WPS & PQR ALL ITEMS (EX BAPCO N. 000-C-MCD-60007-001) | B1304 | CX | 2 | 2019-05-21 | CON-BMP-VTRA-011691 | 2019-05-21 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0570-002 | MATERIAL REQUISITION FOR TRAYS AND INTERNALS FOR COLUMNS | SULZER INDIA PRIVATE LIMITED | 018C0002-I | 9053210-001-002 | 018-C-GAD-40241-001 | 2-PASS ODD RV1 TRAYS 1 UI 9 ID2550 FOR 018C0002-I DIESEL STRIPPER | A1111 | AX | 2 | 2019-06-05 | CON-BMP-VTRA-012008 | 2019-06-05 | FOR BAPCO REVIEW | 2019-06-20 | 2019-06-30 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001110 | CLASS 2
076551C-000R-MR-0570-002 | MATERIAL REQUISITION FOR TRAYS AND INTERNALS FOR COLUMNS | SULZER INDIA PRIVATE LIMITED | 018C0002-I | 9053210-001-003 | 018-C-GAD-40271-001 | 2-PASS EVEN RV1 TRAYS 2 UI 10 ID2550 FOR 18C0002-I DIESEL STRIPPER | A1111 | AX | 2 | 2019-06-05 | CON-BMP-VTRA-012008 | 2019-06-05 | FOR BAPCO REVIEW | 2019-06-20 | 2019-06-30 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001110 | CLASS 2
076551C-000R-MR-0570-002 | MATERIAL REQUISITION FOR TRAYS AND INTERNALS FOR COLUMNS | SULZER INDIA PRIVATE LIMITED | 018C0002-I | 9053210-001-007 | 018-C-GAD-40239-001 | FEED INLET NOZZLE 11 -ID 2550MM 018C0002 | A1111 | AXX | 2 | 2019-05-21 | CON-BMP-VTRA-011686 | 2019-05-21 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0570-002 | MATERIAL REQUISITION FOR TRAYS AND INTERNALS FOR COLUMNS | SULZER INDIA PRIVATE LIMITED | 018C0002-I | 9053210-001-009 | 018-C-GAD-40240-001 | FEED INLET NOZZLE 29 -ID 2550MM 018C0002 | A1111 | AX | 2 | 2019-04-08 | CON-BMP-VTRA-011048 | 2019-04-08 | FOR BAPCO REVIEW | 2019-04-22 | 2019-04-27 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000593 | CLASS 2
076551C-000R-MR-0570-002 | MATERIAL REQUISITION FOR TRAYS AND INTERNALS FOR COLUMNS | SULZER INDIA PRIVATE LIMITED | 018C0002-I | 9053210-001-011 | 018-C-GAD-40237-001 | GENERAL ARRANGEMENT OF 018C0002 (EX BAPCO N. 018-C-GAD-00237-001) | A2001 | BX | 2 | 2019-03-12 | CON-BMP-VTRA-010654 | 2019-03-12 | FOR BAPCO REVIEW | 2019-03-26 | 2019-03-27 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000394 | CLASS 2
076551C-000R-MR-0570-002 | MATERIAL REQUISITION FOR TRAYS AND INTERNALS FOR COLUMNS | SULZER INDIA PRIVATE LIMITED | 018C0002-I | 9053210-001-012 | 018-C-GAD-40238-001 | GENERAL ATTACHMENT DRAWING OF 018C0002 | A1110 | BX | 2 | 2019-06-05 | CON-BMP-VTRA-012011 | 2019-06-05 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0570-002 | MATERIAL REQUISITION FOR TRAYS AND INTERNALS FOR COLUMNS | SULZER INDIA PRIVATE LIMITED | 018C0002-I | 9053210_HCAL_018C0002 | 018-C-CAL-40050-001 | HYDRAULIC CALCULATION OF 018C0002 (EX BAPCO N.018-C-CAL- 00050-001) | A1003 | CX | 4 | 2019-03-08 | CON-BMP-VTRA-010638 | 2019-03-08 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0570-002 | MATERIAL REQUISITION FOR TRAYS AND INTERNALS FOR COLUMNS | SULZER INDIA PRIVATE LIMITED | 018C0002-I | 9053210_ITP | 018-C-PQP-40021-001 | QUALITY CONTROL PLAN (ITP) 018C0002 (EX BAPCO N. 000-C-PQP-60002-001) | B1002 | 0X | 3 | 2019-06-20 | CON-BMP-VTRA-012333 | 2019-06-20 | FOR BAPCO REVIEW | 2019-07-05 | 2019-07-10 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001247 | CLASS 2
076551C-000R-MR-0570-002 | MATERIAL REQUISITION FOR TRAYS AND INTERNALS FOR COLUMNS | SULZER INDIA PRIVATE LIMITED | 018C0002-I | 9053210_MCAL_018C0002 | 018-C-CAL-40049-001 | MECHANICAL CALCULATION OF 018C0002-I | A1003 | 0X | 2 | 2019-06-29 | CON-BMP-VTRA-012578 | 2019-06-29 | FOR BAPCO REVIEW | 2019-07-15 |  |  | CLASS 2
076551C-000R-MR-0570-002 | MATERIAL REQUISITION FOR TRAYS AND INTERNALS FOR COLUMNS | SULZER INDIA PRIVATE LIMITED | 018C0002-I | 9053210_SCAL_018C0002 | 018-C-CAL-40161-001 | STRENGTH CALCULATIONS OF INTERNALS_018C0002-I | A1003 | 0X | 2 | 2019-07-12 | CON-BMP-VTRA-012831 | 2019-07-12 | FOR BAPCO REVIEW | 2019-07-26 |  |  | CLASS 2
076551C-000R-MR-0570-002 | MATERIAL REQUISITION FOR TRAYS AND INTERNALS FOR COLUMNS | SULZER INDIA PRIVATE LIMITED | 018C0005-I | 9053210-002-001 | 018-C-GAD-40244-001 | VEP DISTRIBUTOR -ID 2450MM 018C0005 | A1111 | AXX | 2 | 2019-04-29 | CON-BMP-VTRA-011305 | 2019-04-29 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0570-002 | MATERIAL REQUISITION FOR TRAYS AND INTERNALS FOR COLUMNS | SULZER INDIA PRIVATE LIMITED | 018C0005-I | 9053210-002-003 | 018-C-GAD-40245-001 | TSB SUPPORT GRID -ID 2450MM 018C0005 | A1111 | AXX | 2 | 2019-04-29 | CON-BMP-VTRA-011305 | 2019-04-29 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0570-002 | MATERIAL REQUISITION FOR TRAYS AND INTERNALS FOR COLUMNS | SULZER INDIA PRIVATE LIMITED | 018C0005-I | 9053210-002-005 | 018-C-GAD-40246-001 | LTE -ID 2450MM 018C0005 | A1111 | AXX | 2 | 2019-04-29 | CON-BMP-VTRA-011305 | 2019-04-29 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0570-002 | MATERIAL REQUISITION FOR TRAYS AND INTERNALS FOR COLUMNS | SULZER INDIA PRIVATE LIMITED | 018C0005-I | 9053210-002-007 | 018-C-GAD-40247-001 | LTS -ID 2450MM 018C0005 | A1111 | AXX | 2 | 2019-04-29 | CON-BMP-VTRA-011305 | 2019-04-29 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0570-002 | MATERIAL REQUISITION FOR TRAYS AND INTERNALS FOR COLUMNS | SULZER INDIA PRIVATE LIMITED | 018C0005-I | 9053210-002-009 | 018-C-GAD-40242-001 | GENERAL ARRANGEMENT OF 018C0005 (EX BAPCO N.018-C-GAD-00242-001) | A2001 | CX | 2 | 2019-04-01 | CON-BMP-VTRA-010938 | 2019-04-01 | FOR BAPCO REVIEW | 2019-04-15 | 2019-05-03 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000631 | CLASS 2
076551C-000R-MR-0570-002 | MATERIAL REQUISITION FOR TRAYS AND INTERNALS FOR COLUMNS | SULZER INDIA PRIVATE LIMITED | 018C0005-I | 9053210-002-010 | 018-C-GAD-40243-001 | GENERAL ATTACHMENT DRAWING OF 018C0005 | A1110 | BX | 2 | 2019-04-01 | CON-BMP-VTRA-010936 | 2019-04-01 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0570-002 | MATERIAL REQUISITION FOR TRAYS AND INTERNALS FOR COLUMNS | SULZER INDIA PRIVATE LIMITED | 018C0005-I | 9053210_HCAL_018C0005 | 018-C-CAL-40052-001 | HYDRAULIC CALCULATION OF 018C0005 (EX BAPCO N.018-C-CAL- 00052-001) | A1003 | CX | 4 | 2019-03-08 | CON-BMP-VTRA-010638 | 2019-03-08 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0570-002 | MATERIAL REQUISITION FOR TRAYS AND INTERNALS FOR COLUMNS | SULZER INDIA PRIVATE LIMITED | 018C0005-I | 9053210_ITP_2 | 018-C-PQP-40022-001 | QUALITY CONTROL PLAN (ITP) OF 018C0005 | B1002 | 0X | 3 | 2019-06-20 | CON-BMP-VTRA-012333 | 2019-06-20 | FOR BAPCO REVIEW | 2019-07-05 | 2019-07-10 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001247 | CLASS 2
076551C-000R-MR-0570-002 | MATERIAL REQUISITION FOR TRAYS AND INTERNALS FOR COLUMNS | SULZER INDIA PRIVATE LIMITED | 018C0005-I | 9053210_MCAL_018C0005 | 018-C-CAL-40051-001 | MECHANICAL CALCULATION OF 018C0005 | A1003 | CX | 3 | 2019-04-15 | CON-BMP-VTRA-011177 | 2019-04-15 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0570-002 | MATERIAL REQUISITION FOR TRAYS AND INTERNALS FOR COLUMNS | SULZER INDIA PRIVATE LIMITED | 021C0002-I | 9053210-005-001 | 021-C-GAD-40046-001 | HIGH PRESSURE ABSORBER 2X1 PASS RV1 TRAYS ID:1375 021C0002-I | A1111 | AX | 2 | 2019-07-08 | CON-BMP-VTRA-012707 | 2019-07-08 | FOR BAPCO REVIEW | 2019-07-22 |  |  | CLASS 2
076551C-000R-MR-0570-002 | MATERIAL REQUISITION FOR TRAYS AND INTERNALS FOR COLUMNS | SULZER INDIA PRIVATE LIMITED | 021C0002-I | 9053210-005-005 | 021-C-GAD-40043-001 | GENERAL ARRANGEMENT OF 021C0002 (EX BAPCO N.021-C-GAD-00043-001) | A2001 | CX | 2 | 2019-07-08 | CON-BMP-VTRA-012738 | 2019-07-08 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0570-002 | MATERIAL REQUISITION FOR TRAYS AND INTERNALS FOR COLUMNS | SULZER INDIA PRIVATE LIMITED | 021C0002-I | 9053210-005-006 | 021-C-GAD-40044-001 | GENERAL ATTACHMENT DRAWING OF 021C0002 | A1110 | BX | 2 | 2019-07-08 | CON-BMP-VTRA-012706 | 2019-07-08 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0570-002 | MATERIAL REQUISITION FOR TRAYS AND INTERNALS FOR COLUMNS | SULZER INDIA PRIVATE LIMITED | 021C0002-I | 9053210_HCAL_021C0002 | 021-C-CAL-40008-001 | HYDRAULIC CALCULATION OF 021C0002 (EX BAPCO N.021-CCAL- 00008-001) | A1003 | DX | 2 | 2019-05-24 | CON-BMP-VTRA-011780 | 2019-05-24 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0570-002 | MATERIAL REQUISITION FOR TRAYS AND INTERNALS FOR COLUMNS | SULZER INDIA PRIVATE LIMITED | 021C0002-I | 9053210_ITP_5 | 021-C-PQP-40003-001 | QUALITY CONTROL PLAN (ITP) OF 021C0002 | B1002 | 0X | 3 | 2019-06-20 | CON-BMP-VTRA-012334 | 2019-06-20 | FOR BAPCO REVIEW | 2019-07-05 | 2019-07-04 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001162 | CLASS 2
076551C-000R-MR-0570-002 | MATERIAL REQUISITION FOR TRAYS AND INTERNALS FOR COLUMNS | SULZER INDIA PRIVATE LIMITED | 021C0002-I | 9053210_MCAL_021C0002 | 021-C-CAL-40007-001 | MECHANICAL CALCULATION OF 021C0002 | A1003 | AXX | 2 | 2019-04-09 | CON-BMP-VTRA-011067 | 2019-04-09 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0570-002 | MATERIAL REQUISITION FOR TRAYS AND INTERNALS FOR COLUMNS | SULZER INDIA PRIVATE LIMITED | 021C0003-I | 9053210-004-007 | 021-C-GAD-40037-001 | FEED INLET DISTRIBUTOR AT NOZZLE N2 FOR 021C0003 & STRIPPER | A1111 | AXX | 2 | 2019-05-21 | CON-BMP-VTRA-011686 | 2019-05-21 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0570-002 | MATERIAL REQUISITION FOR TRAYS AND INTERNALS FOR COLUMNS | SULZER INDIA PRIVATE LIMITED | 021C0003-I | 9053210-004-017 | 021-C-GAD-40038-001 | FEED INLET DISTRIBUTOR AT NOZZLE N3 FOR 021C0003 & STRIPPER | A1111 | AXX | 2 | 2019-05-21 | CON-BMP-VTRA-011686 | 2019-05-21 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0570-002 | MATERIAL REQUISITION FOR TRAYS AND INTERNALS FOR COLUMNS | SULZER INDIA PRIVATE LIMITED | 021C0003-I | 9053210-004-019 | 021-C-GAD-40034-001 | GENERAL ARRANGEMENT OF 021C0003 (EX BAPCO N.021-C-GAD-00034-001) | A2001 | BX | 2 | 2019-02-04 | CON-BMP-VTRA-010347 | 2019-02-04 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0570-002 | MATERIAL REQUISITION FOR TRAYS AND INTERNALS FOR COLUMNS | SULZER INDIA PRIVATE LIMITED | 021C0003-I | 9053210-004-020 | 021-C-GAD-40035-001 | GENERAL ATTACHMENT DRAWING OF 021C0003 | A1110 | AXX | 2 | 2019-03-29 | CON-BMP-VTRA-010919 | 2019-03-29 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0570-002 | MATERIAL REQUISITION FOR TRAYS AND INTERNALS FOR COLUMNS | SULZER INDIA PRIVATE LIMITED | 021C0003-I | 9053210_HCAL_021C0003 | 021-C-CAL-40006-001 | HYDRAULIC CALCULATION OF 021C0003 (EX BAPCO N.021-CCAL- 00006-001) | A1003 | 0X | 4 | 2019-06-26 | CON-BMP-VTRA-012484 | 2019-06-26 | FOR BAPCO REVIEW | 2019-07-11 |  |  | CLASS 2
076551C-000R-MR-0570-002 | MATERIAL REQUISITION FOR TRAYS AND INTERNALS FOR COLUMNS | SULZER INDIA PRIVATE LIMITED | 021C0003-I | 9053210_ITP_4 | 021-C-PQP-40002-001 | QUALITY CONTROL PLAN (ITP) OF 021C0003 | B1002 | 0X | 3 | 2019-06-20 | CON-BMP-VTRA-012334 | 2019-06-20 | FOR BAPCO REVIEW | 2019-07-05 | 2019-07-04 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001162 | CLASS 2
076551C-000R-MR-0570-002 | MATERIAL REQUISITION FOR TRAYS AND INTERNALS FOR COLUMNS | SULZER INDIA PRIVATE LIMITED | 021C0003-I | 9053210_MCAL_021C0003 | 021-C-CAL-40005-001 | MECHANICAL CALCULATION OF 021C0003 | A1003 | AXX | 2 | 2019-04-09 | CON-BMP-VTRA-011067 | 2019-04-09 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0570-002 | MATERIAL REQUISITION FOR TRAYS AND INTERNALS FOR COLUMNS | SULZER INDIA PRIVATE LIMITED | 021C0004-I | 9053210-006-001 | 021-C-GAD-40049-001 | 3 X SIDE TO SIDE PAN TRAYS ID 3505 021C0004-I | A1111 | BX | 2 | 2019-07-08 | CON-BMP-VTRA-012709 | 2019-07-08 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0570-002 | MATERIAL REQUISITION FOR TRAYS AND INTERNALS FOR COLUMNS | SULZER INDIA PRIVATE LIMITED | 021C0004-I | 9053210-006-003 | 021-C-GAD-40047-001 | GENERAL ARRANGEMENT OF 021C0004 (EX BAPCO N.021-C-GAD-00047-001) | A2001 | CX | 2 | 2019-03-20 | CON-BMP-VTRA-010781 | 2019-03-20 | FOR BAPCO REVIEW | 2019-04-04 | 2019-04-04 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000453 | CLASS 2
076551C-000R-MR-0570-002 | MATERIAL REQUISITION FOR TRAYS AND INTERNALS FOR COLUMNS | SULZER INDIA PRIVATE LIMITED | 021C0004-I | 9053210-006-004 | 021-C-GAD-40048-001 | GENERAL ATTACHMENT DRAWING OF 021C0004 | A1110 | BX | 2 | 2019-03-20 | CON-BMP-VTRA-010783 | 2019-03-20 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0570-002 | MATERIAL REQUISITION FOR TRAYS AND INTERNALS FOR COLUMNS | SULZER INDIA PRIVATE LIMITED | 021C0004-I | 9053210_HCAL_021C0004 | 021-C-CAL-40010-001 | HYDRAULIC CALCULATION OF 021C0004 (EX BAPCO N.021-CCAL- 00010-001) | A1003 | DX | 2 | 2019-05-24 | CON-BMP-VTRA-011780 | 2019-05-24 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0570-002 | MATERIAL REQUISITION FOR TRAYS AND INTERNALS FOR COLUMNS | SULZER INDIA PRIVATE LIMITED | 021C0004-I | 9053210_ITP_6 | 021-C-PQP-40004-001 | QUALITY CONTROL PLAN (ITP) OF 021C0004 | B1002 | 0X | 3 | 2019-06-20 | CON-BMP-VTRA-012334 | 2019-06-20 | FOR BAPCO REVIEW | 2019-07-05 | 2019-07-04 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001162 | CLASS 2
076551C-000R-MR-0570-002 | MATERIAL REQUISITION FOR TRAYS AND INTERNALS FOR COLUMNS | SULZER INDIA PRIVATE LIMITED | 021C0004-I | 9053210_MCAL_021C0004 | 021-C-CAL-40009-001 | MECHANICAL CALCULATION OF 021C0004 | A1003 | AXX | 2 | 2019-04-09 | CON-BMP-VTRA-011067 | 2019-04-09 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0570-002 | MATERIAL REQUISITION FOR TRAYS AND INTERNALS FOR COLUMNS | SULZER INDIA PRIVATE LIMITED | 021C0004-I | 9053210_SCAL_021C0004 | 021-C-CAL-40031-001 | STRENGTH CALCULATIONS OF INTERNALS 021C0004 | A1003 | AX | 2 | 2019-05-24 | CON-BMP-VTRA-011798 | 2019-05-24 | FOR BAPCO REVIEW | 2019-06-10 | 2019-06-16 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000936 | CLASS 2
076551C-000R-MR-0570-002 | MATERIAL REQUISITION FOR TRAYS AND INTERNALS FOR COLUMNS | SULZER INDIA PRIVATE LIMITED | 021V0005-I | 9053210-007-003 | 021-C-GAD-40051-001 | GENERAL ARRANGEMENT & ATTACHMENT OF 021V0005 | A2001 | AXX | 2 | 2019-05-31 | CON-BMP-VTRA-011888 | 2019-05-31 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0570-002 | MATERIAL REQUISITION FOR TRAYS AND INTERNALS FOR COLUMNS | SULZER INDIA PRIVATE LIMITED | 023C0001-I | 9053210-008-001 | 023-C-GAD-40010-001 | OFFGAS AMINE ABSORBER 22X1 PASS RV1 TRAYS ID 2415 023C0001-I | A1111 | AX | 2 | 2019-07-08 | CON-BMP-VTRA-012710 | 2019-07-08 | FOR BAPCO REVIEW | 2019-07-22 |  |  | CLASS 2
076551C-000R-MR-0570-002 | MATERIAL REQUISITION FOR TRAYS AND INTERNALS FOR COLUMNS | SULZER INDIA PRIVATE LIMITED | 023C0001-I | 9053210-008-005 | 023-C-GAD-40007-001 | GENERAL ARRANGEMENT OF 023C0001 (EX BAPCO N.023-C-GAD-00007-001) | A2001 | CXX | 2 | 2019-04-26 | CON-BMP-VTRA-011270 | 2019-04-26 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0570-002 | MATERIAL REQUISITION FOR TRAYS AND INTERNALS FOR COLUMNS | SULZER INDIA PRIVATE LIMITED | 023C0001-I | 9053210-008-006 | 023-C-GAD-40008-001 | GENERAL ATTACHMENT DRAWING OF 023C0001 | A1110 | BX | 2 | 2019-04-09 | CON-BMP-VTRA-011069 | 2019-04-09 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0570-002 | MATERIAL REQUISITION FOR TRAYS AND INTERNALS FOR COLUMNS | SULZER INDIA PRIVATE LIMITED | 023C0001-I | 9053210_HCAL_023C0001 | 023-C-CAL-40002-001 | HYDRAULIC CALCULATION OF 023C0001 (EX BAPCO N.023-C-CAL- 00002-001) | A1003 | DX | 2 | 2019-05-24 | CON-BMP-VTRA-011780 | 2019-05-24 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0570-002 | MATERIAL REQUISITION FOR TRAYS AND INTERNALS FOR COLUMNS | SULZER INDIA PRIVATE LIMITED | 023C0001-I | 9053210_ITP_7 | 023-C-PQP-40001-001 | QUALITY CONTROL PLAN (ITP) OF 023C0001 | B1002 | 0X | 3 | 2019-06-20 | CON-BMP-VTRA-012335 | 2019-06-20 | FOR BAPCO REVIEW | 2019-07-05 | 2019-07-02 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001138 | CLASS 2
076551C-000R-MR-0570-002 | MATERIAL REQUISITION FOR TRAYS AND INTERNALS FOR COLUMNS | SULZER INDIA PRIVATE LIMITED | 023C0001-I | 9053210_MCAL_023C0001 | 023-C-CAL-40001-001 | MECHANICAL CALCULATION OF 023C0001 | A1003 | AXX | 2 | 2019-03-29 | CON-BMP-VTRA-010920 | 2019-03-29 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E1001 | 29-18/SC | 000-E-TPS-40015-001 | PROCEDURE FOR SCREENING TEST OF THE 1.25CR- 0.5MO AND 2.25CR-1MO WELDING CONSUMABLES ALL ITEMS | B1203 | AX | 2 | 2019-04-09 | CON-BMP-VTRA-011071 | 2019-04-09 | FOR BAPCO REVIEW | 2019-04-24 | 2019-04-21 | 1-APPROVED BMP-ROC-VTRE-000540 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E1001 | 2918-MS | 000-E-TSP-40008-001 | MATERIAL SPECIFICATION ALL ITEMS | B1203 | 0X | 3 | 2019-06-19 | CON-BMP-VTRA-012283 | 2019-06-19 | FOR BAPCO REVIEW | 2019-07-03 | 2019-07-09 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001233 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E1001 | 2918-NDE/SUB | 000-E-PRO-40021-001 | NDE PROCEDURE-SUB SUPPLIERS ALL ITEMS | B1202 | 0X | 3 | 2019-06-14 | CON-BMP-VTRA-012231 | 2019-06-14 | FOR BAPCO REVIEW | 2019-07-01 | 2019-06-29 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001081 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E1001 | 2918-PAINT | 000-E-TSP-40007-001 | PAINT SPECIFICATION ALL ITEMS | A0106 | AX | 2 | 2019-05-16 | CON-BMP-VTRA-011645 | 2019-05-16 | FOR BAPCO REVIEW | 2019-05-31 | 2019-05-27 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000797 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E1001 | 2918-PR | 000-E-MRS-40003-001 | MONTHLY PROGRESS REPORT ALL ITEMS | C1002 | 0X | 4 | 2019-06-18 | CON-BMP-VTRA-012260 | 2019-06-18 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E1001 | 2918-PS | 000-E-SCH-40001-001 | PRODUCTION SCHEDULE ALL ITEMS | C1001 | AX | 2 | 2019-01-15 | CON-BMP-VTRA-010218 | 2019-01-15 | FOR BAPCO INFORMATION |  | 2019-02-05 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000154 | CLASS 3
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E1001 | 2918-SDI | 000-E-INX-40005-001 | SUPPLIER DOCUMENT INDEX ALL ITEMS | A0001 | BX | 4 | 2019-01-30 | CON-BMP-VTRA-010323 | 2019-01-30 | FOR BAPCO REVIEW | 2019-02-13 | 2019-02-13 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000179 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E1001 | 2918-UO | 000-E-INV-40002-001 | UNPRICED COPY OF MAIN SUBORDERS ALL ITEMS | C1005 | BX | 4 | 2019-01-30 | CON-BMP-VTRA-010325 | 2019-01-30 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E1001 | 2918-WCPS | 000-E-TSP-40016-001 | PURCHASE SPECIFICATIONS FOR WELDING CONSUMABLE ALL ITEMS | B1203 | AX | 2 | 2019-03-08 | CON-BMP-VTRA-010621 | 2019-03-08 | FOR BAPCO REVIEW | 2019-03-22 | 2019-03-26 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000380 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E1001 | 2918/NDE | 000-E-PRO-40007-001 | NDE PROCEDURE FOR HIGH PRESSURE HEAT EXCHANGERS ALL ITEMS | B1202 | AX | 2 | 2019-06-06 | CON-BMP-VTRA-012062 | 2019-06-06 | FOR BAPCO REVIEW | 2019-06-20 | 2019-06-16 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000957 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E1001 | 2918/VP | 000-E-PRO-40008-001 | VERIFICATION PROCEDURE ALL ITEMS09 | B1103 | 0X | 2 | 2019-06-19 | CON-BMP-VTRA-012290 | 2019-06-19 | FOR BAPCO REVIEW | 2019-07-03 | 2019-07-02 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001137 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E1001 | 6086 | 018-E-GAD-40173-001 | TRAIN 1 RG+H2 PREHEAT EXCHANGER NO.2 GENERAL ARRANGEMENT 018E1001 | A1103 | BX | 2 | 2019-04-11 | CON-BMP-VTRA-011131 | 2019-04-11 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E1001 | 6086-A1 | 018-E-GAD-40185-001 | TUBE BUNDLE DWG. 018E1001 | A1109 | AX | 2 | 2019-03-28 | CON-BMP-VTRA-010888 | 2019-03-28 | FOR BAPCO REVIEW | 2019-04-12 | 2019-05-13 | 3-REVIEWED WITH COMMENTS BMP-ROC-VTRE-000663 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E1001 | 6086-A2 | 018-E-GAD-40101-001 | CHANNEL DETAILS DWG 018E1001 | A1109 | AX | 2 | 2019-03-28 | CON-BMP-VTRA-010888 | 2019-03-28 | FOR BAPCO REVIEW | 2019-04-12 | 2019-05-13 | 3-REVIEWED WITH COMMENTS BMP-ROC-VTRE-000663 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E1001 | 6086-A3 | 018-E-GAD-40102-001 | NOZZLE DETAIL DWG. 018E1001 | A1109 | AX | 2 | 2019-06-07 | CON-BMP-VTRA-012104 | 2019-06-07 | FOR BAPCO REVIEW | 2019-06-24 | 2019-07-02 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001144 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E1001 | 6086-A4 | 018-E-GAD-40103-001 | PASS PARTITION DETAILS DWG. 018E1001 | A1109 | AX | 2 | 2019-03-28 | CON-BMP-VTRA-010888 | 2019-03-28 | FOR BAPCO REVIEW | 2019-04-12 | 2019-05-13 | 3-REVIEWED WITH COMMENTS BMP-ROC-VTRE-000663 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E1001 | 6086-A5 | 018-E-GAD-40104-001 | SADDLE DETAIL DWG 018E1001 | A1109 | AX | 2 | 2019-03-28 | CON-BMP-VTRA-010888 | 2019-03-28 | FOR BAPCO REVIEW | 2019-04-12 | 2019-05-13 | 3-REVIEWED WITH COMMENTS BMP-ROC-VTRE-000663 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E1001 | 6086-B1 | 018-E-GAD-40186-001 | PART LIST 018E1001 | A1109 | AX | 2 | 2019-03-28 | CON-BMP-VTRA-010888 | 2019-03-28 | FOR BAPCO REVIEW | 2019-04-12 | 2019-05-13 | 3-REVIEWED WITH COMMENTS BMP-ROC-VTRE-000663 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E1001 | 6086-BT | 018-E-TSP-40001-001 | BOLT TIGHTENING PROCEDURE 018E1001 | A1202 | AX | 2 | 2019-04-15 | CON-BMP-VTRA-011180 | 2019-04-15 | FOR BAPCO REVIEW | 2019-04-30 | 2019-05-15 | 3-REVIEWED WITH COMMENTS BMP-ROC-VTRE-000686 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E1001 | 6086-C1 | 018-E-DLB-40001-001 | NAMEPLATE DWG 018E1001 | A1112 | AX | 2 | 2019-03-28 | CON-BMP-VTRA-010886 | 2019-03-28 | FOR BAPCO REVIEW | 2019-04-12 | 2019-05-15 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000680 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E1001 | 6086-E | 018-E-CAL-40033-001 | PRESSURE CALCULATION 018E1001 | A1003 | BX | 2 | 2019-03-28 | CON-BMP-VTRA-010887 | 2019-03-28 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E1001 | 6086-G | 018-E-CAL-40034-001 | SUPPORT CALCULATION 018E1001 | A1003 | BX | 2 | 2019-03-28 | CON-BMP-VTRA-010887 | 2019-03-28 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E1001 | 6086-G1 | 018-E-GAD-40187-001 | GASKET DWG. 018E1001 | A1109 | AX | 2 | 2019-03-28 | CON-BMP-VTRA-010889 | 2019-03-28 | FOR BAPCO REVIEW | 2019-04-12 | 2019-05-14 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000670 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E1001 | 6086-HT | 018-E-PRO-40001-001 | HEAT TREATMENT PROCEDURE 018E1001 | B1201 | AX | 2 | 2019-01-15 | CON-BMP-VTRA-010217 | 2019-01-15 | FOR BAPCO REVIEW | 2019-01-29 | 2019-02-04 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000152 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E1001 | 6086-WP | 018-E-MCD-40001-001 | WELDING BOOK 018E1001 | B1304 | AX | 2 | 2019-01-30 | CON-BMP-VTRA-010326 | 2019-01-30 | FOR BAPCO REVIEW | 2019-02-13 | 2019-02-07 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000160 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E1001 | 6983-ITP | 018-E-PQP-40013-001 | FABRICATION AND QUALITY CONTROL PLAN 018E1001 | B1002 | 0AX | 2 | 2019-07-10 | CON-BMP-VTRA-012788 | 2019-07-10 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E1001 | Q/QA.0113-29-18 | 000-E-PRO-40022-001 | GENERAL PROCEDURE FOR: PREHEATING INTERPASS POSTHEATING INTERMEDIATE STRESS RELIEF ALL ITEMS | B1201 | AX | 2 | 2019-05-16 | CON-BMP-VTRA-011644 | 2019-05-17 | FOR BAPCO REVIEW | 2019-05-31 | 2019-05-29 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000831 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E1002 | 6087 | 018-E-GAD-40175-001 | TRAIN 2 - FEED PREHEAT EXCHANGER GENERAL ARRANGEMENT 018E1002 | A1103 | BX | 2 | 2019-04-11 | CON-BMP-VTRA-011131 | 2019-04-11 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E1002 | 6087-A1 | 018-E-GAD-40193-001 | TRAIN 2 - FEED PREHEAT EXCHANGER TUBE BUNDLE DWG. 018E1002 | A1109 | AX | 2 | 2019-04-12 | CON-BMP-VTRA-011133 | 2019-04-12 | FOR BAPCO REVIEW | 2019-04-26 | 2019-05-15 | 3-REVIEWED WITH COMMENTS BMP-ROC-VTRE-000690 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E1002 | 6087-A2 | 018-E-GAD-40113-001 | TRAIN 2 - FEED PREHEAT EXCHANGER CHANNEL DETAILS DWG. 018E1002 | A1109 | AX | 2 | 2019-04-11 | CON-BMP-VTRA-011130 | 2019-04-12 | FOR BAPCO REVIEW | 2019-04-26 | 2019-05-20 | 3-REVIEWED WITH COMMENTS BMP-ROC-VTRE-000714 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E1002 | 6087-A3 | 018-E-GAD-40114-001 | TRAIN 2 - FEED PREHEAT EXCHANGER NOZZLE DETAIL DWG.018E1002 | A1109 | AX | 2 | 2019-06-07 | CON-BMP-VTRA-012104 | 2019-06-07 | FOR BAPCO REVIEW | 2019-06-24 | 2019-07-02 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001144 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E1002 | 6087-A4 | 018-E-GAD-40115-001 | TRAIN 2 - FEED PREHEAT EXCHANGER NOZZLE DETAIL DWG.018E1002 | A1109 | AX | 2 | 2019-04-12 | CON-BMP-VTRA-011133 | 2019-04-12 | FOR BAPCO REVIEW | 2019-04-26 | 2019-05-15 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000690 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E1002 | 6087-A5 | 018-E-GAD-40116-001 | TRAIN 2 - FEED PREHEAT EXCHANGER PASS PARTITION DETAILS DWG. 018E1002 | A1109 | AX | 2 | 2019-04-12 | CON-BMP-VTRA-011133 | 2019-04-12 | FOR BAPCO REVIEW | 2019-04-26 | 2019-05-15 | 3-REVIEWED WITH COMMENTS BMP-ROC-VTRE-000690 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E1002 | 6087-A6 | 018-E-GAD-40117-001 | TRAIN 2 - FEED PREHEAT EXCHANGER SADDLE DETAIL DWG. 018E1002 | A1109 | AX | 2 | 2019-04-12 | CON-BMP-VTRA-011133 | 2019-04-12 | FOR BAPCO REVIEW | 2019-04-26 | 2019-05-15 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000690 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E1002 | 6087-B1 | 018-E-GAD-40194-001 | TRAIN 2 - FEED PREHEAT EXCHANGER PART LIST 018E1002 | A1109 | AX | 2 | 2019-04-12 | CON-BMP-VTRA-011133 | 2019-04-12 | FOR BAPCO REVIEW | 2019-04-26 | 2019-05-15 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000690 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E1002 | 6087-BT | 018-E-TSP-40003-001 | BOLT TIGHTENING PROCEDURE 018E1002 | A1202 | AX | 2 | 2019-04-15 | CON-BMP-VTRA-011180 | 2019-04-15 | FOR BAPCO REVIEW | 2019-04-30 | 2019-05-15 | 3-REVIEWED WITH COMMENTS BMP-ROC-VTRE-000686 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E1002 | 6087-C1 | 018-E-DLB-40003-001 | NAMEPLATE DWG 018E1002 | A1112 | AX | 2 | 2019-03-28 | CON-BMP-VTRA-010886 | 2019-03-28 | FOR BAPCO REVIEW | 2019-04-12 | 2019-05-15 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000680 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E1002 | 6087-E | 018-E-CAL-40041-001 | PRESSURE CALCULATION 018E1002 | A1003 | BX | 2 | 2019-04-11 | CON-BMP-VTRA-011127 | 2019-04-11 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E1002 | 6087-G | 018-E-CAL-40042-001 | SUPPORT CALCULATION 018E1002 | A1003 | BX | 2 | 2019-04-11 | CON-BMP-VTRA-011127 | 2019-04-11 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E1002 | 6087-G1 | 018-E-GAD-40195-001 | TRAIN 2 - FEED PREHEAT EXCHANGER GASKET DWG. 018E1002 | A1109 | AX | 2 | 2019-04-12 | CON-BMP-VTRA-011133 | 2019-04-12 | FOR BAPCO REVIEW | 2019-04-26 | 2019-05-15 | 3-REVIEWED WITH COMMENTS BMP-ROC-VTRE-000690 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E1002 | 6087-HT | 018-E-PRO-40003-001 | HEAT TREATMENT PROCEDURE 018E1002 | B1201 | AX | 2 | 2019-01-15 | CON-BMP-VTRA-010217 | 2019-01-15 | FOR BAPCO REVIEW | 2019-01-29 | 2019-02-04 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000152 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E1002 | 6087-WP | 018-E-MCD-40003-001 | WELDING BOOK 018E1002 | B1304 | AX | 2 | 2019-01-30 | CON-BMP-VTRA-010326 | 2019-01-30 | FOR BAPCO REVIEW | 2019-02-13 | 2019-02-07 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000160 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E1002 | 6985-ITP | 018-E-PQP-40015-001 | FABRICATION AND QUALITY CONTROL PLAN 18E1002 | B1002 | 0AX | 2 | 2019-07-10 | CON-BMP-VTRA-012788 | 2019-07-10 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E1003 | 6088 | 018-E-GAD-40177-001 | TRAIN 1 RG + H2 PREHEAT EXCHANGER NO.1 GENERAL ARRANGEMENT 018E1003 | A1103 | BX | 2 | 2019-04-11 | CON-BMP-VTRA-011131 | 2019-04-11 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E1003 | 6088-A1 | 018-E-GAD-40201-001 | TRAIN 1 RG + H2 PREHEAT EXCHANGER NO.1 TUBE BUNDLE DWG. 018E1003 | A1109 | AX | 2 | 2019-04-12 | CON-BMP-VTRA-011133 | 2019-04-12 | FOR BAPCO REVIEW | 2019-04-26 | 2019-05-15 | 3-REVIEWED WITH COMMENTS BMP-ROC-VTRE-000690 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E1003 | 6088-A2 | 018-E-GAD-40125-001 | TRAIN 1 - RG + H2 PREHEAT EXCHANGER N1 CHANNEL DETAILS DWG. 018E1003 | A1109 | AX | 2 | 2019-04-11 | CON-BMP-VTRA-011130 | 2019-04-12 | FOR BAPCO REVIEW | 2019-04-26 | 2019-05-20 | 3-REVIEWED WITH COMMENTS BMP-ROC-VTRE-000714 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E1003 | 6088-A3 | 018-E-GAD-40126-001 | NOZZLE DETAIL DWG. 018E1003 | A1109 | AX | 2 | 2019-06-07 | CON-BMP-VTRA-012104 | 2019-06-07 | FOR BAPCO REVIEW | 2019-06-24 | 2019-07-02 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001144 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E1003 | 6088-A4 | 018-E-GAD-40127-001 | TRAIN 1 RG + H2 PREHEAT EXCHANGER NO.1 PASS PARTITION DETAILS DWG. 018E1003 | A1109 | AX | 2 | 2019-04-12 | CON-BMP-VTRA-011133 | 2019-04-12 | FOR BAPCO REVIEW | 2019-04-26 | 2019-05-15 | 3-REVIEWED WITH COMMENTS BMP-ROC-VTRE-000690 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E1003 | 6088-A5 | 018-E-GAD-40128-001 | TRAIN 1 RG + H2 PREHEAT EXCHANGER NO.1 SADDLE DETAIL DWG. 018E1003 | A1109 | AX | 2 | 2019-04-12 | CON-BMP-VTRA-011133 | 2019-04-12 | FOR BAPCO REVIEW | 2019-04-26 | 2019-05-15 | 3-REVIEWED WITH COMMENTS BMP-ROC-VTRE-000690 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E1003 | 6088-B1 | 018-E-GAD-40202-001 | TRAIN 1 RG + H2 PREHEAT EXCHANGER NO.1 PART LIST 018E1003 | A1109 | AX | 2 | 2019-04-12 | CON-BMP-VTRA-011133 | 2019-04-12 | FOR BAPCO REVIEW | 2019-04-26 | 2019-05-15 | 3-REVIEWED WITH COMMENTS BMP-ROC-VTRE-000690 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E1003 | 6088-BT | 018-E-TSP-40005-001 | BOLT TIGHTENING PROCEDURE 018E1003 | A1202 | AX | 2 | 2019-04-15 | CON-BMP-VTRA-011180 | 2019-04-15 | FOR BAPCO REVIEW | 2019-04-30 | 2019-05-15 | 3-REVIEWED WITH COMMENTS BMP-ROC-VTRE-000686 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E1003 | 6088-C1 | 018-E-DLB-40005-001 | NAMEPLATE DWG 018E1003 | A1112 | AX | 2 | 2019-03-28 | CON-BMP-VTRA-010886 | 2019-03-28 | FOR BAPCO REVIEW | 2019-04-12 | 2019-05-15 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000680 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E1003 | 6088-E | 018-E-CAL-40049-001 | PRESSURE CALCULATION 018E1003 | A1003 | BX | 2 | 2019-04-11 | CON-BMP-VTRA-011126 | 2019-04-11 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E1003 | 6088-E-1 | 018-E-CAL-40053-001 | PRESSURE CALCULATION 018E1003 | A1003 | BX | 2 | 2019-04-11 | CON-BMP-VTRA-011126 | 2019-04-11 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E1003 | 6088-G | 018-E-CAL-40050-001 | SUPPORT CALCULATION 018E1003 | A1003 | BX | 2 | 2019-04-11 | CON-BMP-VTRA-011126 | 2019-04-11 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E1003 | 6088-G1 | 018-E-GAD-40203-001 | TRAIN 1 RG + H2 PREHEAT EXCHANGER NO.1 GASKET DWG. 018E1003 | A1109 | AX | 2 | 2019-04-12 | CON-BMP-VTRA-011133 | 2019-04-12 | FOR BAPCO REVIEW | 2019-04-26 | 2019-05-15 | 3-REVIEWED WITH COMMENTS BMP-ROC-VTRE-000690 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E1003 | 6088-HT | 018-E-PRO-40005-001 | HEAT TREATMENT PROCEDURE 018E1003 | B1201 | AX | 2 | 2019-01-15 | CON-BMP-VTRA-010217 | 2019-01-15 | FOR BAPCO REVIEW | 2019-01-29 | 2019-02-04 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000152 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E1003 | 6088-WP | 018-E-MCD-40005-001 | WELDING BOOK 018E1003 | B1304 | AX | 2 | 2019-01-30 | CON-BMP-VTRA-010326 | 2019-01-30 | FOR BAPCO REVIEW | 2019-02-13 | 2019-02-07 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000160 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E1003 | 6987-ITP | 018-E-PQP-40017-001 | FABRICATION AND QUALITY CONTROL PLAN 018E1003 | B1002 | 0AX | 2 | 2019-07-10 | CON-BMP-VTRA-012788 | 2019-07-10 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E1004 | 6089 | 018-E-GAD-40179-001 | TRAIN 1 HP/HT STEAM GENERATOR GENERAL ARRANGEMENT 018E1004 | A1103 | BX | 2 | 2019-04-11 | CON-BMP-VTRA-011131 | 2019-04-11 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E1004 | 6089-A1 | 018-E-GAD-40209-001 | TRAIN 1 HP/HT VAPOR STEAM GENERATOR TUBE BUNDLE DWG 018E1004 | A1109 | AX | 2 | 2019-04-12 | CON-BMP-VTRA-011133 | 2019-04-12 | FOR BAPCO REVIEW | 2019-04-26 | 2019-05-15 | 3-REVIEWED WITH COMMENTS BMP-ROC-VTRE-000690 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E1004 | 6089-A2 | 018-E-GAD-40137-001 | TRAIN 1 HP/HT STEAM GENERATOR CHANNEL DETAILS DWG. 018E1004 | A1109 | AX | 2 | 2019-04-11 | CON-BMP-VTRA-011130 | 2019-04-12 | FOR BAPCO REVIEW | 2019-04-26 | 2019-05-20 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000714 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E1004 | 6089-A3 | 018-E-GAD-40138-001 | NOZZLE DETAIL DWG 018E1004 | A1109 | AX | 2 | 2019-06-07 | CON-BMP-VTRA-012104 | 2019-06-07 | FOR BAPCO REVIEW | 2019-06-24 | 2019-07-02 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001144 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E1004 | 6089-A4 | 018-E-GAD-40139-001 | TRAIN 1 HP/HT VAPOR STEAM GENERATOR NOZZLE DETAIL DWG 018E1004 | A1109 | AX | 2 | 2019-04-12 | CON-BMP-VTRA-011133 | 2019-04-12 | FOR BAPCO REVIEW | 2019-04-26 | 2019-05-15 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000690 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E1004 | 6089-A5 | 018-E-GAD-40140-001 | TRAIN 1 HP/HT STEAM GENERATOR PASS PARTITION DETAILS DWG 018E1004 | A1109 | AX | 2 | 2019-04-12 | CON-BMP-VTRA-011137 | 2019-04-12 | FOR BAPCO REVIEW | 2019-04-26 | 2019-05-15 | 3-REVIEWED WITH COMMENTS BMP-ROC-VTRE-000681 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E1004 | 6089-A6 | 018-E-GAD-40141-001 | TRAIN 1 HP/HT STEAM GENERATOR SADDLE DETAIL DWG 018E1004 | A1109 | AX | 2 | 2019-04-12 | CON-BMP-VTRA-011137 | 2019-04-12 | FOR BAPCO REVIEW | 2019-04-26 | 2019-05-15 | 3-REVIEWED WITH COMMENTS BMP-ROC-VTRE-000681 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E1004 | 6089-B1 | 018-E-GAD-40210-001 | TRAIN 1 HP/HT STEAM GENERATOR PART LIST 018E1004 | A1109 | AX | 2 | 2019-04-12 | CON-BMP-VTRA-011137 | 2019-04-12 | FOR BAPCO REVIEW | 2019-04-26 | 2019-05-15 | 3-REVIEWED WITH COMMENTS BMP-ROC-VTRE-000681 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E1004 | 6089-BT | 018-E-TSP-40007-001 | BOLT TIGHTENING PROCEDURE 018E1004 | A1202 | AX | 2 | 2019-04-15 | CON-BMP-VTRA-011180 | 2019-04-15 | FOR BAPCO REVIEW | 2019-04-30 | 2019-05-15 | 3-REVIEWED WITH COMMENTS BMP-ROC-VTRE-000686 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E1004 | 6089-C1 | 018-E-DLB-40007-001 | NAMEPLATE DWG 018E1004 | A1112 | AX | 2 | 2019-03-28 | CON-BMP-VTRA-010886 | 2019-03-28 | FOR BAPCO REVIEW | 2019-04-12 | 2019-05-15 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000680 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E1004 | 6089-E | 018-E-CAL-40057-001 | PRESSURE CALCULATION 018E1004 | A1003 | BX | 2 | 2019-04-11 | CON-BMP-VTRA-011126 | 2019-04-11 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E1004 | 6089-G | 018-E-CAL-40058-001 | SUPPORT CALCULATION 018E1004 | A1003 | BX | 2 | 2019-04-11 | CON-BMP-VTRA-011126 | 2019-04-11 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E1004 | 6089-G1 | 018-E-GAD-40211-001 | TRAIN 1 HP/HT STEAM GENERATOR GASKET DWG 018E1004 | A1109 | AX | 2 | 2019-04-12 | CON-BMP-VTRA-011137 | 2019-04-12 | FOR BAPCO REVIEW | 2019-04-26 | 2019-05-15 | 3-REVIEWED WITH COMMENTS BMP-ROC-VTRE-000681 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E1004 | 6089-HT | 018-E-PRO-40007-001 | HEAT TREATMENT PROCEDURE 018E1004 | B1201 | AX | 2 | 2019-01-15 | CON-BMP-VTRA-010217 | 2019-01-15 | FOR BAPCO REVIEW | 2019-01-29 | 2019-02-04 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000152 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E1004 | 6089-WP | 018-E-MCD-40007-001 | WELDING BOOK 018E1004 | B1304 | AX | 2 | 2019-01-30 | CON-BMP-VTRA-010326 | 2019-01-30 | FOR BAPCO REVIEW | 2019-02-13 | 2019-02-07 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000160 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E1004 | 6989-ITP | 018-E-PQP-40019-001 | FABRICATION AND QUALITY CONTROL PLAN 018E1004 | B1002 | 0X | 2 | 2019-05-17 | CON-BMP-VTRA-011648 | 2019-05-17 | FOR BAPCO REVIEW | 2019-05-31 | 2019-05-30 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE- | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E1006 | 6090 | 018-E-GAD-40181-001 | GENERAL ARRANGEMENT 018E1006 | A1103 | BX | 2 | 2019-03-25 | CON-BMP-VTRA-010837 | 2019-03-25 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E1006 | 6090-A1 | 018-E-GAD-40217-001 | TUBE BUNDLE DWG. 018E1006 | A1109 | AX | 2 | 2019-03-19 | CON-BMP-VTRA-010744 | 2019-03-19 | FOR BAPCO REVIEW | 2019-04-03 | 2019-04-10 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000501 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E1006 | 6090-A2 | 018-E-GAD-40149-001 | CHANNEL DETAIL DWG 018E1006 | A1109 | AXX | 2 | 2019-03-25 | CON-BMP-VTRA-010857 | 2019-03-25 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E1006 | 6090-A3 | 018-E-GAD-40150-001 | NOZZLE DETAIL DWG.018E1006 | A1109 | AX | 2 | 2019-03-19 | CON-BMP-VTRA-010744 | 2019-03-19 | FOR BAPCO REVIEW | 2019-04-03 | 2019-04-10 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000501 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E1006 | 6090-A4 | 018-E-GAD-40151-001 | PASS PARTITION DETAIL DWG 018E1006 | A1109 | AX | 2 | 2019-03-19 | CON-BMP-VTRA-010744 | 2019-03-19 | FOR BAPCO REVIEW | 2019-04-03 | 2019-04-10 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000501 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E1006 | 6090-A5 | 018-E-GAD-40152-001 | SADDLE DETAIL DWG 018E1006 | A1109 | AX | 2 | 2019-03-19 | CON-BMP-VTRA-010744 | 2019-03-19 | FOR BAPCO REVIEW | 2019-04-03 | 2019-04-10 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000501 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E1006 | 6090-B1 | 018-E-GAD-40218-001 | PART LIST DWG. 018E1006 | A1109 | AX | 2 | 2019-03-19 | CON-BMP-VTRA-010744 | 2019-03-19 | FOR BAPCO REVIEW | 2019-04-03 | 2019-04-10 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000501 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E1006 | 6090-C1 | 018-E-DLB-40009-001 | NAMEPLATE DWG 018E1006 | A1112 | AX | 2 | 2019-03-25 | CON-BMP-VTRA-010842 | 2019-03-25 | FOR BAPCO REVIEW | 2019-04-09 | 2019-04-09 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000491 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E1006 | 6090-E | 018-E-CAL-40065-001 | PRESSURE CALCULATION 018E1006 | A1003 | BX | 2 | 2019-03-25 | CON-BMP-VTRA-010838 | 2019-03-25 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E1006 | 6090-FEA | 018-E-CAL-40068-001 | STRESS ANALYSIS OF BREECH LOCKZ SHAPE CHANNEL FORGING 018E1006 | A1003 | AX | 2 | 2019-07-10 | CON-BMP-VTRA-012790 | 2019-07-10 | FOR BAPCO REVIEW | 2019-07-24 |  |  | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E1006 | 6090-G | 018-E-CAL-40066-001 | SUPPORT CALCULATION 018E1006 | A1003 | BX | 4 | 2019-03-25 | CON-BMP-VTRA-010841 | 2019-03-25 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E1006 | 6090-G1 | 018-E-GAD-40219-001 | GASKET DWG 018E1006 | A1109 | AX | 2 | 2019-03-25 | CON-BMP-VTRA-010843 | 2019-03-25 | FOR BAPCO REVIEW | 2019-04-09 | 2019-05-09 | 3-REVIEWED WITH COMMENTS BMP-ROC-VTRE-000634 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E1006 | 6090-HT | 018-E-PRO-40009-001 | HEAT TREATMENT PROCEDURE 018E1006 | B1201 | AX | 2 | 2019-01-15 | CON-BMP-VTRA-010217 | 2019-01-15 | FOR BAPCO REVIEW | 2019-01-29 | 2019-02-04 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000152 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E1006 | 6090-WP | 018-E-MCD-40009-001 | WELDING BOOK 018E1006 | B1304 | AX | 2 | 2019-01-30 | CON-BMP-VTRA-010326 | 2019-01-30 | FOR BAPCO REVIEW | 2019-02-13 | 2019-02-07 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000160 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E1006 | 6991-ITP | 018-E-PQP-40021-001 | FABRICATION AND QUALITY CONTROL PLAN 018E1006 | B1002 | 0X | 2 | 2019-05-17 | CON-BMP-VTRA-011648 | 2019-05-17 | FOR BAPCO REVIEW | 2019-05-31 | 2019-05-30 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE- | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E1007 | 6091 | 018-E-GAD-40183-001 | GENERAL ARRANGEMENT 018E1007 | A1103 | BX | 2 | 2019-04-01 | CON-BMP-VTRA-010942 | 2019-04-01 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E1007 | 6091-A1 | 018-E-GAD-40225-001 | TUBE BUNDLE DWG. MEMBRANE FEED HEATER 018E1007 | A1109 | AX | 2 | 2019-04-01 | CON-BMP-VTRA-010940 | 2019-04-01 | FOR BAPCO REVIEW | 2019-04-15 | 2019-05-15 | 3-REVIEWED WITH COMMENTS BMP-ROC-VTRE-000678 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E1007 | 6091-A2 | 018-E-GAD-40161-001 | CHANNEL DETAIL DWG. MEMBRANE FEED HEATER 018E1007 | A1109 | AX | 2 | 2019-04-01 | CON-BMP-VTRA-010940 | 2019-04-01 | FOR BAPCO REVIEW | 2019-04-15 | 2019-05-15 | 3-REVIEWED WITH COMMENTS BMP-ROC-VTRE-000678 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E1007 | 6091-A3 | 018-E-GAD-40162-001 | NOZZLE DETAIL DWG. MEMBRANE FEED HEATER 018E1007 | A1109 | AX | 2 | 2019-04-01 | CON-BMP-VTRA-010940 | 2019-04-01 | FOR BAPCO REVIEW | 2019-04-15 | 2019-05-15 | 3-REVIEWED WITH COMMENTS BMP-ROC-VTRE-000678 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E1007 | 6091-A4 | 018-E-GAD-40163-001 | PASS PARTITION DETAIL DWG. - MEMBRANE FEED HEATER 018E1007 | A1109 | AX | 2 | 2019-04-01 | CON-BMP-VTRA-010940 | 2019-04-01 | FOR BAPCO REVIEW | 2019-04-15 | 2019-05-15 | 3-REVIEWED WITH COMMENTS BMP-ROC-VTRE-000678 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E1007 | 6091-A5 | 018-E-GAD-40164-001 | SADDLE DETAIL DWG. - MEMBRANE FEED HEATER 018E1007 | A1109 | AX | 2 | 2019-04-01 | CON-BMP-VTRA-010940 | 2019-04-01 | FOR BAPCO REVIEW | 2019-04-15 | 2019-05-15 | 3-REVIEWED WITH COMMENTS BMP-ROC-VTRE-000678 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E1007 | 6091-B1 | 018-E-GAD-40226-001 | PART LIST DWG. - MEMBRANE FEED HEATER 018E1007 | A1109 | AX | 2 | 2019-04-01 | CON-BMP-VTRA-010940 | 2019-04-01 | FOR BAPCO REVIEW | 2019-04-15 | 2019-05-15 | 3-REVIEWED WITH COMMENTS BMP-ROC-VTRE-000678 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E1007 | 6091-C1 | 018-E-DLB-40011-001 | NAMEPLATE DWG 018E1007 | A1112 | AX | 2 | 2019-03-28 | CON-BMP-VTRA-010886 | 2019-03-28 | FOR BAPCO REVIEW | 2019-04-12 | 2019-05-15 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000680 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E1007 | 6091-E | 018-E-CAL-40073-001 | PRESSURE CALCULATION 018E1007 | A1003 | BX | 2 | 2019-04-01 | CON-BMP-VTRA-010941 | 2019-04-01 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E1007 | 6091-FEA | 018-E-CAL-40076-001 | STRESS ANALYSIS OF BREECH LOCKZ SHAPE CHANNEL FORGING 018E1007 | A1003 | AX | 2 | 2019-07-10 | CON-BMP-VTRA-012790 | 2019-07-10 | FOR BAPCO REVIEW | 2019-07-24 |  |  | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E1007 | 6091-G | 018-E-CAL-40074-001 | SUPPORT CALCULATION 018E1007 | A1003 | BX | 2 | 2019-04-01 | CON-BMP-VTRA-010941 | 2019-04-01 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E1007 | 6091-G1 | 018-E-GAD-40227-001 | GASKET DWG. - MEMBRANE FEED HEATER 018E1007 | A1109 | AX | 2 | 2019-04-01 | CON-BMP-VTRA-010940 | 2019-04-01 | FOR BAPCO REVIEW | 2019-04-15 | 2019-05-15 | 3-REVIEWED WITH COMMENTS BMP-ROC-VTRE-000678 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E1007 | 6091-HT | 018-E-PRO-40011-001 | HEAT TREATMENT PROCEDURE 018E1007 | B1201 | AX | 2 | 2019-01-15 | CON-BMP-VTRA-010217 | 2019-01-15 | FOR BAPCO REVIEW | 2019-01-29 | 2019-02-04 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000152 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E1007 | 6091-WP | 018-E-MCD-40011-001 | WELDING BOOK 018E1007 | B1304 | AX | 2 | 2019-01-30 | CON-BMP-VTRA-010326 | 2019-01-30 | FOR BAPCO REVIEW | 2019-02-13 | 2019-02-07 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000160 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E1007 | 6993-ITP | 018-E-PQP-40023-001 | FABRICATION AND QUALITY CONTROL PLAN 018E1007 | B1002 | 0AX | 2 | 2019-07-10 | CON-BMP-VTRA-012792 | 2019-07-10 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E2001 | 6086-1 | 018-E-GAD-40174-001 | TRAIN 2 RG+H2 PREHEAT EXCHANGER NO.2 GENERAL ARRANGEMENT 018E2001 | A1103 | BX | 2 | 2019-04-11 | CON-BMP-VTRA-011131 | 2019-04-11 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E2001 | 6086-A1-1 | 018-E-GAD-40189-001 | TUBE BUNDLE DWG 018E2001 | A1109 | AX | 2 | 2019-03-28 | CON-BMP-VTRA-010888 | 2019-03-28 | FOR BAPCO REVIEW | 2019-04-12 | 2019-05-13 | 3-REVIEWED WITH COMMENTS BMP-ROC-VTRE-000663 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E2001 | 6086-A2-1 | 018-E-GAD-40107-001 | CHANNEL DETAILS DWG 018E2001 | A1109 | AX | 2 | 2019-03-28 | CON-BMP-VTRA-010888 | 2019-03-28 | FOR BAPCO REVIEW | 2019-04-12 | 2019-05-13 | 3-REVIEWED WITH COMMENTS BMP-ROC-VTRE-000663 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E2001 | 6086-A3-1 | 018-E-GAD-40108-001 | NOZZLE DETAIL DWG 018E2001 | A1109 | AX | 2 | 2019-03-28 | CON-BMP-VTRA-010888 | 2019-03-28 | FOR BAPCO REVIEW | 2019-04-12 | 2019-05-13 | 3-REVIEWED WITH COMMENTS BMP-ROC-VTRE-000663 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E2001 | 6086-A4-1 | 018-E-GAD-40109-001 | PASS PARTITION DETAILS DWG 018E2001 | A1109 | AX | 2 | 2019-03-28 | CON-BMP-VTRA-010888 | 2019-03-28 | FOR BAPCO REVIEW | 2019-04-12 | 2019-05-13 | 3-REVIEWED WITH COMMENTS BMP-ROC-VTRE-000663 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E2001 | 6086-A5-1 | 018-E-GAD-40110-001 | SADDLE DETAIL DWG 018E2001 | A1109 | AX | 2 | 2019-03-28 | CON-BMP-VTRA-010888 | 2019-03-28 | FOR BAPCO REVIEW | 2019-04-12 | 2019-05-13 | 3-REVIEWED WITH COMMENTS BMP-ROC-VTRE-000663 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E2001 | 6086-B1-1 | 018-E-GAD-40190-001 | PART LIST 018E2001 | A1109 | AX | 2 | 2019-03-28 | CON-BMP-VTRA-010888 | 2019-03-28 | FOR BAPCO REVIEW | 2019-04-12 | 2019-05-13 | 3-REVIEWED WITH COMMENTS BMP-ROC-VTRE-000663 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E2001 | 6086-BT-1 | 018-E-TSP-40002-001 | BOLT TIGHTENING PROCEDURE 018E2001 | A1202 | AX | 2 | 2019-04-15 | CON-BMP-VTRA-011180 | 2019-04-15 | FOR BAPCO REVIEW | 2019-04-30 | 2019-05-15 | 3-REVIEWED WITH COMMENTS BMP-ROC-VTRE-000686 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E2001 | 6086-C1-1 | 018-E-DLB-40002-001 | NAMEPLATE DWG 018E2001 | A1112 | AX | 2 | 2019-03-28 | CON-BMP-VTRA-010886 | 2019-03-28 | FOR BAPCO REVIEW | 2019-04-12 | 2019-05-15 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000680 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E2001 | 6086-E-1 | 018-E-CAL-40037-001 | PRESSURE CALCULATION 018E2001 | A1003 | BX | 2 | 2019-03-28 | CON-BMP-VTRA-010887 | 2019-03-28 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E2001 | 6086-G-1 | 018-E-CAL-40038-001 | SUPPORT CALCULATION 018E2001 | A1003 | BX | 2 | 2019-03-28 | CON-BMP-VTRA-010887 | 2019-03-28 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E2001 | 6086-G1-1 | 018-E-GAD-40191-001 | GASKET DWG 018E2001 | A1109 | AX | 2 | 2019-03-28 | CON-BMP-VTRA-010888 | 2019-03-28 | FOR BAPCO REVIEW | 2019-04-12 | 2019-05-13 | 3-REVIEWED WITH COMMENTS BMP-ROC-VTRE-000663 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E2001 | 6086-HT-1 | 018-E-PRO-40002-001 | HEAT TREATMENT PROCEDURE 018E2001 | B1201 | AX | 2 | 2019-01-15 | CON-BMP-VTRA-010217 | 2019-01-15 | FOR BAPCO REVIEW | 2019-01-29 | 2019-02-04 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000152 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E2001 | 6086-WP-1 | 018-E-MCD-40002-001 | WELDING BOOK 018E2001 | B1304 | AX | 2 | 2019-01-30 | CON-BMP-VTRA-010326 | 2019-01-30 | FOR BAPCO REVIEW | 2019-02-13 | 2019-02-07 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000160 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E2001 | 6984-ITP | 018-E-PQP-40014-001 | FABRICATION AND QUALITY CONTROL PLAN 18E20011 | B1002 | 0AX | 2 | 2019-07-10 | CON-BMP-VTRA-012788 | 2019-07-10 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E2002 | 6087-1 | 018-E-GAD-40176-001 | TRAIN 2 - FEED PREHEAT EXCHANGER GENERAL ARRANGEMENT 018E2002 | A1103 | BX | 2 | 2019-04-11 | CON-BMP-VTRA-011131 | 2019-04-11 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E2002 | 6087-A1-1 | 018-E-GAD-40197-001 | TRAIN 2 - FEED PREHEAT EXCHANGER TUBE BUNDLE DWG. 018E2002 | A1109 | AX | 2 | 2019-04-12 | CON-BMP-VTRA-011136 | 2019-04-12 | FOR BAPCO REVIEW | 2019-04-26 | 2019-05-18 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000700 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E2002 | 6087-A2-1 | 018-E-GAD-40119-001 | TRAIN 2 - FEED PREHEAT EXCHANGER CHANNEL DETAILS DWG. 018E2002 | A1109 | AX | 2 | 2019-04-11 | CON-BMP-VTRA-011130 | 2019-04-12 | FOR BAPCO REVIEW | 2019-04-26 | 2019-05-20 | 3-REVIEWED WITH COMMENTS BMP-ROC-VTRE-000714 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E2002 | 6087-A3-1 | 018-E-GAD-40120-001 | TRAIN 2 - FEED PREHEAT EXCHANGER NOZZLE DETAIL DWG. 018E2002 | A1109 | AX | 2 | 2019-04-12 | CON-BMP-VTRA-011137 | 2019-04-12 | FOR BAPCO REVIEW | 2019-04-26 | 2019-05-15 | 3-REVIEWED WITH COMMENTS BMP-ROC-VTRE-000681 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E2002 | 6087-A4-1 | 018-E-GAD-40121-001 | TRAIN 2 - FEED PREHEAT EXCHANGER NOZZLE DETAIL DWG. 018E2002 | A1109 | AX | 2 | 2019-04-12 | CON-BMP-VTRA-011137 | 2019-04-12 | FOR BAPCO REVIEW | 2019-04-26 | 2019-05-15 | 3-REVIEWED WITH COMMENTS BMP-ROC-VTRE-000681 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E2002 | 6087-A5-1 | 018-E-GAD-40122-001 | TRAIN 2 - FEED PREHEAT EXCHANGER PASS PARTITION DETAILS DWG. 018E2002 | A1109 | AX | 2 | 2019-04-12 | CON-BMP-VTRA-011137 | 2019-04-12 | FOR BAPCO REVIEW | 2019-04-26 | 2019-05-15 | 3-REVIEWED WITH COMMENTS BMP-ROC-VTRE-000681 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E2002 | 6087-A6-1 | 018-E-GAD-40123-001 | TRAIN 2 - FEED PREHEAT EXCHANGER SADDLE DETAIL DWG. 018E2002 | A1109 | AX | 2 | 2019-04-12 | CON-BMP-VTRA-011137 | 2019-04-12 | FOR BAPCO REVIEW | 2019-04-26 | 2019-05-15 | 3-REVIEWED WITH COMMENTS BMP-ROC-VTRE-000681 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E2002 | 6087-B1-1 | 018-E-GAD-40198-001 | TRAIN 2 - FEED PREHEAT EXCHANGER PART LIST 018E2002 | A1109 | AX | 2 | 2019-04-12 | CON-BMP-VTRA-011133 | 2019-04-12 | FOR BAPCO REVIEW | 2019-04-26 | 2019-05-15 | 3-REVIEWED WITH COMMENTS BMP-ROC-VTRE-000690 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E2002 | 6087-BT-1 | 018-E-TSP-40004-001 | BOLT TIGHTENING PROCEDURE 018E2002 | A1202 | AX | 2 | 2019-04-15 | CON-BMP-VTRA-011180 | 2019-04-15 | FOR BAPCO REVIEW | 2019-04-30 | 2019-05-15 | 3-REVIEWED WITH COMMENTS BMP-ROC-VTRE-000686 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E2002 | 6087-C1-1 | 018-E-DLB-40004-001 | NAMEPLATE DWG 018E2002 | A1112 | AX | 2 | 2019-03-28 | CON-BMP-VTRA-010886 | 2019-03-28 | FOR BAPCO REVIEW | 2019-04-12 | 2019-05-15 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000680 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E2002 | 6087-E-1 | 018-E-CAL-40045-001 | PRESSURE CALCULATION 018E2002 | A1003 | BX | 2 | 2019-04-11 | CON-BMP-VTRA-011127 | 2019-04-11 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E2002 | 6087-G-1 | 018-E-CAL-40046-001 | SUPPORT CALCULATION 018E2002 | A1003 | BX | 2 | 2019-04-11 | CON-BMP-VTRA-011127 | 2019-04-11 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E2002 | 6087-G1-1 | 018-E-GAD-40199-001 | TRAIN 2 - FEED PREHEAT EXCHANGER GASKET DWG. 018E2002 | A1109 | AX | 2 | 2019-04-12 | CON-BMP-VTRA-011137 | 2019-04-12 | FOR BAPCO REVIEW | 2019-04-26 | 2019-05-15 | 3-REVIEWED WITH COMMENTS BMP-ROC-VTRE-000681 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E2002 | 6087-HT-1 | 018-E-PRO-40004-001 | HEAT TREATMENT PROCEDURE 018E2002 | B1201 | AX | 2 | 2019-01-15 | CON-BMP-VTRA-010217 | 2019-01-15 | FOR BAPCO REVIEW | 2019-01-29 | 2019-02-04 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000152 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E2002 | 6087-WP-1 | 018-E-MCD-40004-001 | WELDING BOOK 018E2002 | B1304 | AX | 2 | 2019-01-30 | CON-BMP-VTRA-010326 | 2019-01-30 | FOR BAPCO REVIEW | 2019-02-13 | 2019-02-07 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000160 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E2002 | 6986-ITP | 018-E-PQP-40016-001 | FABRICATION AND QUALITY CONTROL PLAN 018E2002 | B1002 | 0AX | 2 | 2019-07-10 | CON-BMP-VTRA-012788 | 2019-07-10 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E2003 | 6088-1 | 018-E-GAD-40178-001 | TRAIN 2 RG + H2 PREHEAT EXCHANGER NO.1 GENERAL ARRANGEMENT 018E2003 | A1103 | BX | 2 | 2019-04-11 | CON-BMP-VTRA-011131 | 2019-04-11 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E2003 | 6088-A1-1 | 018-E-GAD-40205-001 | TRAIN 1 RG + H2 PREHEAT EXCHANGER NO.1 TUBE BUNDLE DWG. 018E2003 | A1109 | AX | 2 | 2019-04-12 | CON-BMP-VTRA-011137 | 2019-04-12 | FOR BAPCO REVIEW | 2019-04-26 | 2019-05-15 | 3-REVIEWED WITH COMMENTS BMP-ROC-VTRE-000681 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E2003 | 6088-A2-1 | 018-E-GAD-40131-001 | TRAIN 1 - RG + H2 PREHEAT EXCHANGER N1 CHANNEL DETAILS DWG. 018E2003 | A1109 | AX | 2 | 2019-04-11 | CON-BMP-VTRA-011130 | 2019-04-12 | FOR BAPCO REVIEW | 2019-04-26 | 2019-05-20 | 3-REVIEWED WITH COMMENTS BMP-ROC-VTRE-000714 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E2003 | 6088-A3-1 | 018-E-GAD-40132-001 | TRAIN 1 RG + H2 PREHEAT EXCHANGER NO.1 NOZZLE DETAIL DWG. 018E2003 | A1109 | AX | 2 | 2019-04-12 | CON-BMP-VTRA-011137 | 2019-04-12 | FOR BAPCO REVIEW | 2019-04-26 | 2019-05-15 | 3-REVIEWED WITH COMMENTS BMP-ROC-VTRE-000681 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E2003 | 6088-A4-1 | 018-E-GAD-40133-001 | TRAIN 1 RG + H2 PREHEAT EXCHANGER NO.1 PASS PARTITION DETAILS DWG. 018E2003 | A1109 | AX | 2 | 2019-04-12 | CON-BMP-VTRA-011133 | 2019-04-12 | FOR BAPCO REVIEW | 2019-04-26 | 2019-05-15 | 3-REVIEWED WITH COMMENTS BMP-ROC-VTRE-000690 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E2003 | 6088-A5-1 | 018-E-GAD-40134-001 | TRAIN 1 RG + H2 PREHEAT EXCHANGER NO.1 SADDLE DETAIL DWG. 018E2003 | A1109 | AX | 2 | 2019-04-12 | CON-BMP-VTRA-011133 | 2019-04-12 | FOR BAPCO REVIEW | 2019-04-26 | 2019-05-15 | 3-REVIEWED WITH COMMENTS BMP-ROC-VTRE-000690 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E2003 | 6088-B1-1 | 018-E-GAD-40206-001 | TRAIN 1 RG + H2 PREHEAT EXCHANGER NO.1 PART LIST 018E2003 | A1109 | AX | 2 | 2019-04-12 | CON-BMP-VTRA-011133 | 2019-04-12 | FOR BAPCO REVIEW | 2019-04-26 | 2019-05-15 | 3-REVIEWED WITH COMMENTS BMP-ROC-VTRE-000690 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E2003 | 6088-BT-1 | 018-E-TSP-40006-001 | BOLT TIGHTENING PROCEDURE 018E2003 | A1202 | AX | 2 | 2019-04-15 | CON-BMP-VTRA-011180 | 2019-04-15 | FOR BAPCO REVIEW | 2019-04-30 | 2019-05-15 | 3-REVIEWED WITH COMMENTS BMP-ROC-VTRE-000686 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E2003 | 6088-C1-1 | 018-E-DLB-40006-001 | NAMEPLATE DWG 018E2003 | A1112 | AX | 2 | 2019-03-28 | CON-BMP-VTRA-010886 | 2019-03-28 | FOR BAPCO REVIEW | 2019-04-12 | 2019-05-15 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000680 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E2003 | 6088-G-1 | 018-E-CAL-40054-001 | SUPPORT CALCULATION 018E2003 | A1003 | BX | 2 | 2019-04-11 | CON-BMP-VTRA-011126 | 2019-04-11 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E2003 | 6088-G1-1 | 018-E-GAD-40207-001 | TRAIN 1 RG + H2 PREHEAT EXCHANGER NO.1 GASKET DWG. 018E2003 | A1109 | AX | 2 | 2019-04-12 | CON-BMP-VTRA-011137 | 2019-04-12 | FOR BAPCO REVIEW | 2019-04-26 | 2019-05-15 | 3-REVIEWED WITH COMMENTS BMP-ROC-VTRE-000681 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E2003 | 6088-HT-1 | 018-E-PRO-40006-001 | HEAT TREATMENT PROCEDURE 018E2003 | B1201 | AX | 2 | 2019-01-15 | CON-BMP-VTRA-010217 | 2019-01-15 | FOR BAPCO REVIEW | 2019-01-29 | 2019-02-04 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000152 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E2003 | 6088-WP-1 | 018-E-MCD-40006-001 | WELDING BOOK 018E2003 | B1304 | AX | 2 | 2019-01-30 | CON-BMP-VTRA-010326 | 2019-01-30 | FOR BAPCO REVIEW | 2019-02-13 | 2019-02-07 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000160 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E2003 | 6988-ITP | 018-E-PQP-40018-001 | FABRICATION AND QUALITY CONTROL PLAN 018E2003 | B1002 | 0AX | 2 | 2019-07-10 | CON-BMP-VTRA-012788 | 2019-07-10 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E2004 | 6089-1 | 018-E-GAD-40180-001 | TRAIN 1 HP/HT STEAM GENERATOR GENERAL ARRANGEMENT 018E2004 | A1103 | BX | 2 | 2019-04-11 | CON-BMP-VTRA-011131 | 2019-04-11 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E2004 | 6089-A1-1 | 018-E-GAD-40213-001 | TRAIN 1 HP/HT STEAM GENERATOR TUBE BUNDLE DWG 018E2004 | A1109 | AX | 2 | 2019-04-12 | CON-BMP-VTRA-011137 | 2019-04-12 | FOR BAPCO REVIEW | 2019-04-26 | 2019-05-15 | 3-REVIEWED WITH COMMENTS BMP-ROC-VTRE-000681 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E2004 | 6089-A2-1 | 018-E-GAD-40143-001 | TRAIN 1 HP/HT STEAM GENERATOR CHANNEL DETAILS DWG. 018E2004 | A1109 | AX | 2 | 2019-04-11 | CON-BMP-VTRA-011130 | 2019-04-12 | FOR BAPCO REVIEW | 2019-04-26 | 2019-05-20 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000714 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E2004 | 6089-A3-1 | 018-E-GAD-40144-001 | TRAIN 1 HP/HT STEAM GENERATOR NOZZLE DETAIL DWG 018E2004 | A1109 | AX | 2 | 2019-04-12 | CON-BMP-VTRA-011137 | 2019-04-12 | FOR BAPCO REVIEW | 2019-04-26 | 2019-05-15 | 3-REVIEWED WITH COMMENTS BMP-ROC-VTRE-000681 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E2004 | 6089-A4-1 | 018-E-GAD-40145-001 | TRAIN 1 HP/HT STEAM GENERATOR NOZZLE DETAIL DWG 018E2004 | A1109 | AX | 2 | 2019-04-12 | CON-BMP-VTRA-011137 | 2019-04-12 | FOR BAPCO REVIEW | 2019-04-26 | 2019-05-15 | 3-REVIEWED WITH COMMENTS BMP-ROC-VTRE-000681 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E2004 | 6089-A5-1 | 018-E-GAD-40146-001 | TRAIN 1 HP/HT STEAM GENERATOR PASS PARTITION DETAILS DWG 018E2004 | A1109 | AX | 2 | 2019-04-12 | CON-BMP-VTRA-011137 | 2019-04-12 | FOR BAPCO REVIEW | 2019-04-26 | 2019-05-15 | 3-REVIEWED WITH COMMENTS BMP-ROC-VTRE-000681 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E2004 | 6089-A6-1 | 018-E-GAD-40147-001 | TRAIN 1 HP/HT VAPOR STEAM GENERATOR NOZZLE DETAIL DWG 018E1004 | A1109 | AX | 2 | 2019-04-12 | CON-BMP-VTRA-011133 | 2019-04-12 | FOR BAPCO REVIEW | 2019-04-26 | 2019-05-15 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000690 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E2004 | 6089-B1-1 | 018-E-GAD-40214-001 | TRAIN 1 HP/HT VAPOR STEAM GENERATOR PART LIST 018E2004 | A1109 | AX | 2 | 2019-04-12 | CON-BMP-VTRA-011133 | 2019-04-12 | FOR BAPCO REVIEW | 2019-04-26 | 2019-05-15 | 3-REVIEWED WITH COMMENTS BMP-ROC-VTRE-000690 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E2004 | 6089-BT-1 | 018-E-TSP-40008-001 | BOLT TIGHTENING PROCEDURE 018E2004 | A1202 | AX | 2 | 2019-04-15 | CON-BMP-VTRA-011180 | 2019-04-15 | FOR BAPCO REVIEW | 2019-04-30 | 2019-05-15 | 3-REVIEWED WITH COMMENTS BMP-ROC-VTRE-000686 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E2004 | 6089-C1-1 | 018-E-DLB-40008-001 | NAMEPLATE DWG 018E2004 | A1112 | AX | 2 | 2019-03-28 | CON-BMP-VTRA-010886 | 2019-03-28 | FOR BAPCO REVIEW | 2019-04-12 | 2019-05-15 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000680 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E2004 | 6089-E-1 | 018-E-CAL-40061-001 | PRESSURE CALCULATION 018E2004 | A1003 | BX | 2 | 2019-04-11 | CON-BMP-VTRA-011126 | 2019-04-11 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E2004 | 6089-G-1 | 018-E-CAL-40062-001 | SUPPORT CALCULATION 018E2004 | A1003 | BX | 2 | 2019-04-11 | CON-BMP-VTRA-011126 | 2019-04-11 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E2004 | 6089-G1-1 | 018-E-GAD-40215-001 | TRAIN 1 HP/HT VAPOR STEAM GENERATOR GASKET DWG 018E2004 | A1109 | AX | 2 | 2019-04-12 | CON-BMP-VTRA-011133 | 2019-04-12 | FOR BAPCO REVIEW | 2019-04-26 | 2019-05-15 | 3-REVIEWED WITH COMMENTS BMP-ROC-VTRE-000690 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E2004 | 6089-HT-1 | 018-E-PRO-40008-001 | HEAT TREATMENT PROCEDURE 018E2004 | B1201 | AX | 2 | 2019-01-15 | CON-BMP-VTRA-010217 | 2019-01-15 | FOR BAPCO REVIEW | 2019-01-29 | 2019-02-04 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000152 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E2004 | 6089-WP-1 | 018-E-MCD-40008-001 | WELDING BOOK 018E2004 | B1304 | AX | 2 | 2019-01-30 | CON-BMP-VTRA-010326 | 2019-01-30 | FOR BAPCO REVIEW | 2019-02-13 | 2019-02-07 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000160 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E2004 | 6990-ITP | 018-E-PQP-40020-001 | FABRICATION AND QUALITY CONTROL PLAN 018E2004 | B1002 | 0X | 2 | 2019-05-17 | CON-BMP-VTRA-011648 | 2019-05-17 | FOR BAPCO REVIEW | 2019-05-31 | 2019-05-30 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE- | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E2006 | 6090-1 | 018-E-GAD-40182-001 | GENERAL ARRANGEMENT 018E2006 | A1103 | BX | 2 | 2019-03-25 | CON-BMP-VTRA-010837 | 2019-03-25 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E2006 | 6090-A1-1 | 018-E-GAD-40221-001 | TUBE BUNDLE DWG. 018E2006 | A1109 | AX | 2 | 2019-03-25 | CON-BMP-VTRA-010843 | 2019-03-25 | FOR BAPCO REVIEW | 2019-04-09 | 2019-05-09 | 3-REVIEWED WITH COMMENTS BMP-ROC-VTRE-000634 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E2006 | 6090-A2-1 | 018-E-GAD-40155-001 | CHANNEL DETAIL DWG 018E2006 | A1109 | AX | 2 | 2019-03-25 | CON-BMP-VTRA-010843 | 2019-03-25 | FOR BAPCO REVIEW | 2019-04-09 | 2019-05-09 | 3-REVIEWED WITH COMMENTS BMP-ROC-VTRE-000634 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E2006 | 6090-A3-1 | 018-E-GAD-40156-001 | NOZZLE DETAIL DWG.018E2006 | A1109 | AX | 2 | 2019-03-25 | CON-BMP-VTRA-010843 | 2019-03-25 | FOR BAPCO REVIEW | 2019-04-09 | 2019-05-09 | 3-REVIEWED WITH COMMENTS BMP-ROC-VTRE-000634 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E2006 | 6090-A4-1 | 018-E-GAD-40157-001 | PASS PARTITION DETAIL DWG 018E2006 | A1109 | AX | 2 | 2019-03-25 | CON-BMP-VTRA-010843 | 2019-03-25 | FOR BAPCO REVIEW | 2019-04-09 | 2019-05-09 | 3-REVIEWED WITH COMMENTS BMP-ROC-VTRE-000634 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E2006 | 6090-A5-1 | 018-E-GAD-40158-001 | SADDLE DETAIL DWG. 018E2006 | A1109 | AX | 2 | 2019-03-25 | CON-BMP-VTRA-010843 | 2019-03-25 | FOR BAPCO REVIEW | 2019-04-09 | 2019-05-09 | 3-REVIEWED WITH COMMENTS BMP-ROC-VTRE-000634 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E2006 | 6090-B1-1 | 018-E-GAD-40222-001 | PART LIST DWG. 018E2006 | A1109 | AX | 2 | 2019-03-25 | CON-BMP-VTRA-010843 | 2019-03-25 | FOR BAPCO REVIEW | 2019-04-09 | 2019-05-09 | 3-REVIEWED WITH COMMENTS BMP-ROC-VTRE-000634 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E2006 | 6090-C1-1 | 018-E-DLB-40010-001 | NAMEPLATE DWG. 018E2006 | A1112 | AX | 2 | 2019-03-25 | CON-BMP-VTRA-010842 | 2019-03-25 | FOR BAPCO REVIEW | 2019-04-09 | 2019-04-09 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000491 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E2006 | 6090-E-1 | 018-E-CAL-40069-001 | PRESSURE CALCULATION 018E2006 | A1003 | BX | 2 | 2019-03-25 | CON-BMP-VTRA-010838 | 2019-03-25 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E2006 | 6090-FEA-1 | 018-E-CAL-40072-001 | STRESS ANALYSIS OF BREECH LOCKZ SHAPE CHANNEL FORGING 018E2006 | A1003 | AX | 2 | 2019-07-10 | CON-BMP-VTRA-012790 | 2019-07-10 | FOR BAPCO REVIEW | 2019-07-24 |  |  | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E2006 | 6090-G-1 | 018-E-CAL-40070-001 | SUPPORT CALCULATION 018E2006 | A1003 | BX | 4 | 2019-03-25 | CON-BMP-VTRA-010841 | 2019-03-25 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E2006 | 6090-G1-1 | 018-E-GAD-40223-001 | GASKET DWG. 018E2006 | A1109 | AX | 2 | 2019-03-25 | CON-BMP-VTRA-010843 | 2019-03-25 | FOR BAPCO REVIEW | 2019-04-09 | 2019-05-09 | 3-REVIEWED WITH COMMENTS BMP-ROC-VTRE-000634 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E2006 | 6090-HT-1 | 018-E-PRO-40010-001 | HEAT TREATMENT PROCEDURE 018E2006 | B1201 | AX | 2 | 2019-01-15 | CON-BMP-VTRA-010217 | 2019-01-15 | FOR BAPCO REVIEW | 2019-01-29 | 2019-02-04 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000152 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E2006 | 6090-WP-1 | 018-E-MCD-40010-001 | WELDING BOOK 018E2006 | B1304 | AX | 2 | 2019-01-30 | CON-BMP-VTRA-010326 | 2019-01-30 | FOR BAPCO REVIEW | 2019-02-13 | 2019-02-07 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000160 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E2006 | 6992-ITP | 018-E-PQP-40022-001 | FABRICATION AND QUALITY CONTROL PLAN 018E2006 | B1002 | 0X | 2 | 2019-05-17 | CON-BMP-VTRA-011648 | 2019-05-17 | FOR BAPCO REVIEW | 2019-05-31 | 2019-05-30 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE- | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E2007 | 6091-1 | 018-E-GAD-40184-001 | GENERAL ARRANGEMENT 018E2007 | A1103 | BX | 2 | 2019-04-01 | CON-BMP-VTRA-010942 | 2019-04-01 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E2007 | 6091-A1-1 | 018-E-GAD-40229-001 | TUBE BUNDLE DWG. - MEMBRANE FEED HEATER 018E2007 | A1109 | AX | 2 | 2019-04-01 | CON-BMP-VTRA-010940 | 2019-04-01 | FOR BAPCO REVIEW | 2019-04-15 | 2019-05-15 | 3-REVIEWED WITH COMMENTS BMP-ROC-VTRE-000678 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E2007 | 6091-A2-1 | 018-E-GAD-40167-001 | CHANNEL DETAIL DWG. MEMBRANE FEED HEATER 018E2007 | A1109 | AX | 2 | 2019-04-01 | CON-BMP-VTRA-010940 | 2019-04-01 | FOR BAPCO REVIEW | 2019-04-15 | 2019-05-15 | 3-REVIEWED WITH COMMENTS BMP-ROC-VTRE-000678 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E2007 | 6091-A3-1 | 018-E-GAD-40168-001 | NOZZLE DETAIL DWG. - MEMBRANE FEED HEATER 018E2007 | A1109 | AX | 2 | 2019-04-01 | CON-BMP-VTRA-010940 | 2019-04-01 | FOR BAPCO REVIEW | 2019-04-15 | 2019-05-15 | 3-REVIEWED WITH COMMENTS BMP-ROC-VTRE-000678 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E2007 | 6091-A4-1 | 018-E-GAD-40169-001 | PASS PARTITION DETAIL DWG. - MEMBRANE FEED HEATER - 018E2007 | A1109 | AX | 2 | 2019-04-01 | CON-BMP-VTRA-010940 | 2019-04-01 | FOR BAPCO REVIEW | 2019-04-15 | 2019-05-15 | 3-REVIEWED WITH COMMENTS BMP-ROC-VTRE-000678 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E2007 | 6091-A5-1 | 018-E-GAD-40170-001 | SADDLE DETAIL DWG. - MEMBRANE FEED HEATER 018E2007 | A1109 | AX | 2 | 2019-04-01 | CON-BMP-VTRA-010940 | 2019-04-01 | FOR BAPCO REVIEW | 2019-04-15 | 2019-05-15 | 3-REVIEWED WITH COMMENTS BMP-ROC-VTRE-000678 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E2007 | 6091-B1-1 | 018-E-GAD-40230-001 | PART LIST DWG. - MEMBRANE FEED HEATER 018E2007 | A1109 | AX | 2 | 2019-04-01 | CON-BMP-VTRA-010940 | 2019-04-01 | FOR BAPCO REVIEW | 2019-04-15 | 2019-05-15 | 3-REVIEWED WITH COMMENTS BMP-ROC-VTRE-000678 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E2007 | 6091-C1-1 | 018-E-DLB-40012-001 | NAMEPLATE DWG 018E2007 | A1112 | AX | 2 | 2019-03-28 | CON-BMP-VTRA-010886 | 2019-03-28 | FOR BAPCO REVIEW | 2019-04-12 | 2019-05-15 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000680 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E2007 | 6091-E-1 | 018-E-CAL-40077-001 | PRESSURE CALCULATION 018E2007 | A1003 | BX | 2 | 2019-04-01 | CON-BMP-VTRA-010941 | 2019-04-01 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E2007 | 6091-FEA-1 | 018-E-CAL-40080-001 | STRESS ANALYSIS OF BREECH LOCKZ SHAPE CHANNEL FORGING 018E2007 | A1003 | AX | 2 | 2019-07-10 | CON-BMP-VTRA-012790 | 2019-07-10 | FOR BAPCO REVIEW | 2019-07-24 |  |  | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E2007 | 6091-G-1 | 018-E-CAL-40078-001 | SUPPORT CALCULATION 018E2007 | A1003 | BX | 2 | 2019-04-01 | CON-BMP-VTRA-010941 | 2019-04-01 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E2007 | 6091-G1-1 | 018-E-GAD-40231-001 | GASKET DWG. - MEMBRANE FEED HEATER 018E2007 | A1109 | AX | 2 | 2019-04-01 | CON-BMP-VTRA-010940 | 2019-04-01 | FOR BAPCO REVIEW | 2019-04-15 | 2019-05-15 | 3-REVIEWED WITH COMMENTS BMP-ROC-VTRE-000678 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E2007 | 6091-HT-1 | 018-E-PRO-40012-001 | HEAT TREATMENT PROCEDURE 018E2007 | B1201 | AX | 2 | 2019-01-15 | CON-BMP-VTRA-010217 | 2019-01-15 | FOR BAPCO REVIEW | 2019-01-29 | 2019-02-04 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000152 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E2007 | 6091-WP-1 | 018-E-MCD-40012-001 | WELDING BOOK 018E2007 | B1304 | AX | 2 | 2019-01-30 | CON-BMP-VTRA-010326 | 2019-01-30 | FOR BAPCO REVIEW | 2019-02-13 | 2019-02-07 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000160 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 018E2007 | 6994-ITP | 018-E-PQP-40024-001 | FABRICATION AND QUALITY CONTROL PLAN 018E2007 | B1002 | 0AX | 2 | 2019-07-10 | CON-BMP-VTRA-012792 | 2019-07-10 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 021E0003 | 6092 | 021-E-GAD-40084-001 | REACTOR EFFLUENT / RECYCLE GAS HOT EXCHANGER GENERAL ARRANGEMENT 021E0003 | A1103 | BX | 2 | 2019-04-11 | CON-BMP-VTRA-011131 | 2019-04-11 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 021E0003 | 6092-A1 | 021-E-GAD-40085-001 | REACTOR EFFLUENT / RECYCLE GAS HOT EXCHANGER TUBE BUNDLE DWG. 021E0003 | A1109 | AX | 2 | 2019-04-12 | CON-BMP-VTRA-011137 | 2019-04-12 | FOR BAPCO REVIEW | 2019-04-26 | 2019-05-15 | 3-REVIEWED WITH COMMENTS BMP-ROC-VTRE-000681 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 021E0003 | 6092-A2 | 021-E-GAD-40038-001 | REACTOR EFFLUENT / RECYCLE GAS HOT EXCHANGER CHANNEL DETAILS DWG. 021E0003 | A1109 | AXX | 2 | 2019-04-15 | CON-BMP-VTRA-011176 | 2019-04-15 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 021E0003 | 6092-A3 | 021-E-GAD-40039-001 | REACTOR EFFLUENT / RECYCLE GAS HOT EXCHANGER NOZZLE DETAIL DWG. 021E0003 | A1109 | AX | 2 | 2019-04-12 | CON-BMP-VTRA-011136 | 2019-04-12 | FOR BAPCO REVIEW | 2019-04-26 | 2019-05-18 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000700 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 021E0003 | 6092-A4 | 021-E-GAD-40040-001 | REACTOR EFFLUENT / RECYCLE GAS HOT EXCHANGER PASS PARTITION DETAIL DWG. 021E0003 | A1109 | AX | 2 | 2019-04-12 | CON-BMP-VTRA-011136 | 2019-04-12 | FOR BAPCO REVIEW | 2019-04-26 | 2019-05-18 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000700 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 021E0003 | 6092-A5 | 021-E-GAD-40041-001 | REACTOR EFFLUENT / RECYCLE GAS HOT EXCHANGER SADDLE DETAIL DWG. 021E0003 | A1109 | AX | 2 | 2019-04-12 | CON-BMP-VTRA-011136 | 2019-04-12 | FOR BAPCO REVIEW | 2019-04-26 | 2019-05-18 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000700 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 021E0003 | 6092-B1 | 021-E-GAD-40086-001 | REACTOR EFFLUENT / RECYCLE GAS HOT EXCHANGER PART LIST DWG. 021E0003 | A1109 | AX | 2 | 2019-04-12 | CON-BMP-VTRA-011136 | 2019-04-12 | FOR BAPCO REVIEW | 2019-04-26 | 2019-05-18 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000700 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 021E0003 | 6092-C1 | 021-E-DLB-40001-001 | NAMEPLATE DWG 021E0003 | A1112 | AX | 2 | 2019-03-28 | CON-BMP-VTRA-010886 | 2019-03-28 | FOR BAPCO REVIEW | 2019-04-12 | 2019-05-15 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000680 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 021E0003 | 6092-E | 021-E-CAL-40021-001 | PRESSURE CALCULATION 021E0003 | A1003 | BX | 2 | 2019-04-11 | CON-BMP-VTRA-011126 | 2019-04-11 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 021E0003 | 6092-FEA | 021-E-CAL-40024-001 | STRESS ANALYSIS OF BREECH LOCKZ SHAPE CHANNEL FORGING 021E0003 | A1003 | AX | 2 | 2019-07-10 | CON-BMP-VTRA-012791 | 2019-07-10 | FOR BAPCO REVIEW | 2019-07-24 |  |  | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 021E0003 | 6092-G | 021-E-CAL-40022-001 | SUPPORT CALCULATION 021E0003 | A1003 | BX | 2 | 2019-04-11 | CON-BMP-VTRA-011126 | 2019-04-11 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 021E0003 | 6092-G1 | 021-E-GAD-40087-001 | REACTOR EFFLUENT / RECYCLE GAS HOT EXCHANGER GASKET DWG 021E0003 | A1109 | AX | 2 | 2019-04-12 | CON-BMP-VTRA-011136 | 2019-04-12 | FOR BAPCO REVIEW | 2019-04-26 | 2019-05-18 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000700 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 021E0003 | 6092-HT | 021-E-PRO-40001-001 | HEAT TREATMENT PROCEDURE 021E0003 | B1201 | AX | 2 | 2019-01-15 | CON-BMP-VTRA-010217 | 2019-01-15 | FOR BAPCO REVIEW | 2019-01-29 | 2019-02-04 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000152 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 021E0003 | 6092-WP | 021-E-MCD-40001-001 | WELDING BOOK 021E0003 | B1304 | AX | 2 | 2019-01-30 | CON-BMP-VTRA-010326 | 2019-01-30 | FOR BAPCO REVIEW | 2019-02-13 | 2019-02-07 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000160 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 021E0003 | 6995-ITP | 021-E-PQP-40010-001 | FABRICATION AND QUALITY CONTROL PLAN 021E0003 | B1002 | 0AX | 3 | 2019-07-10 | CON-BMP-VTRA-012793 | 2019-07-10 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 021E0004A | 6093 | 021-E-GAD-40089-001 | REACTOR EFFLUENT / FEED HOT EXCHANGER GENERAL ARRANGEMENT 021E0004A/B | A1103 | BX | 2 | 2019-04-11 | CON-BMP-VTRA-011131 | 2019-04-11 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 021E0004A | 6093-A1 1OF2 | 021-E-GAD-40090-001 | REACTOR EFFLUENT / FEED HOT EXCHANGER TUBE BUNDLE DWG. 021E0004A | A1109 | AX | 2 | 2019-04-11 | CON-BMP-VTRA-011129 | 2019-04-11 | FOR BAPCO REVIEW | 2019-04-26 | 2019-05-20 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000713 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 021E0004A | 6093-A2 | 021-E-GAD-40044-001 | REACTOR EFFLUENT / FEED HOT EXCHANGER CHANNEL DETAILS DWG. 021E0004A/B | A1109 | AXX | 2 | 2019-04-15 | CON-BMP-VTRA-011176 | 2019-04-15 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 021E0004A | 6093-A3 1OF2 | 021-E-GAD-40045-001 | REACTOR EFFLUENT / FEED HOT EXCHANGER NOZZLE DETAILS DWG. 021E0004A/B | A1109 | AX | 2 | 2019-04-11 | CON-BMP-VTRA-011129 | 2019-04-11 | FOR BAPCO REVIEW | 2019-04-26 | 2019-05-20 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000713 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 021E0004A | 6093-A3 2OF2 | 021-E-GAD-40045-002 | REACTOR EFFLUENT / FEED HOT EXCHANGER NOZZLE DETAILS DWG. 021E0004A/B | A1109 | AX | 2 | 2019-04-11 | CON-BMP-VTRA-011129 | 2019-04-11 | FOR BAPCO REVIEW | 2019-04-26 | 2019-05-20 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000713 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 021E0004A | 6093-A4 | 021-E-GAD-40046-001 | REACTOR EFFLUENT / FEED HOT EXCHANGER PASS PARTITION DETAILS DWG. 021E0004A/B | A1109 | AX | 2 | 2019-04-11 | CON-BMP-VTRA-011129 | 2019-04-11 | FOR BAPCO REVIEW | 2019-04-26 | 2019-05-20 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000713 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 021E0004A | 6093-A5 | 021-E-GAD-40047-001 | REACTOR EFFLUENT / FEED HOT EXCHANGER SADDLE DETAILS DWG. 021E0004A/B | A1109 | AX | 2 | 2019-04-11 | CON-BMP-VTRA-011129 | 2019-04-11 | FOR BAPCO REVIEW | 2019-04-26 | 2019-05-20 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000713 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 021E0004A | 6093-A6 | 021-E-GAD-40048-001 | REACTOR EFFLUENT / FEED HOT EXCHANGER SADDLE DETAILS DWG. 021E0004A/B | A1109 | AX | 2 | 2019-04-11 | CON-BMP-VTRA-011129 | 2019-04-11 | FOR BAPCO REVIEW | 2019-04-26 | 2019-05-20 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000713 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 021E0004A | 6093-B1 | 021-E-GAD-40091-001 | REACTOR EFFLUENT / FEED HOT EXCHANGE PART LIST DWG. 021E0004A/B | A1109 | AX | 2 | 2019-04-11 | CON-BMP-VTRA-011129 | 2019-04-11 | FOR BAPCO REVIEW | 2019-04-26 | 2019-05-20 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000713 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 021E0004A | 6093-C1 | 021-E-DLB-40002-001 | NAMEPLATE DWG 021E0004A/B | A1112 | AX | 2 | 2019-03-28 | CON-BMP-VTRA-010886 | 2019-03-28 | FOR BAPCO REVIEW | 2019-04-12 | 2019-05-15 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000680 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 021E0004A | 6093-E | 021-E-CAL-40025-001 | PRESSURE CALCULATION 021E0004A 021E0004B | A1003 | BX | 2 | 2019-04-11 | CON-BMP-VTRA-011126 | 2019-04-11 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 021E0004A | 6093-FEA | 021-E-CAL-40028-001 | STRESS ANALYSIS OF BREECH LOCKZ SHAPE CHANNEL FORGING 021E0004A/B | A1003 | AX | 2 | 2019-07-10 | CON-BMP-VTRA-012791 | 2019-07-10 | FOR BAPCO REVIEW | 2019-07-24 |  |  | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 021E0004A | 6093-G | 021-E-CAL-40026-001 | SUPPORT CALCULATION 021E0004A 021E0004B | A1003 | BX | 2 | 2019-04-11 | CON-BMP-VTRA-011126 | 2019-04-11 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 021E0004A | 6093-G1 | 021-E-GAD-40092-001 | REACTOR EFFLUENT / FEED HOT EXCHANGER GASKET DWG. 021E0004A/B | A1109 | AX | 2 | 2019-04-11 | CON-BMP-VTRA-011129 | 2019-04-11 | FOR BAPCO REVIEW | 2019-04-26 | 2019-05-20 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000713 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 021E0004A | 6093-HT | 021-E-PRO-40002-001 | HEAT TREATMENT PROCEDURE 021E0004A 021E0004B | B1201 | AX | 2 | 2019-01-15 | CON-BMP-VTRA-010217 | 2019-01-15 | FOR BAPCO REVIEW | 2019-01-29 | 2019-02-04 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000152 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 021E0004A | 6093-WP | 021-E-MCD-40002-001 | WELDING BOOK 021E0004A 021E0004B | B1304 | AX | 2 | 2019-01-30 | CON-BMP-VTRA-010326 | 2019-01-30 | FOR BAPCO REVIEW | 2019-02-13 | 2019-02-07 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000160 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 021E0004A | 6996-ITP | 021-E-PQP-40011-001 | FABRICATION AND QUALITY CONTROL PLAN 021E0004A | B1002 | 0AX | 2 | 2019-07-10 | CON-BMP-VTRA-012789 | 2019-07-10 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 021E0004B | 6093-A1 2OF2 | 021-E-GAD-40090-002 | REACTOR EFFLUENT / FEED HOT EXCHANGER TUBE BUNDLE DWG. 021E0004B | A1109 | AX | 2 | 2019-04-11 | CON-BMP-VTRA-011130 | 2019-04-12 | FOR BAPCO REVIEW | 2019-04-26 | 2019-05-20 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000714 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 021E0004B | 6997-ITP | 021-E-PQP-40012-001 | FABRICATION AND QUALITY CONTROL PLAN 021E0004B | B1002 | 0AX | 2 | 2019-07-10 | CON-BMP-VTRA-012789 | 2019-07-10 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 021E0005 | 6094 | 021-E-GAD-40094-001 | REACTOR EFFLUENT / RECYCLE GAS COLD EXCHANGER GENERAL ARRANGEMENT 021E0005 | A1103 | BX | 2 | 2019-04-15 | CON-BMP-VTRA-011163 | 2019-04-15 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 021E0005 | 6094-A1 | 021-E-GAD-40055-001 | REACTOR EFFLUENT / RECYCLE GAS COLD EXCHANGER TUBE BUNDLE DWG 021E0005 | A1109 | AX | 2 | 2019-04-12 | CON-BMP-VTRA-011136 | 2019-04-12 | FOR BAPCO REVIEW | 2019-04-26 | 2019-05-18 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000700 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 021E0005 | 6094-A2 | 021-E-GAD-40050-001 | REACTOR EFFLUENT / RECYCLE GAS COLD EXCHANGER CHANNEL DETAIL DWG. 021E0005 | A1109 | AX | 2 | 2019-04-11 | CON-BMP-VTRA-011130 | 2019-04-12 | FOR BAPCO REVIEW | 2019-04-26 | 2019-05-20 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000714 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 021E0005 | 6094-A3 | 021-E-GAD-40051-001 | REACTOR EFFLUENT / RECYCLE GAS COLD EXCHANGER NOZZLE DETAIL DWG 021E0005 | A1109 | AX | 2 | 2019-04-12 | CON-BMP-VTRA-011136 | 2019-04-12 | FOR BAPCO REVIEW | 2019-04-26 | 2019-05-18 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000700 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 021E0005 | 6094-A4 | 021-E-GAD-40052-001 | REACTOR EFFLUENT / RECYCLE GAS COLD EXCHANGER PASS PARTITION DETAIL DWG 021E0005 | A1109 | AX | 2 | 2019-04-12 | CON-BMP-VTRA-011136 | 2019-04-12 | FOR BAPCO REVIEW | 2019-04-26 | 2019-05-18 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000700 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 021E0005 | 6094-A5 | 021-E-GAD-40053-001 | REACTOR EFFLUENT / RECYCLE GAS COLD EXCHANGER SADDLE DETAIL DWG 021E0005 | A1109 | AX | 2 | 2019-04-12 | CON-BMP-VTRA-011136 | 2019-04-12 | FOR BAPCO REVIEW | 2019-04-26 | 2019-05-18 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000700 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 021E0005 | 6094-B1 | 021-E-GAD-40095-001 | REACTOR EFFLUENT / RECYCLE GAS COLD EXCHANGER PART LIST DWG 021E0005 | A1109 | AX | 2 | 2019-04-12 | CON-BMP-VTRA-011136 | 2019-04-12 | FOR BAPCO REVIEW | 2019-04-26 | 2019-05-18 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000700 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 021E0005 | 6094-C1 | 021-E-DLB-40003-001 | NAMEPLATE DWG 021E0005 | A1112 | AX | 2 | 2019-03-28 | CON-BMP-VTRA-010886 | 2019-03-28 | FOR BAPCO REVIEW | 2019-04-12 | 2019-05-15 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000680 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 021E0005 | 6094-E | 021-E-CAL-40030-001 | PRESSURE CALCULATION 021E0005 | A1003 | BX | 2 | 2019-04-11 | CON-BMP-VTRA-011126 | 2019-04-11 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 021E0005 | 6094-FEA | 021-E-CAL-40033-001 | STRESS ANALYSIS OF BREECH LOCKZ SHAPE CHANNEL FORGING 021E0005 | A1003 | AX | 2 | 2019-07-10 | CON-BMP-VTRA-012791 | 2019-07-10 | FOR BAPCO REVIEW | 2019-07-24 |  |  | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 021E0005 | 6094-G | 021-E-CAL-40031-001 | SUPPORT CALCULATION 021E0005 | A1003 | BX | 2 | 2019-04-11 | CON-BMP-VTRA-011126 | 2019-04-11 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 021E0005 | 6094-G1 | 021-E-GAD-40049-001 | REACTOR EFFLUENT / RECYCLE GAS COLD EXCHANGER GASKET DWG 021E0005 | A1109 | AX | 2 | 2019-04-12 | CON-BMP-VTRA-011136 | 2019-04-12 | FOR BAPCO REVIEW | 2019-04-26 | 2019-05-18 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000700 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 021E0005 | 6094-HT | 021-E-PRO-40003-001 | HEAT TREATMENT PROCEDURE 021E0005 | B1201 | AX | 2 | 2019-01-15 | CON-BMP-VTRA-010217 | 2019-01-15 | FOR BAPCO REVIEW | 2019-01-29 | 2019-02-04 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000152 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 021E0005 | 6094-WP | 021-E-MCD-40003-001 | WELDING BOOK 021E0005 | B1304 | AX | 2 | 2019-01-30 | CON-BMP-VTRA-010326 | 2019-01-30 | FOR BAPCO REVIEW | 2019-02-13 | 2019-02-07 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000160 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 021E0005 | 6998-ITP | 021-E-PQP-40013-001 | FABRICATION AND QUALITY CONTROL PLAN 021E0005 | B1002 | 0AX | 3 | 2019-07-10 | CON-BMP-VTRA-012793 | 2019-07-10 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 021E0006A | 6095 | 021-E-GAD-40097-001 | REACTOR EFFLUENT / FEED COLD EXCHANGER GENERAL ARRANGEMENT 021E0006A/B | A1103 | BX | 2 | 2019-04-15 | CON-BMP-VTRA-011163 | 2019-04-15 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 021E0006A | 6095-A1 1OF2 | 021-E-GAD-40098-001 | REACTOR EFFLUENT FEED COLD EXCHANGERTUBE BUNDLE DWG. 021E0006A | A1109 | AX | 2 | 2019-04-11 | CON-BMP-VTRA-011129 | 2019-04-11 | FOR BAPCO REVIEW | 2019-04-26 | 2019-05-20 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000713 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 021E0006A | 6095-A2 | 021-E-GAD-40056-001 | REACTOR EFFLUENT / FEED COLD EXCHANGER CHANNEL DETAIL DWG. 021E0006A/B | A1109 | AXX | 2 | 2019-04-15 | CON-BMP-VTRA-011176 | 2019-04-15 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 021E0006A | 6095-A3 1OF2 | 021-E-GAD-40057-001 | REACTOR EFFLUENT / FEED COLD EXCHANGER NOZZLE DETAIL DWG. 021E0006A/B | A1109 | AX | 2 | 2019-04-11 | CON-BMP-VTRA-011129 | 2019-04-11 | FOR BAPCO REVIEW | 2019-04-26 | 2019-05-20 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000713 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 021E0006A | 6095-A3 2OF2 | 021-E-GAD-40057-002 | REACTOR EFFLUENT / FEED COLD EXCHANGER NOZZLE DETAIL DWG. 021E0006A/B | A1109 | AX | 2 | 2019-04-11 | CON-BMP-VTRA-011130 | 2019-04-12 | FOR BAPCO REVIEW | 2019-04-26 | 2019-05-20 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000714 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 021E0006A | 6095-A4 | 021-E-GAD-40058-001 | REACTOR EFFLUENT / FEED COLD EXCHANGER PASS PARTITION DETAIL DWG 021E0006A/B. | A1109 | AX | 2 | 2019-04-11 | CON-BMP-VTRA-011129 | 2019-04-11 | FOR BAPCO REVIEW | 2019-04-26 | 2019-05-20 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000713 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 021E0006A | 6095-A5 | 021-E-GAD-40059-001 | REACTOR EFFLUENT / FEED COLD EXCHANGER SADDLE DETAIL DWG. 021E0006A/B | A1109 | AX | 2 | 2019-04-11 | CON-BMP-VTRA-011129 | 2019-04-11 | FOR BAPCO REVIEW | 2019-04-26 | 2019-05-20 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000713 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 021E0006A | 6095-A6 | 021-E-GAD-40060-001 | REACTOR EFFLUENT / FEED COLD EXCHANGER DETAIL DWG. 021E0006A/B | A1109 | AX | 2 | 2019-04-11 | CON-BMP-VTRA-011130 | 2019-04-12 | FOR BAPCO REVIEW | 2019-04-26 | 2019-05-20 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000714 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 021E0006A | 6095-B1 | 021-E-GAD-40099-001 | REACTOR EFFLUENT / FEED COLD EXCHANGER PART LIST DWG. 021E0006A/B | A1109 | AX | 2 | 2019-04-11 | CON-BMP-VTRA-011129 | 2019-04-11 | FOR BAPCO REVIEW | 2019-04-26 | 2019-05-20 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000713 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 021E0006A | 6095-C1 | 021-E-DLB-40004-001 | REACTOR EFFLUENT / FEED COLD EXCHANGER NAMEPLATE DWG. 021E0006A/B | A1112 | AX | 2 | 2019-04-15 | CON-BMP-VTRA-011182 | 2019-04-15 | FOR BAPCO REVIEW | 2019-04-30 | 2019-05-15 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000683 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 021E0006A | 6095-E | 021-E-CAL-40034-001 | PRESSURE CALCULATION 021E0006A 021E0006B | A1003 | BX | 2 | 2019-04-11 | CON-BMP-VTRA-011126 | 2019-04-11 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 021E0006A | 6095-FEA | 021-E-CAL-40037-001 | STRESS ANALYSIS OF BREECH LOCK 0210006AB | A1003 | AX | 2 | 2019-07-10 | CON-BMP-VTRA-012791 | 2019-07-10 | FOR BAPCO REVIEW | 2019-07-24 |  |  | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 021E0006A | 6095-G | 021-E-CAL-40035-001 | SUPPORT CALCULATION 021E0006A 021E0006B | A1003 | BX | 2 | 2019-04-11 | CON-BMP-VTRA-011126 | 2019-04-11 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 021E0006A | 6095-G1 | 021-E-GAD-40100-001 | REACTOR EFFLUENT / FEED HOT EXCHANGER GASKET DWG. 021E0006A/B | A1109 | AX | 2 | 2019-04-11 | CON-BMP-VTRA-011130 | 2019-04-12 | FOR BAPCO REVIEW | 2019-04-26 | 2019-05-20 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000714 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 021E0006A | 6095-HT | 021-E-PRO-40004-001 | HEAT TREATMENT PROCEDURE 021E0006A 021E0006B | B1201 | AX | 2 | 2019-01-15 | CON-BMP-VTRA-010217 | 2019-01-15 | FOR BAPCO REVIEW | 2019-01-29 | 2019-02-04 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000152 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 021E0006A | 6095-WP | 021-E-MCD-40004-001 | WELDING BOOK 021E0006A 021E0006B | B1304 | AX | 2 | 2019-01-30 | CON-BMP-VTRA-010326 | 2019-01-30 | FOR BAPCO REVIEW | 2019-02-13 | 2019-02-07 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000160 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 021E0006A | 6999-ITP | 021-E-PQP-40014-001 | FABRICATION AND QUALITY CONTROL PLAN 021E006A | B1002 | 0AX | 2 | 2019-07-10 | CON-BMP-VTRA-012789 | 2019-07-10 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 021E0006B | 6095-A1 2OF2 | 021-E-GAD-40098-002 | REACTOR EFFLUENT FEED COLD EXCHANGERTUBE BUNDLE DWG. 021E0006B | A1109 | AX | 2 | 2019-04-11 | CON-BMP-VTRA-011129 | 2019-04-11 | FOR BAPCO REVIEW | 2019-04-26 | 2019-05-20 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000713 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 021E0006B | 7000-ITP | 021-E-PQP-40015-001 | FABRICATION AND QUALITY CONTROL PLAN 021E0006B | B1002 | 0AX | 2 | 2019-07-10 | CON-BMP-VTRA-012789 | 2019-07-10 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 021E0007 | 6096-00 | 021-E-GAD-40080-001 | HHPS VAPOR / FEED EXCHANGER GENERAL ARRANGEMENT 021E0007 | A1103 | BX | 2 | 2019-04-11 | CON-BMP-VTRA-011131 | 2019-04-11 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 021E0007 | 6096-A1 | 021-E-GAD-40081-001 | REACTOR EFFLUENT / FEED COLD EXCHANGER TUBE BUNDLE DWG. 021E0007 | A1109 | AX | 2 | 2019-04-11 | CON-BMP-VTRA-011129 | 2019-04-11 | FOR BAPCO REVIEW | 2019-04-26 | 2019-05-20 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000713 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 021E0007 | 6096-A2 | 021-E-GAD-40062-001 | REACTOR EFFLUENT / FEED COLD EXCHANGER CHANNEL DETAIL DWG. 021E0007 | A1109 | AXX | 2 | 2019-04-15 | CON-BMP-VTRA-011176 | 2019-04-15 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 021E0007 | 6096-A3 | 021-E-GAD-40063-001 | REACTOR EFFLUENT / FEED COLD EXCHANGER NOZZLE DETAIL DWG. 021E0007 | A1109 | AX | 2 | 2019-04-11 | CON-BMP-VTRA-011129 | 2019-04-11 | FOR BAPCO REVIEW | 2019-04-26 | 2019-05-20 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000713 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 021E0007 | 6096-A4 | 021-E-GAD-40064-001 | REACTOR EFFLUENT / FEED COLD EXCHANGER PASS PARTITION DETAIL DWG. 021E0007 | A1109 | AX | 2 | 2019-04-11 | CON-BMP-VTRA-011129 | 2019-04-11 | FOR BAPCO REVIEW | 2019-04-26 | 2019-05-20 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000713 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 021E0007 | 6096-A5 | 021-E-GAD-40065-001 | REACTOR EFFLUENT / FEED COLD EXCHANGER SADDLE DETAIL DWG. 021E0007 | A1109 | AX | 2 | 2019-04-11 | CON-BMP-VTRA-011130 | 2019-04-12 | FOR BAPCO REVIEW | 2019-04-26 | 2019-05-20 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000714 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 021E0007 | 6096-B1 | 021-E-GAD-40082-001 | REACTOR EFFLUENT FEED COLD EXCHANGER PART LIST DWG. 021E0007 | A1109 | AX | 2 | 2019-04-11 | CON-BMP-VTRA-011129 | 2019-04-11 | FOR BAPCO REVIEW | 2019-04-26 | 2019-05-20 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000713 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 021E0007 | 6096-C1 | 021-E-DLB-40005-001 | NAMEPLATE DWG 021E0007 | A1112 | AX | 2 | 2019-03-28 | CON-BMP-VTRA-010886 | 2019-03-28 | FOR BAPCO REVIEW | 2019-04-12 | 2019-05-15 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000680 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 021E0007 | 6096-E | 021-E-CAL-40039-001 | PRESSURE CALCULATION 021E0007 | A1003 | BX | 2 | 2019-04-11 | CON-BMP-VTRA-011126 | 2019-04-11 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 021E0007 | 6096-FEA | 021-E-CAL-40042-001 | STRESS ANALYSIS OF BREECH LOCKZ SHAPE CHANNEL FORGING 021E0007 | A1003 | AX | 2 | 2019-07-10 | CON-BMP-VTRA-012791 | 2019-07-10 | FOR BAPCO REVIEW | 2019-07-24 |  |  | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 021E0007 | 6096-G | 021-E-CAL-40040-001 | SUPPORT CALCULATION 021E0007 | A1003 | AX | 2 | 2019-01-14 | CON-BMP-VTRA-010215 | 2019-01-14 | FOR BAPCO REVIEW | 2019-01-29 | 2019-01-29 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000136 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 021E0007 | 6096-G1 | 021-E-GAD-40083-001 | REACTOR EFFLUENT / FEED COLD EXCHANGER GASKET DWG. 021E0007 | A1109 | AX | 2 | 2019-04-11 | CON-BMP-VTRA-011130 | 2019-04-12 | FOR BAPCO REVIEW | 2019-04-26 | 2019-05-20 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000714 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 021E0007 | 6096-HT | 021-E-PRO-40005-001 | HEAT TREATMENT PROCEDURE 021E0007 | B1201 | AX | 2 | 2019-01-15 | CON-BMP-VTRA-010217 | 2019-01-15 | FOR BAPCO REVIEW | 2019-01-29 | 2019-02-04 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000152 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 021E0007 | 6096-WP | 021-E-MCD-40005-001 | WELDING BOOK 021E0007 | B1304 | AX | 2 | 2019-01-30 | CON-BMP-VTRA-010326 | 2019-01-30 | FOR BAPCO REVIEW | 2019-02-13 | 2019-02-07 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000160 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 021E0007 | 7001-ITP | 021-E-PQP-40016-001 | FABRICATION AND QUALITY CONTROL PLAN 021E0007 | B1002 | 0AX | 2 | 2019-07-10 | CON-BMP-VTRA-012789 | 2019-07-10 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 021E0008 | 6097 | 021-E-GAD-40102-001 | HHPS VAPOR / RECYCLE GAS EXCHANGER GENERAL ARRANGEMENT 021E0008 | A1103 | BX | 2 | 2019-04-15 | CON-BMP-VTRA-011163 | 2019-04-15 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 021E0008 | 6097-A1 | 021-E-GAD-40103-001 | HHPS VAPOR / RECYCLE GAS EXCHANGER TUBE BUNDLE DWG. 021E0008 | A1109 | AX | 2 | 2019-04-12 | CON-BMP-VTRA-011136 | 2019-04-12 | FOR BAPCO REVIEW | 2019-04-26 | 2019-05-18 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000700 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 021E0008 | 6097-A2 | 021-E-GAD-40068-001 | HHPS VAPOR / RECYCLE GAS EXCHANGER CHANNEL DETAIL DWG. 021E0008 | A1109 | AXX | 2 | 2019-04-15 | CON-BMP-VTRA-011176 | 2019-04-15 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 021E0008 | 6097-A3 | 021-E-GAD-40069-001 | HHPS VAPOR / RECYCLE GAS EXCHANGER NOZZLE DETAIL DWG. 021E0008 | A1109 | AX | 2 | 2019-04-12 | CON-BMP-VTRA-011136 | 2019-04-12 | FOR BAPCO REVIEW | 2019-04-26 | 2019-05-18 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000700 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 021E0008 | 6097-A4 | 021-E-GAD-40070-001 | HHPS VAPOR / RECYCLE GAS EXCHANGER PASS PARTITION DETAIL DWG. 021E0008 | A1109 | AX | 2 | 2019-04-12 | CON-BMP-VTRA-011136 | 2019-04-12 | FOR BAPCO REVIEW | 2019-04-26 | 2019-05-18 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000700 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 021E0008 | 6097-A5 | 021-E-GAD-40071-001 | HHPS VAPOR / RECYCLE GAS EXCHANGER SADDLE DETAIL DWG. 021E0008 | A1109 | AX | 2 | 2019-04-12 | CON-BMP-VTRA-011136 | 2019-04-12 | FOR BAPCO REVIEW | 2019-04-26 | 2019-05-18 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000700 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 021E0008 | 6097-B1 | 021-E-GAD-40104-001 | HHPS VAPOR / RECYCLE GAS EXCHANGER PART LIST DWG. 021E0008 | A1109 | AX | 2 | 2019-04-12 | CON-BMP-VTRA-011137 | 2019-04-12 | FOR BAPCO REVIEW | 2019-04-26 | 2019-05-15 | 3-REVIEWED WITH COMMENTS BMP-ROC-VTRE-000681 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 021E0008 | 6097-C1 | 021-E-DLB-40006-001 | NAMEPLATE DWG 021E0008 | A1112 | AX | 2 | 2019-03-28 | CON-BMP-VTRA-010886 | 2019-03-28 | FOR BAPCO REVIEW | 2019-04-12 | 2019-05-15 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000680 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 021E0008 | 6097-E | 021-E-CAL-40043-001 | PRESSURE CALCULATION 021E0008 | A1003 | BX | 2 | 2019-04-11 | CON-BMP-VTRA-011126 | 2019-04-11 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 021E0008 | 6097-FEA | 021-E-CAL-40046-001 | STRESS ANALYSIS OF BREECH LOCKZ SHAPE CHANNEL FORGING 021E0008 | A1003 | AX | 2 | 2019-07-10 | CON-BMP-VTRA-012791 | 2019-07-10 | FOR BAPCO REVIEW | 2019-07-24 |  |  | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 021E0008 | 6097-G | 021-E-CAL-40044-001 | SUPPORT CALCULATION 021E0008 | A1003 | BX | 2 | 2019-04-11 | CON-BMP-VTRA-011126 | 2019-04-11 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 021E0008 | 6097-G1 | 021-E-GAD-40105-001 | HHPS VAPOR / RECYCLE GAS EXCHANGER GASKET DWG. 021E0008 | A1109 | AX | 2 | 2019-04-12 | CON-BMP-VTRA-011137 | 2019-04-12 | FOR BAPCO REVIEW | 2019-04-26 | 2019-05-15 | 3-REVIEWED WITH COMMENTS BMP-ROC-VTRE-000681 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 021E0008 | 6097-HT | 021-E-PRO-40006-001 | HEAT TREATMENT PROCEDURE 021E0008 | B1201 | AX | 2 | 2019-01-15 | CON-BMP-VTRA-010217 | 2019-01-15 | FOR BAPCO REVIEW | 2019-01-29 | 2019-02-04 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000152 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 021E0008 | 6097-WP | 021-E-MCD-40006-001 | WELDING BOOK 021E0008 | B1304 | AX | 2 | 2019-01-30 | CON-BMP-VTRA-010326 | 2019-01-30 | FOR BAPCO REVIEW | 2019-02-13 | 2019-02-07 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000160 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 021E0008 | 7002-ITP | 021-E-PQP-40017-001 | FABRICATION AND QUALITY CONTROL PLAN 021E0008 | B1002 | 0AX | 3 | 2019-07-10 | CON-BMP-VTRA-012793 | 2019-07-10 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 021E0009 | 6098-00 | 021-E-GAD-40107-001 | HHPS VAPOR / STRIPPER FEED EXCHANGER GENERAL ARRANGEMENT 021E0009 | A1103 | BX | 2 | 2019-04-15 | CON-BMP-VTRA-011163 | 2019-04-15 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 021E0009 | 6098-A1 | 021-E-GAD-40108-001 | HHPS VAPOR / STRIPPER FEED EXCHANGER TUBE BUNDLE DWG. 021E0009 | A1109 | AX | 2 | 2019-04-12 | CON-BMP-VTRA-011136 | 2019-04-12 | FOR BAPCO REVIEW | 2019-04-26 | 2019-05-18 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000700 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 021E0009 | 6098-A2 | 021-E-GAD-40074-001 | HHPS VAPOR / STRIPPER FEED EXCHANGER CHANNEL DETAILS DWG. 021E0009 | A1109 | AX | 2 | 2019-04-11 | CON-BMP-VTRA-011130 | 2019-04-12 | FOR BAPCO REVIEW | 2019-04-26 | 2019-05-20 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000714 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 021E0009 | 6098-A3 | 021-E-GAD-40075-001 | HHPS VAPOR / STRIPPER FEED EXCHANGER NOZZLE DETAIL DWG. 021E0009 | A1109 | AX | 2 | 2019-04-12 | CON-BMP-VTRA-011137 | 2019-04-12 | FOR BAPCO REVIEW | 2019-04-26 | 2019-05-15 | 3-REVIEWED WITH COMMENTS BMP-ROC-VTRE-000681 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 021E0009 | 6098-A4 | 021-E-GAD-40076-001 | HHPS VAPOR / STRIPPER FEED EXCHANGER PASS PARTITION DETAILS DWG. 021E0009 | A1109 | AX | 2 | 2019-04-12 | CON-BMP-VTRA-011136 | 2019-04-12 | FOR BAPCO REVIEW | 2019-04-26 | 2019-05-18 | 3-REVIEWED WITH COMMENTS BMP-ROC-VTRE-000700 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 021E0009 | 6098-A5 | 021-E-GAD-40077-001 | HHPS VAPOR / STRIPPER FEED EXCHANGER SADDLES DETAILS DWG 021E0009 | A1109 | AX | 2 | 2019-04-12 | CON-BMP-VTRA-011136 | 2019-04-12 | FOR BAPCO REVIEW | 2019-04-26 | 2019-05-18 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000700 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 021E0009 | 6098-B1 | 021-E-GAD-40109-001 | HHPS VAPOR / STRIPPER FEED EXCHANGER PART LIST 021E0009 | A1109 | AX | 2 | 2019-04-12 | CON-BMP-VTRA-011136 | 2019-04-12 | FOR BAPCO REVIEW | 2019-04-26 | 2019-05-18 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000700 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 021E0009 | 6098-BT | 021-E-TSP-40007-001 | BOLT TIGHTENING PROCEDURE 021E0009 | A1202 | AX | 2 | 2019-04-15 | CON-BMP-VTRA-011180 | 2019-04-15 | FOR BAPCO REVIEW | 2019-04-30 | 2019-05-15 | 3-REVIEWED WITH COMMENTS BMP-ROC-VTRE-000686 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 021E0009 | 6098-C1 | 021-E-DLB-40007-001 | HHPS VAPOR / STRIPPER FEED EXCHANGER NAMEPLATE DWG 021E0009 | A1112 | AX | 2 | 2019-04-15 | CON-BMP-VTRA-011182 | 2019-04-15 | FOR BAPCO REVIEW | 2019-04-30 | 2019-05-15 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000683 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 021E0009 | 6098-E | 021-E-CAL-40047-001 | PRESSURE CALCULATION 021E0009 | A1003 | BX | 2 | 2019-04-11 | CON-BMP-VTRA-011126 | 2019-04-11 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 021E0009 | 6098-G | 021-E-CAL-40048-001 | SUPPORT CALCULATION 021E0009 | A1003 | BX | 2 | 2019-04-11 | CON-BMP-VTRA-011127 | 2019-04-11 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 021E0009 | 6098-G1 | 021-E-GAD-40110-001 | HHPS VAPOR / STRIPPER FEED EXCHANGER GASKET DWG 021E0009 | A1109 | AX | 2 | 2019-04-12 | CON-BMP-VTRA-011138 | 2019-04-12 | FOR BAPCO REVIEW | 2019-04-26 | 2019-05-18 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000699 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 021E0009 | 6098-HT | 021-E-PRO-40007-001 | HEAT TREATMENT PROCEDURE 021E0009 | B1201 | AX | 2 | 2019-01-15 | CON-BMP-VTRA-010217 | 2019-01-15 | FOR BAPCO REVIEW | 2019-01-29 | 2019-02-04 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000152 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 021E0009 | 6098-WP | 021-E-MCD-40007-001 | WELDING BOOK 021E0009 | B1304 | AX | 2 | 2019-01-30 | CON-BMP-VTRA-010326 | 2019-01-30 | FOR BAPCO REVIEW | 2019-02-13 | 2019-02-07 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000160 | CLASS 2
076551C-000R-MR-0610-001 | MATERIAL REQUISITION FOR HP SHELL AND TUBE HEAT EXCHANGES | OFF. L. RESTA S.P.A. | 021E0009 | 7003-ITP | 021-E-PQP-40018-001 | FABRICATION AND QUALITY CONTROL PLAN 021E0009 | B1002 | 0AX | 2 | 2019-07-10 | CON-BMP-VTRA-012789 | 2019-07-10 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-002 | MATERIAL REQUISITION FOR CLAD SHELL AND TUBE HEAT EXCHANGERS | HANTECH LTD | 018E0004A | HW18052-018E0004AB-CAL-001 | 018-E-CAL-40081-001 | STRENGTH CALCULATION 018E0004A/B | A1003 | BX | 2 | 2019-05-09 | CON-BMP-VTRA-011506 | 2019-05-09 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-002 | MATERIAL REQUISITION FOR CLAD SHELL AND TUBE HEAT EXCHANGERS | HANTECH LTD | 018E0004A | HW18052-018E0004AB-DWG-001 | 018-E-GAD-40233-001 | MP/ HT VAPOR/ATM COLUMN FEED GENERAL ASSEMBLY 018E0004A/B | A1103 | BX | 2 | 2019-05-09 | CON-BMP-VTRA-011509 | 2019-05-09 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-002 | MATERIAL REQUISITION FOR CLAD SHELL AND TUBE HEAT EXCHANGERS | HANTECH LTD | 018E0004A | HW18052-018E0004AB-DWG-002 | 018-E-GAD-40234-001 | MP/ HT VAPOR/ATM COLUMN FEED EXCHANGER DETAIL OF BODY 018E0004A/B | A1109 | BX | 2 | 2019-05-09 | CON-BMP-VTRA-011502 | 2019-05-09 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-002 | MATERIAL REQUISITION FOR CLAD SHELL AND TUBE HEAT EXCHANGERS | HANTECH LTD | 018E0004A | HW18052-018E0004AB-DWG-003 | 018-E-GAD-40235-001 | MP/ HT VAPOR/ATM TOWER FEED EXCHANGER DETAIL OF BUNDLE 018E0004A/B | A1109 | BX | 2 | 2019-05-16 | CON-BMP-VTRA-011636 | 2019-05-16 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-002 | MATERIAL REQUISITION FOR CLAD SHELL AND TUBE HEAT EXCHANGERS | HANTECH LTD | 018E0004A | HW18052-018E0004AB-DWG-005 | 018-E-GAD-40236-001 | MP/ HT VAPOR/ATM TOWER FEED EXCHANGER DETAIL OF SADDLE 018E0004A/B | A1109 | BX | 2 | 2019-05-16 | CON-BMP-VTRA-011636 | 2019-05-16 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-002 | MATERIAL REQUISITION FOR CLAD SHELL AND TUBE HEAT EXCHANGERS | HANTECH LTD | 018E0004A | HW18052-018E0004AB-DWG-006 | 018-E-GAD-40237-001 | MP/ HT VAPOR/ATM TOWER FEED EXCHANGER DETAIL OF NOZZLE 018E0004A/B | A1109 | BX | 2 | 2019-05-16 | CON-BMP-VTRA-011636 | 2019-05-16 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-002 | MATERIAL REQUISITION FOR CLAD SHELL AND TUBE HEAT EXCHANGERS | HANTECH LTD | 018E0004A | HW18052-018E0004AB-DWG-007 | 018-E-DLB-40013-001 | MP/ HT VAPOR/ATM TOWER FEED EXCHANGER DETAIL OF NAME PLATE 018E0004A/B | A1112 | BX | 2 | 2019-05-10 | CON-BMP-VTRA-011510 | 2019-05-10 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-002 | MATERIAL REQUISITION FOR CLAD SHELL AND TUBE HEAT EXCHANGERS | HANTECH LTD | 018E0004A | HW18052-DOC-100 | 018-E-MRS-40001-001 | MONTHLY PROGRESS REPORT ALL ITEMS | C1002 | CX | 4 | 2019-05-29 | CON-BMP-VTRA-011841 | 2019-05-29 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-0610-002 | MATERIAL REQUISITION FOR CLAD SHELL AND TUBE HEAT EXCHANGERS | HANTECH LTD | 018E0004A | HW18052-DOC-101 | 018-E-INX-40002-001 | LIST OF VENDOR'S DOCUMENTS AND DWGS FOR CLAD AND TUBE EXCHANGERS ALL ITEMS | A0001 | CX | 2 | 2019-05-14 | CON-BMP-VTRA-011559 | 2019-05-14 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-002 | MATERIAL REQUISITION FOR CLAD SHELL AND TUBE HEAT EXCHANGERS | HANTECH LTD | 018E0004A | HW18052-DOC-102 | 018-E-PQS-40001-001 | SUB VENDOR LIST ALL ITEMS | B1401 | AX | 2 | 2019-01-29 | CON-BMP-VTRA-010305 | 2019-01-29 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-0610-002 | MATERIAL REQUISITION FOR CLAD SHELL AND TUBE HEAT EXCHANGERS | HANTECH LTD | 018E0004A | HW18052-DOC-103 | 018-E-PQP-40072-001 | JOB QUALITY ASSURANCE PLAN ALL ITEMS (EX BAPCO N. 018-E-PLN-40001-001) | B1001 | BX | 2 | 2019-04-01 | CON-BMP-VTRA-010944 | 2019-04-01 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-002 | MATERIAL REQUISITION FOR CLAD SHELL AND TUBE HEAT EXCHANGERS | HANTECH LTD | 018E0004A | HW18052-DOC-104 | 018-E-TSP-40013-001 | MATERIAL PURCHASE SPECIFICATION FOR TUBE AND CLAD PLATE ALL ITEMS | B1203 | AX | 2 | 2019-02-05 | CON-BMP-VTRA-010352 | 2019-02-05 | FOR BAPCO REVIEW | 2019-02-19 | 2019-02-19 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000197 | CLASS 2
076551C-000R-MR-0610-002 | MATERIAL REQUISITION FOR CLAD SHELL AND TUBE HEAT EXCHANGERS | HANTECH LTD | 018E0004A | HW18052-DOC-105 | 018-E-SCH-40001-001 | ENGINEERING PROCUREMENT MANUFACTURING & TEST ALL ITEMS | C1001 | CX | 4 | 2019-05-29 | CON-BMP-VTRA-011840 | 2019-05-29 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-0610-002 | MATERIAL REQUISITION FOR CLAD SHELL AND TUBE HEAT EXCHANGERS | HANTECH LTD | 018E0004A | HW18052-DOC-106 | 018-E-INV-40001-001 | UNPRICED COPY OF MAIN SUBORDERS ALL ITEMS | C1005 | BX | 4 | 2019-05-29 | CON-BMP-VTRA-011843 | 2019-05-29 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-0610-002 | MATERIAL REQUISITION FOR CLAD SHELL AND TUBE HEAT EXCHANGERS | HANTECH LTD | 018E0004A | HW18052-DOC-109 | 018-E-PQP-40025-001 | FABRICATION AND QUALITY CONTROL PLAN 018E0004A/B | B1002 | CX | 2 | 2019-06-25 | CON-BMP-VTRA-012427 | 2019-06-25 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-002 | MATERIAL REQUISITION FOR CLAD SHELL AND TUBE HEAT EXCHANGERS | HANTECH LTD | 018E0004A | HW18052-DOC-110 | 018-E-PRO-40020-001 | INSPECTION AND TEST PROCEDURE ALL ITEMS | B1103 | CX | 2 | 2019-06-13 | CON-BMP-VTRA-012186 | 2019-06-13 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-002 | MATERIAL REQUISITION FOR CLAD SHELL AND TUBE HEAT EXCHANGERS | HANTECH LTD | 018E0004A | HW18052-DOC-111 | 018-E-MCD-40025-001 | WPS AND PQR WITH WELD MAP ALL ITEMS | B1304 | CX | 2 | 2019-06-25 | CON-BMP-VTRA-012421 | 2019-06-25 | FOR BAPCO REVIEW | 2019-07-09 | 2019-07-08 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001217 | CLASS 2
076551C-000R-MR-0610-002 | MATERIAL REQUISITION FOR CLAD SHELL AND TUBE HEAT EXCHANGERS | HANTECH LTD | 018E0004A | HW18052-DOC-113 | 018-E-PRO-40013-001 | NDE PROCEDURE ALL ITEMS | B1202 | AX | 2 | 2019-04-09 | CON-BMP-VTRA-011073 | 2019-04-09 | FOR BAPCO REVIEW | 2019-04-24 | 2019-04-21 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000541 | CLASS 2
076551C-000R-MR-0610-002 | MATERIAL REQUISITION FOR CLAD SHELL AND TUBE HEAT EXCHANGERS | HANTECH LTD | 018E0004A | HW18052-DOC-114 | 018-E-PRO-40014-001 | PMI TEST PROCEDURE ALL ITEMS | B1103 | BX | 2 | 2019-06-13 | CON-BMP-VTRA-012186 | 2019-06-13 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-002 | MATERIAL REQUISITION FOR CLAD SHELL AND TUBE HEAT EXCHANGERS | HANTECH LTD | 018E0004A | HW18052-DOC-115 | 018-E-PRO-40015-001 | HEAT TREATMENT PROCEDURE ALL ITEMS | B1201 | 0X | 2 | 2019-06-26 | CON-BMP-VTRA-012485 | 2019-06-26 | FOR BAPCO REVIEW | 2019-07-11 |  |  | CLASS 2
076551C-000R-MR-0610-002 | MATERIAL REQUISITION FOR CLAD SHELL AND TUBE HEAT EXCHANGERS | HANTECH LTD | 018E0004A | HW18052-DOC-116 | 018-E-PRO-40016-001 | MOCK-UP TEST PROCEDURE ALL ITEMS | B1103 | AX | 2 | 2019-05-06 | CON-BMP-VTRA-011435 | 2019-05-06 | FOR BAPCO REVIEW | 2019-05-21 | 2019-05-19 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000706 | CLASS 2
076551C-000R-MR-0610-002 | MATERIAL REQUISITION FOR CLAD SHELL AND TUBE HEAT EXCHANGERS | HANTECH LTD | 018E0004A | HW18052-DOC-117 | 018-E-TSP-40014-001 | BOLT TIGHTENING PROCEDURE ALL ITEMS | A1202 | AX | 2 | 2019-05-29 | CON-BMP-VTRA-011838 | 2019-05-29 | FOR BAPCO REVIEW | 2019-06-13 | 2019-06-11 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000902 | CLASS 2
076551C-000R-MR-0610-002 | MATERIAL REQUISITION FOR CLAD SHELL AND TUBE HEAT EXCHANGERS | HANTECH LTD | 018E0004A | HW18052-DOC-118 | 018-E-TSP-40015-001 | PAINTING PROCEDURE ALL ITEMS | A0106 | 0X | 2 | 2019-06-21 | CON-BMP-VTRA-012342 | 2019-06-21 | FOR BAPCO REVIEW | 2019-07-05 | 2019-07-04 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001161 | CLASS 2
076551C-000R-MR-0610-002 | MATERIAL REQUISITION FOR CLAD SHELL AND TUBE HEAT EXCHANGERS | HANTECH LTD | 018E0004A | HW18052-DOC-119 | 018-E-PRO-40017-001 | HYDROSTATIC TEST PROCEDURE FORCLAD SHELL AND TUBE HEAT EXCHANGERS ALL ITEMS | B1103 | AX | 2 | 2019-06-13 | CON-BMP-VTRA-012185 | 2019-06-13 | FOR BAPCO REVIEW | 2019-06-27 | 2019-06-25 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001034 | CLASS 2
076551C-000R-MR-0610-002 | MATERIAL REQUISITION FOR CLAD SHELL AND TUBE HEAT EXCHANGERS | HANTECH LTD | 018E0004A | HW18052-DOC-120 | 018-E-PRO-40018-001 | PACKING PROCEDURE WITH RUST PREVENTION ALL ITEMS | B1103 | AX | 2 | 2019-05-29 | CON-BMP-VTRA-011831 | 2019-05-29 | FOR BAPCO REVIEW | 2019-06-13 | 2019-06-10 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000894 | CLASS 2
076551C-000R-MR-0610-002 | MATERIAL REQUISITION FOR CLAD SHELL AND TUBE HEAT EXCHANGERS | HANTECH LTD | 018E0005 | HW18052-018E0005-CAL-001 | 018-E-CAL-40082-001 | STRENGTH CALCULATION 018E0005 | A1003 | BX | 2 | 2019-05-15 | CON-BMP-VTRA-011592 | 2019-05-15 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-002 | MATERIAL REQUISITION FOR CLAD SHELL AND TUBE HEAT EXCHANGERS | HANTECH LTD | 018E0005 | HW18052-018E0005-DWG-001 | 018-E-GAD-40238-001 | MP/HT VAPOR/ MP STEAM GENERATOR GENERAL ASSEMBLY 018E0005 | A1103 | 0XX | 2 | 2019-06-25 | CON-BMP-VTRA-012415 | 2019-06-25 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-002 | MATERIAL REQUISITION FOR CLAD SHELL AND TUBE HEAT EXCHANGERS | HANTECH LTD | 018E0005 | HW18052-018E0005-DWG-002 | 018-E-GAD-40239-001 | MP/HT VAPOR/ MP STEAM GENERATOR DETAIL OF BODY 018E0005 | A1109 | BX | 2 | 2019-05-14 | CON-BMP-VTRA-011583 | 2019-05-14 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-002 | MATERIAL REQUISITION FOR CLAD SHELL AND TUBE HEAT EXCHANGERS | HANTECH LTD | 018E0005 | HW18052-018E0005-DWG-003 | 018-E-GAD-40240-001 | MP/HT VAPOR/ MP STEAM GENERATOR DETAIL OF BUNDLE 018E0005 | A1109 | BX | 2 | 2019-05-16 | CON-BMP-VTRA-011637 | 2019-05-16 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-002 | MATERIAL REQUISITION FOR CLAD SHELL AND TUBE HEAT EXCHANGERS | HANTECH LTD | 018E0005 | HW18052-018E0005-DWG-005 | 018-E-GAD-40241-001 | MP/HT VAPOR/ MP STEAM GENERATOR DETAIL OF SADDLE 018E0005 | A1109 | BX | 2 | 2019-05-16 | CON-BMP-VTRA-011637 | 2019-05-16 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-002 | MATERIAL REQUISITION FOR CLAD SHELL AND TUBE HEAT EXCHANGERS | HANTECH LTD | 018E0005 | HW18052-018E0005-DWG-006 | 018-E-GAD-40242-001 | MP/HT VAPOR/ MP STEAM GENERATOR DETAIL OF MANHOLE 018E0005 | A1109 | BX | 2 | 2019-05-16 | CON-BMP-VTRA-011637 | 2019-05-16 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-002 | MATERIAL REQUISITION FOR CLAD SHELL AND TUBE HEAT EXCHANGERS | HANTECH LTD | 018E0005 | HW18052-018E0005-DWG-007 | 018-E-GAD-40453-001 | MP/HT VAPOR/ MP STEAM GENERATOR DETAIL OF NOZZLE 018E0005 | A1109 | BX | 2 | 2019-05-14 | CON-BMP-VTRA-011583 | 2019-05-14 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-002 | MATERIAL REQUISITION FOR CLAD SHELL AND TUBE HEAT EXCHANGERS | HANTECH LTD | 018E0005 | HW18052-018E0005-DWG-009 | 018-E-DLB-40014-001 | MP-HT VAPOR MP STEAM GENERATOR DETAIL OF NAME PLATE 018E0005 | A1112 | BX | 2 | 2019-05-15 | CON-BMP-VTRA-011590 | 2019-05-15 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-002 | MATERIAL REQUISITION FOR CLAD SHELL AND TUBE HEAT EXCHANGERS | HANTECH LTD | 018E0005 | HW18052-DOC-109-2 | 018-E-PQP-40064-001 | FABRICATION AND QUALITY CONTROL PLAN 018E0005 | B1002 | BX | 2 | 2019-06-25 | CON-BMP-VTRA-012427 | 2019-06-25 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-002 | MATERIAL REQUISITION FOR CLAD SHELL AND TUBE HEAT EXCHANGERS | HANTECH LTD | 018E0005 | HW18052-DOC-111-2 | 018-E-MCD-40093-001 | WPS AND PQR WITH WELD MAP MP/HT VAPOR/ MP STEAM GENERATOR - 018E0005 | B1304 | BX | 2 | 2019-06-06 | CON-BMP-VTRA-012064 | 2019-06-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-002 | MATERIAL REQUISITION FOR CLAD SHELL AND TUBE HEAT EXCHANGERS | HANTECH LTD | 018E0008A | HW18052-018E0008AB-CAL-001 | 018-E-CAL-40083-001 | STRENGTH CALCULATION 018E0008A/B | A1003 | BX | 2 | 2019-05-15 | CON-BMP-VTRA-011592 | 2019-05-15 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-002 | MATERIAL REQUISITION FOR CLAD SHELL AND TUBE HEAT EXCHANGERS | HANTECH LTD | 018E0008A | HW18052-018E0008AB-DWG-001 | 018-E-GAD-40243-001 | LT OIL/DIESEL EXCHANGER GENERAL ASSEMBLY 018E0008A/B | A1103 | BX | 2 | 2019-05-15 | CON-BMP-VTRA-011600 | 2019-05-15 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-002 | MATERIAL REQUISITION FOR CLAD SHELL AND TUBE HEAT EXCHANGERS | HANTECH LTD | 018E0008A | HW18052-018E0008AB-DWG-002 | 018-E-GAD-40244-001 | LT OIL/DIESEL EXCHANGER DETAIL OF BODY 018E0008A/B | A1109 | BX | 2 | 2019-05-14 | CON-BMP-VTRA-011583 | 2019-05-14 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-002 | MATERIAL REQUISITION FOR CLAD SHELL AND TUBE HEAT EXCHANGERS | HANTECH LTD | 018E0008A | HW18052-018E0008AB-DWG-003 | 018-E-GAD-40245-001 | LT OIL DIESEL EXCHANGER DETAIL OF BUNDLE 018E0008AB | A1109 | 0X | 2 | 2019-06-14 | CON-BMP-VTRA-012225 | 2019-06-14 | FOR BAPCO REVIEW | 2019-07-01 | 2019-07-08 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001212 | CLASS 2
076551C-000R-MR-0610-002 | MATERIAL REQUISITION FOR CLAD SHELL AND TUBE HEAT EXCHANGERS | HANTECH LTD | 018E0008A | HW18052-018E0008AB-DWG-005 | 018-E-GAD-40246-001 | LT OIL DIESEL EXCHANGER DETAIL OF SADDLE 018E0008AB | A1109 | BX | 2 | 2019-05-14 | CON-BMP-VTRA-011583 | 2019-05-14 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-002 | MATERIAL REQUISITION FOR CLAD SHELL AND TUBE HEAT EXCHANGERS | HANTECH LTD | 018E0008A | HW18052-018E0008AB-DWG-007 | 018-E-GAD-40247-001 | LT OIL DIESEL EXCHANGER DETAIL OF NOZZLE 018E0008AB | A1109 | 0X | 2 | 2019-06-14 | CON-BMP-VTRA-012225 | 2019-06-14 | FOR BAPCO REVIEW | 2019-07-01 | 2019-07-08 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001212 | CLASS 2
076551C-000R-MR-0610-002 | MATERIAL REQUISITION FOR CLAD SHELL AND TUBE HEAT EXCHANGERS | HANTECH LTD | 018E0008A | HW18052-018E0008AB-DWG-009 | 018-E-GAD-40248-001 | LT OIL DIESEL EXCHANGERS DETAIL OF TEST RING 018E0008A/B | A1109 | AX | 2 | 2019-05-14 | CON-BMP-VTRA-011581 | 2019-05-14 | FOR BAPCO REVIEW | 2019-05-29 | 2019-05-30 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000836 | CLASS 2
076551C-000R-MR-0610-002 | MATERIAL REQUISITION FOR CLAD SHELL AND TUBE HEAT EXCHANGERS | HANTECH LTD | 018E0008A | HW18052-018E0008AB-DWG-010 | 018-E-DLB-40015-001 | LT OIL DIESEL EXCHANGER DETAIL OF NAME PLATE 018E0008AB | A1112 | 0X | 2 | 2019-05-30 | CON-BMP-VTRA-011846 | 2019-05-30 | FOR BAPCO REVIEW | 2019-06-13 | 2019-06-17 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000950 | CLASS 2
076551C-000R-MR-0610-002 | MATERIAL REQUISITION FOR CLAD SHELL AND TUBE HEAT EXCHANGERS | HANTECH LTD | 018E0008A | HW18052-DOC-109-3 | 018-E-PQP-40065-001 | FABRICATION AND QUALITY CONTROL PLAN 018E0008A/B | B1002 | BX | 2 | 2019-06-25 | CON-BMP-VTRA-012427 | 2019-06-25 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-002 | MATERIAL REQUISITION FOR CLAD SHELL AND TUBE HEAT EXCHANGERS | HANTECH LTD | 018E0008A | HW18052-DOC-111-3 | 018-E-MCD-40094-001 | WPS AND PQR WITH WELD MAP LT OIL/DIESEL EXCHANGER - 018E0008A/B | B1304 | BX | 2 | 2019-06-06 | CON-BMP-VTRA-012064 | 2019-06-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-002 | MATERIAL REQUISITION FOR CLAD SHELL AND TUBE HEAT EXCHANGERS | HANTECH LTD | 018E0009 | HW18052-018E0009-CAL-001 | 018-E-CAL-40084-001 | STRENGTH CALCULATION 018E0009 | A1003 | BX | 2 | 2019-05-15 | CON-BMP-VTRA-011592 | 2019-05-15 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-002 | MATERIAL REQUISITION FOR CLAD SHELL AND TUBE HEAT EXCHANGERS | HANTECH LTD | 018E0009 | HW18052-018E0009-DWG-001 | 018-E-GAD-40249-001 | LT OIL/DIESEL PUMPAROUND EXCHANGER GENERAL ASSEMBLY 018E0009 | A1103 | BX | 2 | 2019-05-15 | CON-BMP-VTRA-011600 | 2019-05-15 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-002 | MATERIAL REQUISITION FOR CLAD SHELL AND TUBE HEAT EXCHANGERS | HANTECH LTD | 018E0009 | HW18052-018E0009-DWG-002 | 018-E-GAD-40250-001 | LT OIL/DIESEL PUMPAROUND EXCHANGER DETAIL OF BODY 018E0009 | A1109 | BX | 2 | 2019-05-15 | CON-BMP-VTRA-011595 | 2019-05-15 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-002 | MATERIAL REQUISITION FOR CLAD SHELL AND TUBE HEAT EXCHANGERS | HANTECH LTD | 018E0009 | HW18052-018E0009-DWG-003 | 018-E-GAD-40251-001 | LT OIL/DIESEL PUMPAROUND EXCHANGER DETAIL OF BUNDLE 018E0009 | A1109 | BX | 2 | 2019-05-14 | CON-BMP-VTRA-011583 | 2019-05-14 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-002 | MATERIAL REQUISITION FOR CLAD SHELL AND TUBE HEAT EXCHANGERS | HANTECH LTD | 018E0009 | HW18052-018E0009-DWG-005 | 018-E-GAD-40252-001 | LT OIL/DIESEL PUMPAROUND EXCHANGER DETAIL OF SADDLE 018E0009 | A1109 | BX | 2 | 2019-05-14 | CON-BMP-VTRA-011583 | 2019-05-14 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-002 | MATERIAL REQUISITION FOR CLAD SHELL AND TUBE HEAT EXCHANGERS | HANTECH LTD | 018E0009 | HW18052-018E0009-DWG-006 | 018-E-GAD-40253-001 | LT OIL/DIESEL PUMPAROUND EXCHANGER DETAIL OF NOZZLE 018E0009 | A1109 | 0X | 2 | 2019-05-15 | CON-BMP-VTRA-011591 | 2019-05-15 | FOR BAPCO REVIEW | 2019-05-29 | 2019-05-31 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000858 | CLASS 2
076551C-000R-MR-0610-002 | MATERIAL REQUISITION FOR CLAD SHELL AND TUBE HEAT EXCHANGERS | HANTECH LTD | 018E0009 | HW18052-018E0009-DWG-007 | 018-E-GAD-40254-001 | LT OIL DIESEL PUMPAROUND EXCHANGER DETAIL OF TEST RING 018E0009 | A1109 | AX | 2 | 2019-05-14 | CON-BMP-VTRA-011581 | 2019-05-14 | FOR BAPCO REVIEW | 2019-05-29 | 2019-05-30 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000836 | CLASS 2
076551C-000R-MR-0610-002 | MATERIAL REQUISITION FOR CLAD SHELL AND TUBE HEAT EXCHANGERS | HANTECH LTD | 018E0009 | HW18052-018E0009-DWG-008 | 018-E-DLB-40016-001 | LT OIL/DIESEL PUMPAROUND EXCHANGER DETAIL OF NAME PLATE 018E0009 | A1112 | 0X | 2 | 2019-05-15 | CON-BMP-VTRA-011599 | 2019-05-15 | FOR BAPCO REVIEW | 2019-05-29 | 2019-05-31 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000856 | CLASS 2
076551C-000R-MR-0610-002 | MATERIAL REQUISITION FOR CLAD SHELL AND TUBE HEAT EXCHANGERS | HANTECH LTD | 018E0009 | HW18052-DOC-109-4 | 018-E-PQP-40066-001 | FABRICATION AND QUALITY CONTROL PLAN 018E0009 | B1002 | BX | 2 | 2019-06-25 | CON-BMP-VTRA-012427 | 2019-06-25 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-002 | MATERIAL REQUISITION FOR CLAD SHELL AND TUBE HEAT EXCHANGERS | HANTECH LTD | 018E0009 | HW18052-DOC-111-4 | 018-E-MCD-40095-001 | WPS AND PQR WITH WELD MAP LT OIL/ DIESEL PUMPAROUND EXCHANGER - 018E0009 | B1304 | BX | 2 | 2019-06-06 | CON-BMP-VTRA-012064 | 2019-06-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-002 | MATERIAL REQUISITION FOR CLAD SHELL AND TUBE HEAT EXCHANGERS | HANTECH LTD | 018E0024 | HW18052-018E0024-CAL-001 | 018-E-CAL-40085-001 | STRENGTH CALCULATION 018E0024 | A1003 | BX | 2 | 2019-05-14 | CON-BMP-VTRA-011557 | 2019-05-14 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-002 | MATERIAL REQUISITION FOR CLAD SHELL AND TUBE HEAT EXCHANGERS | HANTECH LTD | 018E0024 | HW18052-018E0024-DWG-001 | 018-E-GAD-40255-001 | HVGO FEED EXCHANGER GENERAL ASSEMBLY 018E0024 | A1103 | BX | 2 | 2019-05-14 | CON-BMP-VTRA-011556 | 2019-05-14 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-002 | MATERIAL REQUISITION FOR CLAD SHELL AND TUBE HEAT EXCHANGERS | HANTECH LTD | 018E0024 | HW18052-018E0024-DWG-002 | 018-E-GAD-40256-001 | HVGO FEED EXCHANGER DETAIL OF BODY 018E0024 | A1109 | BX | 2 | 2019-05-14 | CON-BMP-VTRA-011583 | 2019-05-14 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-002 | MATERIAL REQUISITION FOR CLAD SHELL AND TUBE HEAT EXCHANGERS | HANTECH LTD | 018E0024 | HW18052-018E0024-DWG-003 | 018-E-GAD-40257-001 | HVGO FEED EXCHANGER DETAIL OF BUNDLE 018E0024 | A1109 | BX | 2 | 2019-05-14 | CON-BMP-VTRA-011583 | 2019-05-14 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-002 | MATERIAL REQUISITION FOR CLAD SHELL AND TUBE HEAT EXCHANGERS | HANTECH LTD | 018E0024 | HW18052-018E0024-DWG-005 | 018-E-GAD-40258-001 | HVGO FEED EXCHANGER DETAIL OF SADDLE 018E0024 | A1109 | BX | 2 | 2019-05-14 | CON-BMP-VTRA-011583 | 2019-05-14 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-002 | MATERIAL REQUISITION FOR CLAD SHELL AND TUBE HEAT EXCHANGERS | HANTECH LTD | 018E0024 | HW18052-018E0024-DWG-006 | 018-E-GAD-40259-001 | HVGO FEED EXCHANGER DETAIL OF NOZZLE 018E0024 | A1109 | BX | 2 | 2019-05-14 | CON-BMP-VTRA-011583 | 2019-05-14 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-002 | MATERIAL REQUISITION FOR CLAD SHELL AND TUBE HEAT EXCHANGERS | HANTECH LTD | 018E0024 | HW18052-018E0024-DWG-007 | 018-E-GAD-40260-001 | HVGO FEED EXCHANGER DETAIL OF TEST RING 018E0024 | A1109 | AX | 2 | 2019-05-14 | CON-BMP-VTRA-011581 | 2019-05-14 | FOR BAPCO REVIEW | 2019-05-29 | 2019-05-30 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000836 | CLASS 2
076551C-000R-MR-0610-002 | MATERIAL REQUISITION FOR CLAD SHELL AND TUBE HEAT EXCHANGERS | HANTECH LTD | 018E0024 | HW18052-018E0024-DWG-008 | 018-E-DLB-40017-001 | HVGO FEED EXCHANGER DETAIL OF NAME PLATE 018E0024 | A1112 | BX | 2 | 2019-05-15 | CON-BMP-VTRA-011590 | 2019-05-15 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-002 | MATERIAL REQUISITION FOR CLAD SHELL AND TUBE HEAT EXCHANGERS | HANTECH LTD | 018E0024 | HW18052-DOC-109-5 | 018-E-PQP-40067-001 | FABRICATION AND QUALITY CONTROL PLAN 018E0024 | B1002 | BX | 2 | 2019-06-25 | CON-BMP-VTRA-012427 | 2019-06-25 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-002 | MATERIAL REQUISITION FOR CLAD SHELL AND TUBE HEAT EXCHANGERS | HANTECH LTD | 018E0024 | HW18052-DOC-111-5 | 018-E-MCD-40096-001 | WPS AND PQR WITH WELD MAP HVGO/FEED EXCHANGER -018E0024 | B1304 | BX | 2 | 2019-06-06 | CON-BMP-VTRA-012064 | 2019-06-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-002 | MATERIAL REQUISITION FOR CLAD SHELL AND TUBE HEAT EXCHANGERS | HANTECH LTD | 018E0025 | HW18052-018E0025-CAL-001 | 018-E-CAL-40086-001 | STRENGTH CALCULATION 018E0025 | A1003 | BX | 2 | 2019-05-15 | CON-BMP-VTRA-011592 | 2019-05-15 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-002 | MATERIAL REQUISITION FOR CLAD SHELL AND TUBE HEAT EXCHANGERS | HANTECH LTD | 018E0025 | HW18052-018E0025-DWG-001 | 018-E-GAD-40261-001 | HVGO STEAM GENERATOR GENERAL ASSEMBLY 018E0025 | A1103 | BX | 2 | 2019-05-15 | CON-BMP-VTRA-011600 | 2019-05-15 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-002 | MATERIAL REQUISITION FOR CLAD SHELL AND TUBE HEAT EXCHANGERS | HANTECH LTD | 018E0025 | HW18052-018E0025-DWG-002 | 018-E-GAD-40262-001 | HVGO STEAM GENERATOR DETAIL OF BODY 018E0025 | A1109 | 0X | 2 | 2019-06-20 | CON-BMP-VTRA-012316 | 2019-06-20 | FOR BAPCO REVIEW | 2019-07-04 | 2019-07-10 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001271 | CLASS 2
076551C-000R-MR-0610-002 | MATERIAL REQUISITION FOR CLAD SHELL AND TUBE HEAT EXCHANGERS | HANTECH LTD | 018E0025 | HW18052-018E0025-DWG-003 | 018-E-GAD-40263-001 | HVGO STEAM GENERATOR DETAIL OFBUNDLE 018E0025 | A1109 | 0X | 2 | 2019-05-15 | CON-BMP-VTRA-011591 | 2019-05-15 | FOR BAPCO REVIEW | 2019-05-29 | 2019-05-31 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000858 | CLASS 2
076551C-000R-MR-0610-002 | MATERIAL REQUISITION FOR CLAD SHELL AND TUBE HEAT EXCHANGERS | HANTECH LTD | 018E0025 | HW18052-018E0025-DWG-005 | 018-E-GAD-40264-001 | HVGO STEAM GENERATOR DETAIL OFSADDLE 018E0025 | A1109 | 0X | 2 | 2019-06-20 | CON-BMP-VTRA-012316 | 2019-06-20 | FOR BAPCO REVIEW | 2019-07-04 | 2019-07-10 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001271 | CLASS 2
076551C-000R-MR-0610-002 | MATERIAL REQUISITION FOR CLAD SHELL AND TUBE HEAT EXCHANGERS | HANTECH LTD | 018E0025 | HW18052-018E0025-DWG-006 | 018-E-GAD-40265-001 | HVGO STEAM GENERATOR DETAIL OF MANHOLE 018E0025 | A1109 | 0X | 2 | 2019-05-15 | CON-BMP-VTRA-011591 | 2019-05-15 | FOR BAPCO REVIEW | 2019-05-29 | 2019-05-31 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000858 | CLASS 2
076551C-000R-MR-0610-002 | MATERIAL REQUISITION FOR CLAD SHELL AND TUBE HEAT EXCHANGERS | HANTECH LTD | 018E0025 | HW18052-018E0025-DWG-007 | 018-E-GAD-40452-001 | HVGO STEAM GENERATOR DETAIL OF NOZZLE 018E0025 | A1109 | 0X | 2 | 2019-05-15 | CON-BMP-VTRA-011591 | 2019-05-15 | FOR BAPCO REVIEW | 2019-05-29 | 2019-05-31 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000858 | CLASS 2
076551C-000R-MR-0610-002 | MATERIAL REQUISITION FOR CLAD SHELL AND TUBE HEAT EXCHANGERS | HANTECH LTD | 018E0025 | HW18052-018E0025-DWG-009 | 018-E-DLB-40018-001 | HVGO STEAM GENERATOR DETAIL OFNAME PLATE 018E0025 | A1112 | BX | 2 | 2019-05-15 | CON-BMP-VTRA-011590 | 2019-05-15 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-002 | MATERIAL REQUISITION FOR CLAD SHELL AND TUBE HEAT EXCHANGERS | HANTECH LTD | 018E0025 | HW18052-DOC-109-6 | 018-E-PQP-40068-001 | FABRICATION AND QUALITY CONTROL PLAN 018E0025 | B1002 | BX | 2 | 2019-06-25 | CON-BMP-VTRA-012427 | 2019-06-25 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-002 | MATERIAL REQUISITION FOR CLAD SHELL AND TUBE HEAT EXCHANGERS | HANTECH LTD | 018E0025 | HW18052-DOC-111-6 | 018-E-MCD-40097-001 | WPS AND PQR WITH WELD MAP HVGO STEAM GENERATOR - 018E0025 | B1304 | BX | 2 | 2019-06-06 | CON-BMP-VTRA-012064 | 2019-06-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-002 | MATERIAL REQUISITION FOR CLAD SHELL AND TUBE HEAT EXCHANGERS | HANTECH LTD | 018E0026A | HW18052-018E0026AB-CAL-001 | 018-E-CAL-40087-001 | STRENGTH CALCULATION 018E0026A/B | A1003 | BX | 2 | 2019-05-15 | CON-BMP-VTRA-011592 | 2019-05-15 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-002 | MATERIAL REQUISITION FOR CLAD SHELL AND TUBE HEAT EXCHANGERS | HANTECH LTD | 018E0026A | HW18052-018E0026AB-DWG-001 | 018-E-GAD-40266-001 | VAC COLUMN BOTTOM/ FEED EXCHANGER GENERAL ASSEMBLY 018E0026A/B | A1103 | BX | 2 | 2019-05-15 | CON-BMP-VTRA-011600 | 2019-05-15 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-002 | MATERIAL REQUISITION FOR CLAD SHELL AND TUBE HEAT EXCHANGERS | HANTECH LTD | 018E0026A | HW18052-018E0026AB-DWG-002 | 018-E-GAD-40267-001 | VAC COLUMN BOTTOM/FEED EXCHANGER DETAIL OF BODY 018E0026A/B | A1109 | BX | 2 | 2019-05-14 | CON-BMP-VTRA-011583 | 2019-05-14 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-002 | MATERIAL REQUISITION FOR CLAD SHELL AND TUBE HEAT EXCHANGERS | HANTECH LTD | 018E0026A | HW18052-018E0026AB-DWG-003 | 018-E-GAD-40268-001 | VAC COLUMN BTM FEED EXCHANGER DETAIL OF BUNDLE 018E0026AB | A1109 | BX | 2 | 2019-05-15 | CON-BMP-VTRA-011595 | 2019-05-15 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-002 | MATERIAL REQUISITION FOR CLAD SHELL AND TUBE HEAT EXCHANGERS | HANTECH LTD | 018E0026A | HW18052-018E0026AB-DWG-005 | 018-E-GAD-40269-001 | VAC COLUMN BTM FEED EXCHANGER DETAIL OF SADDLE 018E0026AB | A1109 | BX | 2 | 2019-05-14 | CON-BMP-VTRA-011583 | 2019-05-14 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-002 | MATERIAL REQUISITION FOR CLAD SHELL AND TUBE HEAT EXCHANGERS | HANTECH LTD | 018E0026A | HW18052-018E0026AB-DWG-006 | 018-E-GAD-40270-001 | VAC COLUMN BTM FEED EXCHANGER DETAIL OF NOZZLE 018E0026AB | A1109 | BX | 2 | 2019-05-15 | CON-BMP-VTRA-011595 | 2019-05-15 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-002 | MATERIAL REQUISITION FOR CLAD SHELL AND TUBE HEAT EXCHANGERS | HANTECH LTD | 018E0026A | HW18052-018E0026AB-DWG-007 | 018-E-GAD-40271-001 | VAC. COLUMN BOTTOM FEED EXCHANGER DETAIL OF TEST RING 018E0026A/B | A1109 | AX | 2 | 2019-05-14 | CON-BMP-VTRA-011581 | 2019-05-14 | FOR BAPCO REVIEW | 2019-05-29 | 2019-05-30 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000836 | CLASS 2
076551C-000R-MR-0610-002 | MATERIAL REQUISITION FOR CLAD SHELL AND TUBE HEAT EXCHANGERS | HANTECH LTD | 018E0026A | HW18052-018E0026AB-DWG-008 | 018-E-DLB-40019-001 | VAC COLUMN BTM FEED EXCHANGER DETAIL OF NAME PLATE 018E0026AB | A1112 | 0X | 2 | 2019-05-30 | CON-BMP-VTRA-011846 | 2019-05-30 | FOR BAPCO REVIEW | 2019-06-13 | 2019-06-17 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000950 | CLASS 2
076551C-000R-MR-0610-002 | MATERIAL REQUISITION FOR CLAD SHELL AND TUBE HEAT EXCHANGERS | HANTECH LTD | 018E0026A | HW18052-DOC-109-7 | 018-E-PQP-40069-001 | FABRICATION AND QUALITY CONTROL PLAN 018E0026A/B | B1002 | BX | 2 | 2019-06-25 | CON-BMP-VTRA-012427 | 2019-06-25 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-002 | MATERIAL REQUISITION FOR CLAD SHELL AND TUBE HEAT EXCHANGERS | HANTECH LTD | 018E0026A | HW18052-DOC-111-7 | 018-E-MCD-40098-001 | WPS AND PQR WITH WELD MAP VAC. COLUMN BOTTOM/FEED EXCHANGER - 018E0026A/B | B1304 | BX | 2 | 2019-06-06 | CON-BMP-VTRA-012064 | 2019-06-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-002 | MATERIAL REQUISITION FOR CLAD SHELL AND TUBE HEAT EXCHANGERS | HANTECH LTD | 018E0027A | HW18052-018E0027ABC-CAL-001 | 018-E-CAL-40088-001 | STRENGTH CALCULATION 018E0027A/B/C | A1003 | BX | 2 | 2019-05-15 | CON-BMP-VTRA-011592 | 2019-05-15 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-002 | MATERIAL REQUISITION FOR CLAD SHELL AND TUBE HEAT EXCHANGERS | HANTECH LTD | 018E0027A | HW18052-018E0027ABC-DWG-001 | 018-E-GAD-40272-001 | VAC COLUMN BOTTOM STEAM EXCHANGER GENERAL ASSEMBLY 018E0027A/B/C | A1103 | BX | 2 | 2019-05-15 | CON-BMP-VTRA-011600 | 2019-05-15 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-002 | MATERIAL REQUISITION FOR CLAD SHELL AND TUBE HEAT EXCHANGERS | HANTECH LTD | 018E0027A | HW18052-018E0027ABC-DWG-002 | 018-E-GAD-40273-001 | VAC COLUMN BOTTOM/FEED EXCHANGER DETAIL OF BODY 018E0026A/B | A1109 | BX | 2 | 2019-05-14 | CON-BMP-VTRA-011583 | 2019-05-14 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-002 | MATERIAL REQUISITION FOR CLAD SHELL AND TUBE HEAT EXCHANGERS | HANTECH LTD | 018E0027A | HW18052-018E0027ABC-DWG-003 | 018-E-GAD-40274-001 | VAC COLUMN BTM STEAM GENERATOR DETAIL OF BUNDLE 018E0027A/B | A1109 | BX | 2 | 2019-05-14 | CON-BMP-VTRA-011583 | 2019-05-14 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-002 | MATERIAL REQUISITION FOR CLAD SHELL AND TUBE HEAT EXCHANGERS | HANTECH LTD | 018E0027A | HW18052-018E0027ABC-DWG-006 | 018-E-GAD-40275-001 | VAC COLUMN BTM STEAM GENERATOR DETAIL OF SADDLE 018E0027A/B/C | A1109 | BX | 2 | 2019-05-14 | CON-BMP-VTRA-011583 | 2019-05-14 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-002 | MATERIAL REQUISITION FOR CLAD SHELL AND TUBE HEAT EXCHANGERS | HANTECH LTD | 018E0027A | HW18052-018E0027ABC-DWG-007 | 018-E-GAD-40276-001 | VAC COLUMN BTM STEAM GENERATOR DETAIL OF NOZZLE 018E0027A/B/C | A1109 | BX | 2 | 2019-05-14 | CON-BMP-VTRA-011583 | 2019-05-14 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-002 | MATERIAL REQUISITION FOR CLAD SHELL AND TUBE HEAT EXCHANGERS | HANTECH LTD | 018E0027A | HW18052-018E0027ABC-DWG-008 | 018-E-GAD-40277-001 | VAC. COLUMN BOTTOM STEAM EXCHANGER DETAIL OF TEST RING 018E0027A/B/C | A1109 | AX | 2 | 2019-05-14 | CON-BMP-VTRA-011581 | 2019-05-14 | FOR BAPCO REVIEW | 2019-05-29 | 2019-05-30 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000836 | CLASS 2
076551C-000R-MR-0610-002 | MATERIAL REQUISITION FOR CLAD SHELL AND TUBE HEAT EXCHANGERS | HANTECH LTD | 018E0027A | HW18052-018E0027ABC-DWG-009 | 018-E-DLB-40020-001 | VAC COLUMN BTM STEAM GENERATOR DETAIL OF NAME PLATE 018E0027A/B/C | A1112 | BX | 2 | 2019-05-15 | CON-BMP-VTRA-011590 | 2019-05-15 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-002 | MATERIAL REQUISITION FOR CLAD SHELL AND TUBE HEAT EXCHANGERS | HANTECH LTD | 018E0027A | HW18052-DOC-109-8 | 018-E-PQP-40070-001 | FABRICATION AND QUALITY CONTROL PLAN 018E0027A/B/C | B1002 | BX | 2 | 2019-06-25 | CON-BMP-VTRA-012427 | 2019-06-25 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-002 | MATERIAL REQUISITION FOR CLAD SHELL AND TUBE HEAT EXCHANGERS | HANTECH LTD | 018E0027A | HW18052-DOC-111-8 | 018-E-MCD-40099-001 | WPS AND PQR WITH WELD MAP VAC. COLUMN BOTTOM STEAM GENERATOR - 018E00027A/B/C | B1304 | BX | 2 | 2019-06-06 | CON-BMP-VTRA-012064 | 2019-06-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-002 | MATERIAL REQUISITION FOR CLAD SHELL AND TUBE HEAT EXCHANGERS | HANTECH LTD | 018E0033 | HW18052-018E0033-CAL-001 | 018-E-CAL-40089-001 | STRENGTH CALCULATION 018E0033 | A1003 | BX | 2 | 2019-05-15 | CON-BMP-VTRA-011592 | 2019-05-15 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-002 | MATERIAL REQUISITION FOR CLAD SHELL AND TUBE HEAT EXCHANGERS | HANTECH LTD | 018E0033 | HW18052-018E0033-DWG-001 | 018-E-GAD-40278-001 | SHUTDOWN STEAM GENERATOR GENERAL ASSEMBLY 018E0033 | A1103 | BX | 2 | 2019-06-14 | CON-BMP-VTRA-012226 | 2019-06-14 | FOR BAPCO REVIEW | 2019-07-01 | 2019-07-08 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001204 | CLASS 2
076551C-000R-MR-0610-002 | MATERIAL REQUISITION FOR CLAD SHELL AND TUBE HEAT EXCHANGERS | HANTECH LTD | 018E0033 | HW18052-018E0033-DWG-002 | 018-E-GAD-40279-001 | SHUTDOWN STEAM GENERATOR DETAIL OF BODY 018E0033 | A1109 | BX | 2 | 2019-05-15 | CON-BMP-VTRA-011595 | 2019-05-15 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-002 | MATERIAL REQUISITION FOR CLAD SHELL AND TUBE HEAT EXCHANGERS | HANTECH LTD | 018E0033 | HW18052-018E0033-DWG-003 | 018-E-GAD-40280-001 | SHUTDOWN STEAM GENERATORDETAILOF BUNDLE 018E0033 | A1109 | BX | 2 | 2019-05-15 | CON-BMP-VTRA-011595 | 2019-05-15 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-002 | MATERIAL REQUISITION FOR CLAD SHELL AND TUBE HEAT EXCHANGERS | HANTECH LTD | 018E0033 | HW18052-018E0033-DWG-005 | 018-E-GAD-40281-001 | SHUTDOWN STEAM GENERATOR DETAIL OF SADDLE 018E0033 | A1109 | BX | 2 | 2019-05-15 | CON-BMP-VTRA-011595 | 2019-05-15 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-002 | MATERIAL REQUISITION FOR CLAD SHELL AND TUBE HEAT EXCHANGERS | HANTECH LTD | 018E0033 | HW18052-018E0033-DWG-006 | 018-E-GAD-40282-001 | SHUTDOWN STEAM GENERATOR DETAIL OF MANHOLE 018E0033 | A1109 | BX | 2 | 2019-05-15 | CON-BMP-VTRA-011595 | 2019-05-15 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-002 | MATERIAL REQUISITION FOR CLAD SHELL AND TUBE HEAT EXCHANGERS | HANTECH LTD | 018E0033 | HW18052-018E0033-DWG-007 | 018-E-GAD-40283-001 | SHUTDOWN STEAM GENERATOR DETAIL OF NOZZLE 018E0033 | A1109 | BX | 2 | 2019-05-14 | CON-BMP-VTRA-011583 | 2019-05-14 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-002 | MATERIAL REQUISITION FOR CLAD SHELL AND TUBE HEAT EXCHANGERS | HANTECH LTD | 018E0033 | HW18052-018E0033-DWG-009 | 018-E-DLB-40043-001 | SHUTDOWN STEAM GENERATOR DETAIL OF NAME PLATE 018E0033 | A1112 | BX | 2 | 2019-05-15 | CON-BMP-VTRA-011590 | 2019-05-15 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-002 | MATERIAL REQUISITION FOR CLAD SHELL AND TUBE HEAT EXCHANGERS | HANTECH LTD | 018E0033 | HW18052-DOC-109-9 | 018-E-PQP-40071-001 | FABRICATION AND QUALITY CONTROL PLAN 018E0033 | B1002 | BX | 2 | 2019-06-25 | CON-BMP-VTRA-012427 | 2019-06-25 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-002 | MATERIAL REQUISITION FOR CLAD SHELL AND TUBE HEAT EXCHANGERS | HANTECH LTD | 018E0033 | HW18052-DOC-111-9 | 018-E-MCD-40100-001 | WPS AND PQR WITH WELD MAP SHUTDOWN STEAM GENERATOR 018E0033 | B1304 | BX | 2 | 2019-06-06 | CON-BMP-VTRA-012064 | 2019-06-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-003 | MATERIAL REQUISITION FOR WET H2S SERVICE SHELL AND TUBE HEAT EXCHANGER | HANTECH LTD | 018E0003 | HW18062-018E0003-CAL-001 | 018-E-CAL-40107-001 | STRENGTH CALCULATION FOR 018E0003 | A1003 | CX | 2 | 2019-05-24 | CON-BMP-VTRA-011786 | 2019-05-24 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-003 | MATERIAL REQUISITION FOR WET H2S SERVICE SHELL AND TUBE HEAT EXCHANGER | HANTECH LTD | 018E0003 | HW18062-018E0003-DWG-001 | 018-E-GAD-40411-001 | SECON STAGE INTERCOOLER-SPARE TRAIN GENERAL ASSEMBLY 018E0003 | A1103 | 0X | 2 | 2019-06-17 | CON-BMP-VTRA-012237 | 2019-06-17 | FOR BAPCO REVIEW | 2019-07-01 | 2019-07-08 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001210 | CLASS 2
076551C-000R-MR-0610-003 | MATERIAL REQUISITION FOR WET H2S SERVICE SHELL AND TUBE HEAT EXCHANGER | HANTECH LTD | 018E0003 | HW18062-018E0003-DWG-002 | 018-E-GAD-40416-001 | SECOND STAGE INTERCOOLER-SPARE TRAIN DETAIL OF BODY (1/2) 018E0003 | A1109 | 0X | 3 | 2019-06-19 | CON-BMP-VTRA-012288 | 2019-06-19 | FOR BAPCO REVIEW | 2019-07-03 | 2019-07-09 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001244 | CLASS 2
076551C-000R-MR-0610-003 | MATERIAL REQUISITION FOR WET H2S SERVICE SHELL AND TUBE HEAT EXCHANGER | HANTECH LTD | 018E0003 | HW18062-018E0003-DWG-003 | 018-E-GAD-40416-002 | SECOND STAGE INTERCOOLER-SPARE TRAIN DETAIL OF BODY (2/2) 018E0003 | A1109 | 0X | 2 | 2019-06-19 | CON-BMP-VTRA-012287 | 2019-06-19 | FOR BAPCO REVIEW | 2019-07-03 | 2019-07-09 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001243 | CLASS 2
076551C-000R-MR-0610-003 | MATERIAL REQUISITION FOR WET H2S SERVICE SHELL AND TUBE HEAT EXCHANGER | HANTECH LTD | 018E0003 | HW18062-018E0003-DWG-004 | 018-E-GAD-40417-001 | DETAIL OF BUNDLE SECOND-STAGE INTERCOOLER SPARE TRAIN 018E0003 | A1109 | 0X | 3 | 2019-06-04 | CON-BMP-VTRA-011963 | 2019-06-04 | FOR BAPCO REVIEW | 2019-06-19 |  |  | CLASS 2
076551C-000R-MR-0610-003 | MATERIAL REQUISITION FOR WET H2S SERVICE SHELL AND TUBE HEAT EXCHANGER | HANTECH LTD | 018E0003 | HW18062-018E0003-DWG-006 | 018-E-GAD-40418-001 | SECOND-STAGE INTERCOOLER-SPARE TRAIN DETAIL OF NOZZLE 018E0003 | A1109 | 0X | 3 | 2019-06-17 | CON-BMP-VTRA-012234 | 2019-06-17 | FOR BAPCO REVIEW | 2019-07-01 | 2019-07-08 | 5-RETAINED FOR INFORMATION BMP-ROC-TRE-001207 | CLASS 2
076551C-000R-MR-0610-003 | MATERIAL REQUISITION FOR WET H2S SERVICE SHELL AND TUBE HEAT EXCHANGER | HANTECH LTD | 018E0003 | HW18062-018E0003-DWG-007 | 018-E-GAD-40419-001 | SECOND STAGE INTERCOOLER-SPARE TRAIN DETAIL OF INSUL. SUP'T CLIP 018E0003 | A1109 | 0X | 2 | 2019-06-26 | CON-BMP-VTRA-012473 | 2019-06-26 | FOR BAPCO REVIEW | 2019-07-11 |  |  | CLASS 2
076551C-000R-MR-0610-003 | MATERIAL REQUISITION FOR WET H2S SERVICE SHELL AND TUBE HEAT EXCHANGER | HANTECH LTD | 018E0003 | HW18062-018E0003-DWG-009 | 018-E-DLB-40038-001 | SECOND STAGE INTERCOOLER SPARE TRAIN DETAIL OF NAME PLATE 018E0003 | A1112 | BX | 2 | 2019-05-24 | CON-BMP-VTRA-011804 | 2019-05-24 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-003 | MATERIAL REQUISITION FOR WET H2S SERVICE SHELL AND TUBE HEAT EXCHANGER | HANTECH LTD | 018E0003 | HW18062-018E0003-DWG-010 | 018-E-GAD-40458-001 | SECOND STAGE INTERCOOLER-TRAIN 2B GENERAL ASSEMBLY 018E2012 | A1103 | 0X | 2 | 2019-06-01 | CON-BMP-VTRA-011912 | 2019-06-01 | FOR BAPCO REVIEW | 2019-06-17 |  |  | CLASS 2
076551C-000R-MR-0610-003 | MATERIAL REQUISITION FOR WET H2S SERVICE SHELL AND TUBE HEAT EXCHANGER | HANTECH LTD | 018E0003 | HW18062-DOC-100 | 000-E-MRS-40005-001 | MONTHLY PROGRESS REPORT ALL ITEMS | C1002 | CX | 2 | 2019-05-29 | CON-BMP-VTRA-011835 | 2019-05-29 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-0610-003 | MATERIAL REQUISITION FOR WET H2S SERVICE SHELL AND TUBE HEAT EXCHANGER | HANTECH LTD | 018E0003 | HW18062-DOC-101 | 000-E-INX-40009-001 | LIST OF VENDOR'S DOCUMENTS AND DWGS ALL ITEMS | A0001 | 0X | 3 | 2019-05-14 | CON-BMP-VTRA-011573 | 2019-05-14 | FOR BAPCO REVIEW | 2019-05-29 | 2019-05-30 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000843 | CLASS 2
076551C-000R-MR-0610-003 | MATERIAL REQUISITION FOR WET H2S SERVICE SHELL AND TUBE HEAT EXCHANGER | HANTECH LTD | 018E0003 | HW18062-DOC-102 | 000-E-PQS-40003-001 | SUB VENDOR LIST ALL ITEMS | B1401 | CX | 2 | 2019-05-03 | CON-BMP-VTRA-011389 | 2019-05-03 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-0610-003 | MATERIAL REQUISITION FOR WET H2S SERVICE SHELL AND TUBE HEAT EXCHANGER | HANTECH LTD | 018E0003 | HW18062-DOC-103 | 000-E-PQP-40004-001 | JOB QUALITY ASSURANCE PLAN ALLITEMS (EX BAPCO N. 000-E-PLN-40002-001) | B1001 | AX | 2 | 2019-03-20 | CON-BMP-VTRA-010787 | 2019-03-20 | FOR BAPCO REVIEW | 2019-04-04 | 2019-03-30 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000411 | CLASS 2
076551C-000R-MR-0610-003 | MATERIAL REQUISITION FOR WET H2S SERVICE SHELL AND TUBE HEAT EXCHANGER | HANTECH LTD | 018E0003 | HW18062-DOC-104 | 000-E-TSP-40014-001 | MATERIAL PURCHASE SPECIFICATION FOR TUBE AND CARBON STEEL PLATE ALL ITEMS | B1203 | AX | 2 | 2019-02-05 | CON-BMP-VTRA-010353 | 2019-02-05 | FOR BAPCO REVIEW | 2019-02-19 | 2019-02-19 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000198 | CLASS 2
076551C-000R-MR-0610-003 | MATERIAL REQUISITION FOR WET H2S SERVICE SHELL AND TUBE HEAT EXCHANGER | HANTECH LTD | 018E0003 | HW18062-DOC-105 | 000-E-SCH-40003-001 | ENGINEERING PROCUREMENT MANUFACTURING & TEST SCHEDULE ALL ITEMS | C1001 | CX | 4 | 2019-05-29 | CON-BMP-VTRA-011833 | 2019-05-29 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-0610-003 | MATERIAL REQUISITION FOR WET H2S SERVICE SHELL AND TUBE HEAT EXCHANGER | HANTECH LTD | 018E0003 | HW18062-DOC-106 | 000-E-INV-40004-001 | UNPRICED COPY OF MAIN SUBORDERS ALL ITEMS | C1005 | AX | 4 | 2019-05-03 | CON-BMP-VTRA-011390 | 2019-05-03 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-0610-003 | MATERIAL REQUISITION FOR WET H2S SERVICE SHELL AND TUBE HEAT EXCHANGER | HANTECH LTD | 018E0003 | HW18062-DOC-109 | 018-E-PQP-40055-001 | FABRICATION AND QUALITY CONTROL PLAN 018E0003 | B1002 | BX | 2 | 2019-06-25 | CON-BMP-VTRA-012430 | 2019-06-25 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-003 | MATERIAL REQUISITION FOR WET H2S SERVICE SHELL AND TUBE HEAT EXCHANGER | HANTECH LTD | 018E0003 | HW18062-DOC-110 | 000-E-PRO-40012-001 | INSPECTION AND TEST PROCEDURE ALL ITEMS | B1103 | AX | 2 | 2019-04-01 | CON-BMP-VTRA-010947 | 2019-04-01 | FOR BAPCO REVIEW | 2019-04-15 | 2019-04-11 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000505 | CLASS 2
076551C-000R-MR-0610-003 | MATERIAL REQUISITION FOR WET H2S SERVICE SHELL AND TUBE HEAT EXCHANGER | HANTECH LTD | 018E0003 | HW18062-DOC-111 | 018-E-MCD-40092-001 | WPS AND PQR WITH WELD MAP 018E0003 | B1304 | CX | 2 | 2019-05-24 | CON-BMP-VTRA-011792 | 2019-05-24 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-003 | MATERIAL REQUISITION FOR WET H2S SERVICE SHELL AND TUBE HEAT EXCHANGER | HANTECH LTD | 018E0003 | HW18062-DOC-113 | 000-E-PRO-40013-001 | NDE PROCEDURE ALL ITEMS | B1202 | AX | 2 | 2019-02-14 | CON-BMP-VTRA-010896 | 2019-03-28 | FOR BAPCO REVIEW | 2019-04-12 | 2019-04-07 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000486 | CLASS 2
076551C-000R-MR-0610-003 | MATERIAL REQUISITION FOR WET H2S SERVICE SHELL AND TUBE HEAT EXCHANGER | HANTECH LTD | 018E0003 | HW18062-DOC-115 | 000-E-PRO-40015-001 | HEAT TREATMENT PROCEDURE WET H2S AND SPECIAL SERVICE CS SHELL AND TUBE HEAT EXCHANGERS ALL ITEMS | B1201 | 0X | 2 | 2019-05-29 | CON-BMP-VTRA-011824 | 2019-05-29 | FOR BAPCO REVIEW | 2019-06-12 | 2019-06-17 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000967 | CLASS 2
076551C-000R-MR-0610-003 | MATERIAL REQUISITION FOR WET H2S SERVICE SHELL AND TUBE HEAT EXCHANGER | HANTECH LTD | 018E0003 | HW18062-DOC-117 | 000-E-TSP-40012-001 | BOLT TIGHTENING PROCEDURE FOR WET H2S SERVICE SHELL AND TUBEHEAT EXCHANGER ALL ITEMS | A1202 | AX | 2 | 2019-03-16 | CON-BMP-VTRA-011837 | 2019-05-29 | FOR BAPCO REVIEW | 2019-06-13 | 2019-06-11 | 5-RETAINED FOR INFOMATION BMP-ROC-VTRE-000900 | CLASS 2
076551C-000R-MR-0610-003 | MATERIAL REQUISITION FOR WET H2S SERVICE SHELL AND TUBE HEAT EXCHANGER | HANTECH LTD | 018E0003 | HW18062-DOC-118 | 000-E-TSP-40013-001 | PAINTING PROCEDURE FOR WET H2S SERVICE SHELL AND TUBE HEAT EXCHANGER ALL ITEMS | A0106 | 0X | 3 | 2019-06-26 | CON-BMP-VTRA-012476 | 2019-06-26 | FOR BAPCO REVIEW | 2019-07-10 | 2019-07-11 | 3-REVIEWED WITH COMMENTS BMP-ROC-VTRE-001288 | CLASS 2
076551C-000R-MR-0610-003 | MATERIAL REQUISITION FOR WET H2S SERVICE SHELL AND TUBE HEAT EXCHANGER | HANTECH LTD | 018E0003 | HW18062-DOC-119 | 000-E-PRO-40017-001 | HYDROSTATIC TEST PROCEDURE FORWET H2S SERVICE SHELL AND TUBEHEAT EXCHANGERS ALL ITEMS | B1103 | AX | 2 | 2019-06-13 | CON-BMP-VTRA-012187 | 2019-06-13 | FOR BAPCO REVIEW | 2019-06-27 | 2019-06-25 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001033 | CLASS 2
076551C-000R-MR-0610-003 | MATERIAL REQUISITION FOR WET H2S SERVICE SHELL AND TUBE HEAT EXCHANGER | HANTECH LTD | 018E0003 | HW18062-DOC-120 | 000-E-PRO-40018-001 | PACKING PROCEDURE WITH RUST PREVENTION FOR WET H2S SHELL AND TUBE HEAT EXCHANGER ALL ITEMS | B1103 | AX | 2 | 2019-03-16 | CON-BMP-VTRA-011836 | 2019-05-29 | FOR BAPCO REVIEW | 2019-06-13 | 2019-06-10 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000895 | CLASS 2
076551C-000R-MR-0610-003 | MATERIAL REQUISITION FOR WET H2S SERVICE SHELL AND TUBE HEAT EXCHANGER | HANTECH LTD | 018E1009 | HW18062-018E1009-CAL-001 | 018-E-CAL-40108-001 | STRENGTH CALCULATION FOR 018E1009 | A1003 | CX | 2 | 2019-05-24 | CON-BMP-VTRA-011786 | 2019-05-24 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-003 | MATERIAL REQUISITION FOR WET H2S SERVICE SHELL AND TUBE HEAT EXCHANGER | HANTECH LTD | 018E1009 | HW18062-018E1009-DWG-001 | 018-E-GAD-40412-001 | SECOND STAGE INTERCOOLER-TRAIN 1A GENERAL ASSEMBLY 018E1009 | A1103 | 0X | 2 | 2019-06-17 | CON-BMP-VTRA-012237 | 2019-06-17 | FOR BAPCO REVIEW | 2019-07-01 | 2019-07-08 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001210 | CLASS 2
076551C-000R-MR-0610-003 | MATERIAL REQUISITION FOR WET H2S SERVICE SHELL AND TUBE HEAT EXCHANGER | HANTECH LTD | 018E1009 | HW18062-018E1009-DWG-002 | 018-E-GAD-40421-001 | SECOND STAGE INTERCOOLER-TRAIN 1A DETAIL OF BODY (1/2) 018E1009 | A1109 | 0X | 3 | 2019-06-19 | CON-BMP-VTRA-012288 | 2019-06-19 | FOR BAPCO REVIEW | 2019-07-03 | 2019-07-09 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001244 | CLASS 2
076551C-000R-MR-0610-003 | MATERIAL REQUISITION FOR WET H2S SERVICE SHELL AND TUBE HEAT EXCHANGER | HANTECH LTD | 018E1009 | HW18062-018E1009-DWG-003 | 018-E-GAD-40421-002 | SECOND STAGE INTERCOOLER-TRAIN 1A DETAIL OF BODY (2/2) 018E1009 | A1109 | 0X | 2 | 2019-06-19 | CON-BMP-VTRA-012287 | 2019-06-19 | FOR BAPCO REVIEW | 2019-07-03 | 2019-07-09 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001243 | CLASS 2
076551C-000R-MR-0610-003 | MATERIAL REQUISITION FOR WET H2S SERVICE SHELL AND TUBE HEAT EXCHANGER | HANTECH LTD | 018E1009 | HW18062-018E1009-DWG-004 | 018-E-GAD-40422-001 | DETAIL OF BUNDLE SECOND- STAGE INTERCOOLER TRAIN 1A 018E1009 | A1109 | 0X | 3 | 2019-06-04 | CON-BMP-VTRA-011963 | 2019-06-04 | FOR BAPCO REVIEW | 2019-06-19 |  |  | CLASS 2
076551C-000R-MR-0610-003 | MATERIAL REQUISITION FOR WET H2S SERVICE SHELL AND TUBE HEAT EXCHANGER | HANTECH LTD | 018E1009 | HW18062-018E1009-DWG-006 | 018-E-GAD-40423-001 | SECOND-STAGE INTERCOOLER-TRAIN 1A DETAIL OF NOZZLE 018E1009 | A1109 | 0X | 3 | 2019-06-17 | CON-BMP-VTRA-012234 | 2019-06-17 | FOR BAPCO REVIEW | 2019-07-01 | 2019-07-08 | 5-RETAINED FOR INFORMATION BMP-ROC-TRE-001207 | CLASS 2
076551C-000R-MR-0610-003 | MATERIAL REQUISITION FOR WET H2S SERVICE SHELL AND TUBE HEAT EXCHANGER | HANTECH LTD | 018E1009 | HW18062-018E1009-DWG-007 | 018-E-GAD-40424-001 | SECOND STAGE INTERCOOLER-TRAIN 1A DETAIL OF INSUL. SUP'T CLIP 018E1009 | A1109 | 0X | 3 | 2019-06-25 | CON-BMP-VTRA-012420 | 2019-06-25 | FOR BAPCO REVIEW | 2019-07-08 |  |  | CLASS 2
076551C-000R-MR-0610-003 | MATERIAL REQUISITION FOR WET H2S SERVICE SHELL AND TUBE HEAT EXCHANGER | HANTECH LTD | 018E1009 | HW18062-018E1009-DWG-009 | 018-E-DLB-40039-001 | SECOND STAGE INTERCOOLER TRAIN 1A DETAIL OF NAME PLATE 018E1009 | A1112 | BX | 2 | 2019-05-24 | CON-BMP-VTRA-011804 | 2019-05-24 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-003 | MATERIAL REQUISITION FOR WET H2S SERVICE SHELL AND TUBE HEAT EXCHANGER | HANTECH LTD | 018E1009 | HW18062-018E1009-DWG-010 | 018-E-GAD-40459-001 | SECOND STAGE INTERCOOLER-TRAIN 1A GENERAL NOTES 018E1009 | A1103 | 0X | 2 | 2019-06-01 | CON-BMP-VTRA-011912 | 2019-06-01 | FOR BAPCO REVIEW | 2019-06-17 |  |  | CLASS 2
076551C-000R-MR-0610-003 | MATERIAL REQUISITION FOR WET H2S SERVICE SHELL AND TUBE HEAT EXCHANGER | HANTECH LTD | 018E1009 | HW18062-DOC-302 | 018-E-PQP-40056-001 | FABRICATION AND QUALITY CONTROL PLAN 018E1009 | B1002 | BX | 2 | 2019-06-25 | CON-BMP-VTRA-012430 | 2019-06-25 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-003 | MATERIAL REQUISITION FOR WET H2S SERVICE SHELL AND TUBE HEAT EXCHANGER | HANTECH LTD | 018E1009 | HW18062-DOC-314 | 018-E-MCD-40101-001 | WPS AND PQR WITH WELD MAP FOR 018E1009 | B1304 | BX | 2 | 2019-05-27 | CON-BMP-VTRA-011806 | 2019-05-27 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-003 | MATERIAL REQUISITION FOR WET H2S SERVICE SHELL AND TUBE HEAT EXCHANGER | HANTECH LTD | 018E1012 | HW18062-018E1012-CAL-001 | 018-E-CAL-40109-001 | STRENGTH CALCULATION FOR 018E1012 | A1003 | CX | 2 | 2019-05-24 | CON-BMP-VTRA-011786 | 2019-05-24 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-003 | MATERIAL REQUISITION FOR WET H2S SERVICE SHELL AND TUBE HEAT EXCHANGER | HANTECH LTD | 018E1012 | HW18062-018E1012-DWG-001 | 018-E-GAD-40413-001 | SECOND STAGE INTERCOOLER-TRAIN 1B GENERAL ASSEMBLY 018E1012 | A1103 | 0X | 2 | 2019-06-17 | CON-BMP-VTRA-012237 | 2019-06-17 | FOR BAPCO REVIEW | 2019-07-01 | 2019-07-08 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001210 | CLASS 2
076551C-000R-MR-0610-003 | MATERIAL REQUISITION FOR WET H2S SERVICE SHELL AND TUBE HEAT EXCHANGER | HANTECH LTD | 018E1012 | HW18062-018E1012-DWG-002 | 018-E-GAD-40426-001 | SECOND STAGE INTERCOOLER-TRAIN 1B DETAIL OF BODY (1/2) 018E1012 | A1109 | 0X | 2 | 2019-06-26 | CON-BMP-VTRA-012481 | 2019-06-26 | FOR BAPCO REVIEW | 2019-07-11 |  |  | CLASS 2
076551C-000R-MR-0610-003 | MATERIAL REQUISITION FOR WET H2S SERVICE SHELL AND TUBE HEAT EXCHANGER | HANTECH LTD | 018E1012 | HW18062-018E1012-DWG-003 | 018-E-GAD-40426-002 | SECOND STAGE INTERCOOLER-TRAIN 1B DETAIL OF BODY (2/2) 018E1012 | A1109 | 0X | 2 | 2019-06-26 | CON-BMP-VTRA-012479 | 2019-06-26 | FOR BAPCO REVIEW | 2019-07-11 |  |  | CLASS 2
076551C-000R-MR-0610-003 | MATERIAL REQUISITION FOR WET H2S SERVICE SHELL AND TUBE HEAT EXCHANGER | HANTECH LTD | 018E1012 | HW18062-018E1012-DWG-004 | 018-E-GAD-40427-001 | DETAIL OF BUNDLE SECOND-STAGE INTERCOOLER TRAIN 1B 018E1012 | A1109 | 0X | 3 | 2019-06-04 | CON-BMP-VTRA-011963 | 2019-06-04 | FOR BAPCO REVIEW | 2019-06-19 |  |  | CLASS 2
076551C-000R-MR-0610-003 | MATERIAL REQUISITION FOR WET H2S SERVICE SHELL AND TUBE HEAT EXCHANGER | HANTECH LTD | 018E1012 | HW18062-018E1012-DWG-006 | 018-E-GAD-40428-001 | SECOND-STAGE INTERCOOLER-TRAIN 1B DETAIL OF NOZZLE 018E1012 | A1109 | 0X | 2 | 2019-06-26 | CON-BMP-VTRA-012473 | 2019-06-26 | FOR BAPCO REVIEW | 2019-07-11 |  |  | CLASS 2
076551C-000R-MR-0610-003 | MATERIAL REQUISITION FOR WET H2S SERVICE SHELL AND TUBE HEAT EXCHANGER | HANTECH LTD | 018E1012 | HW18062-018E1012-DWG-007 | 018-E-GAD-40429-001 | SECOND STAGE INTERCOOLER-TRAIN 1B DETAIL OF INSUL. SUP'T CLIP 018E1012 | A1109 | 0X | 3 | 2019-06-25 | CON-BMP-VTRA-012420 | 2019-06-25 | FOR BAPCO REVIEW | 2019-07-08 |  |  | CLASS 2
076551C-000R-MR-0610-003 | MATERIAL REQUISITION FOR WET H2S SERVICE SHELL AND TUBE HEAT EXCHANGER | HANTECH LTD | 018E1012 | HW18062-018E1012-DWG-009 | 018-E-DLB-40040-001 | SECOND STAGE INTERCOOLER TRAIN 1B DETAIL OF NAME PLATE 018E1012 | A1112 | BX | 2 | 2019-05-24 | CON-BMP-VTRA-011804 | 2019-05-24 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-003 | MATERIAL REQUISITION FOR WET H2S SERVICE SHELL AND TUBE HEAT EXCHANGER | HANTECH LTD | 018E1012 | HW18062-018E1012-DWG-010 | 018-E-GAD-40460-001 | SECOND STAGE INTERCOOLER-TRAIN 1B GENERAL NOTES 018E1012 | A1103 | 0X | 2 | 2019-06-01 | CON-BMP-VTRA-011912 | 2019-06-01 | FOR BAPCO REVIEW | 2019-06-17 |  |  | CLASS 2
076551C-000R-MR-0610-003 | MATERIAL REQUISITION FOR WET H2S SERVICE SHELL AND TUBE HEAT EXCHANGER | HANTECH LTD | 018E1012 | HW18062-DOC-303 | 018-E-PQP-40057-001 | FABRICATION AND QUALITY CONTROL PLAN 018E1012 | B1002 | BX | 2 | 2019-06-25 | CON-BMP-VTRA-012430 | 2019-06-25 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-003 | MATERIAL REQUISITION FOR WET H2S SERVICE SHELL AND TUBE HEAT EXCHANGER | HANTECH LTD | 018E1012 | HW18062-DOC-315 | 018-E-MCD-40102-001 | WPS AND PQR WITH WELD MAP SECOND STAGE INTERCOOLER TRAIN 1B 018E1012 | B1304 | BX | 2 | 2019-05-30 | CON-BMP-VTRA-011861 | 2019-05-30 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-003 | MATERIAL REQUISITION FOR WET H2S SERVICE SHELL AND TUBE HEAT EXCHANGER | HANTECH LTD | 018E2009 | HW18062-018E2009-CAL-001 | 018-E-CAL-40110-001 | STRENGTH CALCULATION FOR 018E2009 | A1003 | CX | 2 | 2019-05-24 | CON-BMP-VTRA-011786 | 2019-05-24 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-003 | MATERIAL REQUISITION FOR WET H2S SERVICE SHELL AND TUBE HEAT EXCHANGER | HANTECH LTD | 018E2009 | HW18062-018E2009-DWG-001 | 018-E-GAD-40414-001 | SECOND STAGE INTERCOOLER-TRAIN 2A GENERAL AASSEMBLY 018E2009 | A1103 | 0X | 2 | 2019-06-17 | CON-BMP-VTRA-012237 | 2019-06-17 | FOR BAPCO REVIEW | 2019-07-01 | 2019-07-08 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001210 | CLASS 2
076551C-000R-MR-0610-003 | MATERIAL REQUISITION FOR WET H2S SERVICE SHELL AND TUBE HEAT EXCHANGER | HANTECH LTD | 018E2009 | HW18062-018E2009-DWG-002 | 018-E-GAD-40431-001 | SECOND STAGE INTERCOOLER-TRAIN 2A DETAIL OF BODY (1/2) 018E2009 | A1109 | 0X | 2 | 2019-06-26 | CON-BMP-VTRA-012481 | 2019-06-26 | FOR BAPCO REVIEW | 2019-07-11 |  |  | CLASS 2
076551C-000R-MR-0610-003 | MATERIAL REQUISITION FOR WET H2S SERVICE SHELL AND TUBE HEAT EXCHANGER | HANTECH LTD | 018E2009 | HW18062-018E2009-DWG-003 | 018-E-GAD-40431-002 | SECOND STAGE INTERCOOLER-TRAIN 2A DETAIL OF BODY (2/2) 018E2009 | A1109 | 0X | 2 | 2019-06-26 | CON-BMP-VTRA-012479 | 2019-06-26 | FOR BAPCO REVIEW | 2019-07-11 |  |  | CLASS 2
076551C-000R-MR-0610-003 | MATERIAL REQUISITION FOR WET H2S SERVICE SHELL AND TUBE HEAT EXCHANGER | HANTECH LTD | 018E2009 | HW18062-018E2009-DWG-004 | 018-E-GAD-40432-001 | DETAIL OF BUNDLE SECOND-STAGE INTERCOOLER TRAIN 1A 018E2009 | A1109 | 0X | 3 | 2019-06-04 | CON-BMP-VTRA-011963 | 2019-06-04 | FOR BAPCO REVIEW | 2019-06-19 |  |  | CLASS 2
076551C-000R-MR-0610-003 | MATERIAL REQUISITION FOR WET H2S SERVICE SHELL AND TUBE HEAT EXCHANGER | HANTECH LTD | 018E2009 | HW18062-018E2009-DWG-006 | 018-E-GAD-40433-001 | DETAIL OF NOZZLE SECOND-STAGE INTERCOOLER-TRAIN 2A 018E2009 | A1109 | 0X | 2 | 2019-06-26 | CON-BMP-VTRA-012473 | 2019-06-26 | FOR BAPCO REVIEW | 2019-07-11 |  |  | CLASS 2
076551C-000R-MR-0610-003 | MATERIAL REQUISITION FOR WET H2S SERVICE SHELL AND TUBE HEAT EXCHANGER | HANTECH LTD | 018E2009 | HW18062-018E2009-DWG-007 | 018-E-GAD-40434-001 | SECOND STAGE INTERCOOLER-TRAIN 2A DETAIL OF INSUL. SUP'T CLIP 018E2009 | A1109 | 0X | 3 | 2019-06-25 | CON-BMP-VTRA-012420 | 2019-06-25 | FOR BAPCO REVIEW | 2019-07-08 |  |  | CLASS 2
076551C-000R-MR-0610-003 | MATERIAL REQUISITION FOR WET H2S SERVICE SHELL AND TUBE HEAT EXCHANGER | HANTECH LTD | 018E2009 | HW18062-018E2009-DWG-009 | 018-E-DLB-40041-001 | SECOND STAGE INTERCOOLER TRAIN 2A DETAIL OF NAME PLATE 018E2009 | A1112 | BX | 2 | 2019-05-24 | CON-BMP-VTRA-011804 | 2019-05-24 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-003 | MATERIAL REQUISITION FOR WET H2S SERVICE SHELL AND TUBE HEAT EXCHANGER | HANTECH LTD | 018E2009 | HW18062-018E2009-DWG-010 | 018-E-GAD-40461-001 | SECOND STAGE INTERCOOLER-TRAIN 2A GENERAL NOTES 018E2009 | A1103 | 0X | 2 | 2019-06-01 | CON-BMP-VTRA-011912 | 2019-06-01 | FOR BAPCO REVIEW | 2019-06-17 |  |  | CLASS 2
076551C-000R-MR-0610-003 | MATERIAL REQUISITION FOR WET H2S SERVICE SHELL AND TUBE HEAT EXCHANGER | HANTECH LTD | 018E2009 | HW18062-DOC-304 | 018-E-PQP-40058-001 | FABRICATION AND QUALITY CONTROL PLAN 018E2009 | B1002 | BX | 2 | 2019-06-25 | CON-BMP-VTRA-012430 | 2019-06-25 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-003 | MATERIAL REQUISITION FOR WET H2S SERVICE SHELL AND TUBE HEAT EXCHANGER | HANTECH LTD | 018E2009 | HW18062-DOC-316 | 018-E-MCD-40103-001 | WPS AND PQR WITH WELD MAP FOR 018E2009 | B1304 | BX | 2 | 2019-05-27 | CON-BMP-VTRA-011806 | 2019-05-27 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-003 | MATERIAL REQUISITION FOR WET H2S SERVICE SHELL AND TUBE HEAT EXCHANGER | HANTECH LTD | 018E2012 | HW18062-018E2012-CAL-001 | 018-E-CAL-40111-001 | STRENGTH CALCULATION FOR 018E2012 | A1003 | CX | 2 | 2019-05-24 | CON-BMP-VTRA-011786 | 2019-05-24 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-003 | MATERIAL REQUISITION FOR WET H2S SERVICE SHELL AND TUBE HEAT EXCHANGER | HANTECH LTD | 018E2012 | HW18062-018E2012-DWG-001 | 018-E-GAD-40415-001 | SECOND STAGE INTERCOOLER-TRAIN 2B GENERAL ASSEMBLY 018E2012 | A1103 | 0X | 2 | 2019-06-17 | CON-BMP-VTRA-012237 | 2019-06-17 | FOR BAPCO REVIEW | 2019-07-01 | 2019-07-08 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001210 | CLASS 2
076551C-000R-MR-0610-003 | MATERIAL REQUISITION FOR WET H2S SERVICE SHELL AND TUBE HEAT EXCHANGER | HANTECH LTD | 018E2012 | HW18062-018E2012-DWG-002 | 018-E-GAD-40436-001 | SECOND STAGE INTERCOOLER-TRAIN 2B DETAIL OF BODY (1/2) 018E2012 | A1109 | 0X | 2 | 2019-06-26 | CON-BMP-VTRA-012481 | 2019-06-26 | FOR BAPCO REVIEW | 2019-07-11 |  |  | CLASS 2
076551C-000R-MR-0610-003 | MATERIAL REQUISITION FOR WET H2S SERVICE SHELL AND TUBE HEAT EXCHANGER | HANTECH LTD | 018E2012 | HW18062-018E2012-DWG-003 | 018-E-GAD-40436-002 | SECOND STAGE INTERCOOLER- RAIN 2B DETAIL OF BODY (2/2) 018E2012 | A1109 | 0X | 2 | 2019-06-26 | CON-BMP-VTRA-012479 | 2019-06-26 | FOR BAPCO REVIEW | 2019-07-11 |  |  | CLASS 2
076551C-000R-MR-0610-003 | MATERIAL REQUISITION FOR WET H2S SERVICE SHELL AND TUBE HEAT EXCHANGER | HANTECH LTD | 018E2012 | HW18062-018E2012-DWG-004 | 018-E-GAD-40437-001 | DETAIL OF BUNDLE SECOND-STAGE INTERCOOLER TRAIN 2B 018E2012 | A1109 | 0X | 3 | 2019-06-04 | CON-BMP-VTRA-011963 | 2019-06-04 | FOR BAPCO REVIEW | 2019-06-19 |  |  | CLASS 2
076551C-000R-MR-0610-003 | MATERIAL REQUISITION FOR WET H2S SERVICE SHELL AND TUBE HEAT EXCHANGER | HANTECH LTD | 018E2012 | HW18062-018E2012-DWG-006 | 018-E-GAD-40438-001 | SECOND-STAGE INTERCOOLER- RAIN 2B DETAIL OF NOZZLE 018E2012 | A1109 | 0X | 2 | 2019-06-26 | CON-BMP-VTRA-012473 | 2019-06-26 | FOR BAPCO REVIEW | 2019-07-11 |  |  | CLASS 2
076551C-000R-MR-0610-003 | MATERIAL REQUISITION FOR WET H2S SERVICE SHELL AND TUBE HEAT EXCHANGER | HANTECH LTD | 018E2012 | HW18062-018E2012-DWG-007 | 018-E-GAD-40439-001 | SECOND STAGE INTERCOOLER-TRAIN 2B DETAIL OF INSUL. SUP'T CLIP 018E2012 | A1109 | 0X | 3 | 2019-06-25 | CON-BMP-VTRA-012420 | 2019-06-25 | FOR BAPCO REVIEW | 2019-07-08 |  |  | CLASS 2
076551C-000R-MR-0610-003 | MATERIAL REQUISITION FOR WET H2S SERVICE SHELL AND TUBE HEAT EXCHANGER | HANTECH LTD | 018E2012 | HW18062-018E2012-DWG-009 | 018-E-DLB-40042-001 | SECOND STAGE INTERCOOLER TRAIN 2B DETAIL OF NAME PLATE 018E2012 | A1112 | BX | 2 | 2019-05-24 | CON-BMP-VTRA-011804 | 2019-05-24 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-003 | MATERIAL REQUISITION FOR WET H2S SERVICE SHELL AND TUBE HEAT EXCHANGER | HANTECH LTD | 018E2012 | HW18062-018E2012-DWG-010 | 018-E-GAD-40462-001 | SECOND STAGE INTERCOOLER-TRAIN 2B GENERAL NOTES 018E2012 | A1103 | 0X | 2 | 2019-06-01 | CON-BMP-VTRA-011912 | 2019-06-01 | FOR BAPCO REVIEW | 2019-06-17 |  |  | CLASS 2
076551C-000R-MR-0610-003 | MATERIAL REQUISITION FOR WET H2S SERVICE SHELL AND TUBE HEAT EXCHANGER | HANTECH LTD | 018E2012 | HW18062-DOC-305 | 018-E-PQP-40059-001 | FABRICATION AND QUALITY CONTROL PLAN 018E2012 | B1002 | BX | 2 | 2019-06-25 | CON-BMP-VTRA-012430 | 2019-06-25 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-003 | MATERIAL REQUISITION FOR WET H2S SERVICE SHELL AND TUBE HEAT EXCHANGER | HANTECH LTD | 018E2012 | HW18062-DOC-317 | 018-E-MCD-40104-001 | WPS AND PQR WITH WELD MAP FOR 018E2012 | B1304 | BX | 2 | 2019-05-27 | CON-BMP-VTRA-011806 | 2019-05-27 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-003 | MATERIAL REQUISITION FOR WET H2S SERVICE SHELL AND TUBE HEAT EXCHANGER | HANTECH LTD | 021E0018A | HW18062-021E0018A-DWG-001 | 021-E-GAD-40151-001 | SOUR WATER COOLERS GENERAL ASSEMBLY (1/2) 021E0018A | A1103 | 0X | 3 | 2019-06-26 | CON-BMP-VTRA-012483 | 2019-06-26 | FOR BAPCO REVIEW | 2019-07-11 |  |  | CLASS 2
076551C-000R-MR-0610-003 | MATERIAL REQUISITION FOR WET H2S SERVICE SHELL AND TUBE HEAT EXCHANGER | HANTECH LTD | 021E0018A | HW18062-021E0018A/B-DWG-005 | 021-E-GAD-40153-001 | SOUR WATER COOLERS DETAIL OF BUNDLE (1/4) 021E0018A | A1109 | 0X | 3 | 2019-05-24 | CON-BMP-VTRA-011785 | 2019-05-24 | FOR BAPCO REVIEW | 2019-06-07 | 2019-06-16 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000932 | CLASS 2
076551C-000R-MR-0610-003 | MATERIAL REQUISITION FOR WET H2S SERVICE SHELL AND TUBE HEAT EXCHANGER | HANTECH LTD | 021E0018A | HW18062-021E0018A/B-DWG-009 | 021-E-GAD-40154-001 | SOUR WATER COOLERS DETAIL OF NOZZLE 021E0018A/B | A1109 | 0X | 2 | 2019-06-04 | CON-BMP-VTRA-011961 | 2019-06-04 | FOR BAPCO REVIEW | 2019-06-19 | 2019-06-27 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001052 | CLASS 2
076551C-000R-MR-0610-003 | MATERIAL REQUISITION FOR WET H2S SERVICE SHELL AND TUBE HEAT EXCHANGER | HANTECH LTD | 021E0018A | HW18062-021E0018A/B-DWG-014 | 021-E-GAD-40156-001 | SOUR WATER COOLERS DETAIL OF INSUL. SUP'T CLIP 021E0018A/B | A1109 | AX | 2 | 2019-05-24 | CON-BMP-VTRA-011781 | 2019-05-24 | FOR BAPCO REVIEW | 2019-06-07 | 2019-06-16 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000928 | CLASS 2
076551C-000R-MR-0610-003 | MATERIAL REQUISITION FOR WET H2S SERVICE SHELL AND TUBE HEAT EXCHANGER | HANTECH LTD | 021E0018A | HW18062-021E0018A/B-DWG-015 | 021-E-GAD-40157-001 | SOUR WATER COOLER DETAIL OF TEST RING 021E0018A/B | A1109 | AX | 2 | 2019-05-24 | CON-BMP-VTRA-011781 | 2019-05-24 | FOR BAPCO REVIEW | 2019-06-07 | 2019-06-16 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000928 | CLASS 2
076551C-000R-MR-0610-003 | MATERIAL REQUISITION FOR WET H2S SERVICE SHELL AND TUBE HEAT EXCHANGER | HANTECH LTD | 021E0018A | HW18062-021E0018A/B-DWG-016 | 021-E-DLB-40013-001 | SOUR WATER COOLERS DETAIL OF NAME PLATE 021E0018A/B | A1112 | BX | 2 | 2019-06-03 | CON-BMP-VTRA-011935 | 2019-06-03 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-003 | MATERIAL REQUISITION FOR WET H2S SERVICE SHELL AND TUBE HEAT EXCHANGER | HANTECH LTD | 021E0018A | HW18062-021E0018AB-CAL-001 | 021-E-CAL-40056-001 | STRENGTH CALCULATION FOR 021E0018A 021E0018B | A1003 | CX | 2 | 2019-05-24 | CON-BMP-VTRA-011783 | 2019-05-24 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-003 | MATERIAL REQUISITION FOR WET H2S SERVICE SHELL AND TUBE HEAT EXCHANGER | HANTECH LTD | 021E0018A | HW18062-021E0018AB-DWG-003 | 021-E-GAD-40152-001 | SOUR WATER COOLERS DETAIL OF BODY (1/2) 021E0018A 021E0018B | A1109 | 0X | 3 | 2019-05-24 | CON-BMP-VTRA-011785 | 2019-05-24 | FOR BAPCO REVIEW | 2019-06-07 | 2019-06-16 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000932 | CLASS 2
076551C-000R-MR-0610-003 | MATERIAL REQUISITION FOR WET H2S SERVICE SHELL AND TUBE HEAT EXCHANGER | HANTECH LTD | 021E0018A | HW18062-021E0018AB-DWG-004 | 021-E-GAD-40152-002 | SOUR WATER COOLERS DETAIL OF BODY (2/2) 021E0018A 021E0018B | A1109 | 0X | 2 | 2019-06-04 | CON-BMP-VTRA-011961 | 2019-06-04 | FOR BAPCO REVIEW | 2019-06-19 | 2019-06-27 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001052 | CLASS 2
076551C-000R-MR-0610-003 | MATERIAL REQUISITION FOR WET H2S SERVICE SHELL AND TUBE HEAT EXCHANGER | HANTECH LTD | 021E0018A | HW18062-021E0018AB-DWG-006 | 021-E-GAD-40153-002 | SOUR WATER COOLERS DETAIL OF BUNDLE (2/4) 021E0018A | A1109 | 0X | 3 | 2019-06-04 | CON-BMP-VTRA-011963 | 2019-06-04 | FOR BAPCO REVIEW | 2019-06-19 |  |  | CLASS 2
076551C-000R-MR-0610-003 | MATERIAL REQUISITION FOR WET H2S SERVICE SHELL AND TUBE HEAT EXCHANGER | HANTECH LTD | 021E0018A | HW18062-021E0018AB-DWG-013 | 021-E-GAD-40155-001 | SOUR WATER COOLERS DETAIL OF SADDLE 021E0018A 021E0018B | A1109 | 0X | 3 | 2019-06-04 | CON-BMP-VTRA-011963 | 2019-06-04 | FOR BAPCO REVIEW | 2019-06-19 |  |  | CLASS 2
076551C-000R-MR-0610-003 | MATERIAL REQUISITION FOR WET H2S SERVICE SHELL AND TUBE HEAT EXCHANGER | HANTECH LTD | 021E0018A | HW18062-DOC-306 | 021-E-PQP-40028-001 | FABRICATION AND QUALITY CONTROL PLAN 021E0018A | B1002 | BX | 2 | 2019-06-25 | CON-BMP-VTRA-012431 | 2019-06-25 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-003 | MATERIAL REQUISITION FOR WET H2S SERVICE SHELL AND TUBE HEAT EXCHANGER | HANTECH LTD | 021E0018A | HW18062-DOC-318 | 021-E-MCD-40033-001 | WPS AND PQR WITH WELD MAP FOR 021E0018A | B1304 | BX | 2 | 2019-05-27 | CON-BMP-VTRA-011806 | 2019-05-27 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-003 | MATERIAL REQUISITION FOR WET H2S SERVICE SHELL AND TUBE HEAT EXCHANGER | HANTECH LTD | 021E0018B | HW18062-021E0018AB-DWG-007 | 021-E-GAD-40153-003 | SOUR WATER COOLERS DETAIL OF BUNDLE (3/4) 021E0018B | A1109 | 0X | 3 | 2019-05-24 | CON-BMP-VTRA-011785 | 2019-05-24 | FOR BAPCO REVIEW | 2019-06-07 | 2019-06-16 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000932 | CLASS 2
076551C-000R-MR-0610-003 | MATERIAL REQUISITION FOR WET H2S SERVICE SHELL AND TUBE HEAT EXCHANGER | HANTECH LTD | 021E0018B | HW18062-021E0018AB-DWG-008 | 021-E-GAD-40153-004 | SOUR WATER COOLERSDETAIL OF BUNDLE (4/4) 021E0018B | A1109 | 0X | 3 | 2019-06-04 | CON-BMP-VTRA-011963 | 2019-06-04 | FOR BAPCO REVIEW | 2019-06-19 |  |  | CLASS 2
076551C-000R-MR-0610-003 | MATERIAL REQUISITION FOR WET H2S SERVICE SHELL AND TUBE HEAT EXCHANGER | HANTECH LTD | 021E0018B | HW18062-021E0018B-DWG-002 | 021-E-GAD-40158-001 | SOUR WATER COOLERS GENERAL ASSEMBLY (2/2) 021E0018B | A1103 | 0X | 2 | 2019-06-26 | CON-BMP-VTRA-012477 | 2019-06-26 | FOR BAPCO REVIEW | 2019-07-11 |  |  | CLASS 2
076551C-000R-MR-0610-003 | MATERIAL REQUISITION FOR WET H2S SERVICE SHELL AND TUBE HEAT EXCHANGER | HANTECH LTD | 021E0018B | HW18062-DOC-307 | 021-E-PQP-40029-001 | FABRICATION AND QUALITY CONTROL PLAN 021E0018B | B1002 | BX | 2 | 2019-06-25 | CON-BMP-VTRA-012431 | 2019-06-25 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-003 | MATERIAL REQUISITION FOR WET H2S SERVICE SHELL AND TUBE HEAT EXCHANGER | HANTECH LTD | 021E0018B | HW18062-DOC-319 | 021-E-MCD-40034-001 | WPS AND PQR WITH WELD MAP FOR 021E0018B | B1304 | BX | 2 | 2019-05-27 | CON-BMP-VTRA-011806 | 2019-05-27 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-003 | MATERIAL REQUISITION FOR WET H2S SERVICE SHELL AND TUBE HEAT EXCHANGER | HANTECH LTD | 023E0001 | HW18062-023E0001-CAL-001 | 023-E-CAL-40001-001 | STRENGTH CALCULATION FOR 023E0001 | A1003 | CX | 2 | 2019-05-24 | CON-BMP-VTRA-011783 | 2019-05-24 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-003 | MATERIAL REQUISITION FOR WET H2S SERVICE SHELL AND TUBE HEAT EXCHANGER | HANTECH LTD | 023E0001 | HW18062-023E0001-DWG-001 | 023-E-GAD-40008-001 | FEED GAS COOLER GENERAL ASSEMBLY 023E0001 | A1103 | 0X | 2 | 2019-06-26 | CON-BMP-VTRA-012471 | 2019-06-26 | FOR BAPCO REVIEW | 2019-07-10 |  |  | CLASS 2
076551C-000R-MR-0610-003 | MATERIAL REQUISITION FOR WET H2S SERVICE SHELL AND TUBE HEAT EXCHANGER | HANTECH LTD | 023E0001 | HW18062-023E0001-DWG-002 | 023-E-GAD-40014-001 | FEED GAS COOLER DETAIL OF BODY 023E0001 | A1109 | 0X | 2 | 2019-06-20 | CON-BMP-VTRA-012322 | 2019-06-20 | FOR BAPCO REVIEW | 2019-07-04 | 2019-07-10 | 3-REVIEWED WITH COMMENTS BMP-ROC-VTRE-001274 | CLASS 2
076551C-000R-MR-0610-003 | MATERIAL REQUISITION FOR WET H2S SERVICE SHELL AND TUBE HEAT EXCHANGER | HANTECH LTD | 023E0001 | HW18062-023E0001-DWG-004 | 023-E-GAD-40015-001 | FEED GAS COOLER DETAIL OF BUNDLE 023E0001 | A1109 | 0X | 3 | 2019-06-01 | CON-BMP-VTRA-011916 | 2019-06-01 | FOR BAPCO REVIEW | 2019-06-17 | 2019-06-18 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000983 | CLASS 2
076551C-000R-MR-0610-003 | MATERIAL REQUISITION FOR WET H2S SERVICE SHELL AND TUBE HEAT EXCHANGER | HANTECH LTD | 023E0001 | HW18062-023E0001-DWG-006 | 023-E-GAD-40016-001 | FEED GAS COOLER DETAIL OF NOZZLE 023E0001 | A1109 | 0X | 3 | 2019-05-24 | CON-BMP-VTRA-011785 | 2019-05-24 | FOR BAPCO REVIEW | 2019-06-07 | 2019-06-16 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000932 | CLASS 2
076551C-000R-MR-0610-003 | MATERIAL REQUISITION FOR WET H2S SERVICE SHELL AND TUBE HEAT EXCHANGER | HANTECH LTD | 023E0001 | HW18062-023E0001-DWG-008 | 023-E-DLB-40001-001 | FEED GAS COOLER DETAIL OF NAME PLATE 023E0001 | A1112 | BX | 2 | 2019-06-03 | CON-BMP-VTRA-011935 | 2019-06-03 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-003 | MATERIAL REQUISITION FOR WET H2S SERVICE SHELL AND TUBE HEAT EXCHANGER | HANTECH LTD | 023E0001 | HW18062-023E0001-DWG-009 | 023-E-GAD-40043-001 | FEED GAS COOLER 023E0001 GENERAL NOTES | A1103 | 0X | 2 | 2019-06-20 | CON-BMP-VTRA-012325 | 2019-06-20 | FOR BAPCO REVIEW | 2019-07-04 | 2019-07-10 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001267 | CLASS 2
076551C-000R-MR-0610-003 | MATERIAL REQUISITION FOR WET H2S SERVICE SHELL AND TUBE HEAT EXCHANGER | HANTECH LTD | 023E0001 | HW18062-DOC-308 | 023-E-PQP-40001-001 | FABRICATION AND QUALITY CONTROL PLAN 023E0001 | B1002 | BX | 2 | 2019-06-25 | CON-BMP-VTRA-012432 | 2019-06-25 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-003 | MATERIAL REQUISITION FOR WET H2S SERVICE SHELL AND TUBE HEAT EXCHANGER | HANTECH LTD | 023E0001 | HW18062-DOC-320 | 023-E-MCD-40001-001 | WPS AND PQR WITH WELD MAP FOR 023E0001 | B1304 | BX | 2 | 2019-05-27 | CON-BMP-VTRA-011806 | 2019-05-27 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-003 | MATERIAL REQUISITION FOR WET H2S SERVICE SHELL AND TUBE HEAT EXCHANGER | HANTECH LTD | 023E0002 | HW18062-023E0002-CAL-001 | 023-E-CAL-40002-001 | STRENGTH CALCULATION FOR 023E0002 | A1003 | CX | 2 | 2019-05-24 | CON-BMP-VTRA-011783 | 2019-05-24 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-003 | MATERIAL REQUISITION FOR WET H2S SERVICE SHELL AND TUBE HEAT EXCHANGER | HANTECH LTD | 023E0002 | HW18062-023E0002-DWG-001 | 023-E-GAD-40009-001 | COMPRESSED GAS TRIM COOLER GENERAL ASSEMBLY 023E0002 | A1103 | CX | 2 | 2019-05-24 | CON-BMP-VTRA-011782 | 2019-05-24 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-003 | MATERIAL REQUISITION FOR WET H2S SERVICE SHELL AND TUBE HEAT EXCHANGER | HANTECH LTD | 023E0002 | HW18062-023E0002-DWG-002 | 023-E-GAD-40018-001 | COMPRESSED GAS TRIM COOLER DETAIL OF BODY (1/2) 023E0002 | A1109 | CX | 2 | 2019-05-24 | CON-BMP-VTRA-011784 | 2019-05-24 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-003 | MATERIAL REQUISITION FOR WET H2S SERVICE SHELL AND TUBE HEAT EXCHANGER | HANTECH LTD | 023E0002 | HW18062-023E0002-DWG-003 | 023-E-GAD-40018-002 | COMPRESSED GAS TRIM COOLER DETAIL OF BODY (2/2) 023E0002 | A1109 | CX | 2 | 2019-05-24 | CON-BMP-VTRA-011784 | 2019-05-24 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-003 | MATERIAL REQUISITION FOR WET H2S SERVICE SHELL AND TUBE HEAT EXCHANGER | HANTECH LTD | 023E0002 | HW18062-023E0002-DWG-004 | 023-E-GAD-40019-001 | COMPRESSED GAS TRIM COOLER DETAIL OF BUNDLE (1/2) 023E0002 | A1109 | 0X | 2 | 2019-06-26 | CON-BMP-VTRA-012472 | 2019-06-26 | FOR BAPCO REVIEW | 2019-07-10 |  |  | CLASS 2
076551C-000R-MR-0610-003 | MATERIAL REQUISITION FOR WET H2S SERVICE SHELL AND TUBE HEAT EXCHANGER | HANTECH LTD | 023E0002 | HW18062-023E0002-DWG-005 | 023-E-GAD-40019-002 | COMPRESSED GAS TRIM COOLER DETAIL OF BUNDLE (2/2) 023E0002 | A1109 | 0X | 2 | 2019-06-26 | CON-BMP-VTRA-012482 | 2019-06-26 | FOR BAPCO REVIEW | 2019-07-11 |  |  | CLASS 2
076551C-000R-MR-0610-003 | MATERIAL REQUISITION FOR WET H2S SERVICE SHELL AND TUBE HEAT EXCHANGER | HANTECH LTD | 023E0002 | HW18062-023E0002-DWG-006 | 023-E-GAD-40020-001 | COMPRESSED GAS TRIM COOLER DETAIL OF NOZZLE 023E0002 | A1109 | 0X | 2 | 2019-06-26 | CON-BMP-VTRA-012472 | 2019-06-26 | FOR BAPCO REVIEW | 2019-07-10 |  |  | CLASS 2
076551C-000R-MR-0610-003 | MATERIAL REQUISITION FOR WET H2S SERVICE SHELL AND TUBE HEAT EXCHANGER | HANTECH LTD | 023E0002 | HW18062-023E0002-DWG-007 | 023-E-GAD-40021-001 | COMPRESSED GAS TRIM COOLER DETAIL OF INSUL. SUP'T CLIP 023E0002 | A1109 | 0X | 3 | 2019-06-17 | CON-BMP-VTRA-012233 | 2019-06-17 | FOR BAPCO REVIEW | 2019-07-01 | 2019-07-08 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001221 | CLASS 2
076551C-000R-MR-0610-003 | MATERIAL REQUISITION FOR WET H2S SERVICE SHELL AND TUBE HEAT EXCHANGER | HANTECH LTD | 023E0002 | HW18062-023E0002-DWG-008 | 023-E-DLB-40002-001 | COMPRESSED GAS TRIM COOLER DETAIL OF NAME PLATE 023E0002 | A1112 | BX | 2 | 2019-06-03 | CON-BMP-VTRA-011936 | 2019-06-03 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-003 | MATERIAL REQUISITION FOR WET H2S SERVICE SHELL AND TUBE HEAT EXCHANGER | HANTECH LTD | 023E0002 | HW18062-023E0002-DWG-009 | 023-E-GAD-40039-001 | COMPRESSED GAS TRIM COOLER 023E0002 GENERAL NOTES | A1103 | BX | 2 | 2019-05-27 | CON-BMP-VTRA-011805 | 2019-05-27 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-003 | MATERIAL REQUISITION FOR WET H2S SERVICE SHELL AND TUBE HEAT EXCHANGER | HANTECH LTD | 023E0002 | HW18062-DOC-309 | 023-E-PQP-40002-001 | FABRICATION AND QUALITY CONTROL PLAN 023E0002 | B1002 | BX | 2 | 2019-06-25 | CON-BMP-VTRA-012432 | 2019-06-25 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-003 | MATERIAL REQUISITION FOR WET H2S SERVICE SHELL AND TUBE HEAT EXCHANGER | HANTECH LTD | 023E0002 | HW18062-DOC-321 | 023-E-MCD-40002-001 | WPS AND PQR WITH WELD MAP FOR 023E0002 | B1304 | BX | 2 | 2019-05-27 | CON-BMP-VTRA-011806 | 2019-05-27 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-003 | MATERIAL REQUISITION FOR WET H2S SERVICE SHELL AND TUBE HEAT EXCHANGER | HANTECH LTD | 023E0003 | HW18062-023E0003-CAL-001 | 023-E-CAL-40003-001 | STRENGTH CALCULATION FOR 023E0003 | A1003 | CX | 2 | 2019-05-24 | CON-BMP-VTRA-011783 | 2019-05-24 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-003 | MATERIAL REQUISITION FOR WET H2S SERVICE SHELL AND TUBE HEAT EXCHANGER | HANTECH LTD | 023E0003 | HW18062-023E0003-DWG-001 | 023-E-GAD-40010-001 | LEAN AMINE COOLER GENERAL ASSEMBLY 023E0003 | A1103 | 0X | 3 | 2019-06-04 | CON-BMP-VTRA-011965 | 2019-06-04 | FOR BAPCO REVIEW | 2019-06-19 | 2019-06-26 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001043 | CLASS 2
076551C-000R-MR-0610-003 | MATERIAL REQUISITION FOR WET H2S SERVICE SHELL AND TUBE HEAT EXCHANGER | HANTECH LTD | 023E0003 | HW18062-023E0003-DWG-002 | 023-E-GAD-40022-001 | LEAN AMINE COOLER DETAIL OF BODY (1/2) 023E0003 | A1109 | 0X | 2 | 2019-06-26 | CON-BMP-VTRA-012482 | 2019-06-26 | FOR BAPCO REVIEW | 2019-07-11 |  |  | CLASS 2
076551C-000R-MR-0610-003 | MATERIAL REQUISITION FOR WET H2S SERVICE SHELL AND TUBE HEAT EXCHANGER | HANTECH LTD | 023E0003 | HW18062-023E0003-DWG-003 | 023-E-GAD-40022-002 | LEAN AMINE COOLER DETAIL OF BODY (2/2) 023E0003 | A1109 | 0X | 2 | 2019-06-26 | CON-BMP-VTRA-012475 | 2019-06-26 | FOR BAPCO REVIEW | 2019-07-10 |  |  | CLASS 2
076551C-000R-MR-0610-003 | MATERIAL REQUISITION FOR WET H2S SERVICE SHELL AND TUBE HEAT EXCHANGER | HANTECH LTD | 023E0003 | HW18062-023E0003-DWG-004 | 023-E-GAD-40023-001 | LEAN AMINE COOLER DETAIL OF BUNDLE (1/2) 023E0003 | A1109 | 0X | 2 | 2019-06-26 | CON-BMP-VTRA-012472 | 2019-06-26 | FOR BAPCO REVIEW | 2019-07-10 |  |  | CLASS 2
076551C-000R-MR-0610-003 | MATERIAL REQUISITION FOR WET H2S SERVICE SHELL AND TUBE HEAT EXCHANGER | HANTECH LTD | 023E0003 | HW18062-023E0003-DWG-005 | 023-E-GAD-40023-002 | LEAN AMINE COOLER DETAIL OF BUNDLE (2/2) 023E0003 | A1109 | 0X | 2 | 2019-06-26 | CON-BMP-VTRA-012482 | 2019-06-26 | FOR BAPCO REVIEW | 2019-07-11 |  |  | CLASS 2
076551C-000R-MR-0610-003 | MATERIAL REQUISITION FOR WET H2S SERVICE SHELL AND TUBE HEAT EXCHANGER | HANTECH LTD | 023E0003 | HW18062-023E0003-DWG-006 | 023-E-GAD-40024-001 | LEAN AMINE COOLER DETAIL OF NOZZLE 023E0003 | A1109 | 0X | 2 | 2019-06-26 | CON-BMP-VTRA-012472 | 2019-06-26 | FOR BAPCO REVIEW | 2019-07-10 |  |  | CLASS 2
076551C-000R-MR-0610-003 | MATERIAL REQUISITION FOR WET H2S SERVICE SHELL AND TUBE HEAT EXCHANGER | HANTECH LTD | 023E0003 | HW18062-023E0003-DWG-007 | 023-E-GAD-40025-001 | LEAN AMINE COOLER DETAIL OF INSUL. SUP'T CLIP 023E0003 | A1109 | 0X | 2 | 2019-06-26 | CON-BMP-VTRA-012472 | 2019-06-26 | FOR BAPCO REVIEW | 2019-07-10 |  |  | CLASS 2
076551C-000R-MR-0610-003 | MATERIAL REQUISITION FOR WET H2S SERVICE SHELL AND TUBE HEAT EXCHANGER | HANTECH LTD | 023E0003 | HW18062-023E0003-DWG-008 | 023-E-GAD-40026-001 | LEAN AMINE COOLER DETAIL OF TEST RING 023E0003 | A1109 | AX | 2 | 2019-05-24 | CON-BMP-VTRA-011781 | 2019-05-24 | FOR BAPCO REVIEW | 2019-06-07 | 2019-06-16 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000928 | CLASS 2
076551C-000R-MR-0610-003 | MATERIAL REQUISITION FOR WET H2S SERVICE SHELL AND TUBE HEAT EXCHANGER | HANTECH LTD | 023E0003 | HW18062-023E0003-DWG-009 | 023-E-DLB-40003-001 | LEAN AMINE COOLER DETAIL OF NAME PLATE 023E0003 | A1112 | BX | 2 | 2019-06-03 | CON-BMP-VTRA-011935 | 2019-06-03 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-003 | MATERIAL REQUISITION FOR WET H2S SERVICE SHELL AND TUBE HEAT EXCHANGER | HANTECH LTD | 023E0003 | HW18062-023E0003-DWG-010 | 023-E-GAD-40040-001 | LEAN AMINE COOLER 023E0003 GENERAL NOTES | A1103 | 0X | 2 | 2019-06-17 | CON-BMP-VTRA-012232 | 2019-06-17 | FOR BAPCO REVIEW | 2019-07-01 | 2019-07-08 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001215 | CLASS 2
076551C-000R-MR-0610-003 | MATERIAL REQUISITION FOR WET H2S SERVICE SHELL AND TUBE HEAT EXCHANGER | HANTECH LTD | 023E0003 | HW18062-DOC-310 | 023-E-PQP-40003-001 | FABRICATION AND QUALITY CONTROL PLAN 023E0003 | B1002 | BX | 2 | 2019-06-25 | CON-BMP-VTRA-012432 | 2019-06-25 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-003 | MATERIAL REQUISITION FOR WET H2S SERVICE SHELL AND TUBE HEAT EXCHANGER | HANTECH LTD | 023E0003 | HW18062-DOC-322 | 023-E-MCD-40003-001 | WPS AND PQR WITH WELD MAP FOR 023E0003 | B1304 | BX | 2 | 2019-05-27 | CON-BMP-VTRA-011806 | 2019-05-27 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-003 | MATERIAL REQUISITION FOR WET H2S SERVICE SHELL AND TUBE HEAT EXCHANGER | HANTECH LTD | 023E0004 | HW18062-023E0004-CAL-001 | 023-E-CAL-40004-001 | STRENGTH CALCULATION FOR 023E0004 | A1003 | CX | 2 | 2019-05-24 | CON-BMP-VTRA-011786 | 2019-05-24 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-003 | MATERIAL REQUISITION FOR WET H2S SERVICE SHELL AND TUBE HEAT EXCHANGER | HANTECH LTD | 023E0004 | HW18062-023E0004-DWG-001 | 023-E-GAD-40011-001 | PSA INLET COOLER GENERAL ASSEMBLY 023E0004 | A1103 | CX | 2 | 2019-05-24 | CON-BMP-VTRA-011791 | 2019-05-24 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-003 | MATERIAL REQUISITION FOR WET H2S SERVICE SHELL AND TUBE HEAT EXCHANGER | HANTECH LTD | 023E0004 | HW18062-023E0004-DWG-002 | 023-E-GAD-40027-001 | PSA INLET COOLER DETAIL OF BODY (1/2) 023E0004 | A1109 | CX | 2 | 2019-05-24 | CON-BMP-VTRA-011788 | 2019-05-24 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-003 | MATERIAL REQUISITION FOR WET H2S SERVICE SHELL AND TUBE HEAT EXCHANGER | HANTECH LTD | 023E0004 | HW18062-023E0004-DWG-003 | 023-E-GAD-40027-002 | PSA INLET COOLER DETAIL OF BODY (2/2) 023E0004 | A1109 | CX | 2 | 2019-05-24 | CON-BMP-VTRA-011788 | 2019-05-24 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-003 | MATERIAL REQUISITION FOR WET H2S SERVICE SHELL AND TUBE HEAT EXCHANGER | HANTECH LTD | 023E0004 | HW18062-023E0004-DWG-004 | 023-E-GAD-40028-001 | PSA INLET COOLER DETAIL OF BUNDLE (1/2) 023E0004 | A1109 | CX | 2 | 2019-05-24 | CON-BMP-VTRA-011788 | 2019-05-24 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-003 | MATERIAL REQUISITION FOR WET H2S SERVICE SHELL AND TUBE HEAT EXCHANGER | HANTECH LTD | 023E0004 | HW18062-023E0004-DWG-005 | 023-E-GAD-40028-002 | PSA INLET COOLER DETAIL OF BUNDLE (2/2) 023E0004 | A1109 | CX | 2 | 2019-05-24 | CON-BMP-VTRA-011788 | 2019-05-24 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-003 | MATERIAL REQUISITION FOR WET H2S SERVICE SHELL AND TUBE HEAT EXCHANGER | HANTECH LTD | 023E0004 | HW18062-023E0004-DWG-006 | 023-E-GAD-40029-001 | PSA INLET COOLER DETAIL OF NOZZLE 023E0004 | A1109 | 0X | 2 | 2019-06-26 | CON-BMP-VTRA-012474 | 2019-06-26 | FOR BAPCO REVIEW | 2019-07-11 |  |  | CLASS 2
076551C-000R-MR-0610-003 | MATERIAL REQUISITION FOR WET H2S SERVICE SHELL AND TUBE HEAT EXCHANGER | HANTECH LTD | 023E0004 | HW18062-023E0004-DWG-007 | 023-E-DLB-40004-001 | PSA INLET COOLER DETAIL OF NAME PLATE 023E0004 | A1112 | BX | 2 | 2019-05-24 | CON-BMP-VTRA-011804 | 2019-05-24 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-003 | MATERIAL REQUISITION FOR WET H2S SERVICE SHELL AND TUBE HEAT EXCHANGER | HANTECH LTD | 023E0004 | HW18062-023E0004-DWG-008 | 023-E-GAD-40041-001 | PSA INLET COOLER 023E0004 GENERAL NOTES | A1103 | BX | 2 | 2019-05-24 | CON-BMP-VTRA-011802 | 2019-05-24 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-003 | MATERIAL REQUISITION FOR WET H2S SERVICE SHELL AND TUBE HEAT EXCHANGER | HANTECH LTD | 023E0004 | HW18062-DOC-311 | 023-E-PQP-40004-001 | FABRICATION AND QUALITY CONTROL PLAN 023E0004 | B1002 | BX | 2 | 2019-06-25 | CON-BMP-VTRA-012432 | 2019-06-25 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-003 | MATERIAL REQUISITION FOR WET H2S SERVICE SHELL AND TUBE HEAT EXCHANGER | HANTECH LTD | 023E0004 | HW18062-DOC-323 | 023-E-MCD-40004-001 | WPS AND PQR WITH WELD MAP FOR 023E0004 | B1304 | BX | 2 | 2019-05-27 | CON-BMP-VTRA-011806 | 2019-05-27 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-003 | MATERIAL REQUISITION FOR WET H2S SERVICE SHELL AND TUBE HEAT EXCHANGER | HANTECH LTD | 023E0005A | HW18062-023E0005A/B-DWG-006 | 023-E-GAD-40032-001 | 1ST STAGE GAS TRIM COOLER DETAIL OF NOZZLE 023E0005A/B | A1109 | 0X | 2 | 2019-06-26 | CON-BMP-VTRA-012472 | 2019-06-26 | FOR BAPCO REVIEW | 2019-07-10 |  |  | CLASS 2
076551C-000R-MR-0610-003 | MATERIAL REQUISITION FOR WET H2S SERVICE SHELL AND TUBE HEAT EXCHANGER | HANTECH LTD | 023E0005A | HW18062-023E0005A/B-DWG-007 | 023-E-GAD-40033-001 | 1ST STAGE GAS TRIM COOLER DETAIL OF INSUL. SUP'T CLIP 023E0005A/B | A1109 | 0X | 3 | 2019-06-17 | CON-BMP-VTRA-012233 | 2019-06-17 | FOR BAPCO REVIEW | 2019-07-01 | 2019-07-08 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001221 | CLASS 2
076551C-000R-MR-0610-003 | MATERIAL REQUISITION FOR WET H2S SERVICE SHELL AND TUBE HEAT EXCHANGER | HANTECH LTD | 023E0005A | HW18062-023E0005A/B-DWG-008 | 023-E-DLB-40005-001 | 1ST STAGE GAS TRIM COOLER DETAIL OF NAME PLATE 023E0005A/B | A1112 | BX | 2 | 2019-06-03 | CON-BMP-VTRA-011935 | 2019-06-03 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-003 | MATERIAL REQUISITION FOR WET H2S SERVICE SHELL AND TUBE HEAT EXCHANGER | HANTECH LTD | 023E0005A | HW18062-023E0005AB-CAL-001 | 023-E-CAL-40005-001 | STRENGTH CALCULATION FOR 023E0005A 023E0005B | A1003 | CX | 2 | 2019-05-24 | CON-BMP-VTRA-011783 | 2019-05-24 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-003 | MATERIAL REQUISITION FOR WET H2S SERVICE SHELL AND TUBE HEAT EXCHANGER | HANTECH LTD | 023E0005A | HW18062-023E0005AB-DWG-001 | 023-E-GAD-40012-001 | 1ST STAGE GAS TRIM COOLER GENERAL ASSEMBLY 023E0005A 023E0005B | A1103 | CX | 2 | 2019-05-29 | CON-BMP-VTRA-011839 | 2019-05-29 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-003 | MATERIAL REQUISITION FOR WET H2S SERVICE SHELL AND TUBE HEAT EXCHANGER | HANTECH LTD | 023E0005A | HW18062-023E0005AB-DWG-002 | 023-E-GAD-40030-001 | 1ST STAGE GAS TRIM COOLER DETAIL OF BODY (1/2) 023E0005A 023E0005B | A1109 | 0X | 2 | 2019-06-26 | CON-BMP-VTRA-012482 | 2019-06-26 | FOR BAPCO REVIEW | 2019-07-11 |  |  | CLASS 2
076551C-000R-MR-0610-003 | MATERIAL REQUISITION FOR WET H2S SERVICE SHELL AND TUBE HEAT EXCHANGER | HANTECH LTD | 023E0005A | HW18062-023E0005AB-DWG-003 | 023-E-GAD-40030-002 | 1ST STAGE GAS TRIM COOLER DETAIL OF BODY (2/2) 023E0005A 023E0005B | A1109 | CX | 2 | 2019-05-24 | CON-BMP-VTRA-011784 | 2019-05-24 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-003 | MATERIAL REQUISITION FOR WET H2S SERVICE SHELL AND TUBE HEAT EXCHANGER | HANTECH LTD | 023E0005A | HW18062-023E0005AB-DWG-004 | 023-E-GAD-40031-001 | 1ST STAGE GAS TRIM COOLER DETAIL OF BUNDLE (1/2) 023E0005A/B | A1109 | 0X | 2 | 2019-06-26 | CON-BMP-VTRA-012472 | 2019-06-26 | FOR BAPCO REVIEW | 2019-07-10 |  |  | CLASS 2
076551C-000R-MR-0610-003 | MATERIAL REQUISITION FOR WET H2S SERVICE SHELL AND TUBE HEAT EXCHANGER | HANTECH LTD | 023E0005A | HW18062-023E0005AB-DWG-005 | 023-E-GAD-40031-002 | 1ST STAGE GAS TRIM COOLER DETAIL OF BUNDLE (2/2) 023E0005A/B | A1109 | CX | 2 | 2019-05-24 | CON-BMP-VTRA-011784 | 2019-05-24 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-003 | MATERIAL REQUISITION FOR WET H2S SERVICE SHELL AND TUBE HEAT EXCHANGER | HANTECH LTD | 023E0005A | HW18062-023E0005AB-DWG-009 | 023-E-GAD-40042-001 | 1ST STAGE GAS TRIM COOLER 023E0005AB GENERAL NOTES | A1103 | BX | 2 | 2019-05-27 | CON-BMP-VTRA-011805 | 2019-05-27 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-003 | MATERIAL REQUISITION FOR WET H2S SERVICE SHELL AND TUBE HEAT EXCHANGER | HANTECH LTD | 023E0005A | HW18062-DOC-312 | 023-E-PQP-40005-001 | FABRICATION AND QUALITY CONTROL PLAN 023E0005A/B | B1002 | BX | 2 | 2019-06-25 | CON-BMP-VTRA-012432 | 2019-06-25 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-003 | MATERIAL REQUISITION FOR WET H2S SERVICE SHELL AND TUBE HEAT EXCHANGER | HANTECH LTD | 023E0005A | HW18062-DOC-324 | 023-E-MCD-40005-001 | WPS AND PQR WITH WELD MAP FOR 023E0005A/B | B1304 | BX | 2 | 2019-05-27 | CON-BMP-VTRA-011806 | 2019-05-27 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-003 | MATERIAL REQUISITION FOR WET H2S SERVICE SHELL AND TUBE HEAT EXCHANGER | HANTECH LTD | 023E0006A | HW18062-023E0006A/B-DWG-006 | 023-E-GAD-40036-001 | K0002A SPILLBACK COOLER DETAIL OF NOZZLE 023E0006A/B | A1109 | 0X | 3 | 2019-05-24 | CON-BMP-VTRA-011785 | 2019-05-24 | FOR BAPCO REVIEW | 2019-06-07 | 2019-06-16 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000932 | CLASS 2
076551C-000R-MR-0610-003 | MATERIAL REQUISITION FOR WET H2S SERVICE SHELL AND TUBE HEAT EXCHANGER | HANTECH LTD | 023E0006A | HW18062-023E0006A/B-DWG-007 | 023-E-GAD-40037-001 | 023K0002AB SPILLBACK COOLER DETAIL OF INSUL. SUP'T CLIP 023E0006A/B | A1109 | 0X | 2 | 2019-06-26 | CON-BMP-VTRA-012472 | 2019-06-26 | FOR BAPCO REVIEW | 2019-07-10 |  |  | CLASS 2
076551C-000R-MR-0610-003 | MATERIAL REQUISITION FOR WET H2S SERVICE SHELL AND TUBE HEAT EXCHANGER | HANTECH LTD | 023E0006A | HW18062-023E0006A/B-DWG-008 | 023-E-DLB-40006-001 | 023K0002 A/B SPILLBACK COOLER DETAIL OF NAME PLATE 023E0006A/B | A1112 | BX | 2 | 2019-06-03 | CON-BMP-VTRA-011934 | 2019-06-03 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-003 | MATERIAL REQUISITION FOR WET H2S SERVICE SHELL AND TUBE HEAT EXCHANGER | HANTECH LTD | 023E0006A | HW18062-023E0006AB-CAL-001 | 023-E-CAL-40006-001 | STRENGTH CALCULATION FOR 023E0006A 023E0006B | A1003 | CX | 2 | 2019-05-24 | CON-BMP-VTRA-011783 | 2019-05-24 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-003 | MATERIAL REQUISITION FOR WET H2S SERVICE SHELL AND TUBE HEAT EXCHANGER | HANTECH LTD | 023E0006A | HW18062-023E0006AB-DWG-001 | 023-E-GAD-40013-001 | 023K0002AB SPILLBACK COOLER GENERAL ASSEMBLY 023E0006A 023E0006B | A1103 | 0X | 2 | 2019-06-19 | CON-BMP-VTRA-012286 | 2019-06-19 | FOR BAPCO REVIEW | 2019-07-03 | 2019-07-09 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001234 | CLASS 2
076551C-000R-MR-0610-003 | MATERIAL REQUISITION FOR WET H2S SERVICE SHELL AND TUBE HEAT EXCHANGER | HANTECH LTD | 023E0006A | HW18062-023E0006AB-DWG-002 | 023-E-GAD-40034-001 | 023K0002AB SPILLBACK COOLER DETAIL OF BODY (1/2) 023E0006A 023E0006B | A1109 | 0X | 2 | 2019-06-20 | CON-BMP-VTRA-012323 | 2019-06-20 | FOR BAPCO REVIEW | 2019-07-04 | 2019-07-09 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001253 | CLASS 2
076551C-000R-MR-0610-003 | MATERIAL REQUISITION FOR WET H2S SERVICE SHELL AND TUBE HEAT EXCHANGER | HANTECH LTD | 023E0006A | HW18062-023E0006AB-DWG-003 | 023-E-GAD-40034-002 | 023K0002AB SPILLBACK COOLER DETAIL OF BODY (2/2) 023E0006A 023E0006B | A1109 | 0X | 2 | 2019-06-20 | CON-BMP-VTRA-012323 | 2019-06-20 | FOR BAPCO REVIEW | 2019-07-04 | 2019-07-09 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001253 | CLASS 2
076551C-000R-MR-0610-003 | MATERIAL REQUISITION FOR WET H2S SERVICE SHELL AND TUBE HEAT EXCHANGER | HANTECH LTD | 023E0006A | HW18062-023E0006AB-DWG-004 | 023-E-GAD-40035-001 | K0002A SPILLBACK COOLER DETAIL OF BUNDLE (1/2) 023E0006A/B | A1109 | 0X | 3 | 2019-06-17 | CON-BMP-VTRA-012233 | 2019-06-17 | FOR BAPCO REVIEW | 2019-07-01 | 2019-07-08 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001221 | CLASS 2
076551C-000R-MR-0610-003 | MATERIAL REQUISITION FOR WET H2S SERVICE SHELL AND TUBE HEAT EXCHANGER | HANTECH LTD | 023E0006A | HW18062-023E0006AB-DWG-005 | 023-E-GAD-40035-002 | K0002A SPILLBACK COOLER DETAIL OF BUNDLE (2/2) 023E0006A/B | A1109 | 0X | 2 | 2019-06-21 | CON-BMP-VTRA-012343 | 2019-06-21 | FOR BAPCO REVIEW | 2019-07-05 |  |  | CLASS 2
076551C-000R-MR-0610-003 | MATERIAL REQUISITION FOR WET H2S SERVICE SHELL AND TUBE HEAT EXCHANGER | HANTECH LTD | 023E0006A | HW18062-023E0006AB-DWG-009 | 023-E-GAD-40038-001 | 023K0002A SPILLBACK COOLER 023E0006A/B GENERAL NOTES | A1103 | 0X | 2 | 2019-06-17 | CON-BMP-VTRA-012232 | 2019-06-17 | FOR BAPCO REVIEW | 2019-07-01 | 2019-07-08 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001215 | CLASS 2
076551C-000R-MR-0610-003 | MATERIAL REQUISITION FOR WET H2S SERVICE SHELL AND TUBE HEAT EXCHANGER | HANTECH LTD | 023E0006A | HW18062-DOC-313 | 023-E-PQP-40006-001 | FABRICATION AND QUALITY CONTROL PLAN 023E0006A/B | B1002 | BX | 2 | 2019-06-25 | CON-BMP-VTRA-012432 | 2019-06-25 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-003 | MATERIAL REQUISITION FOR WET H2S SERVICE SHELL AND TUBE HEAT EXCHANGER | HANTECH LTD | 023E0006A | HW18062-DOC-325 | 023-E-MCD-40006-001 | WPS AND PQR WITH WELD MAP FOR 023E0006A/B | B1304 | BX | 2 | 2019-05-27 | CON-BMP-VTRA-011806 | 2019-05-27 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E0001 | VP-18TN-009-018E0001-001 | 018-E-GAD-40285-001 | GENERAL ARRANGEMENT DRAWING MAKE-UP HYDROGEN COOLER 018E0001 | A1103 | CX | 2 | 2019-06-05 | CON-BMP-VTRA-012019 | 2019-06-05 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E0001 | VP-18TN-009-018E0001-002 | 018-E-GAD-40286-001 | GENERAL NOTES MAKE-UP HYDROGEN COOLER 018E0001 | A1103 | CX | 2 | 2019-06-05 | CON-BMP-VTRA-012019 | 2019-06-05 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E0001 | VP-18TN-009-018E0001-003 | 018-E-GAD-40287-001 | DETAIL OF BODY MAKE-UP HYDROGEN COOLER 018E0001 | A1109 | CX | 2 | 2019-06-06 | CON-BMP-VTRA-012068 | 2019-06-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E0001 | VP-18TN-009-018E0001-004 | 018-E-GAD-40288-001 | DETAIL OF TUBE BUNDLE (1 TO 2) MAKE-UP HYDROGEN COOLER 018E0001 | A1109 | CX | 2 | 2019-06-06 | CON-BMP-VTRA-012068 | 2019-06-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E0001 | VP-18TN-009-018E0001-006 | 018-E-GAD-40289-001 | DETAIL OF SUPPORT SADDLE MAKEUP HYDROGEN COOLER 018E0001 | A1109 | CX | 2 | 2019-06-06 | CON-BMP-VTRA-012068 | 2019-06-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E0001 | VP-18TN-009-018E0001-007 | 018-E-GAD-40290-001 | DETAIL OF NOZZLE MAKE-UP HYDROGEN COOLER 018E0001 | A1109 | CX | 2 | 2019-06-06 | CON-BMP-VTRA-012068 | 2019-06-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E0001 | VP-18TN-009-018E0001-008 | 018-E-DLB-40021-001 | DETAIL OF NAME PLATE MAKE-UP HYDROGEN COOLER 018E0001 | A1112 | 0X | 3 | 2019-06-20 | CON-BMP-VTRA-012327 | 2019-06-20 | FOR BAPCO REVIEW | 2019-07-04 | 2019-07-11 | 3-REVIEWED WITH COMMENTS BMP-ROC-VTRE-001290 | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E0001 | VP-18TN-009-018E0001-100 | 018-E-CAL-40090-001 | STRENGTH CALCULATION 018E0001 | A1003 | CX | 2 | 2019-06-06 | CON-BMP-VTRA-012037 | 2019-06-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E0001 | VP-18TN-009-COMM-0100 | 000-E-INX-40007-001 | LIST OF VENDOR'S DOCUMENTS AND DWGS ALL ITEMS | A0001 | BX | 2 | 2019-03-21 | CON-BMP-VTRA-010820 | 2019-03-21 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E0001 | VP-18TN-009-COMM-0200 | 000-E-SCH-40002-001 | ENGINEERING PROCUREMENT MANUFACTURING AND TEST SCHEDULE ALL ITEMS | C1001 | CX | 4 | 2019-05-03 | CON-BMP-VTRA-011387 | 2019-05-03 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E0001 | VP-18TN-009-COMM-0300 | 000-E-MRS-40004-001 | MONTHLY PROGRESS REPORT ALL ITEMS | C1002 | DX | 4 | 2019-06-25 | CON-BMP-VTRA-012435 | 2019-06-25 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E0001 | VP-18TN-009-COMM-0400 | 000-E-INV-40003-001 | UNPRICED COPY OF MAIN SUBORDERS ALL ITEMS | C1005 | CX | 4 | 2019-05-03 | CON-BMP-VTRA-011384 | 2019-05-03 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E0001 | VP-18TN-009-COMM-0500 | 000-E-TSP-40009-001 | MATERIAL SPECIFICATION FOR MAIN SUB-ORDERS ALL ITEMS | B1203 | CX | 2 | 2019-05-17 | CON-BMP-VTRA-011653 | 2019-05-17 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E0001 | VP-18TN-009-COMM-0600 | 018-E-MCD-40064-001 | WELDING BOOK (MAP, PROCEDURE, QUALIFICATION REPORT) 018E0001 | B1304 | 0X | 3 | 2019-06-13 | CON-BMP-VTRA-012205 | 2019-06-13 | FOR BAPCO REVIEW | 2019-06-28 | 2019-06-30 | 1-APPROVED BMP-ROC-VTRE-001091 | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E0001 | VP-18TN-009-COMM-0660 | 000-E-PRO-40020-001 | MOCK UP TEST PROCEDURE ALL ITEMS | B1202 | 0X | 3 | 2019-06-26 | CON-BMP-VTRA-012495 | 2019-06-26 | FOR BAPCO REVIEW | 2019-07-11 |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E0001 | VP-18TN-009-COMM-0700 | 000-E-PRO-40009-001 | PWHT PROCEDURE ALL ITEMS | B1201 | 0X | 3 | 2019-06-25 | CON-BMP-VTRA-012434 | 2019-06-25 | FOR BAPCO REVIEW | 2019-07-09 |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E0001 | VP-18TN-009-COMM-0800 | 000-E-TSP-40010-001 | PAINTING SPECIFICATION ALL ITEMS | A0106 | BX | 2 | 2019-04-04 | CON-BMP-VTRA-011011 | 2019-04-04 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E0001 | VP-18TN-009-COMM-0900 | 000-E-TSP-40011-001 | BODY FLANGE TIGHTENING SPECIFICATION ALL ITEMS | A1202 | CX | 2 | 2019-06-05 | CON-BMP-VTRA-012023 | 2019-06-05 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E0001 | VP-18TN-009-COMM-1000 | 000-E-PQP-40005-001 | JOB Q.A.P. (CRITICAL EQPT) FOR CS SHELL AND TUBE HEAT EXCHAN ALL ITEMS (EX BAPCO N. 000-E-PLN-40001-001) | B1001 | 0X | 2 | 2019-05-30 | CON-BMP-VTRA-011847 | 2019-05-30 | FOR BAPCO REVIEW | 2019-06-13 | 2019-06-10 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000898 | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E0001 | VP-18TN-009-COMM-1100 | 000-E-PRO-40010-001 | TESTING PROCEDURES ALL ITEMS | B1103 | BX | 2 | 2019-05-24 | CON-BMP-VTRA-011793 | 2019-05-24 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E0001 | VP-18TN-009-COMM-1200 | 000-E-PRO-40011-001 | NDT PROCEDURE ALL ITEMS | B1202 | BX | 2 | 2019-05-22 | CON-BMP-VTRA-011733 | 2019-05-22 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E0001 | VP-18TN-009-COMM-1500 | 018-E-PQP-40026-001 | FABRICATION AND QUALITY CONTROL PLAN 018E0001 | B1002 | 0X | 3 | 2019-06-13 | CON-BMP-VTRA-012204 | 2019-06-13 | FOR BAPCO REVIEW | 2019-06-28 | 2019-06-29 | 1-APPROVED BMP-ROC-VTRE-001089 | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E0002 | VP-18TN-009-018E0002-001 | 018-E-GAD-40292-001 | GENERAL ARRANGEMENT DRAWING FIRST STAGE INTERCOOLER - SPARE TRAIN 018E0002 | A1103 | CX | 2 | 2019-06-05 | CON-BMP-VTRA-012019 | 2019-06-05 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E0002 | VP-18TN-009-018E0002-002 | 018-E-GAD-40293-001 | GENERAL NOTES FIRST-STAGE INTERCOOLER - SPARE TRAIN 018E0002 | A1103 | CX | 2 | 2019-06-05 | CON-BMP-VTRA-012019 | 2019-06-05 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E0002 | VP-18TN-009-018E0002-003 | 018-E-GAD-40294-001 | DETAIL OF BODY FIRST STAGE INTERCOOLER - SPARE TRAIN 018E0002 | A1109 | CX | 2 | 2019-06-06 | CON-BMP-VTRA-012068 | 2019-06-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E0002 | VP-18TN-009-018E0002-004 | 018-E-GAD-40295-001 | DETAIL OF TUBE BUNDLE (1 TO 2) FIRST STAGE INTERCOOLER-SPARE TRAIN 018E0002 | A1109 | 0X | 3 | 2019-06-06 | CON-BMP-VTRA-012056 | 2019-06-06 | FOR BAPCO REVIEW | 2019-06-20 | 2019-07-02 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001133 | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E0002 | VP-18TN-009-018E0002-006 | 018-E-GAD-40296-001 | DETAIL OF SUPPORT SADDLE FIRST STAGE INTERCOOLER - SPARE TRAIN 018E0002 | A1109 | CX | 2 | 2019-06-06 | CON-BMP-VTRA-012068 | 2019-06-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E0002 | VP-18TN-009-018E0002-007 | 018-E-GAD-40297-001 | DETAIL OF NOZZLE FIRST-STAGE INTERCOOLER 018E0002 | A1109 | CX | 2 | 2019-06-06 | CON-BMP-VTRA-012068 | 2019-06-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E0002 | VP-18TN-009-018E0002-008 | 018-E-DLB-40022-001 | DETAIL OF NAME PLATE MAKE-UP HYDROGEN COOLER 018E0002 | A1112 | CX | 2 | 2019-06-06 | CON-BMP-VTRA-012047 | 2019-06-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E0002 | VP-18TN-009-018E0002-100 | 018-E-CAL-40091-001 | STRENGTH CALCULATION 018E0002 | A1003 | CX | 2 | 2019-06-06 | CON-BMP-VTRA-012040 | 2019-06-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E0002 | VP-18TN-009-COMM-0601 | 018-E-MCD-40065-001 | WELDING BOOK (MAP, PROCEDURE, QUALIFICATION REPORT) 018E0002 | B1304 | 0X | 3 | 2019-06-13 | CON-BMP-VTRA-012205 | 2019-06-13 | FOR BAPCO REVIEW | 2019-06-28 | 2019-06-30 | 1-APPROVED BMP-ROC-VTRE-001091 | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E0002 | VP-18TN-009-COMM-1501 | 018-E-PQP-40027-001 | FABRICATION AND QUALITY CONTROL PLAN 018E0002 | B1002 | 0X | 3 | 2019-06-13 | CON-BMP-VTRA-012204 | 2019-06-13 | FOR BAPCO REVIEW | 2019-06-28 | 2019-06-29 | 1-APPROVED BMP-ROC-VTRE-001089 | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E0013 | VP-18TN-009-018E0013-001 | 018-E-GAD-40299-001 | GENERAL ARRANGEMENT DRAWING DIESEL PUMPAROUND MP STEAM GENERATOR 018E0013 | A1103 | CX | 2 | 2019-06-05 | CON-BMP-VTRA-012019 | 2019-06-05 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E0013 | VP-18TN-009-018E0013-002 | 018-E-GAD-40300-001 | GENERAL NOTES DIESEL PUMPAROUND MP STEAM GENERATOR 018E0013 | A1103 | CX | 2 | 2019-06-05 | CON-BMP-VTRA-012019 | 2019-06-05 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E0013 | VP-18TN-009-018E0013-003 | 018-E-GAD-40301-001 | DETAIL OF BODY DIESEL PUMPAROUND MP STEAM GENERATOR 018E0013 | A1109 | CX | 2 | 2019-06-06 | CON-BMP-VTRA-012065 | 2019-06-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E0013 | VP-18TN-009-018E0013-004 | 018-E-GAD-40302-001 | DETAIL OF TUBE BUNDLE DIESEL PUMPAROUND MP STEAM GENERATOR 018E0013 | A1109 | CX | 2 | 2019-06-06 | CON-BMP-VTRA-012065 | 2019-06-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E0013 | VP-18TN-009-018E0013-006 | 018-E-GAD-40303-001 | DETAIL OF SUPPORT SADDLE DIESEL PUMPAROUND MP STEAM GENERATOR 018E0013 | A1109 | CX | 2 | 2019-06-22 | CON-BMP-VTRA-012386 | 2019-06-22 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E0013 | VP-18TN-009-018E0013-007 | 018-E-GAD-40304-001 | DETAIL OF NOZZLE DIESEL PUMPAROUND MP STEAM GENERATOR 018E0013 | A1109 | 0X | 2 | 2019-06-12 | CON-BMP-VTRA-012170 | 2019-06-12 | FOR BAPCO REVIEW | 2019-06-26 | 2019-07-03 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001152 | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E0013 | VP-18TN-009-018E0013-009 | 018-E-DLB-40023-001 | DETAIL OF NAME PLATE 018E0013 DIESEL PUMPAROUND MP STEAM GENERATOR | A1112 | 0X | 2 | 2019-06-12 | CON-BMP-VTRA-012166 | 2019-06-12 | FOR BAPCO REVIEW | 2019-06-26 | 2019-07-02 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001147 | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E0013 | VP-18TN-009-018E0013-100 | 018-E-CAL-40092-001 | STRENGTH CALCULATION 018E0013 | A1003 | CX | 2 | 2019-06-06 | CON-BMP-VTRA-012040 | 2019-06-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E0013 | VP-18TN-009-COMM-0602 | 018-E-MCD-40066-001 | WELDING BOOK (MAP, PROCEDURE, QUALIFICATION REPORT) 018E0013 | B1304 | 0X | 3 | 2019-06-13 | CON-BMP-VTRA-012205 | 2019-06-13 | FOR BAPCO REVIEW | 2019-06-28 | 2019-06-30 | 1-APPROVED BMP-ROC-VTRE-001091 | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E0013 | VP-18TN-009-COMM-1502 | 018-E-PQP-40028-001 | FABRICATION AND QUALITY CONTROL PLAN 018E0013 | B1002 | 0X | 3 | 2019-06-13 | CON-BMP-VTRA-012204 | 2019-06-13 | FOR BAPCO REVIEW | 2019-06-28 | 2019-06-29 | 1-APPROVED BMP-ROC-VTRE-001089 | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E0014 | VP-18TN-009-018E0014-001 | 018-E-GAD-40306-001 | GENERAL ARRANGEMENT DRAWING DIESEL PUMPAROUND LP STEAM GENERATOR 018E0014 | A1103 | CX | 2 | 2019-06-05 | CON-BMP-VTRA-012019 | 2019-06-05 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E0014 | VP-18TN-009-018E0014-002 | 018-E-GAD-40307-001 | GENERAL NOTE DIESEL PUMPAROUND LP STEAM GENERATOR 018E0014 | A1103 | CX | 2 | 2019-06-05 | CON-BMP-VTRA-012019 | 2019-06-05 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E0014 | VP-18TN-009-018E0014-003 | 018-E-GAD-40308-001 | DETAIL OF BODY DIESEL PUMPAROUND LP STEAM GENERATOR 018E0014 | A1109 | CX | 2 | 2019-06-06 | CON-BMP-VTRA-012065 | 2019-06-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E0014 | VP-18TN-009-018E0014-004 | 018-E-GAD-40309-001 | DETAIL OF TUBE BUNDLE DIESEL PUMPAROUND LP STEAM GENERATOR 018E0014 | A1109 | CX | 2 | 2019-06-06 | CON-BMP-VTRA-012065 | 2019-06-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E0014 | VP-18TN-009-018E0014-006 | 018-E-GAD-40310-001 | DETAIL OF SUPPORT SADDLE DIESEL PUMPAROUND LP STEAM GENERATOR 018E0014 | A1109 | CX | 2 | 2019-06-06 | CON-BMP-VTRA-012065 | 2019-06-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E0014 | VP-18TN-009-018E0014-007 | 018-E-GAD-40311-001 | DETAIL OF NOZZLE DIESEL PUMPAROUND LP STEAM GENERATOR 018E0014 | A1109 | 0X | 2 | 2019-06-06 | CON-BMP-VTRA-012059 | 2019-06-06 | FOR BAPCO REVIEW | 2019-06-20 | 2019-07-01 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001129 | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E0014 | VP-18TN-009-018E0014-009 | 018-E-DLB-40024-001 | DETAIL OF NAME PLATE 018E0014 DIESEL PUMPAROUND LP STEAM GENERATOR | A1112 | 0X | 3 | 2019-06-19 | CON-BMP-VTRA-012285 | 2019-06-19 | FOR BAPCO REVIEW | 2019-07-03 | 2019-07-10 | 3-REVIEWED WITH COMMENTS BMP-ROC-VTRE-001294 | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E0014 | VP-18TN-009-018E0014-100 | 018-E-CAL-40093-001 | STRENGTH CALCULATION 018E0014 | A1003 | CX | 2 | 2019-06-06 | CON-BMP-VTRA-012040 | 2019-06-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E0014 | VP-18TN-009-COMM-0603 | 018-E-MCD-40067-001 | WELDING BOOK (MAP, PROCEDURE, QUALIFICATION REPORT) 018E0014 | B1304 | 0X | 3 | 2019-06-13 | CON-BMP-VTRA-012205 | 2019-06-13 | FOR BAPCO REVIEW | 2019-06-28 | 2019-06-30 | 1-APPROVED BMP-ROC-VTRE-001091 | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E0014 | VP-18TN-009-COMM-1503 | 018-E-PQP-40029-001 | FABRICATION AND QUALITY CONTROL PLAN 018E0014 | B1002 | 0X | 3 | 2019-06-13 | CON-BMP-VTRA-012204 | 2019-06-13 | FOR BAPCO REVIEW | 2019-06-28 | 2019-06-29 | 1-APPROVED BMP-ROC-VTRE-001089 | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E0020A | VP-18TN-009-018E0020A/B/C/D-001 | 018-E-GAD-40313-001 | GENERAL ARRANGEMENT DRAWING 018E0020 A/B/C/D | A1103 | CX | 2 | 2019-06-05 | CON-BMP-VTRA-012019 | 2019-06-05 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E0020A | VP-18TN-009-018E0020A/B/C/D-002 | 018-E-GAD-40314-001 | GENERAL NOTES 018E0020 A/B/C/D | A1103 | CX | 2 | 2019-06-05 | CON-BMP-VTRA-012019 | 2019-06-05 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E0020A | VP-18TN-009-018E0020A/B/C/D-003 | 018-E-GAD-40315-001 | DETAIL OF BODY 018E0020A/B/C/D MVGO/FEED EXCHANGER | A1109 | CX | 2 | 2019-06-06 | CON-BMP-VTRA-012065 | 2019-06-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E0020A | VP-18TN-009-018E0020A/B/C/D-004 | 018-E-GAD-40316-001 | DETAIL OF TUBE ARRANGEMENT 018E0020A/B/C/D MVGO/FEED EXCHANGER | A1109 | 0X | 3 | 2019-06-12 | CON-BMP-VTRA-012169 | 2019-06-12 | FOR BAPCO REVIEW | 2019-06-26 | 2019-07-03 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001155 | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E0020A | VP-18TN-009-018E0020A/B/C/D-005 | 018-E-GAD-40317-001 | DETAIL OF TUBE BUNDLE 018E0020A/B/C/D MVGO/FEED EXCHANGER | A1109 | 0X | 3 | 2019-06-12 | CON-BMP-VTRA-012169 | 2019-06-12 | FOR BAPCO REVIEW | 2019-06-26 | 2019-07-03 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001155 | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E0020A | VP-18TN-009-018E0020A/B/C/D-007 | 018-E-GAD-40318-001 | DETAIL OF SUPPORT SADDLE 018E0020A/B/C/D MVGO/FEED EXCHANGER | A1109 | CX | 2 | 2019-06-06 | CON-BMP-VTRA-012068 | 2019-06-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E0020A | VP-18TN-009-018E0020A/B/C/D-009 | 018-E-GAD-40319-001 | DETAIL OF NOZZLE 018E0020A/B/C/D MVGO/FEED EXCHANGER | A1109 | CX | 2 | 2019-06-06 | CON-BMP-VTRA-012068 | 2019-06-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E0020A | VP-18TN-009-018E0020A/B/C/D-010 | 018-E-DLB-40025-001 | DETAIL OF NAME PLATE 018E0020A/B/C/D MVGO/FEED EXCHANGER | A1112 | 0X | 2 | 2019-06-26 | CON-BMP-VTRA-012480 | 2019-06-26 | FOR BAPCO REVIEW | 2019-07-10 |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E0020A | VP-18TN-009-018E0020A/B/C/D-012 | 018-E-GAD-40454-001 | DETAIL OF TEST RING MVGO/FEED EXCHANGER 018E0020A/B/C/D | A1109 | CX | 2 | 2019-06-06 | CON-BMP-VTRA-012068 | 2019-06-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E0020A | VP-18TN-009-018E0020A/B/C/D-100 | 018-E-CAL-40094-001 | STRENGTH CALCULATION 018E0020 A/B/C/D | A1003 | CX | 2 | 2019-06-06 | CON-BMP-VTRA-012037 | 2019-06-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E0020A | VP-18TN-009-COMM-0604 | 018-E-MCD-40068-001 | WELDING BOOK (MAP PROCEDURE QUALIFICATION REPORT) 018E0020A/B/C/D | B1304 | 0X | 3 | 2019-06-13 | CON-BMP-VTRA-012205 | 2019-06-13 | FOR BAPCO REVIEW | 2019-06-28 | 2019-06-30 | 1-APPROVED BMP-ROC-VTRE-001091 | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E0020A | VP-18TN-009-COMM-0650 | 000-E-PRO-40019-001 | HEAD FORMING PROCEDURE ALL ITEMS | B1202 | 0X | 3 | 2019-06-26 | CON-BMP-VTRA-012495 | 2019-06-26 | FOR BAPCO REVIEW | 2019-07-11 |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E0020A | VP-18TN-009-COMM-1504 | 018-E-PQP-40030-001 | FABRICATION AND QUALITY CONTROL PLAN 018E0020/A/B/C/D | B1002 | 0X | 3 | 2019-06-13 | CON-BMP-VTRA-012204 | 2019-06-13 | FOR BAPCO REVIEW | 2019-06-28 | 2019-06-29 | 1-APPROVED BMP-ROC-VTRE-001089 | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E0021 | VP-18TN-009-018E0021-001 | 018-E-GAD-40321-001 | GENERAL ARRANGEMENT DRAWING MVGO BFW PREHEATER 018E0021 | A1103 | CX | 2 | 2019-06-05 | CON-BMP-VTRA-012019 | 2019-06-05 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E0021 | VP-18TN-009-018E0021-002 | 018-E-GAD-40322-001 | GENERAL NOTE MVGO BFW PREHEATER 018E0021 | A1103 | CX | 2 | 2019-06-05 | CON-BMP-VTRA-012019 | 2019-06-05 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E0021 | VP-18TN-009-018E0021-003 | 018-E-GAD-40323-001 | DETAIL OF BODY MVGO BFW PREHEATER 018E0021 | A1109 | CX | 2 | 2019-06-06 | CON-BMP-VTRA-012060 | 2019-06-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E0021 | VP-18TN-009-018E0021-004 | 018-E-GAD-40324-001 | DETAIL OF TUBE BUNDLE MVGO BFWPREHEATER 018E0021 | A1109 | 0X | 3 | 2019-06-12 | CON-BMP-VTRA-012167 | 2019-06-12 | FOR BAPCO REVIEW | 2019-06-26 | 2019-07-02 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001149 | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E0021 | VP-18TN-009-018E0021-005 | 018-E-GAD-40325-001 | DETAIL OF SUPPORT SADDLE MVGO BFW PREHEATER 018E0021 | A1109 | CX | 2 | 2019-06-06 | CON-BMP-VTRA-012060 | 2019-06-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E0021 | VP-18TN-009-018E0021-006 | 018-E-GAD-40326-001 | DETAIL OF NOZZLE MVGO BFW PREHEATER 018E0021 | A1109 | CX | 2 | 2019-06-06 | CON-BMP-VTRA-012060 | 2019-06-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E0021 | VP-18TN-009-018E0021-007 | 018-E-DLB-40026-001 | DETAIL OF NAME PLATE MVGO BFW PREHEATER 018E0021 | A1112 | 0X | 3 | 2019-06-26 | CON-BMP-VTRA-012486 | 2019-06-26 | FOR BAPCO REVIEW | 2019-07-10 |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E0021 | VP-18TN-009-018E0021-100 | 018-E-CAL-40095-001 | STRENGTH CALCULATION 018E0021 | A1003 | CX | 2 | 2019-06-06 | CON-BMP-VTRA-012037 | 2019-06-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E0021 | VP-18TN-009-COMM-0605 | 018-E-MCD-40069-001 | WELDING BOOK (MAP PROCEDURE QUALIFICATION REPORT) 018E0021 | B1304 | 0X | 3 | 2019-06-13 | CON-BMP-VTRA-012205 | 2019-06-13 | FOR BAPCO REVIEW | 2019-06-28 | 2019-06-30 | 1-APPROVED BMP-ROC-VTRE-001091 | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E0021 | VP-18TN-009-COMM-1508 | 018-E-PQP-40031-001 | FABRICATION AND QUALITY CONTROL PLAN 018E0021 | B1002 | 0X | 3 | 2019-06-13 | CON-BMP-VTRA-012204 | 2019-06-13 | FOR BAPCO REVIEW | 2019-06-28 | 2019-06-29 | 1-APPROVED BMP-ROC-VTRE-001089 | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E0022 | VP-18TN-009-018E0022-001 | 018-E-GAD-40328-001 | GENERAL ARRANGEMENT DRAWING MVGO STEAM GENERATOR 018E0022 | A1103 | CX | 2 | 2019-06-05 | CON-BMP-VTRA-012019 | 2019-06-05 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E0022 | VP-18TN-009-018E0022-002 | 018-E-GAD-40329-001 | GENERAL NOTES MVGO STEAM GENERATOR 018E0022 | A1103 | CX | 2 | 2019-06-05 | CON-BMP-VTRA-012022 | 2019-06-05 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E0022 | VP-18TN-009-018E0022-003 | 018-E-GAD-40330-001 | DETAIL OF BODY 018E0022 MVGO STEAM GENERATOR | A1109 | CX | 2 | 2019-06-06 | CON-BMP-VTRA-012068 | 2019-06-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E0022 | VP-18TN-009-018E0022-004 | 018-E-GAD-40331-001 | DETAIL OF TUBE ARRANGEMENT 018E0022 MVGO STEAM GENERATOR | A1109 | 0X | 3 | 2019-06-06 | CON-BMP-VTRA-012056 | 2019-06-06 | FOR BAPCO REVIEW | 2019-06-20 | 2019-07-02 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001133 | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E0022 | VP-18TN-009-018E0022-005 | 018-E-GAD-40332-001 | DETAIL OF TUBE BUNDLE 018E0022 MVGO STEAM GENERATOR | A1109 | CX | 2 | 2019-06-06 | CON-BMP-VTRA-012068 | 2019-06-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E0022 | VP-18TN-009-018E0022-007 | 018-E-GAD-40333-001 | DETAIL OF SUPPORT SADDLE 018E0022 MVGO STEAM GENERATOR | A1109 | CX | 2 | 2019-06-06 | CON-BMP-VTRA-012071 | 2019-06-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E0022 | VP-18TN-009-018E0022-008 | 018-E-GAD-40334-001 | DETAIL OF NOZZLE 018E0022 MVGO STEAM GENERATOR | A1109 | CX | 2 | 2019-06-06 | CON-BMP-VTRA-012071 | 2019-06-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E0022 | VP-18TN-009-018E0022-010 | 018-E-PLD-40012-001 | DETAIL OF INSULATION SUPPORT CLIP MVGO STEAM GENERATOR 018E0022 | A1105 | 0X | 3 | 2019-07-05 | CON-BMP-VTRA-012679 | 2019-07-05 | FOR BAPCO REVIEW | 2019-07-19 |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E0022 | VP-18TN-009-018E0022-011 | 018-E-DLB-40027-001 | DETAIL OF NAME PLATE 018E0022 MVGO STEAM GENERATOR | A1112 | 0X | 3 | 2019-06-06 | CON-BMP-VTRA-012043 | 2019-06-06 | FOR BAPCO REVIEW | 2019-06-20 | 2019-06-30 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001095 | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E0022 | VP-18TN-009-018E0022-100 | 018-E-CAL-40096-001 | STRENGTH CALCULATION 018E0022 | A1003 | CX | 2 | 2019-06-06 | CON-BMP-VTRA-012040 | 2019-06-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E0022 | VP-18TN-009-COMM-0606 | 018-E-MCD-40070-001 | WELDING BOOK (MAP PROCEDURE QUALIFICATION REPORT) 018E0022 | B1304 | 0X | 3 | 2019-06-13 | CON-BMP-VTRA-012205 | 2019-06-13 | FOR BAPCO REVIEW | 2019-06-28 | 2019-06-30 | 1-APPROVED BMP-ROC-VTRE-001091 | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E0022 | VP-18TN-009-COMM-1509 | 018-E-PQP-40032-001 | FABRICATION AND QUALITY CONTROL PLAN 018E0022 | B1002 | 0X | 3 | 2019-06-13 | CON-BMP-VTRA-012204 | 2019-06-13 | FOR BAPCO REVIEW | 2019-06-28 | 2019-06-29 | 1-APPROVED BMP-ROC-VTRE-001089 | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E0028A | VP-18TN-009-018E0028A-H&J-M-001 | 018-E-GAD-40336-001 | GENERAL ASSEMBLY 018E0028A/B/C/D/E/F/G/H/J/K/L/M | A1103 | CX | 2 | 2019-06-05 | CON-BMP-VTRA-012022 | 2019-06-05 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E0028A | VP-18TN-009-018E0028A-H&J-M-003 | 018-E-GAD-40337-001 | GENERAL NOTES 018E0028A-H&J-M | A1103 | CX | 2 | 2019-06-05 | CON-BMP-VTRA-012022 | 2019-06-05 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E0028A | VP-18TN-009-018E0028A-H&J-M-004 | 018-E-GAD-40338-001 | DETAIL OF BODY VAC COLUMN BTM TEMPERED WATER EXCHANGER 018E0028A/B/CD/E/F/G/H/J/K/L/M | A1109 | 0X | 3 | 2019-06-19 | CON-BMP-VTRA-012289 | 2019-06-19 | FOR BAPCO REVIEW | 2019-07-03 | 2019-07-09 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001237 | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E0028A | VP-18TN-009-018E0028A-H&J-M-005 | 018-E-GAD-40339-001 | DETAIL OF TUBE ARRANGEMENT VAC COLUMN BTM TEMPERED WATER EXCHANGER 018E0028A/B/CD/E/F/G/H/J/K/L/M | A1109 | 0X | 3 | 2019-06-06 | CON-BMP-VTRA-012056 | 2019-06-06 | FOR BAPCO REVIEW | 2019-06-20 | 2019-07-02 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001133 | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E0028A | VP-18TN-009-018E0028A-H&J-M-006 | 018-E-GAD-40340-001 | DETAIL OF TUBE BUNDLE VAC COLUMN BTM TEMPERED WATER EXCHANGER 018E0028A/B/CD/E/F/G/H/J/K/L/M | A1109 | CX | 2 | 2019-06-06 | CON-BMP-VTRA-012071 | 2019-06-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E0028A | VP-18TN-009-018E0028A-H&J-M-010 | 018-E-GAD-40341-001 | DETAIL OF SUPPORT SADDLE VAC COLUMN BTM TEMPERED WATER EXCHANGER 018E0028A/B/CD/E/F/G/H/J/K/L/M | A1109 | CX | 2 | 2019-06-06 | CON-BMP-VTRA-012068 | 2019-06-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E0028A | VP-18TN-009-018E0028A-H&J-M-013 | 018-E-GAD-40342-001 | DETAIL OF NOZZLE VAC COLUMN BTM TEMPERED WATER EXCHANGER 018E0028A/B/CD/E/F/G/H/J/K/L/M | A1109 | CX | 2 | 2019-06-06 | CON-BMP-VTRA-012068 | 2019-06-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E0028A | VP-18TN-009-018E0028A-H&J-M-015 | 018-E-DLB-40028-001 | DETAIL OF NAME PLATE VAC COLUMN BTM TEMPERED WATER EXCHANGER 018E0028A/B/C/D/E/F/G/H/J/K/L/M | A1112 | 0X | 2 | 2019-06-26 | CON-BMP-VTRA-012480 | 2019-06-26 | FOR BAPCO REVIEW | 2019-07-10 |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E0028A | VP-18TN-009-018E0028A-H&J-M-017 | 018-E-GAD-40455-001 | DETAIL OF TEST RING VAC COLUMN BTM TEMPERED WATER EXCHANGER 018E0028A/B/CD/E/F/G/H/J/K/L/M | A1109 | 0X | 3 | 2019-06-06 | CON-BMP-VTRA-012056 | 2019-06-06 | FOR BAPCO REVIEW | 2019-06-20 | 2019-07-02 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001133 | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E0028A | VP-18TN-009-018E0028A-H&J-M-100 | 018-E-CAL-40097-001 | STRENGTH CALCULATION 018E0028A-H&J-M | A1003 | CX | 2 | 2019-06-06 | CON-BMP-VTRA-012037 | 2019-06-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E0028A | VP-18TN-009-COMM-0607 | 018-E-MCD-40071-001 | WELDING BOOK (MAP PROCEDURE QUALIFICATION REPORT) 018E0028A/B/C/D/E/F/G/H/J/K/L/M | B1304 | 0X | 3 | 2019-06-13 | CON-BMP-VTRA-012205 | 2019-06-13 | FOR BAPCO REVIEW | 2019-06-28 | 2019-06-30 | 1-APPROVED BMP-ROC-VTRE-001091 | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E0028A | VP-18TN-009-COMM-1510 | 018-E-PQP-40033-001 | FABRICATION AND QUALITY CONTROL PLAN 018E0028/A/D/G/K | B1002 | 0X | 3 | 2019-06-13 | CON-BMP-VTRA-012204 | 2019-06-13 | FOR BAPCO REVIEW | 2019-06-28 | 2019-06-29 | 1-APPROVED BMP-ROC-VTRE-001089 | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E0028B | VP-18TN-009-COMM-1517 | 018-E-PQP-40034-001 | FABRICATION AND QUALITY CONTROL PLAN 018E0028 B/C/E/F/H/J/L/M | B1002 | 0X | 3 | 2019-06-13 | CON-BMP-VTRA-012204 | 2019-06-13 | FOR BAPCO REVIEW | 2019-06-28 | 2019-06-29 | 1-APPROVED BMP-ROC-VTRE-001089 | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E0031 | VP-18TN-009-018E0031-001 | 018-E-GAD-40344-001 | GENERAL ARRANGEMENT DRAWING COOLING OIL HEATER 018E0031 | A1103 | CX | 2 | 2019-06-05 | CON-BMP-VTRA-012022 | 2019-06-05 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E0031 | VP-18TN-009-018E0031-002 | 018-E-GAD-40345-001 | GENERAL NOTE COOLING OIL HEATER 018E0031 | A1103 | CX | 2 | 2019-06-05 | CON-BMP-VTRA-012022 | 2019-06-05 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E0031 | VP-18TN-009-018E0031-003 | 018-E-GAD-40346-001 | DETAIL OF BODY COOLING OIL HEATER 018E0031 | A1109 | 0X | 3 | 2019-06-12 | CON-BMP-VTRA-012169 | 2019-06-12 | FOR BAPCO REVIEW | 2019-06-26 | 2019-07-03 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001155 | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E0031 | VP-18TN-009-018E0031-004 | 018-E-GAD-40347-001 | DETAIL OF TUBE BUNDLE (1 TO 2) COOLING OIL HEATER 018E0031 | A1109 | 0X | 3 | 2019-06-06 | CON-BMP-VTRA-012056 | 2019-06-06 | FOR BAPCO REVIEW | 2019-06-20 | 2019-07-02 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001133 | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E0031 | VP-18TN-009-018E0031-006 | 018-E-GAD-40348-001 | DETAIL OF SUPPORT SADDLE COOLING OIL HEATER 018E0031 | A1109 | CX | 2 | 2019-06-06 | CON-BMP-VTRA-012068 | 2019-06-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E0031 | VP-18TN-009-018E0031-007 | 018-E-GAD-40349-001 | DETAIL OF NOZZLE COOLING OIL HEATER 018E0031 | A1109 | 0X | 3 | 2019-06-06 | CON-BMP-VTRA-012056 | 2019-06-06 | FOR BAPCO REVIEW | 2019-06-20 | 2019-07-02 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001133 | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E0031 | VP-18TN-009-018E0031-008 | 018-E-GAD-40350-001 | DETAIL OF TEST RING COOLING OIL HEATER 018E0031 | A1109 | 0X | 3 | 2019-06-06 | CON-BMP-VTRA-012056 | 2019-06-06 | FOR BAPCO REVIEW | 2019-06-20 | 2019-07-02 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001133 | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E0031 | VP-18TN-009-018E0031-009 | 018-E-DLB-40029-001 | DETAIL OF NAME PLATE COOLING HEATER 018E0031 | A1112 | CX | 2 | 2019-06-06 | CON-BMP-VTRA-012047 | 2019-06-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E0031 | VP-18TN-009-018E0031-100 | 018-E-CAL-40098-001 | STRENGTH CALCULATION 018E0031 | A1003 | CX | 2 | 2019-06-06 | CON-BMP-VTRA-012037 | 2019-06-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E0031 | VP-18TN-009-COMM-0608 | 018-E-MCD-40072-001 | WELDING BOOK (MAP PROCEDURE QUALIFICATION REPORT) 018E0031 | B1304 | 0X | 3 | 2019-06-13 | CON-BMP-VTRA-012205 | 2019-06-13 | FOR BAPCO REVIEW | 2019-06-28 | 2019-06-30 | 1-APPROVED BMP-ROC-VTRE-001091 | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E0031 | VP-18TN-009-COMM-1522 | 018-E-PQP-40035-001 | FABRICATION AND QUALITY CONTROL PLAN 018E0031 | B1002 | 0X | 3 | 2019-06-13 | CON-BMP-VTRA-012204 | 2019-06-13 | FOR BAPCO REVIEW | 2019-06-28 | 2019-06-29 | 1-APPROVED BMP-ROC-VTRE-001089 | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E0032 | VP-18TN-009-018E0032-001 | 018-E-GAD-40352-001 | GENERAL ARRANGEMENT DRAWING START-UP STEAM HEATER 018E0032 | A1103 | CX | 2 | 2019-06-05 | CON-BMP-VTRA-012022 | 2019-06-05 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E0032 | VP-18TN-009-018E0032-002 | 018-E-GAD-40353-001 | GENERAL NOTE START-UP STEAM HEATER 018E0032 | A1103 | CX | 2 | 2019-06-05 | CON-BMP-VTRA-012022 | 2019-06-05 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E0032 | VP-18TN-009-018E0032-003 | 018-E-GAD-40354-001 | DETAIL OF BODY START-UP STEAM HEATER 018E0032 | A1109 | CX | 2 | 2019-06-06 | CON-BMP-VTRA-012068 | 2019-06-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E0032 | VP-18TN-009-018E0032-004 | 018-E-GAD-40355-001 | DETAIL OF TUBE ARRANGEMENT START-UP STEAM HEATER 018E0032 | A1109 | 0X | 3 | 2019-06-06 | CON-BMP-VTRA-012056 | 2019-06-06 | FOR BAPCO REVIEW | 2019-06-20 | 2019-07-02 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001133 | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E0032 | VP-18TN-009-018E0032-005 | 018-E-GAD-40356-001 | DETAIL OF TUBE BUNDLE (1 TO 2) START-UP STEAM HEATER 018E0032 | A1109 | CX | 2 | 2019-06-06 | CON-BMP-VTRA-012060 | 2019-06-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E0032 | VP-18TN-009-018E0032-007 | 018-E-GAD-40357-001 | DETAIL OF SUPPORT SADDLE START-UP STEAM HEATER 018E0032 | A1109 | CX | 2 | 2019-06-06 | CON-BMP-VTRA-012060 | 2019-06-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E0032 | VP-18TN-009-018E0032-008 | 018-E-GAD-40358-001 | DETAIL OF NOZZLE START-UP STEAM HEATER 018E0032 | A1109 | 0X | 3 | 2019-06-06 | CON-BMP-VTRA-012051 | 2019-06-06 | FOR BAPCO REVIEW | 2019-06-20 | 2019-07-02 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001134 | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E0032 | VP-18TN-009-018E0032-009 | 018-E-DLB-40030-001 | DETAIL OF NAME PLATE START-UP STEAM HEATER 018E0032 | A1112 | CX | 2 | 2019-06-06 | CON-BMP-VTRA-012047 | 2019-06-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E0032 | VP-18TN-009-018E0032-100 | 018-E-CAL-40099-001 | STRENGTH CALCULATION 018E0032 | A1003 | CX | 2 | 2019-06-06 | CON-BMP-VTRA-012037 | 2019-06-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E0032 | VP-18TN-009-062E6242A/B-100 | 062-E-CAL-40001-001 | STRENGTH CALCULATION 018E0032 | A1003 | CX | 2 | 2019-06-18 | CON-BMP-VTRA-012261 | 2019-06-18 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E0032 | VP-18TN-009-COMM-0609 | 018-E-MCD-40073-001 | WELDING BOOK (MAP PROCEDURE QUALIFICATION REPORT) 018E0032 | B1304 | 0X | 3 | 2019-06-13 | CON-BMP-VTRA-012205 | 2019-06-13 | FOR BAPCO REVIEW | 2019-06-28 | 2019-06-30 | 1-APPROVED BMP-ROC-VTRE-001091 | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E0032 | VP-18TN-009-COMM-1523 | 018-E-PQP-40036-001 | FABRICATION AND QUALITY CONTROL PLAN 018E0032 | B1002 | 0X | 3 | 2019-06-13 | CON-BMP-VTRA-012204 | 2019-06-13 | FOR BAPCO REVIEW | 2019-06-28 | 2019-06-29 | 1-APPROVED BMP-ROC-VTRE-001089 | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E0034A | VP-18TN-009-018E0034A-F-001 | 018-E-GAD-40360-001 | GENERAL ARRANGEMENT DRAWINGS 018E0034 A/B/C/D/E/F | A1103 | CX | 2 | 2019-06-05 | CON-BMP-VTRA-012022 | 2019-06-05 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E0034A | VP-18TN-009-018E0034A-F-003 | 018-E-GAD-40361-001 | GENERAL NOTES 018E0034 A/B/C/D/E/F | A1103 | CX | 2 | 2019-06-05 | CON-BMP-VTRA-012022 | 2019-06-05 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E0034A | VP-18TN-009-018E0034A-F-004 | 018-E-GAD-40362-001 | DETAIL OF BODY SHUTDOWN TEMPERED WATER COOLER 018E0034A/B/C/D/E/F | A1109 | 0X | 3 | 2019-06-12 | CON-BMP-VTRA-012167 | 2019-06-12 | FOR BAPCO REVIEW | 2019-06-26 | 2019-07-02 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001149 | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E0034A | VP-18TN-009-018E0034A-F-005 | 018-E-GAD-40363-001 | DETAIL OF TUBE ARRANGEMENT SHUTDOWN TEMPERED WATER COOLER018E0034A/B/C/D/E/F | A1109 | 0X | 3 | 2019-06-12 | CON-BMP-VTRA-012167 | 2019-06-12 | FOR BAPCO REVIEW | 2019-06-26 | 2019-07-02 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001149 | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E0034A | VP-18TN-009-018E0034A-F-006 | 018-E-GAD-40364-001 | DETAIL OF TUBE BUNDLE SHUTDOWNTEMPERED WATER COOLER 018E0034A/B/C/D/E/F | A1109 | 0X | 3 | 2019-06-12 | CON-BMP-VTRA-012167 | 2019-06-12 | FOR BAPCO REVIEW | 2019-06-26 | 2019-07-02 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001149 | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E0034A | VP-18TN-009-018E0034A-F-010 | 018-E-GAD-40365-001 | DETAIL OF SUPPORT SADDLE SHUTDOWN TEMPERED WATER COOLER018E0034A/B/C/D/E/F | A1109 | CX | 2 | 2019-06-06 | CON-BMP-VTRA-012060 | 2019-06-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E0034A | VP-18TN-009-018E0034A-F-013 | 018-E-GAD-40366-001 | DETAIL OF NOZZLE SHUTDOWN TEMPERED WATER COOLER 018E0034A/B/C/D/E/F | A1109 | CX | 2 | 2019-06-06 | CON-BMP-VTRA-012060 | 2019-06-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E0034A | VP-18TN-009-018E0034A-F-015 | 018-E-GAD-40367-001 | DETAIL OF TEST RING SHUTDOWN TEMPERED WATER COOLER 018E0034A/B/C/D/E/F | A1109 | 0X | 3 | 2019-06-06 | CON-BMP-VTRA-012051 | 2019-06-06 | FOR BAPCO REVIEW | 2019-06-20 | 2019-07-02 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001134 | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E0034A | VP-18TN-009-018E0034A-F-016 | 018-E-DLB-40031-001 | DETAIL OF NAME PLATE SHUTDOWN TEMPERED WATER COOLER 018E0034A/B/C/D/E/F | A1112 | 0X | 3 | 2019-06-26 | CON-BMP-VTRA-012478 | 2019-06-26 | FOR BAPCO REVIEW | 2019-07-10 |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E0034A | VP-18TN-009-018E0034A-F-100 | 018-E-CAL-40100-001 | STRENGTH CALCULATION 018E0034 A/B/C/D/E/F | A1003 | CX | 2 | 2019-06-06 | CON-BMP-VTRA-012037 | 2019-06-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E0034A | VP-18TN-009-COMM-0610 | 018-E-MCD-40074-001 | WELDING BOOK (MAP PROCEDURE QUALIFICATION REPORT) 018E0034A/B/C/D/E/F | B1304 | 0X | 3 | 2019-06-14 | CON-BMP-VTRA-012207 | 2019-06-14 | FOR BAPCO REVIEW | 2019-06-28 | 2019-06-29 | 1-APPROVED BMP-ROC-VTRE-001078 | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E0034A | VP-18TN-009-COMM-1524 | 018-E-PQP-40037-001 | FABRICATION AND QUALITY CONTROL PLAN 018E0034A/B/C/D/E/F | B1002 | 0X | 3 | 2019-06-13 | CON-BMP-VTRA-012204 | 2019-06-13 | FOR BAPCO REVIEW | 2019-06-28 | 2019-06-29 | 1-APPROVED BMP-ROC-VTRE-001089 | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E1008 | VP-18TN-009-018E1008-001 | 018-E-GAD-40369-001 | GENERAL ARRANGEMENT DRAWING FIRST STAGE INTERCOOLER-TRAIN 1A 018E1008 | A1103 | CX | 2 | 2019-06-05 | CON-BMP-VTRA-012022 | 2019-06-05 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E1008 | VP-18TN-009-018E1008-002 | 018-E-GAD-40370-001 | GENERAL NOTE FIRST STAGE INTERCOOLER-TRAIN 1A 018E1008 | A1103 | CX | 2 | 2019-06-05 | CON-BMP-VTRA-012022 | 2019-06-05 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E1008 | VP-18TN-009-018E1008-003 | 018-E-GAD-40371-001 | DETAIL OF BODY FIRST STAGE INTERCOOLER-TRAIN 1A 018E1008 | A1109 | CX | 2 | 2019-06-06 | CON-BMP-VTRA-012060 | 2019-06-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E1008 | VP-18TN-009-018E1008-004 | 018-E-GAD-40372-001 | DETAIL OF TUBE BUNDLE (1 TO 2) FIRST STAGE INTERCOOLER-TRAIN 1A 018E1008 | A1109 | 0X | 3 | 2019-06-17 | CON-BMP-VTRA-012239 | 2019-06-17 | FOR BAPCO REVIEW | 2019-07-01 | 2019-07-08 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001211 | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E1008 | VP-18TN-009-018E1008-006 | 018-E-GAD-40373-001 | DETAIL OF SUPPORT SADDLE FIRST STAGE INTERCOOLER-TRAIN 1A 018E1008 | A1109 | CX | 2 | 2019-06-06 | CON-BMP-VTRA-012065 | 2019-06-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E1008 | VP-18TN-009-018E1008-007 | 018-E-GAD-40374-001 | DETAIL OF NOZZLE FIRST STAGE INTERCOOLER-TRAIN 1A 018E1008 | A1109 | CX | 2 | 2019-06-06 | CON-BMP-VTRA-012065 | 2019-06-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E1008 | VP-18TN-009-018E1008-008 | 018-E-DLB-40032-001 | DETAIL OF NAME PLATE FIRST STAGE INTERCOOLER-TRAIN 1A 018E1008 | A1112 | CX | 2 | 2019-06-06 | CON-BMP-VTRA-012047 | 2019-06-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E1008 | VP-18TN-009-018E1008-100 | 018-E-CAL-40101-001 | STRENGTH CALCULATION 018E1008 | A1003 | CX | 2 | 2019-06-06 | CON-BMP-VTRA-012037 | 2019-06-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E1008 | VP-18TN-009-COMM-0611 | 018-E-MCD-40075-001 | WELDING BOOK (MAP PROCEDURE QUALIFICATION REPORT) 018E1008 | B1304 | 0X | 3 | 2019-06-14 | CON-BMP-VTRA-012207 | 2019-06-14 | FOR BAPCO REVIEW | 2019-06-28 | 2019-06-29 | 1-APPROVED BMP-ROC-VTRE-001078 | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E1008 | VP-18TN-009-COMM-1530 | 018-E-PQP-40038-001 | FABRICATION AND QUALITY CONTROL PLAN 018E1008 | B1002 | 0X | 3 | 2019-06-13 | CON-BMP-VTRA-012204 | 2019-06-13 | FOR BAPCO REVIEW | 2019-06-28 | 2019-06-29 | 1-APPROVED BMP-ROC-VTRE-001089 | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E1010 | VP-18TN-009-018E1010-001 | 018-E-GAD-40376-001 | GENERAL ARRANGEMENT DRAWING TRAIN 1 SPILLBACK COOLER 018E1010 | A1103 | CX | 2 | 2019-06-05 | CON-BMP-VTRA-012022 | 2019-06-05 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E1010 | VP-18TN-009-018E1010-002 | 018-E-GAD-40377-001 | GENERAL NOTE TRAIN 1 SPILLBACK COOLER 018E1010 | A1103 | CX | 2 | 2019-06-05 | CON-BMP-VTRA-012022 | 2019-06-05 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E1010 | VP-18TN-009-018E1010-003 | 018-E-GAD-40378-001 | DETAIL OF BODY 018E1010 TRAIN 1 SPILLBACK COOLER | A1109 | CX | 2 | 2019-06-06 | CON-BMP-VTRA-012065 | 2019-06-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E1010 | VP-18TN-009-018E1010-004 | 018-E-GAD-40379-001 | DETAIL OF TUBE BUNDLE 018E1010 TRAIN 1 SPILLBACK COOLER | A1109 | CX | 2 | 2019-06-06 | CON-BMP-VTRA-012065 | 2019-06-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E1010 | VP-18TN-009-018E1010-006 | 018-E-GAD-40380-001 | DETAIL OF SUPPORT SADDLE 018E1010 TRAIN 1 SPILLBACK COOLER | A1109 | CX | 2 | 2019-07-11 | CON-BMP-VTRA-012826 | 2019-07-11 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E1010 | VP-18TN-009-018E1010-007 | 018-E-GAD-40381-001 | DETAIL OF NOZZLE 018E1010 TRAIN 1 SPILLBACK COOLER | A1109 | 0X | 3 | 2019-06-06 | CON-BMP-VTRA-012051 | 2019-06-06 | FOR BAPCO REVIEW | 2019-06-20 | 2019-07-02 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001134 | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E1010 | VP-18TN-009-018E1010-008 | 018-E-DLB-40033-001 | DETAIL OF NAME PLATE 018E1010 TRAIN 1 SPILL BACK COOLER | A1112 | 0X | 3 | 2019-06-19 | CON-BMP-VTRA-012285 | 2019-06-19 | FOR BAPCO REVIEW | 2019-07-03 | 2019-07-10 | 3-REVIEWED WITH COMMENTS BMP-ROC-VTRE-001294 | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E1010 | VP-18TN-009-018E1010-100 | 018-E-CAL-40102-001 | STRENGTH CALCULATION 018E1010 | A1003 | CX | 2 | 2019-06-06 | CON-BMP-VTRA-012037 | 2019-06-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E1010 | VP-18TN-009-COMM-0612 | 018-E-MCD-40076-001 | WELDING BOOK (MAP PROCEDURE QUALIFICATION REPORT) 018E1010 | B1304 | 0X | 3 | 2019-06-14 | CON-BMP-VTRA-012207 | 2019-06-14 | FOR BAPCO REVIEW | 2019-06-28 | 2019-06-29 | 1-APPROVED BMP-ROC-VTRE-001078 | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E1010 | VP-18TN-009-COMM-1531 | 018-E-PQP-40039-001 | FABRICATION AND QUALITY CONTROL PLAN 018E1010 | B1002 | 0X | 3 | 2019-06-13 | CON-BMP-VTRA-012204 | 2019-06-13 | FOR BAPCO REVIEW | 2019-06-28 | 2019-06-29 | 1-APPROVED BMP-ROC-VTRE-001089 | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E1011 | VP-18TN-009-018E1011-001 | 018-E-GAD-40383-001 | GENERAL ARRANGEMENT DRAWING FIRST STAGE INTERCOOLER-TRAIN 1B 018E1011 | A1103 | CX | 2 | 2019-06-05 | CON-BMP-VTRA-012022 | 2019-06-05 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E1011 | VP-18TN-009-018E1011-002 | 018-E-GAD-40384-001 | GENERAL NOTE FIRST STAGE INTERCOOLER-TRAIN 1B 018E1011 | A1103 | CX | 2 | 2019-06-05 | CON-BMP-VTRA-012022 | 2019-06-05 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E1011 | VP-18TN-009-018E1011-003 | 018-E-GAD-40385-001 | DETAIL OF BODY FIRST STAGE INTERCOOLER-TRAIN 1B 018E1011 | A1109 | CX | 2 | 2019-06-06 | CON-BMP-VTRA-012065 | 2019-06-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E1011 | VP-18TN-009-018E1011-004 | 018-E-GAD-40386-001 | DETAIL OF TUBE BUNDLE (1 TO 2) FIRST STAGE INTERCOOLER-TRAIN 1B 018E1011 | A1109 | 0X | 3 | 2019-06-17 | CON-BMP-VTRA-012239 | 2019-06-17 | FOR BAPCO REVIEW | 2019-07-01 | 2019-07-08 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001211 | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E1011 | VP-18TN-009-018E1011-006 | 018-E-GAD-40387-001 | DETAIL OF SUPPORT SADDLE FIRST STAGE INTERCOOLER-TRAIN 1B 018E1011 | A1109 | CX | 2 | 2019-06-06 | CON-BMP-VTRA-012065 | 2019-06-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E1011 | VP-18TN-009-018E1011-007 | 018-E-GAD-40388-001 | DETAIL OF NOZZLE FIRST STAGE INTERCOOLER-TRAIN 1B 018E1011 | A1109 | CX | 2 | 2019-06-06 | CON-BMP-VTRA-012065 | 2019-06-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E1011 | VP-18TN-009-018E1011-008 | 018-E-DLB-40034-001 | DETAIL OF NAME PLATE FIRST STAGE INTERCOOLER-TRAIN 1B 018E1011 | A1112 | 0X | 2 | 2019-06-20 | CON-BMP-VTRA-012328 | 2019-06-20 | FOR BAPCO REVIEW | 2019-07-04 | 2019-07-10 | 3-REVIEWED WITH COMMENTS BMP-ROC-VTRE-001289 | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E1011 | VP-18TN-009-018E1011-100 | 018-E-CAL-40103-001 | STRENGTH CALCULATION 018E1011 | A1003 | CX | 2 | 2019-06-06 | CON-BMP-VTRA-012037 | 2019-06-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E1011 | VP-18TN-009-COMM-0613 | 018-E-MCD-40077-001 | WELDING BOOK (MAP PROCEDURE QUALIFICATION REPORT) 018E1011 | B1304 | 0X | 3 | 2019-06-14 | CON-BMP-VTRA-012207 | 2019-06-14 | FOR BAPCO REVIEW | 2019-06-28 | 2019-06-29 | 1-APPROVED BMP-ROC-VTRE-001078 | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E1011 | VP-18TN-009-COMM-1532 | 018-E-PQP-40040-001 | FABRICATION AND QUALITY CONTROL PLAN 018E1011 | B1002 | 0X | 3 | 2019-06-13 | CON-BMP-VTRA-012198 | 2019-06-13 | FOR BAPCO REVIEW | 2019-06-28 | 2019-06-30 | 1-APPROVED BMP-ROC-VTRE-001092 | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E2008 | VP-18TN-009-018E2008-001 | 018-E-GAD-40390-001 | GENERAL ARRANGEMENT DRAWING FIRST STAGE INTERCOOLER-TRAIN 2A 018E2008 | A1103 | CX | 2 | 2019-06-05 | CON-BMP-VTRA-012025 | 2019-06-05 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E2008 | VP-18TN-009-018E2008-002 | 018-E-GAD-40391-001 | GENERAL NOTE FIRST STAGE INTERCOOLER-TRAIN 2A 018E2008 | A1103 | CX | 2 | 2019-06-05 | CON-BMP-VTRA-012025 | 2019-06-05 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E2008 | VP-18TN-009-018E2008-003 | 018-E-GAD-40392-001 | DETAIL OF BODY FIRST STAGE INTERCOOLER-TRAIN 2A 018E2008 | A1109 | CX | 2 | 2019-06-06 | CON-BMP-VTRA-012065 | 2019-06-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E2008 | VP-18TN-009-018E2008-004 | 018-E-GAD-40393-001 | DETAIL OF TUBE BUNDLE (1 TO 2) FIRST STAGE INTERCOOLER-TRAIN 2A 018E2008 | A1109 | 0X | 3 | 2019-06-06 | CON-BMP-VTRA-012051 | 2019-06-06 | FOR BAPCO REVIEW | 2019-06-20 | 2019-07-02 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001134 | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E2008 | VP-18TN-009-018E2008-006 | 018-E-GAD-40394-001 | DETAIL OF SUPPORT SADDLE FIRST STAGE INTERCOOLER-TRAIN 2A 018E2008 | A1109 | CX | 2 | 2019-06-06 | CON-BMP-VTRA-012060 | 2019-06-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E2008 | VP-18TN-009-018E2008-007 | 018-E-GAD-40395-001 | DETAIL OF NOZZLE FIRST STAGE INTERCOOLER-TRAIN 2A 018E2008 | A1109 | CX | 2 | 2019-06-06 | CON-BMP-VTRA-012065 | 2019-06-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E2008 | VP-18TN-009-018E2008-008 | 018-E-DLB-40035-001 | DETAIL OF NAME PLATE FIRST STAGE INTERCOOLER-TRAIN 2A 018E2008 | A1112 | CX | 2 | 2019-06-06 | CON-BMP-VTRA-012047 | 2019-06-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E2008 | VP-18TN-009-018E2008-100 | 018-E-CAL-40104-001 | STRENGTH CALCULATION 018E2008 | A1003 | CX | 2 | 2019-06-06 | CON-BMP-VTRA-012040 | 2019-06-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E2008 | VP-18TN-009-COMM-0614 | 018-E-MCD-40078-001 | WELDING BOOK (MAP PROCEDURE QUALIFICATION REPORT) 018E2008 | B1304 | 0X | 3 | 2019-06-14 | CON-BMP-VTRA-012207 | 2019-06-14 | FOR BAPCO REVIEW | 2019-06-28 | 2019-06-29 | 1-APPROVED BMP-ROC-VTRE-001078 | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E2008 | VP-18TN-009-COMM-1533 | 018-E-PQP-40041-001 | FABRICATION AND QUALITY CONTROL PLAN 018E2008 | B1002 | 0X | 3 | 2019-06-13 | CON-BMP-VTRA-012198 | 2019-06-13 | FOR BAPCO REVIEW | 2019-06-28 | 2019-06-30 | 1-APPROVED BMP-ROC-VTRE-001092 | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E2010 | VP-18TN-009-018E2010-001 | 018-E-GAD-40397-001 | GENERAL ARRANGEMENT DRAWING TRAIN 2 SPILLBACK COOLER 018E2010 | A1103 | CX | 2 | 2019-06-05 | CON-BMP-VTRA-012025 | 2019-06-05 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E2010 | VP-18TN-009-018E2010-002 | 018-E-GAD-40398-001 | GENERAL NOTE TRAIN 2 SPILLBACK COOLER 018E2010 | A1103 | CX | 2 | 2019-06-05 | CON-BMP-VTRA-012025 | 2019-06-05 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E2010 | VP-18TN-009-018E2010-003 | 018-E-GAD-40399-001 | DETAIL OF BODY 018E2010 TRAIN 2 SPILLBACK COOLER | A1109 | CX | 2 | 2019-06-06 | CON-BMP-VTRA-012065 | 2019-06-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E2010 | VP-18TN-009-018E2010-004 | 018-E-GAD-40400-001 | DETAIL OF TUBE BUNDLE 018E2010 TRAIN 2 SPILLBACK COOLER | A1109 | CX | 2 | 2019-06-06 | CON-BMP-VTRA-012065 | 2019-06-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E2010 | VP-18TN-009-018E2010-006 | 018-E-GAD-40401-011 | DETAIL OF SUPPORT SADDLE 018E2010 TRAIN 2 SPILLBACK COOLER | A1109 | CX | 2 | 2019-06-06 | CON-BMP-VTRA-012065 | 2019-06-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E2010 | VP-18TN-009-018E2010-007 | 018-E-GAD-40402-001 | DETAIL OF NOZZLE 018E2010 TRAIN 2 SPILLBACK COOLER | A1109 | 0X | 3 | 2019-06-06 | CON-BMP-VTRA-012051 | 2019-06-06 | FOR BAPCO REVIEW | 2019-06-20 | 2019-07-02 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001134 | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E2010 | VP-18TN-009-018E2010-008 | 018-E-DLB-40036-001 | DETAIL OF NAME PLATE 018E2010 TRAIN 2 SPILL BACK COOLER | A1112 | 0X | 3 | 2019-06-12 | CON-BMP-VTRA-012164 | 2019-06-12 | FOR BAPCO REVIEW | 2019-06-26 | 2019-07-02 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001145 | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E2010 | VP-18TN-009-018E2010-100 | 018-E-CAL-40105-001 | STRENGTH CALCULATION 018E2010 | A1003 | CX | 2 | 2019-06-06 | CON-BMP-VTRA-012040 | 2019-06-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E2010 | VP-18TN-009-COMM-0615 | 018-E-MCD-40079-001 | WELDING BOOK (MAP PROCEDURE QUALIFICATION REPORT) 018E2010 | B1304 | 0X | 3 | 2019-06-14 | CON-BMP-VTRA-012207 | 2019-06-14 | FOR BAPCO REVIEW | 2019-06-28 | 2019-06-29 | 1-APPROVED BMP-ROC-VTRE-001078 | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E2010 | VP-18TN-009-COMM-1534 | 018-E-PQP-40042-001 | FABRICATION AND QUALITY CONTROL PLAN 018E2010 | B1002 | 0X | 3 | 2019-06-13 | CON-BMP-VTRA-012198 | 2019-06-13 | FOR BAPCO REVIEW | 2019-06-28 | 2019-06-30 | 1-APPROVED BMP-ROC-VTRE-001092 | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E2011 | VP-18TN-009-018E2011-001 | 018-E-GAD-40404-001 | GENERAL ARRANGEMENT DRAWING FIRST STAGE INTERCOOLER-TRAIN 2B 018E2011 | A1103 | CX | 2 | 2019-06-05 | CON-BMP-VTRA-012025 | 2019-06-05 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E2011 | VP-18TN-009-018E2011-002 | 018-E-GAD-40405-001 | GENERAL NOTE FIRST STAGE INTERCOOLER-TRAIN 2B 018E2011 | A1103 | CX | 2 | 2019-06-05 | CON-BMP-VTRA-012025 | 2019-06-05 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E2011 | VP-18TN-009-018E2011-003 | 018-E-GAD-40406-001 | DETAIL OF BODY FIRST STAGE INTERCOOLER-TRAIN 2B 018E2011 | A1109 | CX | 2 | 2019-06-06 | CON-BMP-VTRA-012068 | 2019-06-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E2011 | VP-18TN-009-018E2011-004 | 018-E-GAD-40407-001 | DETAIL OF TUBE BUNDLE (1 TO 2) FIRST STAGE INTERCOOLER-TRAIN 2B 018E2011 | A1109 | 0X | 3 | 2019-06-12 | CON-BMP-VTRA-012167 | 2019-06-12 | FOR BAPCO REVIEW | 2019-06-26 | 2019-07-02 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001149 | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E2011 | VP-18TN-009-018E2011-006 | 018-E-GAD-40408-001 | DETAIL OF SUPPORT SADDLE FIRST STAGE INTERCOOLER-TRAIN 2B 018E2011 | A1109 | CX | 2 | 2019-06-06 | CON-BMP-VTRA-012068 | 2019-06-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E2011 | VP-18TN-009-018E2011-007 | 018-E-GAD-40409-001 | DETAIL OF NOZZLE FIRST STAGE INTERCOOLER-TRAIN 2B 018E2011 | A1109 | CX | 2 | 2019-06-06 | CON-BMP-VTRA-012068 | 2019-06-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E2011 | VP-18TN-009-018E2011-008 | 018-E-DLB-40037-001 | DETAIL OF NAME PLATE FIRST STAGE INTERCOOLER-TRAIN 2B 018E2011 | A1112 | CX | 2 | 2019-06-06 | CON-BMP-VTRA-012047 | 2019-06-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E2011 | VP-18TN-009-018E2011-100 | 018-E-CAL-40106-001 | STRENGTH CALCULATION 018E2011 | A1003 | CX | 2 | 2019-06-06 | CON-BMP-VTRA-012040 | 2019-06-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E2011 | VP-18TN-009-COMM-0616 | 018-E-MCD-40080-001 | WELDING BOOK (MAP PROCEDURE QUALIFICATION REPORT) 018E2011 | B1304 | 0X | 3 | 2019-06-14 | CON-BMP-VTRA-012207 | 2019-06-14 | FOR BAPCO REVIEW | 2019-06-28 | 2019-06-29 | 1-APPROVED BMP-ROC-VTRE-001078 | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 018E2011 | VP-18TN-009-COMM-1535 | 018-E-PQP-40043-001 | FABRICATION AND QUALITY CONTROL PLAN 018E2011 | B1002 | 0X | 3 | 2019-06-13 | CON-BMP-VTRA-012198 | 2019-06-13 | FOR BAPCO REVIEW | 2019-06-28 | 2019-06-30 | 1-APPROVED BMP-ROC-VTRE-001092 | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 021E0001 | VP-18TN-009-021E0001-001 | 021-E-GAD-40112-001 | GENERAL ARRANGEMENT DRAWING VACUM DRIER BOTTOM FEED EXCHANGER 021E0001 | A1103 | CX | 2 | 2019-06-05 | CON-BMP-VTRA-012025 | 2019-06-05 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 021E0001 | VP-18TN-009-021E0001-002 | 021-E-GAD-40113-001 | GENERAL NOTE VACUM DRIER BOTTOM FEED EXCHANGER 021E0001 | A1103 | CX | 2 | 2019-06-05 | CON-BMP-VTRA-012025 | 2019-06-05 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 021E0001 | VP-18TN-009-021E0001-003 | 021-E-GAD-40114-001 | DETAIL OF BODY 021E0001 VACUUM DRIER BOTTOMS/FEED EXCHANGER | A1109 | 0X | 3 | 2019-06-12 | CON-BMP-VTRA-012168 | 2019-06-12 | FOR BAPCO REVIEW | 2019-06-26 | 2019-07-03 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001151 | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 021E0001 | VP-18TN-009-021E0001-004 | 021-E-GAD-40115-001 | DETAIL OF TUBE BUNDLE 021E0001 VACUUM DRIER BOTTOMS/FEED EXCHANGER | A1109 | CX | 2 | 2019-06-06 | CON-BMP-VTRA-012068 | 2019-06-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 021E0001 | VP-18TN-009-021E0001-006 | 021-E-GAD-40116-001 | DETAIL OF SUPPORT SADDLE 021E0001 VACUUM DRIER BOTTOMS/FEED EXCHANGER | A1109 | CX | 2 | 2019-06-06 | CON-BMP-VTRA-012060 | 2019-06-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 021E0001 | VP-18TN-009-021E0001-007 | 021-E-GAD-40117-001 | DETAIL OF NOZZLE 021E0001 VACUUM DRIER BOTTOMS/FEED EXCHANGER | A1109 | 0X | 3 | 2019-06-06 | CON-BMP-VTRA-012051 | 2019-06-06 | FOR BAPCO REVIEW | 2019-06-20 | 2019-07-02 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001134 | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 021E0001 | VP-18TN-009-021E0001-008 | 021-E-GAD-40118-001 | DETAIL OF TEST RING 021E0001 VACUUM DRIER BOTTOMS/FEED EXCHANGER | A1109 | 0X | 3 | 2019-06-06 | CON-BMP-VTRA-012051 | 2019-06-06 | FOR BAPCO REVIEW | 2019-06-20 | 2019-07-02 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001134 | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 021E0001 | VP-18TN-009-021E0001-009 | 021-E-DLB-40008-001 | DETAIL OF NAME PLATE 021E0001 VACUUM DRIER BOTTOMS/FEED EXCHANGER | A1112 | 0X | 3 | 2019-06-12 | CON-BMP-VTRA-012165 | 2019-06-12 | FOR BAPCO REVIEW | 2019-06-26 | 2019-07-02 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001146 | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 021E0001 | VP-18TN-009-021E0001-100 | 021-E-CAL-40051-001 | STRENGTH CALCULATION 021E0001 | A1003 | CX | 2 | 2019-06-06 | CON-BMP-VTRA-012040 | 2019-06-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 021E0001 | VP-18TN-009-COMM-0617 | 021-E-MCD-40024-001 | WELDING BOOK (MAP, PROCEDURE, QUALIFICATION REPORT) 021E0001 | B1304 | 0X | 3 | 2019-06-14 | CON-BMP-VTRA-012208 | 2019-06-14 | FOR BAPCO REVIEW | 2019-06-28 | 2019-06-29 | 1-APPROVED BMP-ROC-VTRE-001072 | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 021E0001 | VP-18TN-009-COMM-1536 | 021-E-PQP-40019-001 | FABRICATION AND QUALITY CONTROL PLAN 021E0001 | B1002 | 0X | 3 | 2019-06-13 | CON-BMP-VTRA-012199 | 2019-06-13 | FOR BAPCO REVIEW | 2019-06-28 | 2019-06-30 | 1-APPROVED BMP-ROC-VTRE-001090 | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 021E0002A | VP-18TN-009-021E0002A/B/C-001 | 021-E-GAD-40120-001 | GENERAL ARRANGEMENT DRAWING 1/2 STRIPPER BOTTOMS FEED EXCHANGER 021E0002A/B/C | A1103 | CX | 2 | 2019-06-05 | CON-BMP-VTRA-012019 | 2019-06-05 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 021E0002A | VP-18TN-009-021E0002A/B/C-003 | 021-E-GAD-40121-001 | GENERAL NOTE STRIPPER BOTTOMS FEED EXCHANGER 021E0002A/B/C | A1103 | CX | 2 | 2019-06-05 | CON-BMP-VTRA-012019 | 2019-06-05 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 021E0002A | VP-18TN-009-021E0002A/B/C-004 | 021-E-GAD-40122-001 | DETAIL OF BODY STRIPPER BOTTOMS/FEED EXCHANGER 021E0002A/B/C | A1109 | 0X | 3 | 2019-06-06 | CON-BMP-VTRA-012051 | 2019-06-06 | FOR BAPCO REVIEW | 2019-06-20 | 2019-07-02 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001134 | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 021E0002A | VP-18TN-009-021E0002A/B/C-005 | 021-E-GAD-40123-001 | DETAIL OF TUBE ARRANGEMENT STRIPPER BOTTOMS/FEED EXCHANGER 021E0002A/B/C | A1109 | 0X | 3 | 2019-06-06 | CON-BMP-VTRA-012051 | 2019-06-06 | FOR BAPCO REVIEW | 2019-06-20 | 2019-07-02 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001134 | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 021E0002A | VP-18TN-009-021E0002A/B/C-006 | 021-E-GAD-40124-001 | DETAIL OF TUBE BUNDLE STRIPPER BOTTOMS/FEED EXCHANGER 021E0002A/B/C | A1109 | CX | 2 | 2019-06-06 | CON-BMP-VTRA-012060 | 2019-06-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 021E0002A | VP-18TN-009-021E0002A/B/C-010 | 021-E-GAD-40125-001 | DETAIL OF SUPPORT SADDLE STRIPPER BOTTOMS/FEED EXCHANGER 021E0002A/B/C | A1109 | CX | 2 | 2019-06-06 | CON-BMP-VTRA-012060 | 2019-06-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 021E0002A | VP-18TN-009-021E0002A/B/C-013 | 021-E-GAD-40126-001 | DETAIL OF NOZZLE STRIPPER BOTTOMS/FEED EXCHANGER 021E0002A/B/C | A1109 | CX | 2 | 2019-06-06 | CON-BMP-VTRA-012060 | 2019-06-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 021E0002A | VP-18TN-009-021E0002A/B/C-015 | 021-E-GAD-40127-001 | DETAIL OF TEST RING STRIPPER BOTTOMS/FEED EXCHANGER 021E0002A/B/C | A1109 | 0X | 3 | 2019-06-06 | CON-BMP-VTRA-012051 | 2019-06-06 | FOR BAPCO REVIEW | 2019-06-20 | 2019-07-02 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001134 | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 021E0002A | VP-18TN-009-021E0002A/B/C-016 | 021-E-DLB-40009-001 | DETAIL OF NAME PLATE STRIPPER BOTTOMS/FEED EXCHANGER 021E0002A/B/C | A1112 | 0X | 3 | 2019-06-12 | CON-BMP-VTRA-012165 | 2019-06-12 | FOR BAPCO REVIEW | 2019-06-26 | 2019-07-02 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001146 | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 021E0002A | VP-18TN-009-021E0002A/B/C-100 | 021-E-CAL-40052-001 | STRENGTH CALCULATION 021E0002A/B/C | A1003 | CX | 2 | 2019-06-06 | CON-BMP-VTRA-012037 | 2019-06-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 021E0002A | VP-18TN-009-COMM-0618 | 021-E-MCD-40025-001 | WELDING BOOK (MAP, PROCEDURE, QUALIFICATION REPORT) 021E0002A/B/C | B1304 | 0X | 3 | 2019-06-14 | CON-BMP-VTRA-012208 | 2019-06-14 | FOR BAPCO REVIEW | 2019-06-28 | 2019-06-29 | 1-APPROVED BMP-ROC-VTRE-001072 | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 021E0002A | VP-18TN-009-COMM-1537 | 021-E-PQP-40020-001 | FABRICATION AND QUALITY CONTROL PLAN 021E0002A/B/C | B1002 | 0X | 3 | 2019-06-13 | CON-BMP-VTRA-012199 | 2019-06-13 | FOR BAPCO REVIEW | 2019-06-28 | 2019-06-30 | 1-APPROVED BMP-ROC-VTRE-001090 | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 021E0013 | VP-18TN-009-021E0013-001 | 021-E-GAD-40129-001 | GENERAL ARRANGEMENT DRAWING STRIPPER FEED BOTTOMS EXCHANGER 021E0013 | A1103 | CX | 2 | 2019-06-05 | CON-BMP-VTRA-012025 | 2019-06-05 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 021E0013 | VP-18TN-009-021E0013-002 | 021-E-GAD-40130-001 | GENERAL NOTE STRIPPER FEED BOTTOMS EXCHANGER 021E0013 | A1103 | CX | 2 | 2019-06-05 | CON-BMP-VTRA-012025 | 2019-06-05 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 021E0013 | VP-18TN-009-021E0013-003 | 021-E-GAD-40131-001 | DETAIL OF BODY STRIPPER FEED / BOTTOMS EXCHANGER 021E0013 | A1109 | CX | 2 | 2019-06-06 | CON-BMP-VTRA-012060 | 2019-06-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 021E0013 | VP-18TN-009-021E0013-004 | 021-E-GAD-40132-001 | DETAIL OF TUBE BUNDLE STRIPPER FEED / BOTTOMS EXCHANGER 021E0013 | A1109 | CX | 2 | 2019-06-06 | CON-BMP-VTRA-012060 | 2019-06-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 021E0013 | VP-18TN-009-021E0013-006 | 021-E-GAD-40133-001 | DETAIL OF SUPPORT SADDLE STRIPPER FEED / BOTTOMS EXCHANGER 021E0013 | A1109 | CX | 2 | 2019-06-06 | CON-BMP-VTRA-012060 | 2019-06-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 021E0013 | VP-18TN-009-021E0013-007 | 021-E-GAD-40134-001 | DETAIL OF NOZZLE STRIPPER FEED/ BOTTOMS EXCHANGER 021E0013 | A1109 | CX | 2 | 2019-06-06 | CON-BMP-VTRA-012060 | 2019-06-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 021E0013 | VP-18TN-009-021E0013-008 | 021-E-DLB-40010-001 | DETAIL OF NAME PLATE STRIPPER FEED / BOTTOMS EXCHANGER 021E0013 | A1112 | CX | 2 | 2019-06-06 | CON-BMP-VTRA-012047 | 2019-06-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 021E0013 | VP-18TN-009-021E0013-100 | 021-E-CAL-40053-001 | STRENGTH CALCULATION 021E0013 | A1003 | CX | 2 | 2019-06-06 | CON-BMP-VTRA-012040 | 2019-06-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 021E0013 | VP-18TN-009-COMM-0619 | 021-E-MCD-40026-001 | WELDING BOOK (MAP PROCEDURE QUALIFICATION REPORT) 021E0013 | B1304 | 0X | 3 | 2019-06-14 | CON-BMP-VTRA-012208 | 2019-06-14 | FOR BAPCO REVIEW | 2019-06-28 | 2019-06-29 | 1-APPROVED BMP-ROC-VTRE-001072 | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 021E0013 | VP-18TN-009-COMM-1540 | 021-E-PQP-40021-001 | FABRICATION AND QUALITY CONTROL PLAN 021E0013 | B1002 | 0X | 3 | 2019-06-13 | CON-BMP-VTRA-012199 | 2019-06-13 | FOR BAPCO REVIEW | 2019-06-28 | 2019-06-30 | 1-APPROVED BMP-ROC-VTRE-001090 | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 021E0015 | VP-18TN-009-021E0015-001 | 021-E-GAD-40136-001 | GENERAL ARRANGEMENT DRAWING STRIPPER BOTTOMS MP STEAM GENERATOR 021E0015 | A1103 | CX | 2 | 2019-06-05 | CON-BMP-VTRA-012020 | 2019-06-05 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 021E0015 | VP-18TN-009-021E0015-002 | 021-E-GAD-40137-001 | GENERAL NOTE STRIPPER BOTTOMS MP STEAM GENERATOR 021E0015 | A1103 | CX | 2 | 2019-06-05 | CON-BMP-VTRA-012020 | 2019-06-05 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 021E0015 | VP-18TN-009-021E0015-003 | 021-E-GAD-40138-001 | DETAIL OF BODY STRIPPER BOTTOMS/MP STEAM GENERATOR 021E0015 | A1109 | 0X | 2 | 2019-06-21 | CON-BMP-VTRA-012344 | 2019-06-21 | FOR BAPCO REVIEW | 2019-07-05 |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 021E0015 | VP-18TN-009-021E0015-004 | 021-E-GAD-40139-001 | DETAIL OF TUBE BUNDLE (1/2) STRIPPER BOTTOMS/MP STEAM GENERATOR 021E0015 | A1109 | CX | 2 | 2019-06-05 | CON-BMP-VTRA-012013 | 2019-06-05 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 021E0015 | VP-18TN-009-021E0015-006 | 021-E-GAD-40140-001 | DETAIL OF SUPPORT SADDLE STRIPPER BOTTOMS/MP STEAM GENERATOR 021E0015 | A1109 | CX | 2 | 2019-06-05 | CON-BMP-VTRA-012013 | 2019-06-05 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 021E0015 | VP-18TN-009-021E0015-007 | 021-E-GAD-40141-001 | DETAIL OF NOZZLE STRIPPER BOTTOMS/MP STEAM GENERATOR 021E0015 | A1109 | CX | 2 | 2019-06-05 | CON-BMP-VTRA-012013 | 2019-06-05 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 021E0015 | VP-18TN-009-021E0015-009 | 021-E-DLB-40011-001 | DETAIL OF NAME PLATE STRIPPER BOTTOMS/MP STEAM GENERATOR 021E0015 | A1112 | 0X | 3 | 2019-06-13 | CON-BMP-VTRA-012197 | 2019-06-13 | FOR BAPCO REVIEW | 2019-06-28 | 2019-07-04 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001171 | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 021E0015 | VP-18TN-009-021E0015-100 | 021-E-CAL-40054-001 | STRENGTH CALCULATION 021E0015 | A1003 | CX | 2 | 2019-06-05 | CON-BMP-VTRA-012024 | 2019-06-05 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 021E0015 | VP-18TN-009-COMM-0620 | 021-E-MCD-40027-001 | WELDING BOOK (MAP PROCEDURE QUALIFICATION REPORT) 021E0015 | B1304 | 0X | 3 | 2019-06-14 | CON-BMP-VTRA-012208 | 2019-06-14 | FOR BAPCO REVIEW | 2019-06-28 | 2019-06-29 | 1-APPROVED BMP-ROC-VTRE-001072 | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 021E0015 | VP-18TN-009-COMM-1541 | 021-E-PQP-40022-001 | FABRICATION AND QUALITY CONTROL PLAN 021E0015 | B1002 | 0X | 3 | 2019-06-13 | CON-BMP-VTRA-012199 | 2019-06-13 | FOR BAPCO REVIEW | 2019-06-28 | 2019-06-30 | 1-APPROVED BMP-ROC-VTRE-001090 | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 021E0017 | VP-18TN-009-021E0017-001 | 021-E-GAD-40143-001 | GENERAL ARRANGEMENT DRAWING DIESEL PRODUCT TRIM COOLER 021E0017 | A1103 | CX | 2 | 2019-06-05 | CON-BMP-VTRA-012025 | 2019-06-05 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 021E0017 | VP-18TN-009-021E0017-002 | 021-E-GAD-40144-001 | GENERAL ARRANGEMENT DRAWING DIESEL PRODUCT TRIM COOLER 021E0017 | A1103 | CX | 2 | 2019-06-05 | CON-BMP-VTRA-012025 | 2019-06-05 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 021E0017 | VP-18TN-009-021E0017-003 | 021-E-GAD-40145-001 | DETAIL OF BODY 021E0017 DIESEL PRODUCT TRIM COOLER | A1109 | CX | 2 | 2019-06-06 | CON-BMP-VTRA-012060 | 2019-06-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 021E0017 | VP-18TN-009-021E0017-004 | 021-E-GAD-40146-001 | DETAIL OF TUBE BUNDLE 021E0017 DIESEL PRODUCT TRIM COOLER | A1109 | 0X | 3 | 2019-06-06 | CON-BMP-VTRA-012051 | 2019-06-06 | FOR BAPCO REVIEW | 2019-06-20 | 2019-07-02 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001134 | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 021E0017 | VP-18TN-009-021E0017-006 | 021-E-GAD-40147-001 | DETAIL OF SUPPORT SADDLE 021E0017 DIESEL PRODUCT TRIM COOLER | A1109 | CX | 2 | 2019-06-06 | CON-BMP-VTRA-012060 | 2019-06-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 021E0017 | VP-18TN-009-021E0017-007 | 021-E-GAD-40148-001 | DETAIL OF NOZZLE 021E0017 DIESEL PRODUCT TRIM COOLER | A1109 | CX | 2 | 2019-06-06 | CON-BMP-VTRA-012060 | 2019-06-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 021E0017 | VP-18TN-009-021E0017-008 | 021-E-GAD-40149-001 | DETAIL OF TEST RING 021E0017 DIESEL PRODUCT TRIM COOLER | A1109 | 0X | 3 | 2019-06-06 | CON-BMP-VTRA-012051 | 2019-06-06 | FOR BAPCO REVIEW | 2019-06-20 | 2019-07-02 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001134 | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 021E0017 | VP-18TN-009-021E0017-009 | 021-E-DLB-40012-001 | DETAIL OF NAME PLATE 021E0017 DIESEL PRODUCT TRIM COOLER | A1112 | CX | 2 | 2019-06-06 | CON-BMP-VTRA-012047 | 2019-06-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 021E0017 | VP-18TN-009-021E0017-100 | 021-E-CAL-40055-001 | STRENGTH CALCULATION 021E0017 | A1003 | CX | 2 | 2019-06-06 | CON-BMP-VTRA-012040 | 2019-06-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 021E0017 | VP-18TN-009-COMM-0621 | 021-E-MCD-40028-001 | WELDING BOOK (MAP PROCEDURE QUALIFICATION REPORT) 021E0017 | B1304 | 0X | 3 | 2019-06-14 | CON-BMP-VTRA-012208 | 2019-06-14 | FOR BAPCO REVIEW | 2019-06-28 | 2019-06-29 | 1-APPROVED BMP-ROC-VTRE-001072 | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 021E0017 | VP-18TN-009-COMM-1542 | 021-E-PQP-40023-001 | FABRICATION AND QUALITY CONTROL PLAN FOR CS SHELL AND TUBE EXCHANGER 021E0017 | B1002 | 0X | 2 | 2019-06-07 | CON-BMP-VTRA-012100 | 2019-06-07 | FOR BAPCO REVIEW | 2019-06-24 | 2019-06-23 | 1-APPROVED BMP-ROC-VRE-001018 | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 051E0002A | VP-18TN-009-051E0002A/B-001 | 051-E-GAD-40007-001 | GENERAL ARRANGEMENT DRAWING BUTANE PRODUCT COOLERS 051E0002A 051E0002B | A1103 | CX | 2 | 2019-06-17 | CON-BMP-VTRA-012241 | 2019-06-17 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 051E0002A | VP-18TN-009-051E0002A/B-002 | 051-E-GAD-40008-001 | GENERAL NOTE BUTANE PRODUCT COOLERS 051E0002A 051E0002B | A1103 | 0X | 3 | 2019-06-25 | CON-BMP-VTRA-012416 | 2019-06-25 | FOR BAPCO REVIEW | 2019-07-09 | 2019-07-09 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001230 | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 051E0002A | VP-18TN-009-051E0002A/B-003 | 051-E-GAD-40009-001 | DETAIL OF BODY 051E0002A/B BUTANE PRODUCT COOLER | A1109 | 0X | 3 | 2019-06-25 | CON-BMP-VTRA-012422 | 2019-06-25 | FOR BAPCO REVIEW | 2019-07-09 | 2019-07-09 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001229 | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 051E0002A | VP-18TN-009-051E0002A/B-004 | 051-E-GAD-40010-001 | DETAIL OF TUBE BUNDLE 051E0002A/B BUTANE PRODUCT COOLER | A1109 | 0X | 2 | 2019-06-21 | CON-BMP-VTRA-012345 | 2019-06-21 | FOR BAPCO REVIEW | 2019-07-05 | 2019-07-07 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001186 | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 051E0002A | VP-18TN-009-051E0002A/B-006 | 051-E-GAD-40011-001 | DETAIL OF SUPPORT SADDLE 051E0002A/B BUTANE PRODUCT COOLER | A1109 | 0X | 3 | 2019-06-25 | CON-BMP-VTRA-012424 | 2019-06-25 | FOR BAPCO REVIEW | 2019-07-09 | 2019-07-09 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001228 | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 051E0002A | VP-18TN-009-051E0002A/B-008 | 051-E-GAD-40012-001 | DETAIL OF NOZZLE 051E0002A/B BUTANE PRODUCT COOLER | A1109 | 0X | 3 | 2019-06-25 | CON-BMP-VTRA-012424 | 2019-06-25 | FOR BAPCO REVIEW | 2019-07-09 | 2019-07-09 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001228 | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 051E0002A | VP-18TN-009-051E0002A/B-009 | 051-E-DLB-40001-001 | DETAIL OF NAME PLATE BUTANE PRODUCT COOLERS 051E0002A/B/C/D | A1112 | 0X | 3 | 2019-07-05 | CON-BMP-VTRA-012680 | 2019-07-05 | FOR BAPCO REVIEW | 2019-07-19 |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 051E0002A | VP-18TN-009-051E0002A/B-100 | 051-E-CAL-40004-001 | STRENGTH CALCULATION 051E0002A 051E0002B | A1003 | CX | 2 | 2019-06-05 | CON-BMP-VTRA-012024 | 2019-06-05 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 051E0002A | VP-18TN-009-COMM-0622 | 051-E-MCD-40003-001 | WELDING BOOK (MAP, PROCEDURE, QUALIFICATION REPORT) 051E0002A/B | B1304 | CX | 2 | 2019-06-11 | CON-BMP-VTRA-012148 | 2019-06-11 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 051E0002A | VP-18TN-009-COMM-1543 | 051-E-PQP-40001-001 | FABRICATION AND QUALITY CONTROL PLAN FOR CS SHELL AND TUBE EXCHANGER 051E0002A/B/C/D | B1002 | 0X | 2 | 2019-06-07 | CON-BMP-VTRA-012100 | 2019-06-07 | FOR BAPCO REVIEW | 2019-06-24 | 2019-06-23 | 1-APPROVED BMP-ROC-VRE-001018 | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 062E6242A | VP-18TN-009-062E6242A/B-001 | 062-E-GAD-40002-001 | GENERAL ARRANGEMENT DRAWING 2HDU DIESEL RUNDOWN COOLERS 062E6242 A/B | A1103 | CX | 2 | 2019-07-01 | CON-BMP-VTRA-012584 | 2019-07-01 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 062E6242A | VP-18TN-009-062E6242A/B-002 | 062-E-GAD-40003-001 | GENERAL NOTES 2HDU DIESEL RUNDOWN COOLERS 062E6242 A/B | A1103 | CX | 2 | 2019-06-21 | CON-BMP-VTRA-012355 | 2019-06-21 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 062E6242A | VP-18TN-009-062E6242A/B-003 | 062-E-GAD-40004-001 | DETAIL OF BODY 2HDU DIESEL RUNDOWN COOLER 062E6242A/B | A1109 | 0X | 2 | 2019-06-14 | CON-BMP-VTRA-012213 | 2019-06-14 | FOR BAPCO REVIEW | 2019-06-28 | 2019-06-27 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001053 | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 062E6242A | VP-18TN-009-062E6242A/B-004 | 062-E-GAD-40005-001 | DETAIL OF TUBE BUNDLE 2HDU DIESEL RUNDOWN COOLER 062E6242A/B | A1109 | 0X | 3 | 2019-06-14 | CON-BMP-VTRA-012211 | 2019-06-14 | FOR BAPCO REVIEW | 2019-06-28 | 2019-06-29 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001087 | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 062E6242A | VP-18TN-009-062E6242A/B-006 | 062-E-GAD-40006-001 | DETAIL OF SUPPORT SADDLE 2HDU DIESEL RUNDOWN COOLER 062E6242A/B | A1109 | CX | 2 | 2019-06-11 | CON-BMP-VTRA-012151 | 2019-06-11 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 062E6242A | VP-18TN-009-062E6242A/B-008 | 062-E-GAD-40007-001 | DETAIL OF NOZZLE 2HDU DIESEL RUNDOWN COOLER 062E6242A/B | A1109 | CX | 2 | 2019-06-11 | CON-BMP-VTRA-012151 | 2019-06-11 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 062E6242A | VP-18TN-009-062E6242A/B-009 | 062-E-GAD-40008-001 | DETAIL OF TEST RING 2HDU DIESEL RUNDOWN COOLER 062E6242A/B | A1109 | 0X | 3 | 2019-06-14 | CON-BMP-VTRA-012211 | 2019-06-14 | FOR BAPCO REVIEW | 2019-06-28 | 2019-06-29 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001087 | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 062E6242A | VP-18TN-009-062E6242A/B-010 | 062-E-DLB-40001-001 | DETAIL OF NAME PLATE 2HDU DIESEL RUNDOWN COOLERS 062E6242A/B | A1112 | CX | 2 | 2019-06-11 | CON-BMP-VTRA-012149 | 2019-06-11 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 062E6242A | VP-18TN-009-COMM-0623 | 062-E-MCD-40003-001 | WELDING BOOK (MAP PROCEDURE QUALIFICATION REPORT)062E6242A/B | B1304 | 0X | 3 | 2019-06-14 | CON-BMP-VTRA-012209 | 2019-06-14 | FOR BAPCO REVIEW | 2019-06-28 | 2019-06-30 | 1-APPROVED BMP-ROC-VTRE-001094 | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 062E6242A | VP-18TN-009-COMM-1545 | 062-E-PQP-40001-001 | FABRICATION AND QUALITY CONTROL PLAN 062E6242A/B | B1002 | 0X | 3 | 2019-06-13 | CON-BMP-VTRA-012200 | 2019-06-13 | FOR BAPCO REVIEW | 2019-06-28 | 2019-06-27 | 1-APPROVED BMP-ROC-VTRE-001068 | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 077E7762A | VP-18TN-009-077E7762A/B-001 | 077-E-GAD-40002-001 | GENERAL ARRANGEMENT DRAWING 1HCU COMBINED DIESEL RUNDOWN COOLERS 077E7762 A/B | A1103 | CX | 2 | 2019-07-01 | CON-BMP-VTRA-012587 | 2019-07-01 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 077E7762A | VP-18TN-009-077E7762A/B-002 | 077-E-GAD-40003-001 | GENERAL NOTES 1HCU COMBINED DIESEL RUNDOWN COOLERS 077E7762 A/B | A1103 | CX | 2 | 2019-06-11 | CON-BMP-VTRA-012150 | 2019-06-11 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 077E7762A | VP-18TN-009-077E7762A/B-003 | 077-E-GAD-40004-001 | DETAIL OF BODY 1HCU DIESEL RUNDOWN COOLER 077E7762A/B | A1109 | 0X | 3 | 2019-06-14 | CON-BMP-VTRA-012212 | 2019-06-14 | FOR BAPCO REVIEW | 2019-06-28 | 2019-06-27 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001060 | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 077E7762A | VP-18TN-009-077E7762A/B-004 | 077-E-GAD-40005-001 | DETAIL OF TUBE BUNDLE 1HCU DIESEL RUNDOWN COOLER 077E7762A/B | A1109 | 0X | 3 | 2019-06-14 | CON-BMP-VTRA-012212 | 2019-06-14 | FOR BAPCO REVIEW | 2019-06-28 | 2019-06-27 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001060 | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 077E7762A | VP-18TN-009-077E7762A/B-006 | 077-E-GAD-40006-001 | DETAIL OF SUPPORT SADDLE 1HCU DIESEL RUNDOWN COOLER 077E7762A/B | A1109 | CX | 2 | 2019-06-11 | CON-BMP-VTRA-012152 | 2019-06-11 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 077E7762A | VP-18TN-009-077E7762A/B-008 | 077-E-GAD-40007-001 | DETAIL OF NOZZLE 1HCU DIESEL RUNDOWN COOLER 077E7762A/B | A1109 | CX | 2 | 2019-06-11 | CON-BMP-VTRA-012152 | 2019-06-11 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 077E7762A | VP-18TN-009-077E7762A/B-009 | 077-E-GAD-40008-001 | DETAIL OF TEST RING 1HCU DIESEL RUNDOWN COOLER 077E7762A/B | A1109 | 0X | 3 | 2019-06-14 | CON-BMP-VTRA-012212 | 2019-06-14 | FOR BAPCO REVIEW | 2019-06-28 | 2019-06-27 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001060 | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 077E7762A | VP-18TN-009-077E7762A/B-010 | 077-E-DLB-40001-001 | DETAIL OF NAME PLATE 021E0017 DIESEL PRODUCT TRIM COOLERS | A1112 | 0X | 3 | 2019-06-26 | CON-BMP-VTRA-012488 | 2019-06-26 | FOR BAPCO REVIEW | 2019-07-10 |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 077E7762A | VP-18TN-009-077E7762A/B-100 | 077-E-CAL-40001-001 | STRENGTH CALCULATION 077E7762A/B | A1003 | CX | 2 | 2019-06-18 | CON-BMP-VTRA-012262 | 2019-06-18 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 077E7762A | VP-18TN-009-COMM-0624 | 077-E-MCD-40003-001 | WELDING BOOK (MAP PROCEDURE QUALIFICATION REPORT) 077E7762A/B | B1304 | 0X | 3 | 2019-06-14 | CON-BMP-VTRA-012210 | 2019-06-14 | FOR BAPCO REVIEW | 2019-06-28 | 2019-06-29 | 1-APPROVED BMP-ROC-VTRE-001064 | CLASS 2
076551C-000R-MR-0610-004 | MATERIAL REQUISITION FOR CS SHELL AND TUBE HEAT EXCHANGER | ILSUNG HISCO LTD | 077E7762A | VP-18TN-009-COMM-1547 | 077-E-PQP-40001-001 | FABRICATION AND QUALITY CONTROL PLAN 077E7762A/B | B1002 | 0X | 3 | 2019-06-13 | CON-BMP-VTRA-012201 | 2019-06-13 | FOR BAPCO REVIEW | 2019-06-28 | 2019-06-27 | 1-APPROVED BMP-ROC-VTRE-001067 | CLASS 2
076551C-000R-MR-0710-001 | MATERIAL REQUISITION FOR H.P. AND SPECIAL MATERIALS AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0006 | 000-E-CAL-60001-001 | 000-E-CAL-40001-001 | LIFTING FRAME CALCULATION AND DRAWING FOR AIR COOLERS ALL ITEMS | A2201 | AX | 2 | 2019-06-26 | CON-BMP-VTRA-012511 | 2019-06-26 | FOR BAPCO REVIEW | 2019-07-11 |  |  | CLASS 2
076551C-000R-MR-0710-001 | MATERIAL REQUISITION FOR H.P. AND SPECIAL MATERIALS AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0006 | 000-E-DAT-60001-001 | 000-E-DAT-40001-001 | FAN DATA SHEET WITH PERFORMANCE CURVES ALL ITEMS | A1002 | 0X | 2 | 2019-06-24 | CON-BMP-VTRA-012398 | 2019-06-24 | FOR BAPCO REVIEW | 2019-07-08 |  |  | CLASS 2
076551C-000R-MR-0710-001 | MATERIAL REQUISITION FOR H.P. AND SPECIAL MATERIALS AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0006 | 000-E-DAT-60002-001 | 000-E-DAT-40002-001 | BELT AND PULLEY DATA SHEET ALL ITEMS | A1006 | 0AX | 3 | 2019-07-03 | CON-BMP-VTRA-012631 | 2019-07-03 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0710-001 | MATERIAL REQUISITION FOR H.P. AND SPECIAL MATERIALS AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0006 | 000-E-DAT-60003-001 | 000-E-DAT-40003-001 | NOISE DATA SHEET ALL ITEMS | A0105 | BX | 2 | 2019-06-05 | CON-BMP-VTRA-012003 | 2019-06-05 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0710-001 | MATERIAL REQUISITION FOR H.P. AND SPECIAL MATERIALS AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0006 | 000-E-DAT-60004-001 | 000-E-DAT-40004-001 | INSTRUMENT LIST AND DATA SHEET ALL ITEMS | A3101 | BX | 2 | 2019-05-10 | CON-BMP-VTRA-011513 | 2019-05-10 | FOR BAPCO REVIEW | 2019-05-24 | 2019-05-28 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000821 | CLASS 2
076551C-000R-MR-0710-001 | MATERIAL REQUISITION FOR H.P. AND SPECIAL MATERIALS AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0006 | 000-E-DAT-60005-001 | 000-E-DAT-40005-001 | MOTOR DATA SHEET & DRAWING 018E0006/7/10/30 018E1005/2005 021E0010/11 | A4102 | BX | 2 | 2019-06-24 | CON-BMP-VTRA-012397 | 2019-06-24 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0710-001 | MATERIAL REQUISITION FOR H.P. AND SPECIAL MATERIALS AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0006 | 000-E-DAT-60006-001 | 000-E-DAT-40006-001 | VSD PANEL DATA SHEET & DRAWING 018E0006/7/10/30 018E1005/2005 021E0010/11 | A4102 | BX | 2 | 2019-06-24 | CON-BMP-VTRA-012397 | 2019-06-24 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0710-001 | MATERIAL REQUISITION FOR H.P. AND SPECIAL MATERIALS AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0006 | 000-E-DAT-60007-001 | 000-E-INX-40013-001 | SPECIAL TOOL LIST ALL ITEMS | A5008 | 0AX | 3 | 2019-06-11 | CON-BMP-VTRA-012139 | 2019-06-11 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0710-001 | MATERIAL REQUISITION FOR H.P. AND SPECIAL MATERIALS AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0006 | 000-E-DAT-60015-001 | 000-E-INX-40015-001 | INSTRUMENT LIST ALL ITEMS | A3004 | AX | 2 | 2019-05-10 | CON-BMP-VTRA-011514 | 2019-05-10 | FOR BAPCO REVIEW | 2019-05-24 | 2019-05-27 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000808 | CLASS 2
076551C-000R-MR-0710-001 | MATERIAL REQUISITION FOR H.P. AND SPECIAL MATERIALS AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0006 | 000-E-DLB-60001-001 | 000-E-DLB-40001-001 | NAMEPLATE DWG ALL ITEMS (EX BAPCO N. 000-E-DLB-60001-001) | A1112 | BX | 2 | 2019-05-21 | CON-BMP-VTRA-011701 | 2019-05-21 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0710-001 | MATERIAL REQUISITION FOR H.P. AND SPECIAL MATERIALS AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0006 | 000-E-GAD-60008-001 | 000-E-GAD-40008-001 | MOTOR DRAWINGS 018E0006/7/10/30 018E1005/2005 021E0010/11 | A4207 | BX | 2 | 2019-06-24 | CON-BMP-VTRA-012396 | 2019-06-24 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0710-001 | MATERIAL REQUISITION FOR H.P. AND SPECIAL MATERIALS AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0006 | 000-E-INV-60001-001 | 000-E-INV-40001-001 | UNPRICED COPY OF MAIN SUBORDERS FOR H.P. AND SPECIAL MATERIALS AIR COOLERS ALL ITEMS (EX BAPCO N.000-E-INV-60009-001) | C1005 | CX | 2 | 2019-06-26 | CON-BMP-VTRA-012514 | 2019-06-26 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-0710-001 | MATERIAL REQUISITION FOR H.P. AND SPECIAL MATERIALS AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0006 | 000-E-INX-60005-001 | 000-E-INX-40012-001 | EL CONSUMER LIST POWERSUPP REQUIR(NORMAL-EMERG UPS) ALL ITEMS | A4001 | BX | 2 | 2019-04-18 | CON-BMP-VTRA-011231 | 2019-04-18 | FOR BAPCO REVIEW | 2019-05-06 | 2019-05-15 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000674 | CLASS 2
076551C-000R-MR-0710-001 | MATERIAL REQUISITION FOR H.P. AND SPECIAL MATERIALS AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0006 | 000-E-MCD-60002-001 | 018-E-MCD-40081-001 | WELDING BOOK (MAP PROCEDURE QUALIFICATION REPORT) 018E0006 | B1304 | AX | 2 | 2019-02-25 | CON-BMP-VTRA-010497 | 2019-02-25 | FOR BAPCO REVIEW | 2019-03-12 | 2019-03-07 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000260 | CLASS 2
076551C-000R-MR-0710-001 | MATERIAL REQUISITION FOR H.P. AND SPECIAL MATERIALS AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0006 | 000-E-MRS-60001-001 | 000-E-MRS-40001-001 | MONTHLY PROGRESS REPORT FOR H.P. AND SPECIAL MATERIALS AIR COOLERS ALL ITEMS (EX BAPCO N.000-E-MRS-60001-001) | C1002 | FX | 2 | 2019-06-26 | CON-BMP-VTRA-012515 | 2019-06-26 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-0710-001 | MATERIAL REQUISITION FOR H.P. AND SPECIAL MATERIALS AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0006 | 000-E-PLD-60001-001 | 000-E-PLD-40001-001 | WALKWAY STANDARD DRAWING ALL ITEMS | A2008 | BX | 2 | 2019-05-14 | CON-BMP-VTRA-011560 | 2019-05-14 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0710-001 | MATERIAL REQUISITION FOR H.P. AND SPECIAL MATERIALS AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0006 | 000-E-PLD-60003-001 | 000-E-GAD-40003-001 | FRONT VIEW AND TYPICAL SECTIONDRAWINGS FOR VFD PANEL ALL ITEMS | A4204 | AX | 2 | 2019-07-09 | CON-BMP-VTRA-012762 | 2019-07-09 | FOR BAPCO REVIEW | 2019-07-23 |  |  | CLASS 2
076551C-000R-MR-0710-001 | MATERIAL REQUISITION FOR H.P. AND SPECIAL MATERIALS AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0006 | 000-E-PLD-60007-001 | 000-E-SCH-40004-001 | ENGINEERING PROCUREMEN MANUFACTURING & TEST SCHEDULE ALL ITEMS | C1001 | AX | 2 | 2019-01-30 | CON-BMP-VTRA-010321 | 2019-01-30 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-0710-001 | MATERIAL REQUISITION FOR H.P. AND SPECIAL MATERIALS AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0006 | 000-E-PQP-40001-001 | 018-E-PQP-40044-001 | FABRICATION AND QUALITY CONTROL PLAN 018E0006 AIR COOLER | B1002 | 0AX | 3 | 2019-06-05 | CON-BMP-VTRA-011997 | 2019-06-05 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0710-001 | MATERIAL REQUISITION FOR H.P. AND SPECIAL MATERIALS AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0006 | 000-E-PQS-60001-001 | 000-E-PQS-40001-001 | SUB-VENDOR'S AND MAIN SUPPLIER'S LIST ALL ITEMS | B1401 | BX | 2 | 2019-02-20 | CON-BMP-VTRA-010471 | 2019-02-20 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0710-001 | MATERIAL REQUISITION FOR H.P. AND SPECIAL MATERIALS AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0006 | 000-E-PRO-40008-001 | 000-E-PRO-40024-001 | HYDROSTATIC TEST PROCEDURE ALL ITEMS | B1103 | AX | 2 | 2019-04-18 | CON-BMP-VTRA-011225 | 2019-04-18 | FOR BAPCO REVIEW | 2019-05-06 | 2019-05-02 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000627 | CLASS 2
076551C-000R-MR-0710-001 | MATERIAL REQUISITION FOR H.P. AND SPECIAL MATERIALS AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0006 | 000-E-PRO-60001-001 | 000-E-PRO-40001-001 | TESTING PROCEDURES ALL ITEMS | B1103 | AX | 2 | 2019-04-18 | CON-BMP-VTRA-011225 | 2019-04-18 | FOR BAPCO REVIEW | 2019-05-06 | 2019-05-02 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000627 | CLASS 2
076551C-000R-MR-0710-001 | MATERIAL REQUISITION FOR H.P. AND SPECIAL MATERIALS AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0006 | 000-E-PRO-60002-001 | 000-E-PRO-40002-001 | PWHT PROCEDURE ALL ITEMS | B1201 | BX | 2 | 2019-07-04 | CON-BMP-VTRA-012671 | 2019-07-04 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0710-001 | MATERIAL REQUISITION FOR H.P. AND SPECIAL MATERIALS AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0006 | 000-E-PRO-60003-001 | 000-E-PRO-40003-001 | NDT PROCEDURE FOR H.P. AND SPECIAL MATERIALS AIR COOLERS ALL ITEMS | B1202 | 0X | 2 | 2019-05-29 | CON-BMP-VTRA-011823 | 2019-05-29 | FOR BAPCO REVIEW | 2019-06-12 | 2019-06-09 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000892 | CLASS 2
076551C-000R-MR-0710-001 | MATERIAL REQUISITION FOR H.P. AND SPECIAL MATERIALS AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0006 | 000-E-TSP-60001-001 | 000-E-TSP-40001-001 | PAINTING SPECIFICATION ALL ITEMS | A0106 | BX | 2 | 2019-06-03 | CON-BMP-VTRA-011939 | 2019-06-03 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0710-001 | MATERIAL REQUISITION FOR H.P. AND SPECIAL MATERIALS AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0006 | 000-E-TSP-60002-001 | 000-E-TSP-40002-001 | LUBRICANT LIST ALL ITEMS | A1015 | 0X | 2 | 2019-06-24 | CON-BMP-VTRA-012399 | 2019-06-24 | FOR BAPCO REVIEW | 2019-07-08 |  |  | CLASS 2
076551C-000R-MR-0710-001 | MATERIAL REQUISITION FOR H.P. AND SPECIAL MATERIALS AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0006 | 000-E-TSP-6003-001 | 000-E-TSP-6003-001 | MATERIAL SPECIFICATION FOR MAIN SUB-ORDERS ALL ITEMS | B1203 | AX | 2 | 2018-12-07 | CON-BMP-VTRA-010128 | 2018-12-07 | FOR BAPCO REVIEW | 2018-12-22 | 2018-12-20 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000081 | CLASS 2
076551C-000R-MR-0710-001 | MATERIAL REQUISITION FOR H.P. AND SPECIAL MATERIALS AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0006 | 018-E-CAL-00001-001 | 018-E-CAL-40001-001 | MECHANICAL STRENGTH CALCULATION 018E0006 | A1003 | BX | 2 | 2019-06-05 | CON-BMP-VTRA-012002 | 2019-06-05 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0710-001 | MATERIAL REQUISITION FOR H.P. AND SPECIAL MATERIALS AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0006 | 018-E-CAL-00006-001 | 018-E-CAL-40006-001 | THERMAL RATING FOR HEAT EXCHANGERS 018E0006 (EX BAPCO N.018-E-CAL-00006-001) | A1012 | BX | 2 | 2019-02-13 | CON-BMP-VTRA-010419 | 2019-02-13 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0710-001 | MATERIAL REQUISITION FOR H.P. AND SPECIAL MATERIALS AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0006 | 018-E-CAL-00011-001 | 018-E-CAL-40011-001 | STRUCTURE STEEL CALCULATION NOTE 018E0006 (EX BAPCO N.018- E-CAL-00011-001) | A2201 | 0X | 3 | 2019-07-04 | CON-BMP-VTRA-012675 | 2019-07-04 | FOR BAPCO REVIEW | 2019-07-19 |  |  | CLASS 2
076551C-000R-MR-0710-001 | MATERIAL REQUISITION FOR H.P. AND SPECIAL MATERIALS AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0006 | 018-E-DAT-00001-001 | 018-E-DAT-40059-001 | EQPT FILLED-IN DATA SHEET 018E0006 (EX BAPCO N.018-EDAT- 00059-001) | A1001 | BX | 2 | 2019-02-12 | CON-BMP-VTRA-010403 | 2019-02-12 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0710-001 | MATERIAL REQUISITION FOR H.P. AND SPECIAL MATERIALS AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0006 | 018-E-GAD-00003-001 | 018-E-GAD-40086-001 | STRUCTURE ASSEMBLY DRAWING 018E0006 | A2007 | CX | 2 | 2019-05-21 | CON-BMP-VTRA-011702 | 2019-05-21 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0710-001 | MATERIAL REQUISITION FOR H.P. AND SPECIAL MATERIALS AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0006 | 018-E-GAD-00016-001 | 018-E-GAD-40060-001 | GENERAL ARRANGEMENT DRAWING WITH FOUNDATION LOADING DATA 018E006 018E0007 018E0030 (EX BAPCO N.018-E-GAD-00060-001) | A2001 | CX | 2 | 2019-07-04 | CON-BMP-VTRA-012674 | 2019-07-04 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0710-001 | MATERIAL REQUISITION FOR H.P. AND SPECIAL MATERIALS AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0006 | 018-E-GAD-00045-001 | 018-E-GAD-40045-001 | BUNDLE SCREEN DWG 018E0006 | A1109 | 0X | 3 | 2019-07-05 | CON-BMP-VTRA-012677 | 2019-07-05 | FOR BAPCO REVIEW | 2019-07-19 |  |  | CLASS 2
076551C-000R-MR-0710-001 | MATERIAL REQUISITION FOR H.P. AND SPECIAL MATERIALS AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0006 | 018-E-GAD-00050-001 | 018-E-GAD-40050-001 | PERSONAL PROTECTION GUARD DWG 018E0006 | A1109 | BX | 2 | 2019-07-04 | CON-BMP-VTRA-012672 | 2019-07-04 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0710-001 | MATERIAL REQUISITION FOR H.P. AND SPECIAL MATERIALS AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0006 | 018-E-GAD-00055-001 | 018-E-GAD-00055-001 | HEAT EXCHANGER CONSTRUCTION DWG 018E006 (HEADER DETAIL DRAWING) | A1103 | BX | 2 | 2019-06-05 | CON-BMP-VTRA-012005 | 2019-06-05 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0710-001 | MATERIAL REQUISITION FOR H.P. AND SPECIAL MATERIALS AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0006 | 018-E-GAD-40100-001 | 018-E-GAD-40441-001 | ROTATING ASSEMBLY DRAWING 018E0006 | A2007 | BX | 2 | 2019-06-26 | CON-BMP-VTRA-012513 | 2019-06-26 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0710-001 | MATERIAL REQUISITION FOR H.P. AND SPECIAL MATERIALS AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0006 | 018-E-INX-00001-001 | 000-E-INX-40001-001 | LIST OF VENDOR'S DOCUMENTS AND DWGS FOR H.P. AND SPECIAL MATERIALS AIR COOLERS ALL ITEMS(EX BAPCO N.000-E-INX-60001-001) | A0001 | CX | 2 | 2019-05-06 | CON-BMP-VTRA-011428 | 2019-05-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0710-001 | MATERIAL REQUISITION FOR H.P. AND SPECIAL MATERIALS AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0006 | 018-E-PLD-00001-001 | 018-E-PLD-40001-001 | WALKWAY ASSEMBLY DRAWING 018E0006 | A2008 | BX | 2 | 2019-05-14 | CON-BMP-VTRA-011560 | 2019-05-14 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0710-001 | MATERIAL REQUISITION FOR H.P. AND SPECIAL MATERIALS AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0006 | 3AKR502449996 | 000-E-CWD-40004-001 | WIRING DRAWINGS FOR VFD PANEL H.P. AND SPECIAL MATERIALS AIRCOOLERS ALL ITEMS | A4211 | AX | 2 | 2019-07-08 | CON-BMP-VTRA-012746 | 2019-07-08 | FOR BAPCO REVIEW | 2019-07-23 |  |  | CLASS 2
076551C-000R-MR-0710-001 | MATERIAL REQUISITION FOR H.P. AND SPECIAL MATERIALS AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0007 | 000-E-PQP-40003-001 | 018-E-PQP-40045-001 | FABRICATION AND QUALITY CONTROL PLAN 018E0007 AIR COOLER | B1002 | 0AX | 3 | 2019-06-05 | CON-BMP-VTRA-011996 | 2019-06-05 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0710-001 | MATERIAL REQUISITION FOR H.P. AND SPECIAL MATERIALS AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0007 | 000-E-PQP-60005-001 | 018-E-MCD-40083-001 | WELDING BOOK (MAP, PROCEDURE, QUALIFICATION REPORT) 018E0007 | B1304 | BX | 2 | 2019-04-03 | CON-BMP-VTRA-010990 | 2019-04-03 | FOR BAPCO REVIEW | 2019-04-18 | 2019-04-15 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000521 | CLASS 2
076551C-000R-MR-0710-001 | MATERIAL REQUISITION FOR H.P. AND SPECIAL MATERIALS AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0007 | 000-E-PRO-60009-001 | 000-E-PRO-40025-001 | DHT PROCEDURE 018E0007 | B1103 | AX | 2 | 2019-05-21 | CON-BMP-VTRA-011700 | 2019-05-21 | FOR BAPCO REVIEW | 2019-06-05 | 2019-06-01 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000867 | CLASS 2
076551C-000R-MR-0710-001 | MATERIAL REQUISITION FOR H.P. AND SPECIAL MATERIALS AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0007 | 018-E-CAL-00002-001 | 018-E-CAL-40002-001 | MECHANICAL STRENGTH CALCULATION 018E0007 | A1003 | BX | 2 | 2019-06-05 | CON-BMP-VTRA-012002 | 2019-06-05 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0710-001 | MATERIAL REQUISITION FOR H.P. AND SPECIAL MATERIALS AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0007 | 018-E-CAL-00007-001 | 018-E-CAL-40007-001 | THERMAL RATING FOR HEAT EXCHANGERS 018E0007 (EX BAPCO N.018-E-CAL-00007-001) | A1012 | BX | 2 | 2019-02-13 | CON-BMP-VTRA-010419 | 2019-02-13 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0710-001 | MATERIAL REQUISITION FOR H.P. AND SPECIAL MATERIALS AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0007 | 018-E-CAL-00012-001 | 018-E-CAL-40012-001 | STRUCTURE STEEL CALCULATION NOTE 018E0007 (EX BAPCO N.018- E-CAL-00012-001) | A2201 | 0X | 3 | 2019-07-04 | CON-BMP-VTRA-012675 | 2019-07-04 | FOR BAPCO REVIEW | 2019-07-19 |  |  | CLASS 2
076551C-000R-MR-0710-001 | MATERIAL REQUISITION FOR H.P. AND SPECIAL MATERIALS AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0007 | 018-E-DAT-00060-001 | 018-E-DAT-40060-001 | EQPT FILLED-IN DATA SHEET 018E0007 (EX BAPCO N.018-EDAT- 00060-001) | A1001 | BX | 2 | 2019-02-12 | CON-BMP-VTRA-010403 | 2019-02-12 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0710-001 | MATERIAL REQUISITION FOR H.P. AND SPECIAL MATERIALS AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0007 | 018-E-GAD-00004-001 | 018-E-GAD-40087-001 | STRUCTURE ASSEMBLY DRAWING 018E0007 | A2007 | CX | 2 | 2019-05-21 | CON-BMP-VTRA-011702 | 2019-05-21 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0710-001 | MATERIAL REQUISITION FOR H.P. AND SPECIAL MATERIALS AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0007 | 018-E-GAD-00046-001 | 018-E-GAD-40046-001 | BUNDLE SCREEN DWG 018E0007 | A1109 | 0X | 3 | 2019-07-05 | CON-BMP-VTRA-012677 | 2019-07-05 | FOR BAPCO REVIEW | 2019-07-19 |  |  | CLASS 2
076551C-000R-MR-0710-001 | MATERIAL REQUISITION FOR H.P. AND SPECIAL MATERIALS AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0007 | 018-E-GAD-00051-001 | 018-E-GAD-40051-001 | PERSONAL PROTECTION GUARD DWG 018E0007 | A1109 | BX | 2 | 2019-07-04 | CON-BMP-VTRA-012672 | 2019-07-04 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0710-001 | MATERIAL REQUISITION FOR H.P. AND SPECIAL MATERIALS AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0007 | 018-E-GAD-00056-001 | 018-E-GAD-40056-001 | HEAT EXCHANGER CONSTRUCTION DWG 018E007 (HEADER DETAIL DRAWING) (EX BAPCO N.018-E-GAD-00056-001) | A1103 | CX | 2 | 2019-06-05 | CON-BMP-VTRA-012005 | 2019-06-05 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0710-001 | MATERIAL REQUISITION FOR H.P. AND SPECIAL MATERIALS AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0007 | 018-E-GAD-40101-001 | 018-E-GAD-40442-001 | ROTATING ASSEMBLY DRAWING 018E0007 | A2007 | BX | 2 | 2019-06-26 | CON-BMP-VTRA-012513 | 2019-06-26 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0710-001 | MATERIAL REQUISITION FOR H.P. AND SPECIAL MATERIALS AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0007 | 018-E-PLD-00002-001 | 018-E-PLD-40002-001 | WALKWAY ASSEMBLY DRAWING 018E0007 | A2008 | BX | 2 | 2019-05-14 | CON-BMP-VTRA-011560 | 2019-05-14 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0710-001 | MATERIAL REQUISITION FOR H.P. AND SPECIAL MATERIALS AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0010 | 000-E-MCD-60006-001 | 018-E-MCD-40082-001 | WELDING BOOK (MAP PROCEDURE QUALIFICATION REPORT) 018E0010 | B1304 | AX | 2 | 2019-02-25 | CON-BMP-VTRA-010497 | 2019-02-25 | FOR BAPCO REVIEW | 2019-03-12 | 2019-03-07 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000260 | CLASS 2
076551C-000R-MR-0710-001 | MATERIAL REQUISITION FOR H.P. AND SPECIAL MATERIALS AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0010 | 000-E-PQP-40004-001 | 018-E-PQP-40046-001 | FABRICATION AND QUALITY CONTROL PLAN 018E0010 AIR COOLER | B1002 | 0AX | 3 | 2019-06-05 | CON-BMP-VTRA-011996 | 2019-06-05 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0710-001 | MATERIAL REQUISITION FOR H.P. AND SPECIAL MATERIALS AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0010 | 018-E-CAL-00003-001 | 018-E-CAL-40003-001 | MECHANICAL STRENGTH CALCULATION 018E010 | A1003 | BX | 2 | 2019-06-05 | CON-BMP-VTRA-012002 | 2019-06-05 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0710-001 | MATERIAL REQUISITION FOR H.P. AND SPECIAL MATERIALS AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0010 | 018-E-CAL-00008-001 | 018-E-CAL-40008-001 | THERMAL RATING FOR HEAT EXCHANGERS 018E0010 (EX BAPCO N.018-E-CAL-00008-001) | A1012 | BX | 2 | 2019-02-13 | CON-BMP-VTRA-010419 | 2019-02-13 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0710-001 | MATERIAL REQUISITION FOR H.P. AND SPECIAL MATERIALS AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0010 | 018-E-CAL-00013-001 | 018-E-CAL-40013-001 | STRUCTURE STEEL CALCULATION NOTE 018E0010 (EX BAPCO N.018- E-CAL-00013-001) | A2201 | 0X | 3 | 2019-07-04 | CON-BMP-VTRA-012675 | 2019-07-04 | FOR BAPCO REVIEW | 2019-07-19 |  |  | CLASS 2
076551C-000R-MR-0710-001 | MATERIAL REQUISITION FOR H.P. AND SPECIAL MATERIALS AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0010 | 018-E-DAT-00061-001 | 018-E-DAT-40061-001 | EQPT FILLED-IN DATA SHEET 018E0010 (EX BAPCO N.018-EDAT- 00061-001) | A1001 | BX | 2 | 2019-02-12 | CON-BMP-VTRA-010403 | 2019-02-12 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0710-001 | MATERIAL REQUISITION FOR H.P. AND SPECIAL MATERIALS AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0010 | 018-E-GAD-00005-001 | 018-E-GAD-40088-001 | STRUCTURE ASSEMBLY DRAWING 018E0010 | A2007 | CX | 2 | 2019-05-21 | CON-BMP-VTRA-011702 | 2019-05-21 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0710-001 | MATERIAL REQUISITION FOR H.P. AND SPECIAL MATERIALS AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0010 | 018-E-GAD-00017-001 | 018-E-GAD-40061-001 | GENERAL ARRANGEMENT DRAWING WITH FOUNDATION LOADING DATA 018E0010 (EX BAPCO N.018-E-GAD-00061-001) | A2001 | CX | 2 | 2019-07-04 | CON-BMP-VTRA-012674 | 2019-07-04 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0710-001 | MATERIAL REQUISITION FOR H.P. AND SPECIAL MATERIALS AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0010 | 018-E-GAD-00047-001 | 018-E-GAD-40047-001 | BUNDLE SCREEN DWG 018E0010 | A1109 | 0X | 3 | 2019-07-05 | CON-BMP-VTRA-012677 | 2019-07-05 | FOR BAPCO REVIEW | 2019-07-19 |  |  | CLASS 2
076551C-000R-MR-0710-001 | MATERIAL REQUISITION FOR H.P. AND SPECIAL MATERIALS AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0010 | 018-E-GAD-00052-001 | 018-E-GAD-40052-001 | PERSONAL PROTECTION GUARD DWG 018E0010 | A1109 | BX | 2 | 2019-07-04 | CON-BMP-VTRA-012672 | 2019-07-04 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0710-001 | MATERIAL REQUISITION FOR H.P. AND SPECIAL MATERIALS AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0010 | 018-E-GAD-00057-001 | 018-E-GAD-00057-001 | HEAT EXCHANGER CONSTRUCTION DWG 018E010 (HEADER DETAIL DRAWING) | A1103 | BX | 2 | 2019-06-05 | CON-BMP-VTRA-012005 | 2019-06-05 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0710-001 | MATERIAL REQUISITION FOR H.P. AND SPECIAL MATERIALS AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0010 | 018-E-GAD-40102-001 | 018-E-GAD-40443-001 | ROTATING ASSEMBLY DRAWING 018E0010 | A2007 | BX | 2 | 2019-06-26 | CON-BMP-VTRA-012513 | 2019-06-26 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0710-001 | MATERIAL REQUISITION FOR H.P. AND SPECIAL MATERIALS AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0010 | 018-E-PLD-00003-001 | 018-E-PLD-40003-001 | WALKWAY ASSEMBLY DRAWING 018E0010 | A2008 | BX | 2 | 2019-05-14 | CON-BMP-VTRA-011560 | 2019-05-14 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0710-001 | MATERIAL REQUISITION FOR H.P. AND SPECIAL MATERIALS AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0030 | 000-E-PQP-40005-001 | 018-E-PQP-40047-001 | FABRICATION AND QUALITY CONTROL PLAN 018E0030 AIR COOLER | B1002 | 0AX | 3 | 2019-06-05 | CON-BMP-VTRA-011996 | 2019-06-05 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0710-001 | MATERIAL REQUISITION FOR H.P. AND SPECIAL MATERIALS AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0030 | 000-E-PQP-60007-001 | 018-E-MCD-40084-001 | WELDING BOOK (MAP PROCEDURE QUALIFICATION REPORT) 018E0030 | B1304 | AX | 2 | 2019-03-08 | CON-BMP-VTRA-010633 | 2019-03-08 | FOR BAPCO REVIEW | 2019-03-25 | 2019-03-19 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000345 | CLASS 2
076551C-000R-MR-0710-001 | MATERIAL REQUISITION FOR H.P. AND SPECIAL MATERIALS AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0030 | 018-E-CAL-00004-001 | 018-E-CAL-40004-001 | MECHANICAL STRENGTH CALCULATION 018E030 | A1003 | BX | 2 | 2019-06-05 | CON-BMP-VTRA-012002 | 2019-06-05 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0710-001 | MATERIAL REQUISITION FOR H.P. AND SPECIAL MATERIALS AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0030 | 018-E-CAL-00009-001 | 018-E-CAL-40009-001 | THERMAL RATING FOR HEAT EXCHANGERS 018E0030 (EX BAPCO N.018-E-CAL-00009-001) | A1012 | BX | 2 | 2019-02-13 | CON-BMP-VTRA-010420 | 2019-02-13 | FOR BAPCO REVIEW | 2019-02-28 | 2019-03-05 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000253 | CLASS 2
076551C-000R-MR-0710-001 | MATERIAL REQUISITION FOR H.P. AND SPECIAL MATERIALS AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0030 | 018-E-CAL-00014-001 | 018-E-CAL-40014-001 | STRUCTURE STEEL CALCULATION NOTE 018E0030 (EX BAPCO N.018- E-CAL-00014-001) | A2201 | 0X | 3 | 2019-07-04 | CON-BMP-VTRA-012675 | 2019-07-04 | FOR BAPCO REVIEW | 2019-07-19 |  |  | CLASS 2
076551C-000R-MR-0710-001 | MATERIAL REQUISITION FOR H.P. AND SPECIAL MATERIALS AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0030 | 018-E-DAT-00062-001 | 018-E-DAT-40062-001 | EQPT FILLED-IN DATA SHEET 018E0030 (EX BAPCO N.018-EDAT- 00062-001) | A1001 | BX | 2 | 2019-02-12 | CON-BMP-VTRA-010403 | 2019-02-12 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0710-001 | MATERIAL REQUISITION FOR H.P. AND SPECIAL MATERIALS AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0030 | 018-E-GAD-00006-001 | 018-E-GAD-40089-001 | STRUCTURE ASSEMBLY DRAWING 018E0030 | A2007 | CX | 2 | 2019-05-21 | CON-BMP-VTRA-011702 | 2019-05-21 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0710-001 | MATERIAL REQUISITION FOR H.P. AND SPECIAL MATERIALS AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0030 | 018-E-GAD-00048-001 | 018-E-GAD-40048-001 | BUNDLE SCREEN DWG 018E0030 | A1109 | 0X | 3 | 2019-07-05 | CON-BMP-VTRA-012677 | 2019-07-05 | FOR BAPCO REVIEW | 2019-07-19 |  |  | CLASS 2
076551C-000R-MR-0710-001 | MATERIAL REQUISITION FOR H.P. AND SPECIAL MATERIALS AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0030 | 018-E-GAD-00053-001 | 018-E-GAD-40053-001 | PERSONAL PROTECTION GUARD DWG 018E0030 | A1109 | BX | 2 | 2019-07-04 | CON-BMP-VTRA-012672 | 2019-07-04 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0710-001 | MATERIAL REQUISITION FOR H.P. AND SPECIAL MATERIALS AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0030 | 018-E-GAD-00058-001 | 018-E-GAD-40058-001 | HEAT EXCHANGER CONSTRUCTION DWG 018E030 (HEADER DETAIL DRAWING) (EX BAPCO N.018-E-GAD-00058-001) | A1103 | CX | 2 | 2019-06-05 | CON-BMP-VTRA-012005 | 2019-06-05 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0710-001 | MATERIAL REQUISITION FOR H.P. AND SPECIAL MATERIALS AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0030 | 018-E-GAD-40103-001 | 018-E-GAD-40444-001 | ROTATING ASSEMBLY DRAWING 018E0030 | A2007 | BX | 2 | 2019-06-26 | CON-BMP-VTRA-012513 | 2019-06-26 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0710-001 | MATERIAL REQUISITION FOR H.P. AND SPECIAL MATERIALS AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0030 | 018-E-PLD-00004-001 | 018-E-PLD-40004-001 | WALKWAY ASSEMBLY DRAWING 018E0030 | A2008 | BX | 2 | 2019-05-14 | CON-BMP-VTRA-011560 | 2019-05-14 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0710-001 | MATERIAL REQUISITION FOR H.P. AND SPECIAL MATERIALS AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E1005 | 000-E-PQP-40006-001 | 018-E-PQP-40048-001 | FABRICATION AND QUALITY CONTROL PLAN 018E1005/018E2005 | B1002 | 0X | 3 | 2019-05-08 | CON-BMP-VTRA-011471 | 2019-05-08 | FOR BAPCO REVIEW | 2019-05-22 | 2019-05-19 | 1-APPROVED BMP-ROC-VTRE-000705 | CLASS 2
076551C-000R-MR-0710-001 | MATERIAL REQUISITION FOR H.P. AND SPECIAL MATERIALS AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E1005 | 000-E-PQP-60008-001 | 018-E-MCD-40085-001 | WELDING BOOK (MAP, PROCEDURE, QUALIFICATION REPORT) 018E1005 018E2005 | B1304 | BX | 2 | 2019-04-03 | CON-BMP-VTRA-010990 | 2019-04-03 | FOR BAPCO REVIEW | 2019-04-18 | 2019-04-15 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000521 | CLASS 2
076551C-000R-MR-0710-001 | MATERIAL REQUISITION FOR H.P. AND SPECIAL MATERIALS AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E1005 | 018-E-CAL-00005-001 | 018-E-CAL-40005-001 | MECHANICAL STRENGTH CALCULATION 018E1005/018E2005 | A1003 | BX | 2 | 2019-06-05 | CON-BMP-VTRA-012002 | 2019-06-05 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0710-001 | MATERIAL REQUISITION FOR H.P. AND SPECIAL MATERIALS AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E1005 | 018-E-CAL-00010-001 | 018-E-CAL-40010-001 | THERMAL RATING FOR HEAT EXCHANGERS 018E1005/018E2005 (EX BAPCO N.018-E-CAL-00010- 001) | A1012 | BX | 2 | 2019-02-13 | CON-BMP-VTRA-010419 | 2019-02-13 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0710-001 | MATERIAL REQUISITION FOR H.P. AND SPECIAL MATERIALS AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E1005 | 018-E-CAL-00015-001 | 018-E-CAL-40015-001 | STRUCTURE STEEL CALCULATION NOTE 018E1005/018E2005 (EX BAPCO N.018-E-CAL-00015-001) | A2201 | 0X | 3 | 2019-07-04 | CON-BMP-VTRA-012675 | 2019-07-04 | FOR BAPCO REVIEW | 2019-07-19 |  |  | CLASS 2
076551C-000R-MR-0710-001 | MATERIAL REQUISITION FOR H.P. AND SPECIAL MATERIALS AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E1005 | 018-E-DAT-00063-001 | 018-E-DAT-40063-001 | EQPT FILLED-IN DATA SHEET 018E1005 018E2005 (EX BAPCO N.018-E-DAT-00063-001) | A1001 | BX | 2 | 2019-02-12 | CON-BMP-VTRA-010403 | 2019-02-12 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0710-001 | MATERIAL REQUISITION FOR H.P. AND SPECIAL MATERIALS AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E1005 | 018-E-GAD-00007-001 | 018-E-GAD-40090-001 | STRUCTURE ASSEMBLY DRAWING 018E1005/018E2005 | A2007 | CX | 2 | 2019-05-21 | CON-BMP-VTRA-011702 | 2019-05-21 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0710-001 | MATERIAL REQUISITION FOR H.P. AND SPECIAL MATERIALS AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E1005 | 018-E-GAD-00018-001 | 018-E-GAD-40062-001 | GENERAL ARRANGEMENT DRAWING WITH FOUNDATION LOADING DATA 018E1005 018E2005 (EX BAPCO N. 018-E-GAD-00062-001) | A2001 | CX | 2 | 2019-07-04 | CON-BMP-VTRA-012674 | 2019-07-04 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0710-001 | MATERIAL REQUISITION FOR H.P. AND SPECIAL MATERIALS AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E1005 | 018-E-GAD-00049-001 | 018-E-GAD-40049-001 | BUNDLE SCREEN DWG 018E1005/018E2005 | A1109 | 0X | 3 | 2019-07-05 | CON-BMP-VTRA-012677 | 2019-07-05 | FOR BAPCO REVIEW | 2019-07-19 |  |  | CLASS 2
076551C-000R-MR-0710-001 | MATERIAL REQUISITION FOR H.P. AND SPECIAL MATERIALS AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E1005 | 018-E-GAD-00054-001 | 018-E-GAD-40054-001 | PERSONAL PROTECTION GUARD DWG 018E1005/018E2005 | A1109 | BX | 2 | 2019-07-04 | CON-BMP-VTRA-012672 | 2019-07-04 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0710-001 | MATERIAL REQUISITION FOR H.P. AND SPECIAL MATERIALS AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E1005 | 018-E-GAD-00059-001 | 018-E-GAD-00059-001 | HEAT EXCHANGER CONSTRUCTION DWG 018E1005 018E2005 (HEADER DETAIL DRAWING) | A1103 | BX | 2 | 2019-06-05 | CON-BMP-VTRA-012005 | 2019-06-05 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0710-001 | MATERIAL REQUISITION FOR H.P. AND SPECIAL MATERIALS AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E1005 | 018-E-GAD-40104-001 | 018-E-GAD-40445-001 | ROTATING ASSEMBLY DRAWING 018E1005/018E2005 | A2007 | BX | 2 | 2019-06-26 | CON-BMP-VTRA-012513 | 2019-06-26 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0710-001 | MATERIAL REQUISITION FOR H.P. AND SPECIAL MATERIALS AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E1005 | 018-E-PLD-00005-001 | 018-E-PLD-40005-001 | WALKWAY ASSEMBLY DRAWING 018E1005 018E2005 | A2008 | BX | 2 | 2019-05-14 | CON-BMP-VTRA-011560 | 2019-05-14 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0710-001 | MATERIAL REQUISITION FOR H.P. AND SPECIAL MATERIALS AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E2005 | 018-E-DAT-00070-001 | 018-E-DAT-40072-001 | EQPT FILLED-IN DATA SHEET 018E2005 | A1001 | BX | 2 | 2019-05-31 | CON-BMP-VTRA-011886 | 2019-05-31 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0710-001 | MATERIAL REQUISITION FOR H.P. AND SPECIAL MATERIALS AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 021E0010 | 000-E-PQP-40007-001 | 021-E-PQP-40024-001 | FABRICATION AND QUALITY CONTROL PLAN 021E0010 | B1002 | 0X | 3 | 2019-05-08 | CON-BMP-VTRA-011471 | 2019-05-08 | FOR BAPCO REVIEW | 2019-05-22 | 2019-05-19 | 1-APPROVED BMP-ROC-VTRE-000705 | CLASS 2
076551C-000R-MR-0710-001 | MATERIAL REQUISITION FOR H.P. AND SPECIAL MATERIALS AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 021E0010 | 000-E-PQP-60009-001 | 021-E-MCD-40030-001 | WELDING BOOK (MAP PROCEDURE QUALIFICATION REPORT) 021E0010 | B1304 | AX | 2 | 2019-03-08 | CON-BMP-VTRA-010633 | 2019-03-08 | FOR BAPCO REVIEW | 2019-03-25 | 2019-03-19 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000345 | CLASS 2
076551C-000R-MR-0710-001 | MATERIAL REQUISITION FOR H.P. AND SPECIAL MATERIALS AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 021E0010 | 021-E-CAL-00001-001 | 021-E-CAL-40001-001 | MECHANICAL STRENGTH CALCULATION 021E0010 | A1003 | BX | 2 | 2019-06-05 | CON-BMP-VTRA-012002 | 2019-06-05 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0710-001 | MATERIAL REQUISITION FOR H.P. AND SPECIAL MATERIALS AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 021E0010 | 021-E-CAL-00002-001 | 021-E-CAL-40002-001 | THERMAL RATING FOR HEAT EXCHANGERS 021E0010 (EX BAPCO N.021-E-CAL-00002-001) | A1012 | CX | 2 | 2019-06-21 | CON-BMP-VTRA-012358 | 2019-06-21 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0710-001 | MATERIAL REQUISITION FOR H.P. AND SPECIAL MATERIALS AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 021E0010 | 021-E-CAL-00004-001 | 021-E-CAL-40004-001 | STRUCTURE STEEL CALCULATION NOTE 021E0010 (EX BAPCO N.021- E-CAL-00004-001) | A2201 | 0X | 3 | 2019-07-04 | CON-BMP-VTRA-012676 | 2019-07-04 | FOR BAPCO REVIEW | 2019-07-19 |  |  | CLASS 2
076551C-000R-MR-0710-001 | MATERIAL REQUISITION FOR H.P. AND SPECIAL MATERIALS AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 021E0010 | 021-E-DAT-00021-001 | 021-E-DAT-40021-001 | EQPT FILLED-IN DATA SHEET 021E0010 (EX BAPCO N.021-EDAT- 00021-001) | A1001 | CX | 2 | 2019-06-21 | CON-BMP-VTRA-012356 | 2019-06-21 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0710-001 | MATERIAL REQUISITION FOR H.P. AND SPECIAL MATERIALS AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 021E0010 | 021-E-GAD-00001-001 | 021-E-GAD-40033-001 | STRUCTURE ASSEMBLY DRAWING 021E0010 | A2007 | CX | 2 | 2019-05-21 | CON-BMP-VTRA-011702 | 2019-05-21 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0710-001 | MATERIAL REQUISITION FOR H.P. AND SPECIAL MATERIALS AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 021E0010 | 021-E-GAD-00007-001 | 021-E-GAD-40021-001 | GENERAL ARRANGEMENT DRAWING WITH FOUNDATION LOADING DATA 021E0010 021E0011 (EX BAPCO N.021-E-GAD-00021-001) | A2001 | BX | 2 | 2019-02-20 | CON-BMP-VTRA-010472 | 2019-02-20 | FOR BAPCO REVIEW | 2019-03-06 | 2019-03-08 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000275 | CLASS 2
076551C-000R-MR-0710-001 | MATERIAL REQUISITION FOR H.P. AND SPECIAL MATERIALS AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 021E0010 | 021-E-GAD-00017-001 | 021-E-GAD-40017-001 | PERSONAL PROTECTION GUARD DWG 021E0010 | A1109 | BX | 2 | 2019-07-04 | CON-BMP-VTRA-012673 | 2019-07-04 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0710-001 | MATERIAL REQUISITION FOR H.P. AND SPECIAL MATERIALS AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 021E0010 | 021-E-GAD-00019-001 | 021-E-GAD-00019-001 | HEAT EXCHANGER CONSTRUCTION DWG 021E0010 (HEADER DETAIL DRAWING) | A1103 | BX | 2 | 2019-06-05 | CON-BMP-VTRA-012005 | 2019-06-05 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0710-001 | MATERIAL REQUISITION FOR H.P. AND SPECIAL MATERIALS AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 021E0010 | 021-E-GAD-40015-001 | 021-E-GAD-40015-001 | BUNDLE SCREEN DWG 021E0010 | A1109 | 0X | 3 | 2019-07-05 | CON-BMP-VTRA-012678 | 2019-07-05 | FOR BAPCO REVIEW | 2019-07-19 |  |  | CLASS 2
076551C-000R-MR-0710-001 | MATERIAL REQUISITION FOR H.P. AND SPECIAL MATERIALS AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 021E0010 | 021-E-GAD-40038-001 | 021-E-GAD-40159-001 | ROTATING ASSEMBLY DRAWING 021E0010 | A2007 | BX | 2 | 2019-06-26 | CON-BMP-VTRA-012512 | 2019-06-26 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0710-001 | MATERIAL REQUISITION FOR H.P. AND SPECIAL MATERIALS AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 021E0010 | 021-E-PLD-00001-001 | 021-E-PLD-40001-001 | WALKWAY ASSEMBLY DRAWING 021E0010 | A2008 | BX | 2 | 2019-05-15 | CON-BMP-VTRA-011617 | 2019-05-15 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0710-001 | MATERIAL REQUISITION FOR H.P. AND SPECIAL MATERIALS AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 021E0011 | 000-E-MCD-60007-010 | 021-E-MCD-40029-001 | WELDING BOOK (MAP PROCEDURE QUALIFICATION REPORT) 021E0011 | B1304 | AX | 2 | 2019-02-25 | CON-BMP-VTRA-010497 | 2019-02-25 | FOR BAPCO REVIEW | 2019-03-12 | 2019-03-07 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000260 | CLASS 2
076551C-000R-MR-0710-001 | MATERIAL REQUISITION FOR H.P. AND SPECIAL MATERIALS AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 021E0011 | 000-E-PQP-40008-001 | 021-E-PQP-40025-001 | FABRICATION AND QUALITY CONTROL PLAN 021E0011 | B1002 | 0X | 3 | 2019-05-08 | CON-BMP-VTRA-011471 | 2019-05-08 | FOR BAPCO REVIEW | 2019-05-22 | 2019-05-19 | 1-APPROVED BMP-ROC-VTRE-000705 | CLASS 2
076551C-000R-MR-0710-001 | MATERIAL REQUISITION FOR H.P. AND SPECIAL MATERIALS AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 021E0011 | 021-E-CAL-00003-001 | 021-E-CAL-40003-001 | THERMAL RATING FOR HEAT EXCHANGERS 021E0011 (EX BAPCO N.021-E-CAL-00003-001) | A1012 | CX | 2 | 2019-06-25 | CON-BMP-VTRA-012433 | 2019-06-25 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0710-001 | MATERIAL REQUISITION FOR H.P. AND SPECIAL MATERIALS AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 021E0011 | 021-E-CAL-00005-001 | 021-E-CAL-40005-001 | STRUCTURE STEEL CALCULATION NOTE 021E0011 (EX BAPCO N.021- E-CAL-00005-001) | A2201 | 0X | 3 | 2019-07-04 | CON-BMP-VTRA-012676 | 2019-07-04 | FOR BAPCO REVIEW | 2019-07-19 |  |  | CLASS 2
076551C-000R-MR-0710-001 | MATERIAL REQUISITION FOR H.P. AND SPECIAL MATERIALS AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 021E0011 | 021-E-CAL-00006-001 | 021-E-CAL-40006-001 | MECHANICAL STRENGTH CALCULATION 021E0011 | A1003 | BX | 2 | 2019-06-05 | CON-BMP-VTRA-012002 | 2019-06-05 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0710-001 | MATERIAL REQUISITION FOR H.P. AND SPECIAL MATERIALS AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 021E0011 | 021-E-DAT-00022-001 | 021-E-DAT-40022-001 | EQPT FILLED-IN DATA SHEET 021E0011 (EX BAPCO N. 021-E-DAT-00022-001) | A1001 | BX | 2 | 2019-06-21 | CON-BMP-VTRA-012357 | 2019-06-21 | FOR BAPCO REVIEW | 2019-07-05 | 2019-07-11 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001301 | CLASS 2
076551C-000R-MR-0710-001 | MATERIAL REQUISITION FOR H.P. AND SPECIAL MATERIALS AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 021E0011 | 021-E-GAD-00002-001 | 021-E-GAD-40034-001 | STRUCTURE ASSEMBLY DRAWING 021E0011 | A2007 | CX | 2 | 2019-05-21 | CON-BMP-VTRA-011702 | 2019-05-21 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0710-001 | MATERIAL REQUISITION FOR H.P. AND SPECIAL MATERIALS AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 021E0011 | 021-E-GAD-00016-001 | 021-E-GAD-40016-001 | BUNDLE SCREEN DWG 021E0011 | A1109 | 0X | 3 | 2019-07-05 | CON-BMP-VTRA-012678 | 2019-07-05 | FOR BAPCO REVIEW | 2019-07-19 |  |  | CLASS 2
076551C-000R-MR-0710-001 | MATERIAL REQUISITION FOR H.P. AND SPECIAL MATERIALS AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 021E0011 | 021-E-GAD-00018-001 | 021-E-GAD-40018-001 | PERSONAL PROTECTION GUARD DWG 021E0011 | A1109 | BX | 2 | 2019-07-04 | CON-BMP-VTRA-012673 | 2019-07-04 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0710-001 | MATERIAL REQUISITION FOR H.P. AND SPECIAL MATERIALS AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 021E0011 | 021-E-GAD-00020-001 | 021-E-GAD-40020-001 | HEAT EXCHANGER CONSTRUCTION DWG 021E0011 (HEADER DETAIL DRAWING) (EX BAPCO N.021-E-GAD-00020-001) | A1103 | CX | 2 | 2019-06-05 | CON-BMP-VTRA-012005 | 2019-06-05 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0710-001 | MATERIAL REQUISITION FOR H.P. AND SPECIAL MATERIALS AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 021E0011 | 021-E-GAD-40039-001 | 021-E-GAD-40160-001 | ROTATING ASSEMBLY DRAWING 021E0011 | A2007 | BX | 2 | 2019-06-26 | CON-BMP-VTRA-012512 | 2019-06-26 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0710-001 | MATERIAL REQUISITION FOR H.P. AND SPECIAL MATERIALS AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 021E0011 | 021-E-PLD-00002-001 | 021-E-PLD-40002-001 | WALKWAY ASSEMBLY DRAWING 021E0011 | A2008 | BX | 2 | 2019-05-15 | CON-BMP-VTRA-011617 | 2019-05-15 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0710-002 | MATERIAL REQUISITION FOR AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0011 | 000-E-CAL-60002-001 | 000-E-CAL-40002-001 | LIFTING FRAME CALCULATION AND DRAWING FOR AIR COOLERS ALL ITEMS | A2201 | AX | 2 | 2019-06-27 | CON-BMP-VTRA-012529 | 2019-06-27 | FOR BAPCO REVIEW | 2019-07-11 |  |  | CLASS 2
076551C-000R-MR-0710-002 | MATERIAL REQUISITION FOR AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0011 | 000-E-DAT-60008-001 | 000-E-DAT-40008-001 | FAN DATA SHEET WITH PERFORMANCE CUREVES FOR AIR COOLER ALL ITEMS | A1002 | 0AX | 3 | 2019-07-02 | CON-BMP-VTRA-012627 | 2019-07-03 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0710-002 | MATERIAL REQUISITION FOR AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0011 | 000-E-DAT-60009-001 | 000-E-DAT-40009-001 | BELT AND PULLEY DATA SHEET ALL ITEMS | A1006 | 0AX | 3 | 2019-07-03 | CON-BMP-VTRA-012630 | 2019-07-03 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0710-002 | MATERIAL REQUISITION FOR AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0011 | 000-E-DAT-60010-001 | 000-E-DAT-40010-001 | NOISE DATA SHEET ALL ITEMS | A0105 | BX | 2 | 2019-06-10 | CON-BMP-VTRA-012109 | 2019-06-10 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0710-002 | MATERIAL REQUISITION FOR AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0011 | 000-E-DAT-60011-001 | 000-E-DAT-40011-001 | INSTRUMENT LIST AND DATA SHEET ALL ITEMS | A3101 | BX | 2 | 2019-05-10 | CON-BMP-VTRA-011516 | 2019-05-10 | FOR BAPCO REVIEW | 2019-05-24 | 2019-05-27 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000806 | CLASS 2
076551C-000R-MR-0710-002 | MATERIAL REQUISITION FOR AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0011 | 000-E-DAT-60012-001 | 000-E-DAT-40012-001 | MOTOR DATA SHEET & DRAWING 018E0011 018E0012A/B 018E0015/19/23/35 021E0012/16 051E0001A/B 371E0001 | A4102 | BX | 2 | 2019-06-11 | CON-BMP-VTRA-012154 | 2019-06-11 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0710-002 | MATERIAL REQUISITION FOR AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0011 | 000-E-DAT-60013-001 | 000-E-DAT-40013-001 | VSD PANEL DATA SHEET & DRAWING018E0011 018E0012A/B 018E0015/19/23/35 021E0012/16 051E0001A/B 371E0001 | A4102 | BX | 2 | 2019-06-24 | CON-BMP-VTRA-012401 | 2019-06-24 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0710-002 | MATERIAL REQUISITION FOR AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0011 | 000-E-DAT-60014-001 | 000-E-INX-40014-001 | SPECIAL TOOL LIST 018E0011 018E0012A/B 018E0015/19/23/35 021E0012/16 051E0001A/B 371E0001 | A5008 | 0X | 2 | 2019-06-26 | CON-BMP-VTRA-012468 | 2019-06-26 | FOR BAPCO REVIEW | 2019-07-10 | 2019-07-11 | 3-REVIEWED WITH COMMENTS BMP-ROC-VTRE-001296 | CLASS 2
076551C-000R-MR-0710-002 | MATERIAL REQUISITION FOR AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0011 | 000-E-DAT-60016-001 | 000-E-INX-40016-001 | INSTRUMENT LIST ALL ITEMS | A3004 | AX | 2 | 2019-05-14 | CON-BMP-VTRA-011574 | 2019-05-14 | FOR BAPCO REVIEW | 2019-05-29 | 2019-05-30 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000847 | CLASS 2
076551C-000R-MR-0710-002 | MATERIAL REQUISITION FOR AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0011 | 000-E-DLB-60002-001 | 000-E-DLB-40002-001 | NAMEPLATE DWG ALL ITEMS (EX BAPCO N. 000-E-DLB-60002-001) | A1112 | BX | 2 | 2019-05-21 | CON-BMP-VTRA-011705 | 2019-05-21 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0710-002 | MATERIAL REQUISITION FOR AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0011 | 000-E-GAD-60009-001 | 000-E-GAD-40009-001 | MOTOR DRAWINGS 018E0011 018E0012A/B 018E0015/19/23/35 021E0012/16 051E0001A/B 371E0001 | A4207 | BX | 2 | 2019-06-24 | CON-BMP-VTRA-012400 | 2019-06-24 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0710-002 | MATERIAL REQUISITION FOR AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0011 | 000-E-INV-60002-001 | 000-E-INV-40006-001 | UNPRICED COPY OF MAIN SUBORDERS FOR AIR COOLER ALL ITEMS | C1005 | AX | 2 | 2019-06-26 | CON-BMP-VTRA-012516 | 2019-06-26 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-0710-002 | MATERIAL REQUISITION FOR AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0011 | 000-E-INX-60006-001 | 000-E-INX-40011-001 | ELECTRICAL CONSUMER LIST FOR UNIT 018 & 021 & 051 &371 HEAT EXCHANGERS AIR FAN MOTORS ALL ITEMS | A4001 | BX | 2 | 2019-04-18 | CON-BMP-VTRA-011224 | 2019-04-18 | FOR BAPCO REVIEW | 2019-05-06 | 2019-05-08 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000633 | CLASS 2
076551C-000R-MR-0710-002 | MATERIAL REQUISITION FOR AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0011 | 000-E-MCD-60004-001 | 018-E-MCD-40086-001 | WELDING BOOK (MAP PROCEDURE QUALIFICATION REPORT) 018E0011 | B1304 | AX | 2 | 2019-02-25 | CON-BMP-VTRA-010506 | 2019-02-25 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0710-002 | MATERIAL REQUISITION FOR AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0011 | 000-E-MRS-60002-001 | 000-E-MRS-40002-001 | MONTHLY PROGRESS REPORT FOR AIR COOLER ALL ITEMS (EX BAPCO N.000-E-MRS-60002-001) | C1002 | FX | 2 | 2019-06-26 | CON-BMP-VTRA-012517 | 2019-06-26 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-0710-002 | MATERIAL REQUISITION FOR AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0011 | 000-E-PLD-60002-001 | 000-E-PLD-40002-001 | WALKWAY STANDARD DRAWING ALL ITEMS | A2008 | BX | 2 | 2019-05-14 | CON-BMP-VTRA-011563 | 2019-05-14 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0710-002 | MATERIAL REQUISITION FOR AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0011 | 000-E-PLD-60010-001 | 000-E-SCH-40005-001 | ENGINEERING PROCUREMENT MANUFACTURING & TEST SCHEDULE ALL ITEMS | C1001 | AX | 2 | 2019-01-29 | CON-BMP-VTRA-010307 | 2019-01-29 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-0710-002 | MATERIAL REQUISITION FOR AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0011 | 000-E-PQP-40002-001 | 018-E-PQP-40049-001 | FABRICATION AND QUALITY CONTROL PLAN 018E0011 | B1002 | 0AX | 3 | 2019-06-05 | CON-BMP-VTRA-012000 | 2019-06-05 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0710-002 | MATERIAL REQUISITION FOR AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0011 | 000-E-PQS-60002-001 | 000-E-PQS-40002-001 | SUB-VENDOR'S AND MAIN SUPPLIER'S LIST ALL ITEMS | B1401 | BX | 2 | 2019-02-19 | CON-BMP-VTRA-010464 | 2019-02-19 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0710-002 | MATERIAL REQUISITION FOR AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0011 | 000-E-PRO-40007-001 | 000-E-PRO-40023-001 | HYDROSTATIC TEST PROCEDURE ALL ITEMS | B1103 | AX | 2 | 2019-03-25 | CON-BMP-VTRA-011229 | 2019-04-18 | FOR BAPCO REVIEW | 2019-05-06 | 2019-05-02 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000630 | CLASS 2
076551C-000R-MR-0710-002 | MATERIAL REQUISITION FOR AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0011 | 000-E-PRO-60004-001 | 000-E-PRO-40004-001 | TESTING PROCEDURES ALL ITEMS | B1103 | 0X | 2 | 2019-06-17 | CON-BMP-VTRA-012238 | 2019-06-17 | FOR BAPCO REVIEW | 2019-07-01 | 2019-06-30 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001105 | CLASS 2
076551C-000R-MR-0710-002 | MATERIAL REQUISITION FOR AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0011 | 000-E-PRO-60005-001 | 000-E-PRO-40005-001 | PWHT PROCEDURE FOR AIR COOLER ALL ITEMS | B1201 | BX | 2 | 2019-07-04 | CON-BMP-VTRA-012657 | 2019-07-04 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0710-002 | MATERIAL REQUISITION FOR AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0011 | 000-E-PRO-60006-001 | 000-E-PRO-40006-001 | NDT PROCEDURE ALL ITEMS | B1202 | AX | 2 | 2019-05-23 | CON-BMP-VTRA-011764 | 2019-05-23 | FOR BAPCO REVIEW | 2019-06-07 | 2019-06-04 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000873 | CLASS 2
076551C-000R-MR-0710-002 | MATERIAL REQUISITION FOR AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0011 | 000-E-TSP-60004-001 | 000-E-TSP-40004-001 | PAINTING SPECIFICATION ALL ITEMS | A0106 | BX | 2 | 2019-06-03 | CON-BMP-VTRA-011943 | 2019-06-03 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0710-002 | MATERIAL REQUISITION FOR AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0011 | 000-E-TSP-60005-001 | 000-E-TSP-40005-001 | LUBRICANT LIST FOR AIR COOLER ALL ITEMS | A1015 | 0X | 2 | 2019-06-06 | CON-BMP-VTRA-012032 | 2019-06-06 | FOR BAPCO REVIEW | 2019-06-20 | 2019-07-01 | 3-REVIEWED WITH COMMENTS BMP-ROC-VTRE-001130 | CLASS 2
076551C-000R-MR-0710-002 | MATERIAL REQUISITION FOR AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0011 | 000-E-TSP-6006-001 | 000-E-TSP-6006-001 | MATERIAL SPECIFICATION FOR MAIN SUB-ORDERS ALL ITEMS | B1203 | AX | 2 | 2018-12-07 | CON-BMP-VTRA-010129 | 2018-12-07 | FOR BAPCO REVIEW | 2018-12-22 | 2018-12-20 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000084 | CLASS 2
076551C-000R-MR-0710-002 | MATERIAL REQUISITION FOR AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0011 | 018-E-CAL-00016-001 | 018-E-CAL-40016-001 | MECHANICAL STRENGTH CALCULATION 018E0011 | A1003 | BX | 2 | 2019-07-03 | CON-BMP-VTRA-012652 | 2019-07-03 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0710-002 | MATERIAL REQUISITION FOR AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0011 | 018-E-CAL-00021-001 | 018-E-CAL-40021-001 | THERMAL RATING FOR HEAT EXCHANGERS 018E0011 (EX BAPCO N.018-E-CAL-00021-001) | A1012 | 0X | 3 | 2019-06-14 | CON-BMP-VTRA-012214 | 2019-06-14 | FOR BAPCO REVIEW | 2019-06-28 | 2019-07-08 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001198 | CLASS 2
076551C-000R-MR-0710-002 | MATERIAL REQUISITION FOR AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0011 | 018-E-CAL-00026-001 | 018-E-CAL-40026-001 | STRUCTURE STEEL CALCULATION NOTE 018E0011 (EX BAPCO N.018- E-CAL-00026-001) | A2201 | 0X | 3 | 2019-07-03 | CON-BMP-VTRA-012648 | 2019-07-03 | FOR BAPCO REVIEW | 2019-07-18 |  |  | CLASS 2
076551C-000R-MR-0710-002 | MATERIAL REQUISITION FOR AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0011 | 018-E-DAT-00064-001 | 018-E-DAT-40064-001 | EQPT FILLED-IN DATA SHEET 018E0011 (EX BAPCO N. 018-E-DAT-00064-001) | A1001 | 0X | 3 | 2019-06-06 | CON-BMP-VTRA-012075 | 2019-06-06 | FOR BAPCO REVIEW | 2019-06-21 | 2019-06-30 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001114 | CLASS 2
076551C-000R-MR-0710-002 | MATERIAL REQUISITION FOR AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0011 | 018-E-GAD-00040-001 | 018-E-GAD-40079-001 | GENERAL ARRANGEMENT DRAWING WITH FOUNDATION LOADING DATA 018E0011 (EX BAPCO N.018-E-GAD-00079-001) | A2001 | CX | 2 | 2019-07-04 | CON-BMP-VTRA-012666 | 2019-07-04 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0710-002 | MATERIAL REQUISITION FOR AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0011 | 018-E-GAD-00063-001 | 018-E-GAD-40063-001 | BUNDLE SCREEN DWG 018E0011 | A1109 | AX | 2 | 2019-05-14 | CON-BMP-VTRA-011568 | 2019-05-14 | FOR BAPCO REVIEW | 2019-05-29 | 2019-05-31 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000860 | CLASS 2
076551C-000R-MR-0710-002 | MATERIAL REQUISITION FOR AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0011 | 018-E-GAD-00068-001 | 018-E-GAD-40068-001 | PERSONAL PROTECTION GUARD DWG 018E0011 | A1109 | 0X | 3 | 2019-07-03 | CON-BMP-VTRA-012644 | 2019-07-03 | FOR BAPCO REVIEW | 2019-07-18 |  |  | CLASS 2
076551C-000R-MR-0710-002 | MATERIAL REQUISITION FOR AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0011 | 018-E-GAD-00074-001 | 018-E-GAD-40074-001 | HEAT EXCHANGER CONSTRUCTION DWG 018E0011 HEADER DETAIL DRAWING (EX BAPCO N.018-E-GAD-00074-001) | A1103 | CX | 2 | 2019-07-04 | CON-BMP-VTRA-012660 | 2019-07-04 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0710-002 | MATERIAL REQUISITION FOR AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0011 | 018-E-GAD-00091-001 | 018-E-GAD-40091-001 | STRUCTURE ASSEMBLY DRAWING 018E0011 | A2007 | CX | 2 | 2019-05-21 | CON-BMP-VTRA-011703 | 2019-05-21 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0710-002 | MATERIAL REQUISITION FOR AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0011 | 018-E-GAD-40105-001 | 018-E-GAD-40446-001 | ROTATING ASSEMBLY DRAWING 018E0011 | A2007 | BX | 2 | 2019-06-27 | CON-BMP-VTRA-012531 | 2019-06-27 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0710-002 | MATERIAL REQUISITION FOR AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0011 | 018-E-INX-00003-001 | 000-E-INX-40003-001 | LIST OF VENDOR'S DOCUMENTS AND DWGS ALL ITEMS (EX BAPCO N.018-E-INX-60003-001) | A0001 | CX | 2 | 2019-05-08 | CON-BMP-VTRA-011475 | 2019-05-08 | FOR BAPCO REVIEW | 2019-05-22 | 2019-05-26 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000788 | CLASS 2
076551C-000R-MR-0710-002 | MATERIAL REQUISITION FOR AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0011 | 018-E-PLD-00006-001 | 018-E-PLD-40006-001 | WALKWAY ASSEMBLY DRAWING 018E0011 | A2008 | BX | 2 | 2019-05-14 | CON-BMP-VTRA-011563 | 2019-05-14 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0710-002 | MATERIAL REQUISITION FOR AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0011 | 3AKR502449996 OUTLINE DIAGRAM | 000-E-GAD-40011-001 | FRONT VIEW AND TYPICAL SECTIONDRAWINGS FOR VFD PANEL 018E0035/23/19/11 021E0016 | A4204 | AX | 2 | 2019-07-08 | CON-BMP-VTRA-012748 | 2019-07-08 | FOR BAPCO REVIEW | 2019-07-23 |  |  | CLASS 2
076551C-000R-MR-0710-002 | MATERIAL REQUISITION FOR AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0011 | 3AKR502449996 SINGLE LINE DIAGRAM | 000-E-CWD-40002-001 | WIRING DRAWINGS FOR VFD PANEL 018E0011/19/23/35 021E0016 | A4211 | AX | 2 | 2019-07-08 | CON-BMP-VTRA-012749 | 2019-07-08 | FOR BAPCO REVIEW | 2019-07-23 |  |  | CLASS 2
076551C-000R-MR-0710-002 | MATERIAL REQUISITION FOR AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0012A | 000-E-MCD-60011-001 | 018-E-MCD-40087-001 | WELDING BOOK(MAP PROCEDURE QUALIFICATION REPORT) 018E0012A/B | B1304 | AX | 2 | 2019-02-25 | CON-BMP-VTRA-010506 | 2019-02-25 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0710-002 | MATERIAL REQUISITION FOR AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0012A | 000-E-PQP-40009-001 | 018-E-PQP-40050-001 | FABRICATION AND QUALITY CONTROL PLAN 018E0012A/B | B1002 | 0AX | 3 | 2019-06-05 | CON-BMP-VTRA-012000 | 2019-06-05 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0710-002 | MATERIAL REQUISITION FOR AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0012A | 018-E-CAL-00017-001 | 018-E-CAL-40017-001 | MECHANICAL STRENGTH CALCULATION 018E0012A/B | A1003 | BX | 2 | 2019-07-03 | CON-BMP-VTRA-012652 | 2019-07-03 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0710-002 | MATERIAL REQUISITION FOR AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0012A | 018-E-CAL-00022-001 | 018-E-CAL-40022-001 | THERMAL RATING FOR HEAT EXCHANGERS 018E0012A/B (EX BAPCO N.018-E-CAL-00022-001) | A1012 | 0X | 3 | 2019-06-14 | CON-BMP-VTRA-012214 | 2019-06-14 | FOR BAPCO REVIEW | 2019-06-28 | 2019-07-08 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001198 | CLASS 2
076551C-000R-MR-0710-002 | MATERIAL REQUISITION FOR AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0012A | 018-E-CAL-00027-001 | 018-E-CAL-40027-001 | STRUCTURE STEEL CALCULATION NOTE 018E0012A/B (EX BAPCO N.018-E-CAL-00027-001) | A2201 | 0X | 3 | 2019-07-03 | CON-BMP-VTRA-012648 | 2019-07-03 | FOR BAPCO REVIEW | 2019-07-18 |  |  | CLASS 2
076551C-000R-MR-0710-002 | MATERIAL REQUISITION FOR AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0012A | 018-E-DAT-00065-001 | 018-E-DAT-40065-001 | EQPT FILLED-IN DATA SHEET 018E0012A/B (EX BAPCO N.018-EDAT-00065-001) | A1001 | 0X | 3 | 2019-06-06 | CON-BMP-VTRA-012075 | 2019-06-06 | FOR BAPCO REVIEW | 2019-06-21 | 2019-06-30 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001114 | CLASS 2
076551C-000R-MR-0710-002 | MATERIAL REQUISITION FOR AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0012A | 018-E-GAD-00041-001 | 018-E-GAD-40080-001 | GENERAL ARRANGEMENT DRAWING WITH FOUNDATION LOADING DATA 018E0012A/B (EX BAPCO N.018-E-GAD-00080-001) | A2001 | CX | 2 | 2019-07-04 | CON-BMP-VTRA-012666 | 2019-07-04 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0710-002 | MATERIAL REQUISITION FOR AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0012A | 018-E-GAD-00064-001 | 018-E-GAD-40064-001 | BUNDLE SCREEN DWG 018E0012A/B | A1109 | 0X | 3 | 2019-07-03 | CON-BMP-VTRA-012644 | 2019-07-03 | FOR BAPCO REVIEW | 2019-07-18 |  |  | CLASS 2
076551C-000R-MR-0710-002 | MATERIAL REQUISITION FOR AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0012A | 018-E-GAD-00069-001 | 018-E-GAD-40069-001 | PERSONAL PROTECTION GUARD DWG 018E0012A/B | A1109 | 0X | 3 | 2019-07-03 | CON-BMP-VTRA-012644 | 2019-07-03 | FOR BAPCO REVIEW | 2019-07-18 |  |  | CLASS 2
076551C-000R-MR-0710-002 | MATERIAL REQUISITION FOR AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0012A | 018-E-GAD-00075-001 | 018-E-GAD-40075-001 | HEAT EXCHANGER CONSTRUCTION DWG 018E0012A/B HEADER DETAIL DRAWING (EX BAPCO N.018-E-GAD-00075-001) | A1103 | CX | 2 | 2019-07-04 | CON-BMP-VTRA-012660 | 2019-07-04 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0710-002 | MATERIAL REQUISITION FOR AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0012A | 018-E-GAD-00092-001 | 018-E-GAD-40092-001 | STRUCTURE ASSEMBLY DRAWING 018E0012A/B | A2007 | CX | 2 | 2019-05-21 | CON-BMP-VTRA-011703 | 2019-05-21 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0710-002 | MATERIAL REQUISITION FOR AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0012A | 018-E-GAD-40106-001 | 018-E-GAD-40447-001 | ROTATING ASSEMBLY DRAWING 018E0012A/B | A2007 | BX | 2 | 2019-06-27 | CON-BMP-VTRA-012531 | 2019-06-27 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0710-002 | MATERIAL REQUISITION FOR AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0012A | 018-E-PLD-00007-001 | 018-E-PLD-40007-001 | WALKWAY ASSEMBLY DRAWING 018E0012A 018E0012B | A2008 | BX | 2 | 2019-05-14 | CON-BMP-VTRA-011563 | 2019-05-14 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0710-002 | MATERIAL REQUISITION FOR AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0015 | 000-E-MCD-60012-001 | 018-E-MCD-40088-001 | WELDING BOOK (MAP PROCEDURE QUALIFICATION REPORT) 018E0015 | B1304 | AX | 2 | 2019-02-25 | CON-BMP-VTRA-010506 | 2019-02-25 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0710-002 | MATERIAL REQUISITION FOR AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0015 | 000-E-PQP-40010-001 | 018-E-PQP-40051-001 | FABRICATION AND QUALITY CONTROL PLAN 018E0015 | B1002 | 0X | 3 | 2019-05-08 | CON-BMP-VTRA-011488 | 2019-05-08 | FOR BAPCO REVIEW | 2019-05-23 | 2019-05-19 | 1-APPROVED BMP-ROC-VTRE-000709 | CLASS 2
076551C-000R-MR-0710-002 | MATERIAL REQUISITION FOR AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0015 | 018-E-CAL-00018-001 | 018-E-CAL-40018-001 | MECHANICAL STRENGTH CALCULATION 018E0015 | A1003 | BX | 2 | 2019-07-03 | CON-BMP-VTRA-012652 | 2019-07-03 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0710-002 | MATERIAL REQUISITION FOR AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0015 | 018-E-CAL-00023-001 | 018-E-CAL-40023-001 | THERMAL RATING FOR HEAT EXCHANGERS 018E0015 (EX BAPCO N.018-E-CAL-00023-001) | A1012 | 0X | 3 | 2019-06-14 | CON-BMP-VTRA-012214 | 2019-06-14 | FOR BAPCO REVIEW | 2019-06-28 | 2019-07-08 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001198 | CLASS 2
076551C-000R-MR-0710-002 | MATERIAL REQUISITION FOR AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0015 | 018-E-CAL-00028-001 | 018-E-CAL-40028-001 | STRUCTURE STEEL CALCULATION NOTE 018E0015 (EX BAPCO N.018- E-CAL-00028-001) | A2201 | 0X | 3 | 2019-07-03 | CON-BMP-VTRA-012648 | 2019-07-03 | FOR BAPCO REVIEW | 2019-07-18 |  |  | CLASS 2
076551C-000R-MR-0710-002 | MATERIAL REQUISITION FOR AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0015 | 018-E-DAT-00066-001 | 018-E-DAT-40066-001 | EQPT FILLED-IN DATA SHEET 018E0015 (EX BAPCO N.018-EDAT- 00066-001) | A1001 | 0X | 3 | 2019-06-06 | CON-BMP-VTRA-012075 | 2019-06-06 | FOR BAPCO REVIEW | 2019-06-21 | 2019-06-30 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001114 | CLASS 2
076551C-000R-MR-0710-002 | MATERIAL REQUISITION FOR AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0015 | 018-E-GAD-00042-001 | 018-E-GAD-40081-001 | GENERAL ARRANGEMENT DRAWING WITH FOUNDATION LOADING DATA 018E0015/018E0035 (EX BAPCO N.018-E-GAD-00081-001) | A2001 | CX | 2 | 2019-07-04 | CON-BMP-VTRA-012666 | 2019-07-04 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0710-002 | MATERIAL REQUISITION FOR AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0015 | 018-E-GAD-00070-001 | 018-E-GAD-40070-001 | PERSONAL PROTECTION GUARD DWG 018E0015 | A1109 | 0X | 3 | 2019-07-03 | CON-BMP-VTRA-012644 | 2019-07-03 | FOR BAPCO REVIEW | 2019-07-18 |  |  | CLASS 2
076551C-000R-MR-0710-002 | MATERIAL REQUISITION FOR AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0015 | 018-E-GAD-00073-001 | 018-E-GAD-40073-001 | DETAILED DWGS FOR LOUVER 018E0015 | A1109 | BX | 2 | 2019-07-04 | CON-BMP-VTRA-012664 | 2019-07-04 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0710-002 | MATERIAL REQUISITION FOR AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0015 | 018-E-GAD-00076-001 | 018-E-GAD-40076-001 | HEAT EXCHANGER CONSTRUCTION DWG 018E0015 HEADER DETAIL DRAWING (EX BAPCO N.018-E-GAD-00076-001) | A1103 | CX | 2 | 2019-07-04 | CON-BMP-VTRA-012660 | 2019-07-04 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0710-002 | MATERIAL REQUISITION FOR AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0015 | 018-E-GAD-00093-001 | 018-E-GAD-40093-001 | STRUCTURE ASSEMBLY DRAWING 018E0015 | A2007 | CX | 2 | 2019-05-21 | CON-BMP-VTRA-011703 | 2019-05-21 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0710-002 | MATERIAL REQUISITION FOR AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0015 | 018-E-GAD-40107-001 | 018-E-GAD-40448-001 | ROTATING ASSEMBLY DRAWING 018E0015 | A2007 | BX | 2 | 2019-06-27 | CON-BMP-VTRA-012531 | 2019-06-27 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0710-002 | MATERIAL REQUISITION FOR AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0015 | 018-E-PLD-00008-001 | 018-E-PLD-40008-001 | WALKWAY ASSEMBLY DRAWING 018E0015 | A2008 | BX | 2 | 2019-05-14 | CON-BMP-VTRA-011563 | 2019-05-14 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0710-002 | MATERIAL REQUISITION FOR AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0019 | 000-E-MCD-60013-001 | 018-E-MCD-40089-001 | WELDING BOOK (MAP PROCEDURE QUALIFICATION REPORT) 018E0019 | B1304 | AX | 2 | 2019-02-25 | CON-BMP-VTRA-010506 | 2019-02-25 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0710-002 | MATERIAL REQUISITION FOR AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0019 | 000-E-PQP-40011-001 | 018-E-PQP-40052-001 | FABRICATION AND QUALITY CONTROL PLAN 018E0019 | B1002 | 0X | 3 | 2019-05-08 | CON-BMP-VTRA-011488 | 2019-05-08 | FOR BAPCO REVIEW | 2019-05-23 | 2019-05-19 | 1-APPROVED BMP-ROC-VTRE-000709 | CLASS 2
076551C-000R-MR-0710-002 | MATERIAL REQUISITION FOR AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0019 | 018-E-CAL-00019-001 | 018-E-CAL-40019-001 | MECHANICAL STRENGTH CALCULATION 018E0019 | A1003 | BX | 2 | 2019-07-03 | CON-BMP-VTRA-012652 | 2019-07-03 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0710-002 | MATERIAL REQUISITION FOR AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0019 | 018-E-CAL-00024-001 | 018-E-CAL-40024-001 | THERMAL RATING FOR HEAT EXCHANGERS 018E0019 (EX BAPCO N.018-E-CAL-00024-001) | A1012 | 0X | 3 | 2019-06-14 | CON-BMP-VTRA-012214 | 2019-06-14 | FOR BAPCO REVIEW | 2019-06-28 | 2019-07-08 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001198 | CLASS 2
076551C-000R-MR-0710-002 | MATERIAL REQUISITION FOR AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0019 | 018-E-CAL-00029-001 | 018-E-CAL-40029-001 | STRUCTURE STEEL CALCULATION NOTE 018E0019 (EX BAPCO N.018- E-CAL-00029-001) | A2201 | 0X | 3 | 2019-07-03 | CON-BMP-VTRA-012648 | 2019-07-03 | FOR BAPCO REVIEW | 2019-07-18 |  |  | CLASS 2
076551C-000R-MR-0710-002 | MATERIAL REQUISITION FOR AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0019 | 018-E-DAT-00067-001 | 018-E-DAT-40067-001 | EQPT FILLED-IN DATA SHEET 018E0019 (EX BAPCO N.018-EDAT- 00067-001) | A1001 | 0X | 3 | 2019-06-06 | CON-BMP-VTRA-012075 | 2019-06-06 | FOR BAPCO REVIEW | 2019-06-21 | 2019-06-30 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001114 | CLASS 2
076551C-000R-MR-0710-002 | MATERIAL REQUISITION FOR AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0019 | 018-E-GAD-00043-001 | 018-E-GAD-40082-001 | GENERAL ARRANGEMENT DRAWING WITH FOUNDATION LOADING DATA 018E0019 (EX BAPCO N.018-E-GAD-00082-001) | A2001 | CX | 2 | 2019-07-04 | CON-BMP-VTRA-012666 | 2019-07-04 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0710-002 | MATERIAL REQUISITION FOR AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0019 | 018-E-GAD-00066-001 | 018-E-GAD-40066-001 | BUNDLE SCREEN DWG 018E0019 | A1109 | 0X | 3 | 2019-07-03 | CON-BMP-VTRA-012644 | 2019-07-03 | FOR BAPCO REVIEW | 2019-07-18 |  |  | CLASS 2
076551C-000R-MR-0710-002 | MATERIAL REQUISITION FOR AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0019 | 018-E-GAD-00071-001 | 018-E-GAD-40071-001 | PERSONAL PROTECTION GUARD DWG 018E0019 | A1109 | 0X | 3 | 2019-07-03 | CON-BMP-VTRA-012644 | 2019-07-03 | FOR BAPCO REVIEW | 2019-07-18 |  |  | CLASS 2
076551C-000R-MR-0710-002 | MATERIAL REQUISITION FOR AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0019 | 018-E-GAD-00077-001 | 018-E-GAD-40077-001 | HEAT EXCHANGER CONSTRUCTION DWG 018E0019 HEADER DETAIL DRAWING (EX BAPCO N. 018-E-GAD-00077-001) | A1103 | CX | 2 | 2019-07-04 | CON-BMP-VTRA-012660 | 2019-07-04 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0710-002 | MATERIAL REQUISITION FOR AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0019 | 018-E-GAD-00094-001 | 018-E-GAD-40094-001 | STRUCTURE ASSEMBLY DRAWING 018E0019 | A2007 | CX | 2 | 2019-05-21 | CON-BMP-VTRA-011703 | 2019-05-21 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0710-002 | MATERIAL REQUISITION FOR AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0019 | 018-E-GAD-40108-001 | 018-E-GAD-40449-001 | ROTATING ASSEMBLY DRAWING 018E0019 | A2007 | BX | 2 | 2019-06-27 | CON-BMP-VTRA-012531 | 2019-06-27 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0710-002 | MATERIAL REQUISITION FOR AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0019 | 018-E-PLD-00009-001 | 018-E-PLD-40009-001 | WALKWAY ASSEMBLY DRAWING 018E0019 | A2008 | BX | 2 | 2019-05-14 | CON-BMP-VTRA-011563 | 2019-05-14 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0710-002 | MATERIAL REQUISITION FOR AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0023 | 000-E-MCD-60014-001 | 018-E-MCD-40090-001 | WELDING BOOK (MAP PROCEDURE QUALIFICATION REPORT) 018E0023 | B1304 | AX | 2 | 2019-02-25 | CON-BMP-VTRA-010506 | 2019-02-25 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0710-002 | MATERIAL REQUISITION FOR AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0023 | 000-E-PQP-40012-001 | 018-E-PQP-40053-001 | FABRICATION AND QUALITY CONTROL PLAN 018E0023 | B1002 | 0X | 3 | 2019-05-08 | CON-BMP-VTRA-011488 | 2019-05-08 | FOR BAPCO REVIEW | 2019-05-23 | 2019-05-19 | 1-APPROVED BMP-ROC-VTRE-000709 | CLASS 2
076551C-000R-MR-0710-002 | MATERIAL REQUISITION FOR AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0023 | 018-E-CAL-00020-001 | 018-E-CAL-40020-001 | MECHANICAL STRENGTH CALCULATION 018E0023 | A1003 | 0X | 2 | 2019-07-03 | CON-BMP-VTRA-012653 | 2019-07-03 | FOR BAPCO REVIEW | 2019-07-18 |  |  | CLASS 2
076551C-000R-MR-0710-002 | MATERIAL REQUISITION FOR AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0023 | 018-E-CAL-00025-001 | 018-E-CAL-40025-001 | THERMAL RATING FOR HEAT EXCHANGERS 018E0023 (EX BAPCO N.018-E-CAL-00025-001) | A1012 | 0X | 3 | 2019-06-14 | CON-BMP-VTRA-012214 | 2019-06-14 | FOR BAPCO REVIEW | 2019-06-28 | 2019-07-08 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001198 | CLASS 2
076551C-000R-MR-0710-002 | MATERIAL REQUISITION FOR AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0023 | 018-E-CAL-00030-001 | 018-E-CAL-40030-001 | STRUCTURE STEEL CALCULATION NOTE 018E0023 (EX BAPCO N.018- E-CAL-00030-001) | A2201 | 0X | 3 | 2019-07-03 | CON-BMP-VTRA-012648 | 2019-07-03 | FOR BAPCO REVIEW | 2019-07-18 |  |  | CLASS 2
076551C-000R-MR-0710-002 | MATERIAL REQUISITION FOR AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0023 | 018-E-DAT-00068-001 | 018-E-DAT-40068-001 | EQPT FILLED-IN DATA SHEET 018E0023 (EX BAPCO N.018-E-DAT-00068-001 | A1001 | 0X | 3 | 2019-06-17 | CON-BMP-VTRA-012240 | 2019-06-17 | FOR BAPCO REVIEW | 2019-07-01 | 2019-07-08 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001214 | CLASS 2
076551C-000R-MR-0710-002 | MATERIAL REQUISITION FOR AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0023 | 018-E-GAD-00044-001 | 018-E-GAD-00083-001 | GENERAL ARRANGEMENT DRAWING WITH FOUNDATION LOADING DATA 018E0023 | A2001 | AX | 1 | 2018-12-03 | CON-BMP-VTRA-010098 | 2018-12-03 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0710-002 | MATERIAL REQUISITION FOR AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0023 | 018-E-GAD-00067-001 | 018-E-GAD-40067-001 | BUNDLE SCREEN DWG 018E0023 | A1109 | 0X | 3 | 2019-07-03 | CON-BMP-VTRA-012644 | 2019-07-03 | FOR BAPCO REVIEW | 2019-07-18 |  |  | CLASS 2
076551C-000R-MR-0710-002 | MATERIAL REQUISITION FOR AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0023 | 018-E-GAD-00072-001 | 018-E-GAD-40072-001 | PERSONAL PROTECTION GUARD DWG 018E0023 | A1109 | 0X | 3 | 2019-07-03 | CON-BMP-VTRA-012644 | 2019-07-03 | FOR BAPCO REVIEW | 2019-07-18 |  |  | CLASS 2
076551C-000R-MR-0710-002 | MATERIAL REQUISITION FOR AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0023 | 018-E-GAD-00078-001 | 018-E-GAD-40078-001 | HEAT EXCHANGER CONSTRUCTION DWG 018E0023 HEADER DETAIL DRAWING (EX BAPCO N. 018-E-GAD-00078-001) | A1103 | CX | 2 | 2019-07-04 | CON-BMP-VTRA-012660 | 2019-07-04 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0710-002 | MATERIAL REQUISITION FOR AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0023 | 018-E-GAD-00095-001 | 018-E-GAD-40095-001 | STRUCTURE ASSEMBLY DRAWING 018E0023 | A2007 | CX | 2 | 2019-05-21 | CON-BMP-VTRA-011703 | 2019-05-21 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0710-002 | MATERIAL REQUISITION FOR AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0023 | 018-E-GAD-40109-001 | 018-E-GAD-40450-001 | ROTATING ASSEMBLY DRAWING 018E0023 | A2007 | BX | 2 | 2019-06-27 | CON-BMP-VTRA-012531 | 2019-06-27 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0710-002 | MATERIAL REQUISITION FOR AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0023 | 018-E-PLD-00010-001 | 018-E-PLD-40010-001 | WALKWAY ASSEMBLY DRAWING 018E0023 | A2008 | BX | 2 | 2019-05-14 | CON-BMP-VTRA-011563 | 2019-05-14 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0710-002 | MATERIAL REQUISITION FOR AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0035 | 000-E-MCD-60016-001 | 018-E-MCD-40091-001 | WELDING BOOK (MAP PROCEDURE QUALIFICATION REPORT) 018E0035 | B1304 | AX | 2 | 2019-02-25 | CON-BMP-VTRA-010506 | 2019-02-25 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0710-002 | MATERIAL REQUISITION FOR AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0035 | 000-E-PQP-40013-001 | 018-E-PQP-40054-001 | FABRICATION AND QUALITY CONTROL PLAN 018E0035 | B1002 | 0X | 3 | 2019-05-08 | CON-BMP-VTRA-011488 | 2019-05-08 | FOR BAPCO REVIEW | 2019-05-23 | 2019-05-19 | 1-APPROVED BMP-ROC-VTRE-000709 | CLASS 2
076551C-000R-MR-0710-002 | MATERIAL REQUISITION FOR AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0035 | 018-E-CAL-00031-001 | 018-E-CAL-40031-001 | THERMAL RATING FOR HEAT EXCHANGERS 018E0035 (EX BAPCO N.018-E-CAL-00031-001) | A1012 | 0X | 3 | 2019-06-14 | CON-BMP-VTRA-012214 | 2019-06-14 | FOR BAPCO REVIEW | 2019-06-28 | 2019-07-08 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001198 | CLASS 2
076551C-000R-MR-0710-002 | MATERIAL REQUISITION FOR AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0035 | 018-E-CAL-00032-001 | 018-E-CAL-40032-001 | STRUCTURE STEEL CALCULATION NOTE 018E0035 (EX BAPCO N.018- E-CAL-00032-001) | A2201 | 0X | 3 | 2019-07-03 | CON-BMP-VTRA-012648 | 2019-07-03 | FOR BAPCO REVIEW | 2019-07-18 |  |  | CLASS 2
076551C-000R-MR-0710-002 | MATERIAL REQUISITION FOR AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0035 | 018-E-CAL-00064-001 | 018-E-CAL-40064-001 | MECHANICAL STRENGTH CALCULATION 018E0035 | A1003 | BX | 2 | 2019-07-03 | CON-BMP-VTRA-012652 | 2019-07-03 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0710-002 | MATERIAL REQUISITION FOR AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0035 | 018-E-DAT-00069-001 | 018-E-DAT-40069-001 | EQPT FILLED-IN DATA SHEET 018E0035 (EX BAPCO N.018E0035 018-E-DAT-00069-001) | A1001 | 0X | 3 | 2019-06-06 | CON-BMP-VTRA-012075 | 2019-06-06 | FOR BAPCO REVIEW | 2019-06-21 | 2019-06-30 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001114 | CLASS 2
076551C-000R-MR-0710-002 | MATERIAL REQUISITION FOR AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0035 | 018-E-GAD-00096-001 | 018-E-GAD-40096-001 | BUNDLE SCREEN DWG 018E0035 | A1109 | 0X | 3 | 2019-07-03 | CON-BMP-VTRA-012644 | 2019-07-03 | FOR BAPCO REVIEW | 2019-07-18 |  |  | CLASS 2
076551C-000R-MR-0710-002 | MATERIAL REQUISITION FOR AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0035 | 018-E-GAD-00097-001 | 018-E-GAD-40097-001 | PERSONAL PROTECTION GUARD DWG 018E0035 | A1109 | 0X | 3 | 2019-07-03 | CON-BMP-VTRA-012644 | 2019-07-03 | FOR BAPCO REVIEW | 2019-07-18 |  |  | CLASS 2
076551C-000R-MR-0710-002 | MATERIAL REQUISITION FOR AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0035 | 018-E-GAD-00098-001 | 018-E-GAD-40098-001 | HEAT EXCHANGER CONSTRUCTION DWG 018E0035 HEADER DETAIL DRAWING (EX BAPCO N.018-E-GAD-00098-001) | A1103 | CX | 2 | 2019-07-04 | CON-BMP-VTRA-012660 | 2019-07-04 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0710-002 | MATERIAL REQUISITION FOR AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0035 | 018-E-GAD-00099-001 | 018-E-GAD-40099-001 | STRUCTURE ASSEMBLY DRAWING 018E0035 | A2007 | CX | 2 | 2019-05-21 | CON-BMP-VTRA-011703 | 2019-05-21 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0710-002 | MATERIAL REQUISITION FOR AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0035 | 018-E-GAD-40110-001 | 018-E-GAD-40451-001 | ROTATING ASSEMBLY DRAWING 018E0035 | A2007 | BX | 2 | 2019-06-27 | CON-BMP-VTRA-012531 | 2019-06-27 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0710-002 | MATERIAL REQUISITION FOR AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 018E0035 | 018-E-PLD-00011-001 | 018-E-PLD-40011-001 | WALKWAY ASSEMBLY DRAWING 018E0035 | A2008 | BX | 2 | 2019-05-14 | CON-BMP-VTRA-011563 | 2019-05-14 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0710-002 | MATERIAL REQUISITION FOR AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 021E0012 | 000-E-MCD-60015-001 | 021-E-MCD-40031-001 | WELDING BOOK (MAP PROCEDURE QUALIFICATION REPORT) 021E0012 | B1304 | AX | 2 | 2019-02-25 | CON-BMP-VTRA-010506 | 2019-02-25 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0710-002 | MATERIAL REQUISITION FOR AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 021E0012 | 000-E-PQP-40014-001 | 021-E-PQP-40026-001 | FABRICATION AND QUALITY CONTROL PLAN 021E0012 | B1002 | 0AX | 3 | 2019-06-05 | CON-BMP-VTRA-012000 | 2019-06-05 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0710-002 | MATERIAL REQUISITION FOR AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 021E0012 | 021-E-CAL-00008-001 | 021-E-CAL-40008-001 | MECHANICAL STRENGTH CALCULATION 021E0012 | A1003 | BX | 2 | 2019-07-03 | CON-BMP-VTRA-012654 | 2019-07-03 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0710-002 | MATERIAL REQUISITION FOR AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 021E0012 | 021-E-CAL-00011-001 | 021-E-CAL-40011-001 | THERMAL RATING FOR HEAT EXCHANGERS 021E0012 (EX BAPCO N.021-E-CAL-00011-001) | A1012 | 0X | 3 | 2019-06-14 | CON-BMP-VTRA-012215 | 2019-06-14 | FOR BAPCO REVIEW | 2019-06-28 | 2019-07-07 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001177 | CLASS 2
076551C-000R-MR-0710-002 | MATERIAL REQUISITION FOR AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 021E0012 | 021-E-CAL-00014-001 | 021-E-CAL-40014-001 | STRUCTURE STEEL CALCULATION NOTE 021E0012 (EX BAPCO N.021- E-CAL-00014-001) | A2201 | 0X | 3 | 2019-07-03 | CON-BMP-VTRA-012649 | 2019-07-03 | FOR BAPCO REVIEW | 2019-07-18 |  |  | CLASS 2
076551C-000R-MR-0710-002 | MATERIAL REQUISITION FOR AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 021E0012 | 021-E-DAT-00023-001 | 021-E-DAT-40023-001 | EQPT FILLED-IN DATA SHEET 021E0012 (EX BAPCO N.021-EDAT- 00023-001) | A1001 | 0X | 3 | 2019-06-06 | CON-BMP-VTRA-012075 | 2019-06-06 | FOR BAPCO REVIEW | 2019-06-21 | 2019-06-30 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001114 | CLASS 2
076551C-000R-MR-0710-002 | MATERIAL REQUISITION FOR AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 021E0012 | 021-E-GAD-00015-001 | 021-E-GAD-40032-001 | GENERAL ARRANGEMENT DRAWING WITH FOUNDATION LOADING DATA 021E0012/021E0016 (EX BAPCO N.021-E-GAD-00032-001) | A2001 | BX | 2 | 2019-02-19 | CON-BMP-VTRA-010467 | 2019-02-19 | FOR BAPCO REVIEW | 2019-03-06 | 2019-03-07 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000269 | CLASS 2
076551C-000R-MR-0710-002 | MATERIAL REQUISITION FOR AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 021E0012 | 021-E-GAD-00026-001 | 021-E-GAD-40026-001 | PERSONAL PROTECTION GUARD DWG 021E0012 | A1109 | 0X | 3 | 2019-07-03 | CON-BMP-VTRA-012645 | 2019-07-03 | FOR BAPCO REVIEW | 2019-07-18 |  |  | CLASS 2
076551C-000R-MR-0710-002 | MATERIAL REQUISITION FOR AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 021E0012 | 021-E-GAD-00028-001 | 021-E-GAD-40028-001 | DETAILED DWGS FOR LOUVER 021E0012 | A1109 | BX | 2 | 2019-07-04 | CON-BMP-VTRA-012665 | 2019-07-04 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0710-002 | MATERIAL REQUISITION FOR AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 021E0012 | 021-E-GAD-00030-001 | 021-E-GAD-40030-001 | HEAT EXCHANGER CONSTRUCTION DWG 021E0012 HEADER DETAIL DRAWING (EX BAPCO N.021-E-GAD-00030-001) | A1103 | CX | 2 | 2019-07-04 | CON-BMP-VTRA-012661 | 2019-07-04 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0710-002 | MATERIAL REQUISITION FOR AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 021E0012 | 021-E-GAD-00036-001 | 021-E-GAD-40036-001 | STRUCTURE ASSEMBLY DRAWING 021E0012 | A2007 | CX | 2 | 2019-05-21 | CON-BMP-VTRA-011703 | 2019-05-21 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0710-002 | MATERIAL REQUISITION FOR AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 021E0012 | 021-E-GAD-40040-001 | 021-E-GAD-40161-001 | ROTATING ASSEMBLY DRAWING 021E0012 | A2007 | BX | 2 | 2019-06-27 | CON-BMP-VTRA-012530 | 2019-06-27 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0710-002 | MATERIAL REQUISITION FOR AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 021E0012 | 021-E-PLD-00004-001 | 021-E-PLD-40004-001 | WALKWAY ASSEMBLY DRAWING 021E0012 | A2008 | BX | 2 | 2019-05-17 | CON-BMP-VTRA-011659 | 2019-05-17 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0710-002 | MATERIAL REQUISITION FOR AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 021E0016 | 000-E-MCD-60017-001 | 021-E-MCD-40032-001 | WELDING BOOK (MAP PROCEDURE QUALIFICATION REPORT) 021E0016 | B1304 | AX | 2 | 2019-02-25 | CON-BMP-VTRA-010506 | 2019-02-25 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0710-002 | MATERIAL REQUISITION FOR AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 021E0016 | 000-E-PQP-40015-001 | 021-E-PQP-40027-001 | FABRICATION AND QUALITY CONTROL PLAN 021E0016 | B1002 | 0X | 3 | 2019-05-08 | CON-BMP-VTRA-011488 | 2019-05-08 | FOR BAPCO REVIEW | 2019-05-23 | 2019-05-19 | 1-APPROVED BMP-ROC-VTRE-000709 | CLASS 2
076551C-000R-MR-0710-002 | MATERIAL REQUISITION FOR AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 021E0016 | 021-E-CAL-00009-001 | 021-E-CAL-40009-001 | MECHANICAL STRENGTH CALCULATION 021E0016 | A1003 | BX | 2 | 2019-07-03 | CON-BMP-VTRA-012654 | 2019-07-03 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0710-002 | MATERIAL REQUISITION FOR AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 021E0016 | 021-E-CAL-00012-001 | 021-E-CAL-40012-001 | THERMAL RATING FOR HEAT EXCHANGERS 021E0016 (EX BAPCO N.021-E-CAL-00012-001) | A1012 | 0X | 3 | 2019-06-14 | CON-BMP-VTRA-012215 | 2019-06-14 | FOR BAPCO REVIEW | 2019-06-28 | 2019-07-07 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001177 | CLASS 2
076551C-000R-MR-0710-002 | MATERIAL REQUISITION FOR AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 021E0016 | 021-E-CAL-00015-001 | 021-E-CAL-40015-001 | STRUCTURE STEEL CALCULATION NOTE 021E0016 (EX BAPCO N.021- E-CAL-00015-001) | A2201 | 0X | 3 | 2019-07-03 | CON-BMP-VTRA-012649 | 2019-07-03 | FOR BAPCO REVIEW | 2019-07-18 |  |  | CLASS 2
076551C-000R-MR-0710-002 | MATERIAL REQUISITION FOR AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 021E0016 | 021-E-DAT-00024-001 | 021-E-DAT-40024-001 | EQPT FILLED-IN DATA SHEET 021E0016 (EX BAPCO N.021-EDAT- 00024-001) | A1001 | 0X | 3 | 2019-06-06 | CON-BMP-VTRA-012075 | 2019-06-06 | FOR BAPCO REVIEW | 2019-06-21 | 2019-06-30 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001114 | CLASS 2
076551C-000R-MR-0710-002 | MATERIAL REQUISITION FOR AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 021E0016 | 021-E-GAD-00024-001 | 021-E-GAD-40024-001 | BUNDLE SCREEN DWG 021E0016 | A1109 | 0X | 3 | 2019-07-03 | CON-BMP-VTRA-012645 | 2019-07-03 | FOR BAPCO REVIEW | 2019-07-18 |  |  | CLASS 2
076551C-000R-MR-0710-002 | MATERIAL REQUISITION FOR AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 021E0016 | 021-E-GAD-00027-001 | 021-E-GAD-40027-001 | PERSONAL PROTECTION GUARD DWG 021E0016 | A1109 | 0X | 3 | 2019-07-03 | CON-BMP-VTRA-012645 | 2019-07-03 | FOR BAPCO REVIEW | 2019-07-18 |  |  | CLASS 2
076551C-000R-MR-0710-002 | MATERIAL REQUISITION FOR AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 021E0016 | 021-E-GAD-00031-001 | 021-E-GAD-40031-001 | HEAT EXCHANGER CONSTRUCTION DWG 021E0016 HEADER DETAIL DRAWING (EX BAPCO N.021-E-GAD-00031-001) | A1103 | CX | 2 | 2019-07-04 | CON-BMP-VTRA-012661 | 2019-07-04 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0710-002 | MATERIAL REQUISITION FOR AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 021E0016 | 021-E-GAD-00037-001 | 021-E-GAD-40037-001 | STRUCTURE ASSEMBLY DRAWING 021E0016 | A2007 | CX | 2 | 2019-05-21 | CON-BMP-VTRA-011703 | 2019-05-21 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0710-002 | MATERIAL REQUISITION FOR AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 021E0016 | 021-E-GAD-40041-001 | 021-E-GAD-40162-001 | ROTATING ASSEMBLY DRAWING 021E0016 | A2007 | BX | 2 | 2019-06-27 | CON-BMP-VTRA-012530 | 2019-06-27 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0710-002 | MATERIAL REQUISITION FOR AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 021E0016 | 021-E-PLD-00005-001 | 021-E-PLD-40005-001 | WALKWAY ASSEMBLY DRAWING 021E0016 | A2008 | BX | 2 | 2019-05-17 | CON-BMP-VTRA-011659 | 2019-05-17 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0710-002 | MATERIAL REQUISITION FOR AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 051E0001A | 000-E-MCD-60018-001 | 051-E-MCD-40004-001 | WELDING BOOK (MAP PROCEDURE QUALIFICATION REPORT) 051E0001A/B | B1304 | AX | 2 | 2019-03-13 | CON-BMP-VTRA-010668 | 2019-03-13 | FOR BAPCO REVIEW | 2019-03-28 | 2019-03-25 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000370 | CLASS 2
076551C-000R-MR-0710-002 | MATERIAL REQUISITION FOR AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 051E0001A | 000-E-PQP-40016-001 | 051-E-PQP-40002-001 | FABRICATION AND QUALITY CONTROL PLAN 051E0001A/B | B1002 | 0X | 3 | 2019-05-08 | CON-BMP-VTRA-011488 | 2019-05-08 | FOR BAPCO REVIEW | 2019-05-23 | 2019-05-19 | 1-APPROVED BMP-ROC-VTRE-000709 | CLASS 2
076551C-000R-MR-0710-002 | MATERIAL REQUISITION FOR AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 051E0001A | 051-E-CAL-00001-001 | 051-E-CAL-40001-001 | MECHANICAL STRENGTH CALCULATION 051E0001A/B | A1003 | BX | 2 | 2019-07-03 | CON-BMP-VTRA-012655 | 2019-07-03 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0710-002 | MATERIAL REQUISITION FOR AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 051E0001A | 051-E-CAL-00002-001 | 051-E-CAL-40002-001 | THERMAL RATING FOR HEAT EXCHANGERS 051E0001A/B 8EX BAPCO N.051-E-CAL-00002-001) | A1012 | 0X | 3 | 2019-07-08 | CON-BMP-VTRA-012750 | 2019-07-08 | FOR BAPCO REVIEW | 2019-07-23 |  |  | CLASS 2
076551C-000R-MR-0710-002 | MATERIAL REQUISITION FOR AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 051E0001A | 051-E-CAL-00003-001 | 051-E-CAL-40003-001 | STRUCTURE STEEL CALCULATION NOTE 051E0001A/B (EX BAPCO N.051-E-CAL-00003-001) | A2201 | 0X | 3 | 2019-07-03 | CON-BMP-VTRA-012650 | 2019-07-03 | FOR BAPCO REVIEW | 2019-07-18 |  |  | CLASS 2
076551C-000R-MR-0710-002 | MATERIAL REQUISITION FOR AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 051E0001A | 051-E-DAT-00004-001 | 051-E-DAT-40004-001 | EQPT FILLED-IN DATA SHEET 051E0001A/B 8EX BAPCO N.051-E-DAT-00004-001) | A1001 | 0X | 3 | 2019-07-12 | CON-BMP-VTRA-012833 | 2019-07-12 | FOR BAPCO REVIEW | 2019-07-26 |  |  | CLASS 2
076551C-000R-MR-0710-002 | MATERIAL REQUISITION FOR AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 051E0001A | 051-E-GAD-00002-001 | 051-E-GAD-40002-001 | BUNDLE SCREEN DWG 051E0001A/B | A1109 | 0X | 3 | 2019-07-03 | CON-BMP-VTRA-012646 | 2019-07-03 | FOR BAPCO REVIEW | 2019-07-18 |  |  | CLASS 2
076551C-000R-MR-0710-002 | MATERIAL REQUISITION FOR AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 051E0001A | 051-E-GAD-00003-001 | 051-E-GAD-40003-001 | PERSONAL PROTECTION GUARD DWG 051E0001A/B | A1109 | 0X | 3 | 2019-07-03 | CON-BMP-VTRA-012646 | 2019-07-03 | FOR BAPCO REVIEW | 2019-07-18 |  |  | CLASS 2
076551C-000R-MR-0710-002 | MATERIAL REQUISITION FOR AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 051E0001A | 051-E-GAD-00004-001 | 051-E-GAD-40004-001 | HEAT EXCHANGER CONSTRUCTION DWG 051E0001A/B HEADER DETAIL DRAWING (EX BAPCO N.051-E-GAD-00004-001) | A1103 | CX | 2 | 2019-07-04 | CON-BMP-VTRA-012662 | 2019-07-04 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0710-002 | MATERIAL REQUISITION FOR AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 051E0001A | 051-E-GAD-00005-001 | 051-E-GAD-40005-001 | GENERAL ARRANGEMENT DRAWING WITH FOUNDATION LOADING DATA 051E0001A 051E0001B (EX 051-E-GAD-00005-001) | A2001 | BX | 2 | 2019-03-05 | CON-BMP-VTRA-010577 | 2019-03-05 | FOR BAPCO REVIEW | 2019-03-19 | 2019-03-31 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000433 | CLASS 2
076551C-000R-MR-0710-002 | MATERIAL REQUISITION FOR AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 051E0001A | 051-E-GAD-00006-001 | 051-E-GAD-40006-001 | STRUCTURE ASSEMBLY DRAWING 051E0001A/B | A2007 | CX | 2 | 2019-06-05 | CON-BMP-VTRA-011998 | 2019-06-05 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0710-002 | MATERIAL REQUISITION FOR AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 051E0001A | 051-E-GAD-40007-001 | 051-E-GAD-40022-001 | ROTATING ASSEMBLY DRAWING 051E0001A/B | A2007 | BX | 2 | 2019-07-04 | CON-BMP-VTRA-012658 | 2019-07-04 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0710-002 | MATERIAL REQUISITION FOR AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 051E0001A | 051-E-PLD-00001-001 | 051-E-PLD-40001-001 | WALKWAY ASSEMBLY DRAWING 051E0001A 051E0001B | A2008 | BX | 2 | 2019-06-03 | CON-BMP-VTRA-011942 | 2019-06-03 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0710-002 | MATERIAL REQUISITION FOR AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 371E0001 | 000-E-MCD-60019-001 | 371-E-MCD-40001-001 | WELDING BOOK (MAP PROCEDURE QUALIFICATION REPORT) 371E0001 | B1304 | AX | 2 | 2019-02-25 | CON-BMP-VTRA-010506 | 2019-02-25 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0710-002 | MATERIAL REQUISITION FOR AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 371E0001 | 000-E-PQP-40017-001 | 371-E-PQP-40001-001 | FABRICATION AND QUALITY CONTROL PLAN 371E0001 | B1002 | 0X | 3 | 2019-05-08 | CON-BMP-VTRA-011488 | 2019-05-08 | FOR BAPCO REVIEW | 2019-05-23 | 2019-05-19 | 1-APPROVED BMP-ROC-VTRE-000709 | CLASS 2
076551C-000R-MR-0710-002 | MATERIAL REQUISITION FOR AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 371E0001 | 371-E-CAL-50001-001 | 371-E-CAL-40001-001 | MECHANICAL STRENGTH CALCULATION 371E0001A/B | A1003 | BX | 2 | 2019-07-03 | CON-BMP-VTRA-012656 | 2019-07-03 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0710-002 | MATERIAL REQUISITION FOR AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 371E0001 | 371-E-CAL-50002-001 | 371-E-CAL-40002-001 | THERMAL RATING FOR HEAT EXCHANGERS 371E0001 (EX BAPCO N. 371-E-CAL-50002-001) | A1012 | CX | 2 | 2019-05-17 | CON-BMP-VTRA-011661 | 2019-05-21 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0710-002 | MATERIAL REQUISITION FOR AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 371E0001 | 371-E-CAL-50003-001 | 371-E-CAL-40003-001 | STRUCTURE STEEL CALCULATION NOTE 371E0001 (EX BAPCO N.371- E-CAL-50003-001) | A2201 | 0X | 3 | 2019-07-03 | CON-BMP-VTRA-012651 | 2019-07-03 | FOR BAPCO REVIEW | 2019-07-18 |  |  | CLASS 2
076551C-000R-MR-0710-002 | MATERIAL REQUISITION FOR AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 371E0001 | 371-E-DAT-50003-001 | 371-E-DAT-40003-001 | EQPT FILLED-IN DATA SHEET 371E0001 (EX BAPCO N.371-EDAT- 50003-001) | A1001 | CX | 2 | 2019-05-14 | CON-BMP-VTRA-011578 | 2019-05-14 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0710-002 | MATERIAL REQUISITION FOR AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 371E0001 | 371-E-GAD-00004-001 | 371-E-GAD-40004-001 | GENERAL ARRANGEMENT DRAWING WITH FOUNDATION LOADING DATA 371E0001 (EX BAPCO N.371-E-GAD-50004-001) | A2001 | CX | 2 | 2019-07-04 | CON-BMP-VTRA-012667 | 2019-07-04 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0710-002 | MATERIAL REQUISITION FOR AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 371E0001 | 371-E-GAD-40006-001 | 371-E-GAD-40006-001 | ROTATING ASSEMBLY DRAWING 371E0001 | A2007 | BX | 2 | 2019-07-04 | CON-BMP-VTRA-012659 | 2019-07-04 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0710-002 | MATERIAL REQUISITION FOR AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 371E0001 | 371-E-GAD-50001-001 | 371-E-GAD-40001-001 | BUNDLE SCREEN DWG 371E0001 | A1109 | 0X | 3 | 2019-07-03 | CON-BMP-VTRA-012647 | 2019-07-03 | FOR BAPCO REVIEW | 2019-07-18 |  |  | CLASS 2
076551C-000R-MR-0710-002 | MATERIAL REQUISITION FOR AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 371E0001 | 371-E-GAD-50002-001 | 371-E-GAD-40002-001 | PERSONAL PROTECTION GUARD DWG 371E0001 | A1109 | 0X | 3 | 2019-07-03 | CON-BMP-VTRA-012647 | 2019-07-03 | FOR BAPCO REVIEW | 2019-07-18 |  |  | CLASS 2
076551C-000R-MR-0710-002 | MATERIAL REQUISITION FOR AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 371E0001 | 371-E-GAD-50003-001 | 371-E-GAD-40003-001 | HEAT EXCHANGER CONSTRUCTION DWG 371E0001 HEADER DETAIL DRAWING (EX BAPCO N.371-E-GAD-50003-001) | A1103 | CX | 2 | 2019-07-04 | CON-BMP-VTRA-012663 | 2019-07-04 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0710-002 | MATERIAL REQUISITION FOR AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 371E0001 | 371-E-GAD-50005-001 | 371-E-GAD-40005-001 | STRUCTURE ASSEMBLY DRAWING 371E0001 | A2007 | CX | 2 | 2019-06-05 | CON-BMP-VTRA-011998 | 2019-06-05 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0710-002 | MATERIAL REQUISITION FOR AIR COOLERS | KOREA HEAT EXCHANGER_MR-0710 | 371E0001 | 371-E-PLD-50001-001 | 371-E-PLD-40001-001 | WALKWAY ASSEMBLY DRAWING 371E0001 | A2008 | BX | 2 | 2019-06-10 | CON-BMP-VTRA-012108 | 2019-06-10 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V H.P. VESSELS | WALTER TOSTO S.P.A. | 018V1002 | CUO-18112 | 018-C-INV-00001-001 | COPY OF UNPRICED ORDERS ALL ITEMS | C1005 | AX | 4 | 2018-10-26 | CON-BMP-VTRA-010029 | 2018-10-26 | FOR BAPCO REVIEW | 2018-11-14 | 2018-11-09 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000026 | CLASS 2
076551C-000R-MR-0811-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V H.P. VESSELS | WALTER TOSTO S.P.A. | 018V1002 | DIM-18112 | 018-C-PRO-40005-001 | DIMENSIONAL INSPECTION PROCEDURE ALL ITEMS (EX BAPCO N.018-C-PRO-00005-001) | B1202 | 0X | 3 | 2019-03-04 | CON-BMP-VTRA-010569 | 2019-03-05 | FOR BAPCO REVIEW | 2019-03-19 |  |  | CLASS 2
076551C-000R-MR-0811-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V H.P. VESSELS | WALTER TOSTO S.P.A. | 018V1002 | DL-18112 | 018-C-INX-00001-001 | LIST OF VENDOR'S DOCUMENTS AND DRAWINGS ALL ITEMS | A0001 | AX | 2 | 2018-10-24 | CON-BMP-VTRA-010021 | 2018-10-24 | FOR BAPCO REVIEW | 2018-11-12 | 2018-11-07 | 2-REVIEWED WITH COMMENTS BMP-ROC-VTRE-000017 | CLASS 2
076551C-000R-MR-0811-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V H.P. VESSELS | WALTER TOSTO S.P.A. | 018V1002 | DWG-18112.01-01 | 018-C-GAD-40088-001 | TRAIN 1 INTERSTAGE SEPARATOR 018V1002 GENERAL ASSEMBLY 1/2 (EX BAPCO N.018-C-GAD-00088- 001) | A1103 | 0AX | 2 | 2019-07-12 | CON-BMP-VTRA-012830 | 2019-07-12 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V H.P. VESSELS | WALTER TOSTO S.P.A. | 018V1002 | DWG-18112.01-02 | 018-C-GAD-40088-002 | TRAIN 1 INTERSTAGE SEPARATOR 018V1002 GENERAL ASSEMBLY 2/2 (EX BAPCO N.018-C-GAD-00088- 002) | A1103 | 0X | 2 | 2019-06-14 | CON-BMP-VTRA-012228 | 2019-06-14 | FOR BAPCO REVIEW |  | 2019-07-08 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001209 | CLASS 2
076551C-000R-MR-0811-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V H.P. VESSELS | WALTER TOSTO S.P.A. | 018V1002 | DWG-18112.01-03 | 018-C-GAD-40091-001 | TRAIN 1 INTERSTAGE SEPARATOR BODY DETAILS 018V1002 018V2002 (EX BAPCO N.018-C-GAD-00091- 001) | A1109 | 0BX | 3 | 2019-06-21 | CON-BMP-VTRA-012368 | 2019-06-21 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V H.P. VESSELS | WALTER TOSTO S.P.A. | 018V1002 | DWG-18112.01-04 | 018-C-GAD-40091-002 | INTERSTAGE SEPARATOR 018V1002 018V2002 NOZZLE DETAIL 1/2 (EX BAPCO N.018-C-GAD-00091-002 | A1109 | 0AX | 3 | 2019-06-21 | CON-BMP-VTRA-012370 | 2019-06-21 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V H.P. VESSELS | WALTER TOSTO S.P.A. | 018V1002 | DWG-18112.01-05 | 018-C-GAD-40091-003 | INTERSTAGE SEPARATOR 018V1002 018V2002 NOZZLE DETAIL 2/2 (EX BAPCO N.018-C-GAD-00091-003) | A1109 | 0AX | 3 | 2019-06-21 | CON-BMP-VTRA-012370 | 2019-06-21 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V H.P. VESSELS | WALTER TOSTO S.P.A. | 018V1002 | DWG-18112.01A-06 | 018-C-GAD-40091-004 | TRAIN 1 INTERSTAGE SEPARATOR 018V1002 INTERNALS DETAILS 1/2 | A1109 | 0AX | 3 | 2019-06-21 | CON-BMP-VTRA-012370 | 2019-06-21 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V H.P. VESSELS | WALTER TOSTO S.P.A. | 018V1002 | DWG-18112.01A-07 | 018-C-GAD-40091-005 | TRAIN 1 INTERSTAGE SEPARATOR 018V1002 INTERNALS DETAILS 2/2 | A1109 | 0AX | 3 | 2019-06-21 | CON-BMP-VTRA-012370 | 2019-06-21 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V H.P. VESSELS | WALTER TOSTO S.P.A. | 018V1002 | DWG-18112.01A-08 | 018-C-GAD-40091-006 | TRAIN 1 INTERSTAGE SEPARATOR 018V1002 - EXTERNALS DETAILS 1/2 | A1109 | 0X | 3 | 2019-06-22 | CON-BMP-VTRA-012371 | 2019-06-22 | FOR BAPCO REVIEW | 2019-07-08 |  |  | CLASS 2
076551C-000R-MR-0811-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V H.P. VESSELS | WALTER TOSTO S.P.A. | 018V1002 | DWG-18112.01A-09 | 018-C-GAD-40333-001 | TRAIN 1 INTERSTAGE SEPARATOR 018V1002 - EXTERNALS DETAILS 2/2 | A1109 | 0X | 3 | 2019-06-22 | CON-BMP-VTRA-012371 | 2019-06-22 | FOR BAPCO REVIEW | 2019-07-08 |  |  | CLASS 2
076551C-000R-MR-0811-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V H.P. VESSELS | WALTER TOSTO S.P.A. | 018V1002 | DWG-18112.01A-10 | 018-C-DLB-40001-001 | TRAIN 1 INTERSTAGE SEPARATOR 018V1002 - NAMEPLATE DRAWING (EX BAPCO N.018-C-DLB-00001-001) | A1112 | 0X | 3 | 2019-05-29 | CON-BMP-VTRA-011822 | 2019-05-29 | FOR BAPCO REVIEW | 2019-06-12 | 2019-06-17 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000964 | CLASS 2
076551C-000R-MR-0811-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V H.P. VESSELS | WALTER TOSTO S.P.A. | 018V1002 | DWG-18112.01A-11 | 018-C-GAD-40334-001 | TRAIN 1 INTERSTAGE SEPARATOR 018V1002 WELDING DRAWING 1/2 | A1109 | 0X | 2 | 2019-06-26 | CON-BMP-VTRA-012489 | 2019-06-26 | FOR BAPCO REVIEW | 2019-07-10 |  |  | CLASS 2
076551C-000R-MR-0811-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V H.P. VESSELS | WALTER TOSTO S.P.A. | 018V1002 | DWG-18112.01A-14 | 018-C-DLB-40004-001 | TRAIN 1 INTERSTAGE SEPARATOR 018V1002 - TEMPLATE DRAWING (EX BAPCO N. 018-C-DLB-00004- 001) | A2010 | 0X | 3 | 2019-07-08 | CON-BMP-VTRA-012702 | 2019-07-08 | FOR BAPCO REVIEW | 2019-07-22 |  |  | CLASS 2
076551C-000R-MR-0811-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V H.P. VESSELS | WALTER TOSTO S.P.A. | 018V1002 | DWG-18112.01A-15 | 018-C-GAD-40334-002 | TRAIN 1 INTERSTAGE SEPARATOR 018V1002 WELDING DRAWING 2/2 | A1109 | 0X | 2 | 2019-06-25 | CON-BMP-VTRA-012436 | 2019-06-25 | FOR BAPCO REVIEW | 2019-07-09 |  |  | CLASS 2
076551C-000R-MR-0811-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V H.P. VESSELS | WALTER TOSTO S.P.A. | 018V1002 | FCP-18112 | 018-C-PRO-00006-001 | FERRITE CONTENT EXAMINATION PROCEDURE ALL ITEMS | B1202 | BX | 3 | 2018-12-11 | CON-BMP-VTRA-010145 | 2018-12-11 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V H.P. VESSELS | WALTER TOSTO S.P.A. | 018V1002 | FEA-18112.01A-1 | 018-C-CAL-40003-001 | TRAIN 1 HP-MT SEPARATORFEA REPORT 018V1002 | A1003 | AX | 2 | 2019-01-21 | CON-BMP-VTRA-010257 | 2019-01-21 | FOR BAPCO REVIEW | 2019-02-04 | 2019-02-03 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000149 | CLASS 2
076551C-000R-MR-0811-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V H.P. VESSELS | WALTER TOSTO S.P.A. | 018V1002 | FP-18112.01 | 018-C-PRO-40018-001 | FORMING PROCEDURE ALL ITEMS | B1201 | 0X | 3 | 2019-04-15 | CON-BMP-VTRA-011181 | 2019-04-15 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V H.P. VESSELS | WALTER TOSTO S.P.A. | 018V1002 | HDT-18112 | 018-C-PRO-00007-001 | HARDNESS TEST PROCEDURE ALL ITEMS | B1202 | BX | 3 | 2018-12-11 | CON-BMP-VTRA-010145 | 2018-12-11 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V H.P. VESSELS | WALTER TOSTO S.P.A. | 018V1002 | HTP-18112.01 | 018-C-PRO-40002-001 | HEAT TREATMENT PROCEDURE PWHT INTERSTAGE SEPARATOR 018V1002 018V2002 | B1201 | AX | 2 | 2019-01-18 | CON-BMP-VTRA-010247 | 2019-01-18 | FOR BAPCO REVIEW | 2019-02-04 | 2019-01-29 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000134 | CLASS 2
076551C-000R-MR-0811-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V H.P. VESSELS | WALTER TOSTO S.P.A. | 018V1002 | HYT-18112 | 018-C-PRO-40016-001 | HYDROSTATIC TEST PROCEDURE FORALL HP/HT SEPARATORS | B1103 | AX | 2 | 2019-06-13 | CON-BMP-VTRA-012189 | 2019-06-13 | FOR BAPCO REVIEW | 2019-06-27 | 2019-06-29 | 1-APPROVED BMP-ROC-VTRE-001075 | CLASS 2
076551C-000R-MR-0811-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V H.P. VESSELS | WALTER TOSTO S.P.A. | 018V1002 | ITP-18112.01A | 018-C-PQP-40001-001 | INSPECTION TEST PLAN - INTERSTAGE SEPARATOR 018V1002 (EX B018-C-PQP-00001-001) | B1002 | 0X | 3 | 2019-06-14 | CON-BMP-VTRA-012219 | 2019-06-14 | FOR BAPCO REVIEW | 2019-06-28 | 2019-06-30 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001097 | CLASS 2
076551C-000R-MR-0811-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V H.P. VESSELS | WALTER TOSTO S.P.A. | 018V1002 | MCR-18112.01 | 018-C-CAL-40001-001 | INTERSTAGE SEPARATOR 018V1002 MECHANICAL CALCULATION REPORT (EX BAPCO N.018-C-CAL-00001-001) | A1003 | DX | 2 | 2019-05-16 | CON-BMP-VTRA-011647 | 2019-05-16 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V H.P. VESSELS | WALTER TOSTO S.P.A. | 018V1002 | MIP_2018_28_TOSTO | 018-C-PQP-00007-001 | MANUFACTURING - AND MANUFACTURING AND INSPECTION PLAN - PLATES ALL ITEMS (EX BAPCO NUMBER 018-C-ITP-00011- 001) | B1002 | AX | 3 | 2018-11-14 | CON-BMP-VTRA-010041 | 2018-11-14 | FOR BAPCO REVIEW | 2018-11-29 | 2018-11-27 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000038 | CLASS 2
076551C-000R-MR-0811-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V H.P. VESSELS | WALTER TOSTO S.P.A. | 018V1002 | MITPF-18112 | 018-C-PQP-40008-001 | MANUFACTURING - AND INSPECTION PLAN FORGINGS ALL ITEMS (EX BAPCO NUMBER 018-C-ITP-00012- 001 EX 018-C-PQP-00008-001) | B1002 | 0X | 3 | 2019-04-05 | CON-BMP-VTRA-011024 | 2019-04-05 | FOR BAPCO REVIEW | 2019-04-22 | 2019-04-18 | 1-APPROVED BMP-ROC-VTRE-000537 | CLASS 2
076551C-000R-MR-0811-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V H.P. VESSELS | WALTER TOSTO S.P.A. | 018V1002 | MITPN1-18112 | 018-C-PQP-40014-001 | MANUFACTURING AND INSPECTION PLAN NOZZLES 1 ALL ITEMS | B1002 | 0X | 3 | 2019-06-25 | CON-BMP-VTRA-012462 | 2019-06-25 | FOR BAPCO REVIEW | 2019-07-10 | 2019-07-09 | 1-APPROVED BMP-ROC-VTRE- 001205 | CLASS 2
076551C-000R-MR-0811-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V H.P. VESSELS | WALTER TOSTO S.P.A. | 018V1002 | MITPN2-18112 | 018-C-PQP-40024-001 | MANUFACTURING AND INSPECTION PLAN NOZZLES 2 ALL ITEMS | B1002 | 0X | 3 | 2019-06-25 | CON-BMP-VTRA-012462 | 2019-06-25 | FOR BAPCO REVIEW | 2019-07-10 | 2019-07-09 | 1-APPROVED BMP-ROC-VTRE- 001205 | CLASS 2
076551C-000R-MR-0811-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V H.P. VESSELS | WALTER TOSTO S.P.A. | 018V1002 | MITPN3-18112 | 018-C-PQP-40058-001 | MANUFACTURING AND INSPECTION PLAN NOZZLE 3 - ALL ITEMS | B1002 | AX | 4 | 2019-04-16 | CON-BMP-VTRA-011202 | 2019-04-16 | FOR BAPCO REVIEW | 2019-05-02 | 2019-04-29 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000615 | CLASS 2
076551C-000R-MR-0811-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V H.P. VESSELS | WALTER TOSTO S.P.A. | 018V1002 | MPT-18112.01A | 018-C-CAL-40066-001 | MINIMUM PRESSURIZATION TEMPERATURE (MPT) - TRAIN 1 INTSERSTAGE SEPARATOR 018V1002 | A1003 | 0X | 4 | 2019-06-26 | CON-BMP-VTRA-012487 | 2019-06-26 | FOR BAPCO REVIEW | 2019-07-10 |  |  | CLASS 2
076551C-000R-MR-0811-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V H.P. VESSELS | WALTER TOSTO S.P.A. | 018V1002 | MR-18112 | 018-C-MRS-00001-001 | MONTHLY REPORT ALL ITEMS | C1002 | BX | 4 | 2018-12-20 | CON-BMP-VTRA-010178 | 2018-12-20 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-0811-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V H.P. VESSELS | WALTER TOSTO S.P.A. | 018V1002 | MT-18112 | 018-C-PRO-00009-001 | MAGNETIC PARTICLE TEST PROCEDURE - ALL ITEMS | B1202 | BX | 3 | 2018-11-23 | CON-BMP-VTRA-010067 | 2018-11-23 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V H.P. VESSELS | WALTER TOSTO S.P.A. | 018V1002 | PA-18112 | 018-C-PRO-40015-001 | PHASED ARRAY EXAMINATION PROCEDURE ALL ITEMS | B1202 | 0XX | 2 | 2019-07-01 | CON-BMP-VTRA-012588 | 2019-07-01 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V H.P. VESSELS | WALTER TOSTO S.P.A. | 018V1002 | PCP-18112 | 018-C-PRO-40029-001 | PICKLING AND PASSIVATION PROCEDURE - ALL ITEMS | B1201 | AX | 2 | 2019-02-05 | CON-BMP-VTRA-010363 | 2019-02-05 | FOR BAPCO REVIEW | 2019-02-20 | 2019-02-15 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000182 | CLASS 2
076551C-000R-MR-0811-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V H.P. VESSELS | WALTER TOSTO S.P.A. | 018V1002 | PMI-18112 | 018-C-PRO-00010-001 | PMI TEST PROCEDURE ALL ITEMS | B1202 | BX | 3 | 2018-12-11 | CON-BMP-VTRA-010145 | 2018-12-11 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V H.P. VESSELS | WALTER TOSTO S.P.A. | 018V1002 | PS-18112.01 | 018-C-TSP-40001-001 | PAINTING / SURFACE PROTECTION PROCEDURE - TRAIN 1 & 2 INTERSTAGE SEPARATORS 018V1002 018V2002 | A0106 | 0X | 3 | 2019-06-21 | CON-BMP-VTRA-012363 | 2019-06-21 | FOR BAPCO REVIEW | 2019-07-05 | 2019-07-04 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001160 | CLASS 2
076551C-000R-MR-0811-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V H.P. VESSELS | WALTER TOSTO S.P.A. | 018V1002 | PT-18112 | 018-C-PRO-00011-001 | DYE PENETRANT TEST PROCEDURE ALL ITEMS | B1202 | BX | 3 | 2018-11-13 | CON-BMP-VTRA-010067 | 2018-11-23 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V H.P. VESSELS | WALTER TOSTO S.P.A. | 018V1002 | PTP-18112.01 | 018-C-MCD-40010-001 | PRODUCTION TEST PLATE PROCEDURE - 018V1002 / 018V2002 | B1304 | AX | 2 | 2019-01-14 | CON-BMP-VTRA-010210 | 2019-01-14 | FOR BAPCO REVIEW | 2019-01-29 | 2019-01-25 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000128 | CLASS 2
076551C-000R-MR-0811-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V H.P. VESSELS | WALTER TOSTO S.P.A. | 018V1002 | QAP-18112 | 018-C-PLN-00001-001 | QUALITY ASSURANCE PLAN ALL ITEMS | B1001 | AX | 3 | 2018-10-23 | CON-BMP-VTRA-010022 | 2018-10-24 | FOR BAPCO REVIEW | 2018-11-12 | 2018-11-07 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000018 | CLASS 2
076551C-000R-MR-0811-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V H.P. VESSELS | WALTER TOSTO S.P.A. | 018V1002 | RT-18112 | 018-C-PRO-00012-001 | RADIOGRAPHIC TEST PROCEDURE ALL ITEMS | B1202 | BX | 3 | 2018-11-23 | CON-BMP-VTRA-010067 | 2018-11-23 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V H.P. VESSELS | WALTER TOSTO S.P.A. | 018V1002 | SCR-18112.01 | 018-C-CAL-40002-001 | STRUCTURAL CALCULATION REPORT INTERSTAGE SEPARATOR 018V1002 (EX BAPCO N.018-C-CAL-00002-001) | A1003 | 0X | 2 | 2019-05-17 | CON-BMP-VTRA-011652 | 2019-05-17 | FOR BAPCO REVIEW | 2019-05-31 | 2019-05-31 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000859 | CLASS 2
076551C-000R-MR-0811-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V H.P. VESSELS | WALTER TOSTO S.P.A. | 018V1002 | TOFD-18112 | 018-C-PRO-40008-001 | UT-TOFD EXAMINATION PROCEDURE ALL ITEMS | B1202 | 0XX | 2 | 2019-07-01 | CON-BMP-VTRA-012588 | 2019-07-01 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V H.P. VESSELS | WALTER TOSTO S.P.A. | 018V1002 | TS-18112.01-1 | 018-C-TSP-40005-001 | TECHNICAL REQUIREMENT SHEET FOR MATERIAL ORDER FOR PLATES OF HEADS ALL ITEMS (EX BAPCO N. 018-C-TSP-00005-001) | B1203 | 0X | 4 | 2019-04-05 | CON-BMP-VTRA-011023 | 2019-04-05 | FOR BAPCO REVIEW | 2019-04-22 | 2019-04-25 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000573 | CLASS 2
076551C-000R-MR-0811-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V H.P. VESSELS | WALTER TOSTO S.P.A. | 018V1002 | TS-18112.01-2 | 018-C-TSP-40006-001 | TECHNICAL REQUIREMENT SHEET FOR MATERIAL ORDER FOR PLATES OF SHELL ALL ITEMS (EX BAPCO N. 018-C-TSP-00006-001) | B1203 | 0X | 4 | 2019-04-05 | CON-BMP-VTRA-011023 | 2019-04-05 | FOR BAPCO REVIEW | 2019-04-22 | 2019-04-25 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000573 | CLASS 2
076551C-000R-MR-0811-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V H.P. VESSELS | WALTER TOSTO S.P.A. | 018V1002 | TS-18112.01-3 | 018-C-TSP-40007-001 | TECHNICAL REQUIREMENT SHEET FOR MATERIAL ORDER FOR FORGIN ALL ITEMS (EX BAPCO N. 018-C-TSP-00007-001) | B1203 | 0X | 4 | 2019-04-05 | CON-BMP-VTRA-011023 | 2019-04-05 | FOR BAPCO REVIEW | 2019-04-22 | 2019-04-25 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000573 | CLASS 2
076551C-000R-MR-0811-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V H.P. VESSELS | WALTER TOSTO S.P.A. | 018V1002 | TS-18112.01-4 | 018-C-TSP-40028-001 | TECHNICAL REQUIREMENTS SHEET FOR MATERIAL ORDER - PLATES FOR SKIRT SA 387 GR.22 CL.2 - ALL ITEMS | B1203 | AX | 2 | 2019-04-04 | CON-BMP-VTRA-011005 | 2019-04-04 | FOR BAPCO REVIEW | 2019-04-19 | 2019-04-24 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000550 | CLASS 2
076551C-000R-MR-0811-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V H.P. VESSELS | WALTER TOSTO S.P.A. | 018V1002 | TS-18112.01-5 | 018-C-TSP-40029-001 | TECHNICAL REQUIREMENTS SHEET FOR MATERIAL ORDER - PLATES FOR SKIRT SA 516 GR.70 - ALL ITEMS | B1203 | AX | 2 | 2019-04-04 | CON-BMP-VTRA-011005 | 2019-04-04 | FOR BAPCO REVIEW | 2019-04-19 | 2019-04-24 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000550 | CLASS 2
076551C-000R-MR-0811-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V H.P. VESSELS | WALTER TOSTO S.P.A. | 018V1002 | TS-18112.01-6 | 018-C-TSP-40030-001 | TECHNICAL REQUIREMENTS SHEET FOR MATERIAL ORDER - FORGINGS SA 182 F347 - ALL ITEMS | B1203 | AX | 2 | 2019-04-04 | CON-BMP-VTRA-011005 | 2019-04-04 | FOR BAPCO REVIEW | 2019-04-19 | 2019-04-24 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000550 | CLASS 2
076551C-000R-MR-0811-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V H.P. VESSELS | WALTER TOSTO S.P.A. | 018V1002 | TS-18112.01-7 | 018-C-TSP-40031-001 | TECHNICAL REQUIREMENTS SHEET FOR MATERIAL ORDER - FORGINGS SA 182 F321 - ALL ITEMS | B1203 | AX | 2 | 2019-04-04 | CON-BMP-VTRA-011005 | 2019-04-04 | FOR BAPCO REVIEW | 2019-04-19 | 2019-04-24 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000550 | CLASS 2
076551C-000R-MR-0811-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V H.P. VESSELS | WALTER TOSTO S.P.A. | 018V1002 | TS-18112.01-ESW | 018-C-TSP-40008-001 | TECHNICAL REQUIREMENTS SHEET FOR MATERIAL ORDER - PRODUCT TYPE: ESW STRIP FOR SS347 ALL ITEMS | B1203 | 0X | 4 | 2019-04-30 | CON-BMP-VTRA-011325 | 2019-04-30 | FOR BAPCO REVIEW | 2019-05-16 | 2019-05-23 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000733 | CLASS 2
076551C-000R-MR-0811-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V H.P. VESSELS | WALTER TOSTO S.P.A. | 018V1002 | TS-18112.01-SAW | 018-C-TSP-00014-001 | TECHNICAL REQUIREMENTS SHEET FOR MATER ORDER PRODUCT TYPE: SAW WELDING CONSUMABLES (2.25 CR-1MO-V) - ALL ITEMS | B1203 | AX | 3 | 2018-10-25 | CON-BMP-VTRA-010026 | 2018-10-25 | FOR BAPCO REVIEW | 2018-11-13 | 2018-11-08 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000023 | CLASS 2
076551C-000R-MR-0811-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V H.P. VESSELS | WALTER TOSTO S.P.A. | 018V1002 | TS-18112.01-SMAW | 018-C-TSP-00015-001 | TECHNICAL REQUIREMENTS SHEET FOR MATER ORDER PRODUCT TYPE: SMAW WELDING CONSUMABLES (2.25 CR-1MO-V) - ALL ITEMS | B1203 | AX | 3 | 2018-10-25 | CON-BMP-VTRA-010026 | 2018-10-25 | FOR BAPCO REVIEW | 2018-11-13 | 2018-11-08 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000023 | CLASS 2
076551C-000R-MR-0811-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V H.P. VESSELS | WALTER TOSTO S.P.A. | 018V1002 | TSC-18112 | 018-C-SCH-00001-001 | TIME SCHEDULE ALL ITEMS | C1001 | BX | 4 | 2018-12-20 | CON-BMP-VTRA-010179 | 2018-12-20 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-0811-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V H.P. VESSELS | WALTER TOSTO S.P.A. | 018V1002 | UT-18112 | 018-C-PRO-40013-001 | ULTRASONIC TEST PROCEDURE FOR 2.25CR-1MO-V H.P. VESSELS ALL ITEMS (EX BAPCO N.018-C-PRO- 00013-001) | B1202 | 0X | 3 | 2019-06-25 | CON-BMP-VTRA-012461 | 2019-06-25 | FOR BAPCO REVIEW | 2019-07-10 | 2019-07-08 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001216 | CLASS 2
076551C-000R-MR-0811-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V H.P. VESSELS | WALTER TOSTO S.P.A. | 018V1002 | VT-18112 | 018-C-PRO-00014-001 | VISUAL TEST PROCEDURE - ALL ITEMS | B1202 | BX | 3 | 2018-11-23 | CON-BMP-VTRA-010067 | 2018-11-23 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V H.P. VESSELS | WALTER TOSTO S.P.A. | 018V1002 | WB 18112.01 | 018-C-MCD-40007-001 | WELDING BOOK - INTERSTAGE SEPARATOR 018V1002 018V2002 | B1304 | 0X | 2 | 2019-05-22 | CON-BMP-VTRA-011710 | 2019-05-22 | FOR BAPCO REVIEW | 2019-06-05 | 2019-07-01 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001122 | CLASS 2
076551C-000R-MR-0811-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V H.P. VESSELS | WALTER TOSTO S.P.A. | 018V1002 | WRP-18112 | 018-C-MCD-00013-001 | WELD REPAIR PROCEDURE - ALL ITEMS | B1304 | BX | 3 | 2018-12-03 | CON-BMP-VTRA-010082 | 2018-12-03 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V H.P. VESSELS | WALTER TOSTO S.P.A. | 018V1003 | DWG-18112.02-01 | 018-C-GAD-40089-001 | TRAIN 1 HP-HT SEPARATOR 018V1003 GENERAL ASSEMBLY 1/2 (EX BAPCO N.018-C-GAD-00089- 001) | A1103 | 0AX | 2 | 2019-07-12 | CON-BMP-VTRA-012830 | 2019-07-12 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V H.P. VESSELS | WALTER TOSTO S.P.A. | 018V1003 | DWG-18112.02-02 | 018-C-GAD-40089-002 | TRAIN 1 HP-HT SEPARATOR 018V1003 GENERAL ASSEMBLY 2/2 (EX BAPCO N.018-C-GAD-00089- 002) | A1103 | DX | 2 | 2019-06-14 | CON-BMP-VTRA-012230 | 2019-06-14 | FOR BAPCO REVIEW | 2019-07-01 | 2019-07-08 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001213 | CLASS 2
076551C-000R-MR-0811-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V H.P. VESSELS | WALTER TOSTO S.P.A. | 018V1003 | DWG-18112.02-03 | 018-C-GAD-40092-001 | TRAIN 1 HP-HR SEPARATOR 018V1003 BODY DETAILS (EX BAPCO DOC N. 018-C-GAD-00092- 001) | A1109 | 0BX | 3 | 2019-06-21 | CON-BMP-VTRA-012368 | 2019-06-21 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V H.P. VESSELS | WALTER TOSTO S.P.A. | 018V1003 | DWG-18112.02-04 | 018-C-GAD-40092-002 | HP HT SEPARATOR 018V1003 018V2003 NOZZLE DETAIL 1/2 (EX BAPCO N. 018-C-GAD-00092-002) | A1109 | 0AX | 3 | 2019-06-21 | CON-BMP-VTRA-012370 | 2019-06-21 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V H.P. VESSELS | WALTER TOSTO S.P.A. | 018V1003 | DWG-18112.02-05 | 018-C-GAD-40092-003 | HP HT SEPARATOR 018V1003 018V2003 NOZZLE DETAIL 2/2 (EX BAPCO N. 018-C-GAD-00092-003) | A1109 | 0AX | 3 | 2019-06-21 | CON-BMP-VTRA-012370 | 2019-06-21 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V H.P. VESSELS | WALTER TOSTO S.P.A. | 018V1003 | DWG-18112.02A-06 | 018-C-GAD-40092-004 | TRAIN 1 HP-HT SEPARATOR 018V1003 INTERNALS DETAILS 1/2 | A1109 | 0AX | 3 | 2019-06-21 | CON-BMP-VTRA-012370 | 2019-06-21 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V H.P. VESSELS | WALTER TOSTO S.P.A. | 018V1003 | DWG-18112.02A-07 | 018-C-GAD-40092-005 | TRAIN 1 HP-HT SEPARATOR 018V1003 - INTERNALS DETAILS 2/2 | A1109 | 0AX | 3 | 2019-06-21 | CON-BMP-VTRA-012370 | 2019-06-21 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V H.P. VESSELS | WALTER TOSTO S.P.A. | 018V1003 | DWG-18112.02A-08 | 018-C-GAD-40092-006 | TRAIN 1 HP-HT SEPARATOR 018V1003 - EXTERNALS DETAILS 1/2 | A1109 | 0AX | 3 | 2019-06-21 | CON-BMP-VTRA-012370 | 2019-06-21 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V H.P. VESSELS | WALTER TOSTO S.P.A. | 018V1003 | DWG-18112.02A-09 | 018-C-GAD-40337-001 | TRAIN 1 HP-HT SEPARATOR 018V1003 - EXTERNALS DETAILS 2/2 | A1109 | 0AX | 3 | 2019-06-21 | CON-BMP-VTRA-012370 | 2019-06-21 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V H.P. VESSELS | WALTER TOSTO S.P.A. | 018V1003 | DWG-18112.02A-10 | 018-C-DLB-40002-001 | TRAIN 1 HP-HT SEPARATOR 018V1003 - NAMEPLATE DRAWING (EX BAPCO DOC N. 018-C-DLB-00002- 001) | A1112 | 0X | 3 | 2019-05-29 | CON-BMP-VTRA-011822 | 2019-05-29 | FOR BAPCO REVIEW | 2019-06-12 | 2019-06-17 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000964 | CLASS 2
076551C-000R-MR-0811-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V H.P. VESSELS | WALTER TOSTO S.P.A. | 018V1003 | DWG-18112.02A-11 | 018-C-GAD-40338-001 | TRAIN 1 HP-HT SEPARATOR 018V1003 WELDING DRAWING 1/2 | A1109 | 0X | 2 | 2019-06-26 | CON-BMP-VTRA-012489 | 2019-06-26 | FOR BAPCO REVIEW | 2019-07-10 |  |  | CLASS 2
076551C-000R-MR-0811-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V H.P. VESSELS | WALTER TOSTO S.P.A. | 018V1003 | DWG-18112.02A-14 | 018-C-DLB-40005-001 | TRAIN 1 HP-HT SEPARATOR 018V1003 - TEMPLATE DRAWING (EX BAPCO DOC N. 018-C-DLB- 00005-001) | A2010 | 0X | 3 | 2019-07-08 | CON-BMP-VTRA-012702 | 2019-07-08 | FOR BAPCO REVIEW | 2019-07-22 |  |  | CLASS 2
076551C-000R-MR-0811-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V H.P. VESSELS | WALTER TOSTO S.P.A. | 018V1003 | DWG-18112.02A-15 | 018-C-GAD-40360-001 | TRAIN 1 HP-HT SEPARATOR 018V1003 WELDING DRAWING 2/2 | A1109 | 0X | 2 | 2019-06-26 | CON-BMP-VTRA-012490 | 2019-06-26 | FOR BAPCO REVIEW | 2019-07-10 |  |  | CLASS 2
076551C-000R-MR-0811-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V H.P. VESSELS | WALTER TOSTO S.P.A. | 018V1003 | HTP-18112.02 | 018-C-PRO-40003-001 | HEAT TREATMENT PROCEDURE PWHT PROCEDURE HP/HT SEPARATOR 018V1003 018V2003 | B1201 | AX | 2 | 2019-01-18 | CON-BMP-VTRA-010247 | 2019-01-18 | FOR BAPCO REVIEW | 2019-02-04 | 2019-01-29 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000134 | CLASS 2
076551C-000R-MR-0811-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V H.P. VESSELS | WALTER TOSTO S.P.A. | 018V1003 | ITP-18112.02A | 018-C-PQP-40003-001 | INSPECTION TEST PLAN - HP-HT SEPARATOR 018V1003 (EX BAPCO N.018-C-PQP-00003-001) | B1002 | 0X | 3 | 2019-06-14 | CON-BMP-VTRA-012219 | 2019-06-14 | FOR BAPCO REVIEW | 2019-06-28 | 2019-06-30 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001097 | CLASS 2
076551C-000R-MR-0811-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V H.P. VESSELS | WALTER TOSTO S.P.A. | 018V1003 | MCR-18112.02 | 018-C-CAL-40005-001 | HP-HT SEPARATOR 018V1003 MECHANICAL CALCULATION REPORT (EX BAPCO N.018-C-CAL-00005-001) | A1003 | 0AX | 4 | 2019-07-08 | CON-BMP-VTRA-012705 | 2019-07-08 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V H.P. VESSELS | WALTER TOSTO S.P.A. | 018V1003 | MPT-18112.02A | 018-C-CAL-40067-001 | MINIMUM PRESSURIZATION TEMPERATURE (MPT) - TRAIN 1 HP-HT SEPARATOR 018V1003 | A1003 | AX | 2 | 2019-06-11 | CON-BMP-VTRA-012155 | 2019-06-11 | FOR BAPCO REVIEW | 2019-06-26 | 2019-07-02 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001143 | CLASS 2
076551C-000R-MR-0811-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V H.P. VESSELS | WALTER TOSTO S.P.A. | 018V1003 | PS-18112.02 | 018-C-TSP-40002-001 | PAINTING SURFACE PROTECTION PROCDURE TRAIN 1 & 2 HP-HT SEPARATORS - 018V1003 / 018V2003 | A0106 | 0X | 3 | 2019-06-25 | CON-BMP-VTRA-012423 | 2019-06-25 | FOR BAPCO REVIEW | 2019-07-09 | 2019-07-08 | 1-APPROVED BMP-ROC-VTRE-001222 | CLASS 2
076551C-000R-MR-0811-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V H.P. VESSELS | WALTER TOSTO S.P.A. | 018V1003 | PTP-18112.02 | 018-C-MCD-40011-001 | PRODUCTION TEST PLATE PROCEDURE - 018V1003 / 018V2003 | B1304 | AX | 2 | 2019-01-14 | CON-BMP-VTRA-010210 | 2019-01-14 | FOR BAPCO REVIEW | 2019-01-29 | 2019-01-25 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000128 | CLASS 2
076551C-000R-MR-0811-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V H.P. VESSELS | WALTER TOSTO S.P.A. | 018V1003 | SCR-18112.02 | 018-C-CAL-40006-001 | STRUCTURAL CALCULATION REPORT HP-HT SEPARATOR 018V1003 (EX BAPCO N.018-C-CAL-00006-001) | A1003 | 0X | 2 | 2019-05-17 | CON-BMP-VTRA-011652 | 2019-05-17 | FOR BAPCO REVIEW | 2019-05-31 | 2019-05-31 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000859 | CLASS 2
076551C-000R-MR-0811-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V H.P. VESSELS | WALTER TOSTO S.P.A. | 018V1003 | WB 18112.02 | 018-C-MCD-40008-001 | WELDING BOOK - HP-HT SEPARATOR 018V1003 018V2003 | B1304 | 0X | 2 | 2019-05-22 | CON-BMP-VTRA-011710 | 2019-05-22 | FOR BAPCO REVIEW | 2019-06-05 | 2019-07-01 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001122 | CLASS 2
076551C-000R-MR-0811-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V H.P. VESSELS | WALTER TOSTO S.P.A. | 018V1005 | DWG-18112.03-01 | 018-C-GAD-40090-001 | TRAIN 1 HT-MT SEPARATOR 018V1005 GENERAL ASSEMBLY 1/2 (EX BAPCO N.018-C-GAD-00090- 001) | A1103 | DX | 2 | 2019-06-14 | CON-BMP-VTRA-012230 | 2019-06-14 | FOR BAPCO REVIEW | 2019-07-01 | 2019-07-08 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001213 | CLASS 2
076551C-000R-MR-0811-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V H.P. VESSELS | WALTER TOSTO S.P.A. | 018V1005 | DWG-18112.03-02 | 018-C-GAD-40090-002 | TRAIN 1 HT-MT SEPARATOR 018V1005 GENERAL ASSEMBLY 2/2 (EX BAPCO N.018-C-GAD-00090- 002) | A1103 | DX | 2 | 2019-06-14 | CON-BMP-VTRA-012230 | 2019-06-14 | FOR BAPCO REVIEW | 2019-07-01 | 2019-07-08 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001213 | CLASS 2
076551C-000R-MR-0811-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V H.P. VESSELS | WALTER TOSTO S.P.A. | 018V1005 | DWG-18112.03-03 | 018-C-GAD-40093-001 | TRAIN 1 INTERSTAGE SEPARATOR BODY DETAILS 018V1002 018V2002 (EX BAPCO N.018-C-GAD-00091- 001) | A1109 | 0AX | 3 | 2019-06-06 | CON-BMP-VTRA-012035 | 2019-06-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V H.P. VESSELS | WALTER TOSTO S.P.A. | 018V1005 | DWG-18112.03-04 | 018-C-GAD-40093-002 | TRAIN 1 HP-MT SEPARATOR 018V1005 NOZZLE DETAIL (EX BAPCO N. 018-C-GAD-00093-002) | A1109 | 0AX | 3 | 2019-06-29 | CON-BMP-VTRA-012558 | 2019-06-29 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V H.P. VESSELS | WALTER TOSTO S.P.A. | 018V1005 | DWG-18112.03A-06 | 018-C-GAD-40093-004 | TRAIN 1 HP-MT SEPARATOR 018V1005 - INTERNALS DETAILS 1/2 | A1109 | 0AX | 2 | 2019-07-11 | CON-BMP-VTRA-012828 | 2019-07-11 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V H.P. VESSELS | WALTER TOSTO S.P.A. | 018V1005 | DWG-18112.03A-07 | 018-C-GAD-40093-005 | TRAIN 1 HP-MT SEPARATOR 018V1005 INTERNALS DETAILS 2/2 | A1109 | 0X | 3 | 2019-06-20 | CON-BMP-VTRA-012318 | 2019-06-20 | FOR BAPCO REVIEW | 2019-07-04 | 2019-07-10 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001265 | CLASS 2
076551C-000R-MR-0811-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V H.P. VESSELS | WALTER TOSTO S.P.A. | 018V1005 | DWG-18112.03A-08 | 018-C-GAD-40093-006 | TRAIN 1 HP-MT SEPARATOR 018V1005 - EXTERNALS DETAILS 1/2 | A1109 | 0AX | 3 | 2019-07-11 | CON-BMP-VTRA-012827 | 2019-07-11 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V H.P. VESSELS | WALTER TOSTO S.P.A. | 018V1005 | DWG-18112.03A-09 | 018-C-GAD-40341-001 | TRAIN 1 HP-MT SEPARATOR 018V1005 - EXTERNALS DETAILS 2/2 | A1109 | 0AX | 3 | 2019-07-11 | CON-BMP-VTRA-012827 | 2019-07-11 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V H.P. VESSELS | WALTER TOSTO S.P.A. | 018V1005 | DWG-18112.03A-10 | 018-C-DLB-40003-001 | TRAIN 1 HP-MT SEPARATOR 018V1005 - NAMEPLATE DRAWING (EX BAPCO DOC N. 018-C-DLB-00003-001) | A1112 | 0X | 3 | 2019-05-29 | CON-BMP-VTRA-011822 | 2019-05-29 | FOR BAPCO REVIEW | 2019-06-12 | 2019-06-17 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000964 | CLASS 2
076551C-000R-MR-0811-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V H.P. VESSELS | WALTER TOSTO S.P.A. | 018V1005 | DWG-18112.03A-11 | 018-C-GAD-40342-001 | TRAIN 1 HP-MT SEPARATOR 018V1005 - WELDING DRAWING 1/2 | A1109 | 0X | 2 | 2019-06-29 | CON-BMP-VTRA-012561 | 2019-06-29 | FOR BAPCO REVIEW | 2019-07-15 |  |  | CLASS 2
076551C-000R-MR-0811-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V H.P. VESSELS | WALTER TOSTO S.P.A. | 018V1005 | DWG-18112.03A-14 | 018-C-DLB-40006-001 | TRAIN 1 HP-MT SEPARATOR 018V1005 - TEMPLATE DRAWING (EX BAPCO DOC. N. 018-C-DLB- 00006-001) | A2010 | 0X | 3 | 2019-07-08 | CON-BMP-VTRA-012702 | 2019-07-08 | FOR BAPCO REVIEW | 2019-07-22 |  |  | CLASS 2
076551C-000R-MR-0811-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V H.P. VESSELS | WALTER TOSTO S.P.A. | 018V1005 | DWG-18112.03A-15 | 018-C-GAD-40361-001 | TRAIN 1 HP-MT SEPARATOR 018V1005 WELDING DRAWING 2/2 | A1109 | 0X | 2 | 2019-06-29 | CON-BMP-VTRA-012561 | 2019-06-29 | FOR BAPCO REVIEW | 2019-07-15 |  |  | CLASS 2
076551C-000R-MR-0811-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V H.P. VESSELS | WALTER TOSTO S.P.A. | 018V1005 | FEA-18112.03A-1 | 018-C-CAL-40011-001 | TRAIN 1 HP-MT SEPARATOR 018V1005 FEA REPORT | A1003 | AX | 2 | 2019-01-21 | CON-BMP-VTRA-010257 | 2019-01-21 | FOR BAPCO REVIEW | 2019-02-04 | 2019-02-03 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000149 | CLASS 2
076551C-000R-MR-0811-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V H.P. VESSELS | WALTER TOSTO S.P.A. | 018V1005 | HTP-18112.03 | 018-C-PRO-40004-001 | HEAT TREATMENT PROCEDURE PWHT PROCEDURE HP/MT SEPARATOR 018V1005 018V2005 | B1201 | AX | 2 | 2019-01-18 | CON-BMP-VTRA-010247 | 2019-01-18 | FOR BAPCO REVIEW | 2019-02-04 | 2019-01-29 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000134 | CLASS 2
076551C-000R-MR-0811-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V H.P. VESSELS | WALTER TOSTO S.P.A. | 018V1005 | ITP-18112.03A | 018-C-PQP-40005-001 | INSPECTION TEST PLAN - HP-MT SEPARATOR 018V1005 (EX BAPCO N.018-C-PQP-00005-001) | B1002 | 0X | 3 | 2019-06-14 | CON-BMP-VTRA-012219 | 2019-06-14 | FOR BAPCO REVIEW | 2019-06-28 | 2019-06-30 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001097 | CLASS 2
076551C-000R-MR-0811-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V H.P. VESSELS | WALTER TOSTO S.P.A. | 018V1005 | MCR-18112.03 | 018-C-CAL-40009-001 | HP-MT SEPARATOR 018V1005 MECHANICAL CALCULATION REPORT (EX BAPCO N.018-C-CAL-00009-001) | A1003 | 0AX | 4 | 2019-07-08 | CON-BMP-VTRA-012705 | 2019-07-08 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V H.P. VESSELS | WALTER TOSTO S.P.A. | 018V1005 | MPT-18112.03A | 018-C-CAL-40065-001 | MINIMUM PRESSURIZATION TEMPERATURE (MPT) - TRAIN 1 HP-MT SEPARATOR 018V1005 | A1003 | AX | 2 | 2019-06-21 | CON-BMP-VTRA-012362 | 2019-06-21 | FOR BAPCO REVIEW | 2019-07-05 | 2019-07-11 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001303 | CLASS 2
076551C-000R-MR-0811-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V H.P. VESSELS | WALTER TOSTO S.P.A. | 018V1005 | PS-18112.03 | 018-C-TSP-40003-001 | PAINTING SURFACE PROTECTION PROCDURE TRAIN 1 & 2 HP-MT SEPARATORS - 018V1005 / 018V2005 | A0106 | 0X | 3 | 2019-06-25 | CON-BMP-VTRA-012423 | 2019-06-25 | FOR BAPCO REVIEW | 2019-07-09 | 2019-07-08 | 1-APPROVED BMP-ROC-VTRE-001222 | CLASS 2
076551C-000R-MR-0811-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V H.P. VESSELS | WALTER TOSTO S.P.A. | 018V1005 | PTP-18112.03 | 018-C-MCD-40012-001 | PRODUCTION TEST PLATE PROCEDURE - 018V1005 / 018V2005 | B1304 | AX | 2 | 2019-01-14 | CON-BMP-VTRA-010210 | 2019-01-14 | FOR BAPCO REVIEW | 2019-01-29 | 2019-01-25 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000128 | CLASS 2
076551C-000R-MR-0811-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V H.P. VESSELS | WALTER TOSTO S.P.A. | 018V1005 | SCR-18112.03 | 018-C-CAL-40010-001 | STRUCTURAL CALCULATION REPORT HP-MT SEPARATOR 018V1005 (EX BAPCO N.018-C-CAL-00010-001) | A1003 | 0X | 2 | 2019-05-17 | CON-BMP-VTRA-011652 | 2019-05-17 | FOR BAPCO REVIEW | 2019-05-31 | 2019-05-31 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000859 | CLASS 2
076551C-000R-MR-0811-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V H.P. VESSELS | WALTER TOSTO S.P.A. | 018V1005 | WB 18112.03 | 018-C-MCD-40009-001 | WELDING BOOK - HP-MT SEPARATOR 018V1005 018V2005 | B1304 | 0X | 2 | 2019-05-22 | CON-BMP-VTRA-011710 | 2019-05-22 | FOR BAPCO REVIEW | 2019-06-05 | 2019-07-01 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001122 | CLASS 2
076551C-000R-MR-0811-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V H.P. VESSELS | WALTER TOSTO S.P.A. | 018V2002 | DWG-18112.01B-01 | 018-C-GAD-40124-001 | TRAIN 2 INTERSTAGE SEPARATOR 018V2002 - GENERAL ASSEMBLY 1/2 (EX BAPCO N.018-C-GAD- 00124-001) | A1103 | 0AX | 2 | 2019-07-08 | CON-BMP-VTRA-012708 | 2019-07-08 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V H.P. VESSELS | WALTER TOSTO S.P.A. | 018V2002 | DWG-18112.01B-02 | 018-C-GAD-40124-002 | TRAIN 2 INTERSTAGE SEPARATOR 018V2002 - GENERAL ASSEMBLY 2/2 (EX BAPCO N.018-C-GAD- 00124-002) | A1103 | 0AX | 3 | 2019-07-08 | CON-BMP-VTRA-012703 | 2019-07-08 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V H.P. VESSELS | WALTER TOSTO S.P.A. | 018V2002 | DWG-18112.01B-03 | 018-C-GAD-40127-001 | TRAIN 2 INTERSTAGE SEPARATOR 018V2002 BODY DETAIL | A1109 | 0BX | 3 | 2019-06-21 | CON-BMP-VTRA-012368 | 2019-06-21 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V H.P. VESSELS | WALTER TOSTO S.P.A. | 018V2002 | DWG-18112.01B-04 | 018-C-GAD-40127-002 | TRAIN 2 INTERSTAGE SEPARATOR 018V2002 NOZZLES DETAILS 1/2 | A1109 | 0X | 3 | 2019-06-22 | CON-BMP-VTRA-012371 | 2019-06-22 | FOR BAPCO REVIEW | 2019-07-08 |  |  | CLASS 2
076551C-000R-MR-0811-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V H.P. VESSELS | WALTER TOSTO S.P.A. | 018V2002 | DWG-18112.01B-05 | 018-C-GAD-40127-003 | TRAIN 2 INTERSTAGE SEPARATOR 018V2002 NOZZLES DETAILS 2/2 | A1109 | 0X | 3 | 2019-06-22 | CON-BMP-VTRA-012371 | 2019-06-22 | FOR BAPCO REVIEW | 2019-07-08 |  |  | CLASS 2
076551C-000R-MR-0811-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V H.P. VESSELS | WALTER TOSTO S.P.A. | 018V2002 | DWG-18112.01B-06 | 018-C-GAD-40127-004 | TRAIN 2 INTERSTAGE SEPARATOR 018V2002 INTERNALS DETAILS 1/2 | A1109 | 0X | 3 | 2019-06-21 | CON-BMP-VTRA-012360 | 2019-06-21 | FOR BAPCO REVIEW | 2019-07-05 | 2019-07-11 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001304 | CLASS 2
076551C-000R-MR-0811-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V H.P. VESSELS | WALTER TOSTO S.P.A. | 018V2002 | DWG-18112.01B-07 | 018-C-GAD-40127-005 | TRAIN 2 INTERSTAGE SEPARATOR 018V2002 INTERNALS DETAILS 2/2 | A1109 | 0X | 3 | 2019-06-22 | CON-BMP-VTRA-012371 | 2019-06-22 | FOR BAPCO REVIEW | 2019-07-08 |  |  | CLASS 2
076551C-000R-MR-0811-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V H.P. VESSELS | WALTER TOSTO S.P.A. | 018V2002 | DWG-18112.01B-08 | 018-C-GAD-40127-006 | TRAIN 2 INTERSTAGE SEPARATOR 018V2002 - EXTERNALS DETAILS 1/2 | A1109 | 0X | 3 | 2019-06-22 | CON-BMP-VTRA-012371 | 2019-06-22 | FOR BAPCO REVIEW | 2019-07-08 |  |  | CLASS 2
076551C-000R-MR-0811-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V H.P. VESSELS | WALTER TOSTO S.P.A. | 018V2002 | DWG-18112.01B-09 | 018-C-GAD-40345-001 | TRAIN 2 INTERSTAGE SEPARATOR - EXTERNAL DETAILS 2/2 018V2002 | A1109 | 0X | 3 | 2019-06-26 | CON-BMP-VTRA-012491 | 2019-06-26 | FOR BAPCO REVIEW | 2019-07-11 |  |  | CLASS 2
076551C-000R-MR-0811-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V H.P. VESSELS | WALTER TOSTO S.P.A. | 018V2002 | DWG-18112.01B-10 | 018-C-DLB-40015-001 | TRAIN 2 INTERSTAGE SEPARATOR 018V2002 - NAMEPLATE DRAWING (EX BAPCO N. 018-C-DLB-00015- 001) | A1112 | 0X | 3 | 2019-05-29 | CON-BMP-VTRA-011822 | 2019-05-29 | FOR BAPCO REVIEW | 2019-06-12 | 2019-06-17 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000964 | CLASS 2
076551C-000R-MR-0811-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V H.P. VESSELS | WALTER TOSTO S.P.A. | 018V2002 | DWG-18112.01B-11 | 018-C-GAD-40346-001 | TRAIN 2 INTERSTAGE SEPARATOR 018V2002 - WELDING DRAWING 1/2 | A1109 | AX | 2 | 2019-06-21 | CON-BMP-VTRA-012361 | 2019-06-21 | FOR BAPCO REVIEW | 2019-07-05 |  |  | CLASS 2
076551C-000R-MR-0811-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V H.P. VESSELS | WALTER TOSTO S.P.A. | 018V2002 | DWG-18112.01B-14 | 018-C-DLB-40018-001 | TRAIN 2 INTERSTAGE SEPARATOR 018V2002 - TEMPLATE DRAWING (EX BAPCO DOC.N. 018-C-DLB- 00018-001) | A2010 | 0X | 3 | 2019-07-08 | CON-BMP-VTRA-012702 | 2019-07-08 | FOR BAPCO REVIEW | 2019-07-22 |  |  | CLASS 2
076551C-000R-MR-0811-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V H.P. VESSELS | WALTER TOSTO S.P.A. | 018V2002 | DWG-18112.01B-15 | 018-C-GAD-40346-002 | TRAIN 2 INTERSTAGE SEPARATOR 018V2002 - WELDING DRAWING 2/2 | A1109 | AX | 2 | 2019-06-21 | CON-BMP-VTRA-012361 | 2019-06-21 | FOR BAPCO REVIEW | 2019-07-05 |  |  | CLASS 2
076551C-000R-MR-0811-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V H.P. VESSELS | WALTER TOSTO S.P.A. | 018V2002 | FEA-18112.01B-1 | 018-C-CAL-40031-001 | TRAIN 1 HP-MT SEPARATOR FEA REPORT 018V2002 | A1003 | AX | 2 | 2019-01-21 | CON-BMP-VTRA-010257 | 2019-01-21 | FOR BAPCO REVIEW | 2019-02-04 | 2019-02-03 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000149 | CLASS 2
076551C-000R-MR-0811-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V H.P. VESSELS | WALTER TOSTO S.P.A. | 018V2002 | ITP-18112.01B | 018-C-PQP-40002-001 | INSPECTION TEST PLAN - INTERSTAGE SEPARATOR 018V2002 (EX BAPCO 018-C-PQP-00002-001) | B1002 | 0X | 3 | 2019-06-14 | CON-BMP-VTRA-012219 | 2019-06-14 | FOR BAPCO REVIEW | 2019-06-28 | 2019-06-30 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001097 | CLASS 2
076551C-000R-MR-0811-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V H.P. VESSELS | WALTER TOSTO S.P.A. | 018V2002 | MCR-18112.01B | 018-C-CAL-40029-001 | MECHANICAL CALCULATION REPORT - TRAIN 2 INTERSTAGESEPARATOR 018V2002 | A1003 | 0X | 4 | 2019-07-12 | CON-BMP-VTRA-012829 | 2019-07-12 | FOR BAPCO REVIEW | 2019-07-26 |  |  | CLASS 2
076551C-000R-MR-0811-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V H.P. VESSELS | WALTER TOSTO S.P.A. | 018V2002 | MPT-18112.01B | 018-C-CAL-40068-001 | MINIMUM PRESSURIZATION TEMPERATURE (MPT) - TRAIN 2 INTERSTAGE SEPARATOR 018V2002 | A1003 | AX | 2 | 2019-06-11 | CON-BMP-VTRA-012155 | 2019-06-11 | FOR BAPCO REVIEW | 2019-06-26 | 2019-07-02 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001143 | CLASS 2
076551C-000R-MR-0811-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V H.P. VESSELS | WALTER TOSTO S.P.A. | 018V2002 | SCR-18112.01B | 018-C-CAL-40030-001 | STRUCTURAL CALCULATION REPORT - TRAIN 2 INTERSTAGE SEPARATOR 018V2002 | A1003 | AX | 2 | 2019-05-22 | CON-BMP-VTRA-011709 | 2019-05-22 | FOR BAPCO REVIEW | 2019-06-05 | 2019-07-10 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001255 | CLASS 2
076551C-000R-MR-0811-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V H.P. VESSELS | WALTER TOSTO S.P.A. | 018V2002 | WB 18112.01B | 018-C-MCD-40022-001 | WELDING BOOK - INTERSTAGE SEPARATOR 018V2002 | B1304 | 0X | 2 | 2019-05-22 | CON-BMP-VTRA-011719 | 2019-05-22 | FOR BAPCO REVIEW | 2019-06-05 | 2019-06-12 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000915 | CLASS 2
076551C-000R-MR-0811-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V H.P. VESSELS | WALTER TOSTO S.P.A. | 018V2003 | DWG-18112.02B-01 | 018-C-GAD-40125-001 | TRAIN 2 HP-HT SEPARATOR 018V2003 - GENERAL ASSEMBLY 1/2 (EX BAPCO N.018-C-GAD- 00125-001) | A1103 | 0AX | 2 | 2019-07-08 | CON-BMP-VTRA-012708 | 2019-07-08 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V H.P. VESSELS | WALTER TOSTO S.P.A. | 018V2003 | DWG-18112.02B-02 | 018-C-GAD-40125-002 | TRAIN 2 HP-HT SEPARATOR 018V2003 - GENERAL ASSEMBLY 2/2 (EX BAPCO N. 018-C-GAD-00125-002) | A1103 | 0AX | 3 | 2019-07-08 | CON-BMP-VTRA-012703 | 2019-07-08 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V H.P. VESSELS | WALTER TOSTO S.P.A. | 018V2003 | DWG-18112.02B-03 | 018-C-GAD-40128-001 | TRAIN 2 HP-HT SEPARATOR 018V2003 BODY DETAIL | A1109 | 0BX | 3 | 2019-06-21 | CON-BMP-VTRA-012368 | 2019-06-21 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V H.P. VESSELS | WALTER TOSTO S.P.A. | 018V2003 | DWG-18112.02B-04 | 018-C-GAD-40349-001 | TRAIN 2 HP-HT SEPARATOR 018V2003 NOZZLES DETAILS 1/2 | A1109 | 0X | 3 | 2019-06-22 | CON-BMP-VTRA-012371 | 2019-06-22 | FOR BAPCO REVIEW | 2019-07-08 |  |  | CLASS 2
076551C-000R-MR-0811-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V H.P. VESSELS | WALTER TOSTO S.P.A. | 018V2003 | DWG-18112.02B-05 | 018-C-GAD-40350-001 | TRAIN 2 HP-HT SEPARATOR 018V2003 NOZZLES DETAILS 2/2 | A1109 | 0X | 3 | 2019-06-22 | CON-BMP-VTRA-012371 | 2019-06-22 | FOR BAPCO REVIEW | 2019-07-08 |  |  | CLASS 2
076551C-000R-MR-0811-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V H.P. VESSELS | WALTER TOSTO S.P.A. | 018V2003 | DWG-18112.02B-06 | 018-C-GAD-40128-004 | TRAIN 2 HP-HT SEPARATOR 018V2003 INTERNAL DETAILS 1/2 | A1109 | 0AX | 3 | 2019-06-21 | CON-BMP-VTRA-012370 | 2019-06-21 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V H.P. VESSELS | WALTER TOSTO S.P.A. | 018V2003 | DWG-18112.02B-07 | 018-C-GAD-40128-005 | TRAIN 2 HP-HT SEPARATOR 018V2003 INTERNAL DETAILS 2/2 | A1109 | 0X | 3 | 2019-06-22 | CON-BMP-VTRA-012371 | 2019-06-22 | FOR BAPCO REVIEW | 2019-07-08 |  |  | CLASS 2
076551C-000R-MR-0811-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V H.P. VESSELS | WALTER TOSTO S.P.A. | 018V2003 | DWG-18112.02B-08 | 018-C-GAD-40128-006 | TRAIN 2 HP-HT SEPARATOR 018V2003 - EXTERNALS DETAILS 1/2 | A1109 | 0X | 3 | 2019-06-22 | CON-BMP-VTRA-012371 | 2019-06-22 | FOR BAPCO REVIEW | 2019-07-08 |  |  | CLASS 2
076551C-000R-MR-0811-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V H.P. VESSELS | WALTER TOSTO S.P.A. | 018V2003 | DWG-18112.02B-09 | 018-C-GAD-40351-001 | TRAIN 2 HP-HT SEPARATOR 018V2003 - EXTERNALS DETAILS 2/2 | A1109 | AX | 2 | 2019-06-21 | CON-BMP-VTRA-012361 | 2019-06-21 | FOR BAPCO REVIEW | 2019-07-05 |  |  | CLASS 2
076551C-000R-MR-0811-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V H.P. VESSELS | WALTER TOSTO S.P.A. | 018V2003 | DWG-18112.02B-10 | 018-C-DLB-40016-001 | TRAIN 2 HP-HT SEPARATOR 018V2003 - NAMEPLATE DRAWING (EX BAPCO DOC N. 018-C-DLB-00016-001) | A1112 | 0X | 3 | 2019-05-29 | CON-BMP-VTRA-011822 | 2019-05-29 | FOR BAPCO REVIEW | 2019-06-12 | 2019-06-17 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000964 | CLASS 2
076551C-000R-MR-0811-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V H.P. VESSELS | WALTER TOSTO S.P.A. | 018V2003 | DWG-18112.02B-11 | 018-C-GAD-40352-001 | TRAIN 2 HP-HT SEPARATOR 018V2003 - WELDING DRAWING 1/2 | A1109 | AX | 2 | 2019-06-29 | CON-BMP-VTRA-012559 | 2019-06-29 | FOR BAPCO REVIEW | 2019-07-15 |  |  | CLASS 2
076551C-000R-MR-0811-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V H.P. VESSELS | WALTER TOSTO S.P.A. | 018V2003 | DWG-18112.02B-14 | 018-C-DLB-40019-001 | TRAIN 2 HP-HT SEPARATOR 018V2003 - TEMPLATE DRAWING (EX BAPCO DOC N. 018-C-DLB- 00019-001) | A2010 | 0X | 3 | 2019-07-08 | CON-BMP-VTRA-012702 | 2019-07-08 | FOR BAPCO REVIEW | 2019-07-22 |  |  | CLASS 2
076551C-000R-MR-0811-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V H.P. VESSELS | WALTER TOSTO S.P.A. | 018V2003 | DWG-18112.02B-15 | 018-C-GAD-40352-002 | TRAIN 2 HP-HT SEPARATOR 018V2003 - WELDING DRAWING 2/2 | A1109 | AX | 2 | 2019-06-21 | CON-BMP-VTRA-012361 | 2019-06-21 | FOR BAPCO REVIEW | 2019-07-05 |  |  | CLASS 2
076551C-000R-MR-0811-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V H.P. VESSELS | WALTER TOSTO S.P.A. | 018V2003 | ITP-18112.02B | 018-C-PQP-40004-001 | INSPECTION TEST PLAN - HP-HT SEPARATOR 018V2003 (EX BAPCO N.018-C-PQP-00004-001) | B1002 | 0X | 3 | 2019-06-14 | CON-BMP-VTRA-012219 | 2019-06-14 | FOR BAPCO REVIEW | 2019-06-28 | 2019-06-30 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001097 | CLASS 2
076551C-000R-MR-0811-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V H.P. VESSELS | WALTER TOSTO S.P.A. | 018V2003 | MPT-18112.02B | 018-C-CAL-40069-001 | MINIMUM PRESSURIZATION TEMPERATURE (MPT) - TRAIN 2 HP-HT SEPARATOR 018V2003 | A1003 | AX | 2 | 2019-06-11 | CON-BMP-VTRA-012155 | 2019-06-11 | FOR BAPCO REVIEW | 2019-06-26 | 2019-07-02 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001143 | CLASS 2
076551C-000R-MR-0811-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V H.P. VESSELS | WALTER TOSTO S.P.A. | 018V2003 | WB 18112.02B | 018-C-MCD-40023-001 | WELDING BOOK - HP/HT SEPARATOR 018V2003 | B1304 | 0X | 2 | 2019-05-22 | CON-BMP-VTRA-011719 | 2019-05-22 | FOR BAPCO REVIEW | 2019-06-05 | 2019-06-12 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000915 | CLASS 2
076551C-000R-MR-0811-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V H.P. VESSELS | WALTER TOSTO S.P.A. | 018V2005 | DWG-18112.03B-01 | 018-C-GAD-40126-001 | TRAIN 2 HP-MT SEPARATOR 018V2005 - GENERAL ASSEMBLY 1/2 (EX BAPCO N.018-C-GAD-00126- 001) | A1103 | 0AX | 3 | 2019-07-08 | CON-BMP-VTRA-012715 | 2019-07-08 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V H.P. VESSELS | WALTER TOSTO S.P.A. | 018V2005 | DWG-18112.03B-02 | 018-C-GAD-40126-002 | TRAIN 2 HP-MT SEPARATOR 018V2005 - GENERAL ASSEMBLY 2/2 (EX BAPCO N. 018-C-GAD-00126-002) | A1103 | 0AX | 3 | 2019-07-08 | CON-BMP-VTRA-012715 | 2019-07-08 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V H.P. VESSELS | WALTER TOSTO S.P.A. | 018V2005 | DWG-18112.03B-03 | 018-C-GAD-40129-001 | TRAIN 2 HP-MT SEPARATOR 018V2005 BODY DETAILS | A1109 | 0AX | 3 | 2019-05-22 | CON-BMP-VTRA-011715 | 2019-05-22 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V H.P. VESSELS | WALTER TOSTO S.P.A. | 018V2005 | DWG-18112.03B-04 | 018-C-GAD-40355-001 | TRAIN 2 HP-MT SEPARATOR 018V2005 NOZZLE DETAILS | A1109 | 0X | 3 | 2019-06-29 | CON-BMP-VTRA-012557 | 2019-06-29 | FOR BAPCO REVIEW | 2019-07-15 |  |  | CLASS 2
076551C-000R-MR-0811-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V H.P. VESSELS | WALTER TOSTO S.P.A. | 018V2005 | DWG-18112.03B-06 | 018-C-GAD-40129-003 | TRAIN 2 HP-MT SEPARATOR 018V2005 - INTERNAL DETAILS 1/2 | A1109 | 0X | 2 | 2019-06-29 | CON-BMP-VTRA-012562 | 2019-06-29 | FOR BAPCO REVIEW | 2019-07-15 |  |  | CLASS 2
076551C-000R-MR-0811-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V H.P. VESSELS | WALTER TOSTO S.P.A. | 018V2005 | DWG-18112.03B-07 | 018-C-GAD-40129-004 | TRAIN 2 HP-MT SEPARATOR 018V2005 - INTERNAL DETAILS 2/2 | A1109 | 0X | 3 | 2019-06-20 | CON-BMP-VTRA-012321 | 2019-06-20 | FOR BAPCO REVIEW | 2019-07-04 | 2019-07-11 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001299 | CLASS 2
076551C-000R-MR-0811-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V H.P. VESSELS | WALTER TOSTO S.P.A. | 018V2005 | DWG-18112.03B-08 | 018-C-GAD-40129-005 | TRAIN 2 HP-MT SEPARATOR 018V2005 - EXTERNALS DETAILS 1/2 | A1109 | 0X | 3 | 2019-06-29 | CON-BMP-VTRA-012556 | 2019-06-29 | FOR BAPCO REVIEW | 2019-07-15 |  |  | CLASS 2
076551C-000R-MR-0811-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V H.P. VESSELS | WALTER TOSTO S.P.A. | 018V2005 | DWG-18112.03B-09 | 018-C-GAD-40356-001 | TRAIN 2 HP-MT SEPARATOR EXTERNAL DETAILS (2/2) 018V2005 | A1109 | AX | 2 | 2019-05-21 | CON-BMP-VTRA-011704 | 2019-05-21 | FOR BAPCO REVIEW | 2019-06-05 | 2019-06-06 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000888 | CLASS 2
076551C-000R-MR-0811-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V H.P. VESSELS | WALTER TOSTO S.P.A. | 018V2005 | DWG-18112.03B-10 | 018-C-DLB-40017-001 | TRAIN 2 HP-MT SEPARATOR 018V2005 - NAMEPLATE DRAWING (EX BAPCO DOC N. 018-C-DLB-00017-001) | A1112 | 0X | 3 | 2019-05-29 | CON-BMP-VTRA-011822 | 2019-05-29 | FOR BAPCO REVIEW | 2019-06-12 | 2019-06-17 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000964 | CLASS 2
076551C-000R-MR-0811-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V H.P. VESSELS | WALTER TOSTO S.P.A. | 018V2005 | DWG-18112.03B-11 | 018-C-GAD-40357-001 | TRAIN 2 HP-MT SEPARATOR WELDING DRAWING 1/2 018V2005 | A1109 | AX | 2 | 2019-06-29 | CON-BMP-VTRA-012559 | 2019-06-29 | FOR BAPCO REVIEW | 2019-07-15 |  |  | CLASS 2
076551C-000R-MR-0811-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V H.P. VESSELS | WALTER TOSTO S.P.A. | 018V2005 | DWG-18112.03B-14 | 018-C-DLB-40020-001 | TRAIN 2 HP-MT SEPARATOR 018V2005 - TEMPLATE DRAWING (EX BAPCO DOC. N. 018-C-DLB- 00020-001) | A2010 | 0X | 3 | 2019-07-08 | CON-BMP-VTRA-012702 | 2019-07-08 | FOR BAPCO REVIEW | 2019-07-22 |  |  | CLASS 2
076551C-000R-MR-0811-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V H.P. VESSELS | WALTER TOSTO S.P.A. | 018V2005 | DWG-18112.03B-15 | 018-C-GAD-40357-002 | TRAIN 2 HP-MT SEPARATOR WELDING DRAWING 2/2 018V2005 | A1109 | AX | 2 | 2019-06-29 | CON-BMP-VTRA-012560 | 2019-06-29 | FOR BAPCO REVIEW | 2019-07-15 |  |  | CLASS 2
076551C-000R-MR-0811-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V H.P. VESSELS | WALTER TOSTO S.P.A. | 018V2005 | FEA-18112.03B | 018-C-CAL-40039-001 | TRAIN 2 HP-MT SEPARATOR 018V2005 FEA REPORT | A1003 | AX | 2 | 2019-01-21 | CON-BMP-VTRA-010257 | 2019-01-21 | FOR BAPCO REVIEW | 2019-02-04 | 2019-02-03 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000149 | CLASS 2
076551C-000R-MR-0811-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V H.P. VESSELS | WALTER TOSTO S.P.A. | 018V2005 | ITP-18112.03B | 018-C-PQP-40006-001 | INSPECTION TEST PLAN - HP-MT SEPARATOR 018V2005 (EX BAPCO N.018-C-PQP-00006-001) | B1002 | 0X | 3 | 2019-06-14 | CON-BMP-VTRA-012219 | 2019-06-14 | FOR BAPCO REVIEW | 2019-06-28 | 2019-06-30 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001097 | CLASS 2
076551C-000R-MR-0811-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V H.P. VESSELS | WALTER TOSTO S.P.A. | 018V2005 | MPT-18112.03B | 018-C-CAL-40070-001 | MINIMUM PRESSURIZATION TEMPERATURE (MPT) - TRAIN 2 HP-MT SEPARATOR 018V2005 | A1003 | AX | 2 | 2019-06-21 | CON-BMP-VTRA-012362 | 2019-06-21 | FOR BAPCO REVIEW | 2019-07-05 | 2019-07-11 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001303 | CLASS 2
076551C-000R-MR-0811-001 | MATERIAL REQUISITION FOR 2.25CR-1MO-V H.P. VESSELS | WALTER TOSTO S.P.A. | 018V2005 | WB 18112.03B | 018-C-MCD-40024-001 | WELDING BOOK - HP/MT SEPARATOR 018V2005 | B1304 | 0X | 2 | 2019-05-22 | CON-BMP-VTRA-011719 | 2019-05-22 | FOR BAPCO REVIEW | 2019-06-05 | 2019-06-12 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000915 | CLASS 2
076551C-000R-MR-0811-002 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | HANTECH LTD | 018V0003 | HW19008-018V0003-CAL-001 | 018-C-CAL-40072-001 | STRENGTH CALCULATION 018V0003 | A1003 | AXX | 2 | 2019-04-15 | CON-BMP-VTRA-011178 | 2019-04-15 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-002 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | HANTECH LTD | 018V0003 | HW19008-018V0003-DWG-001 | 018-C-GAD-40362-001 | MP/MT SEPARATOR GENERAL ASSEMBLY 018V0003 | A1103 | AXX | 2 | 2019-05-30 | CON-BMP-VTRA-011862 | 2019-05-30 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-002 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | HANTECH LTD | 018V0003 | HW19008-018V0003-DWG-002 | 018-C-GAD-40363-001 | MP/MT SEPARATOR DETAIL OF BODY 018V0003 | A1109 | AXC | 2 | 2019-05-17 | CON-BMP-VTRA-011663 | 2019-05-17 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-002 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | HANTECH LTD | 018V0003 | HW19008-018V0003-DWG-003 | 018-C-GAD-40364-001 | MP/MT SEPARATOR DETAIL OF MANHOLE 018V0003 | A1109 | AX | 2 | 2019-04-29 | CON-BMP-VTRA-011310 | 2019-04-29 | FOR BAPCO REVIEW | 2019-05-15 | 2019-05-23 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000742 | CLASS 2
076551C-000R-MR-0811-002 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | HANTECH LTD | 018V0003 | HW19008-018V0003-DWG-004 | 018-C-GAD-40365-001 | MP/MT SEPARATOR DETAIL OF NOZZLE (1/3) 018V0003 | A1109 | AX | 2 | 2019-04-29 | CON-BMP-VTRA-011310 | 2019-04-29 | FOR BAPCO REVIEW | 2019-05-15 | 2019-05-23 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000742 | CLASS 2
076551C-000R-MR-0811-002 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | HANTECH LTD | 018V0003 | HW19008-018V0003-DWG-005 | 018-C-GAD-40365-002 | MP/MT SEPARATOR DETAIL OF NOZZLE (2/3) 018V0003 | A1109 | AX | 2 | 2019-04-29 | CON-BMP-VTRA-011310 | 2019-04-29 | FOR BAPCO REVIEW | 2019-05-15 | 2019-05-23 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000742 | CLASS 2
076551C-000R-MR-0811-002 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | HANTECH LTD | 018V0003 | HW19008-018V0003-DWG-006 | 018-C-GAD-40365-003 | MP/MT SEPARATOR DETAIL OF NOZZLE (3/3) 018V0003 | A1109 | AX | 2 | 2019-04-29 | CON-BMP-VTRA-011310 | 2019-04-29 | FOR BAPCO REVIEW | 2019-05-15 | 2019-05-23 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000742 | CLASS 2
076551C-000R-MR-0811-002 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | HANTECH LTD | 018V0003 | HW19008-018V0003-DWG-009 | 018-C-DLB-40035-001 | MP/MT SEPARATOR DETAIL OF TEMPLATE 018V0003 | A2010 | BX | 2 | 2019-07-03 | CON-BMP-VTRA-012642 | 2019-07-03 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-002 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | HANTECH LTD | 018V0003 | HW19008-DOC-100 | 000-C-MRS-40006-001 | MONTHLY PROGRESS REPORT 018V0003 018V0004 018V0037-0038 018V0039 018V0050 021V0004 021V0008 018V1048-2048 | C1002 | BX | 2 | 2019-05-23 | CON-BMP-VTRA-011739 | 2019-05-23 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-0811-002 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | HANTECH LTD | 018V0003 | HW19008-DOC-110 | 000-C-INX-40008-001 | LIST OF VENDOR'S DOCUMENTS AND DWGS ALL ITEMS | A0001 | AX | 2 | 2019-05-06 | CON-BMP-VTRA-011440 | 2019-05-06 | FOR BAPCO REVIEW | 2019-05-21 | 2019-05-25 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000763 | CLASS 2
076551C-000R-MR-0811-002 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | HANTECH LTD | 018V0003 | HW19008-DOC-120 | 000-C-PQS-40002-001 | SUB VENDOR LIST ALL ITEMS | B1401 | AX | 2 | 2019-05-06 | CON-BMP-VTRA-011443 | 2019-05-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-0811-002 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | HANTECH LTD | 018V0003 | HW19008-DOC-130 | 000-C-TSP-40006-001 | MATERIAL PURCHASE SPECIFICATION FOR MAIN SUBORDERS ALL ITEMS | B1203 | AXX | 2 | 2019-07-04 | CON-BMP-VTRA-012670 | 2019-07-04 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-002 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | HANTECH LTD | 018V0003 | HW19008-DOC-140 | 000-C-SCH-40005-001 | ENGINEERING PROCUREMENT MANUFACTURING AND TEST SCHEDULE ALL ITEMS | C1001 | AX | 2 | 2019-05-06 | CON-BMP-VTRA-011426 | 2019-05-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-0811-002 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | HANTECH LTD | 018V0003 | HW19008-DOC-150 | 018-C-PQP-40025-001 | FABRICATION AND QUIALITY CONTROL PLAN FOR 018V0003 | B1002 | AXX | 2 | 2019-06-27 | CON-BMP-VTRA-012536 | 2019-06-27 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-002 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | HANTECH LTD | 018V0003 | HW19008-DOC-180 | 018-C-MCD-40034-001 | WPS AND PQR WITH WELD MAP (WELDER QUALIFICATION RECORD) FOR 018V0003 | B1103 | AX | 2 | 2019-03-12 | CON-BMP-VTRA-010657 | 2019-03-12 | FOR BAPCO REVIEW | 2019-03-26 | 2019-03-20 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000351 | CLASS 2
076551C-000R-MR-0811-002 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | HANTECH LTD | 018V0003 | HW19008-DOC-200 | 000-C-PRO-40035-001 | NDE PROCEDURE ALL ITEMS | B1202 | AX | 2 | 2019-04-16 | CON-BMP-VTRA-011195 | 2019-04-16 | FOR BAPCO REVIEW | 2019-04-30 | 2019-04-23 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000546 | CLASS 2
076551C-000R-MR-0811-002 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | HANTECH LTD | 018V0003 | HW19008-DOC-210 | 000-C-PRO-40036-001 | PMI TEST PROCEDURE ALL ITEMS | B1202 | AXX | 2 | 2019-05-07 | CON-BMP-VTRA-011469 | 2019-05-08 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-002 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | HANTECH LTD | 018V0003 | HW19008-DOC-220 | 000-C-PRO-40037-001 | HEAT TREATMENT PROCEDURE ALL ITEMS | B1201 | AX | 2 | 2019-05-22 | CON-BMP-VTRA-011720 | 2019-05-22 | FOR BAPCO REVIEW | 2019-06-05 | 2019-06-03 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000877 | CLASS 2
076551C-000R-MR-0811-002 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | HANTECH LTD | 018V0003 | HW19008-DOC-230 | 000-C-PRO-40038-001 | HYDROSTATIC TEST PROCEDURE ALL ITEMS | B1103 | AX | 2 | 2019-05-21 | CON-BMP-VTRA-011707 | 2019-05-21 | FOR BAPCO REVIEW | 2019-06-05 | 2019-06-06 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000890 | CLASS 2
076551C-000R-MR-0811-002 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | HANTECH LTD | 018V0003 | HW19008-DOC-240 | 000-C-TSP-40007-001 | BOLT TIGHTENING PROCEDURE 018V0003 018V0004 018V0037/0038 018V0039 018V0050 021V0004 021V0008 018V1048/2048 | A1202 | AX | 2 | 2019-05-21 | CON-BMP-VTRA-011706 | 2019-05-21 | FOR BAPCO REVIEW | 2019-06-05 | 2019-06-13 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000920 | CLASS 2
076551C-000R-MR-0811-002 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | HANTECH LTD | 018V0003 | HW19008-DOC-700 | 000-C-INV-40007-001 | UNPRICED COPY OF MAIN SUBORDERS ALL ITEMS | C1005 | BX | 2 | 2019-05-28 | CON-BMP-VTRA-011819 | 2019-05-29 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-002 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | HANTECH LTD | 018V0004 | HW19008-018V0004-CAL-001 | 018-C-CAL-40073-001 | STRENGTH CALCULATION 018V0004 | A1003 | AXX | 2 | 2019-05-10 | CON-BMP-VTRA-011528 | 2019-05-10 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-002 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | HANTECH LTD | 018V0004 | HW19008-018V0004-DWG-001 | 018-C-GAD-40367-001 | MP/LT SEPARATOR GENERAL ASSEMBLY 018V0004 | A1103 | AXX | 2 | 2019-05-30 | CON-BMP-VTRA-011862 | 2019-05-30 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-002 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | HANTECH LTD | 018V0004 | HW19008-018V0004-DWG-002 | 018-C-GAD-40368-001 | MP/LT SEPARATOR DETAIL OF BODY 018V0004 | A1109 | AXX | 2 | 2019-05-17 | CON-BMP-VTRA-011663 | 2019-05-17 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-002 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | HANTECH LTD | 018V0004 | HW19008-018V0004-DWG-003 | 018-C-GAD-40369-001 | MP/MT SEPARATOR DETAIL OF MANHOLE 18V0004 | A1109 | AX | 2 | 2019-04-29 | CON-BMP-VTRA-011310 | 2019-04-29 | FOR BAPCO REVIEW | 2019-05-15 | 2019-05-23 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000742 | CLASS 2
076551C-000R-MR-0811-002 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | HANTECH LTD | 018V0004 | HW19008-018V0004-DWG-004 | 018-C-GAD-40370-001 | MP/LT SEPARATOR DETAIL OF NOZZLE (1/3) 18V0004 | A1109 | AX | 2 | 2019-04-29 | CON-BMP-VTRA-011310 | 2019-04-29 | FOR BAPCO REVIEW | 2019-05-15 | 2019-05-23 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000742 | CLASS 2
076551C-000R-MR-0811-002 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | HANTECH LTD | 018V0004 | HW19008-018V0004-DWG-005 | 018-C-GAD-40370-002 | MP/LT SEPARATOR DETAIL OF NOZZLE (2/3) 018V0004 | A1109 | AX | 2 | 2019-04-29 | CON-BMP-VTRA-011310 | 2019-04-29 | FOR BAPCO REVIEW | 2019-05-15 | 2019-05-23 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000742 | CLASS 2
076551C-000R-MR-0811-002 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | HANTECH LTD | 018V0004 | HW19008-018V0004-DWG-006 | 018-C-GAD-40370-003 | MP/LT SEPARATOR DETAIL OF NOZZLE (3/3) 018V0004 | A1109 | AX | 2 | 2019-04-29 | CON-BMP-VTRA-011310 | 2019-04-29 | FOR BAPCO REVIEW | 2019-05-15 | 2019-05-23 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000742 | CLASS 2
076551C-000R-MR-0811-002 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | HANTECH LTD | 018V0004 | HW19008-018V0004-DWG-011 | 018-C-DLB-40037-001 | MP/LT SEPARATOR DETAIL OF TEMPLATE 018V0004 | A2010 | BX | 2 | 2019-07-03 | CON-BMP-VTRA-012642 | 2019-07-03 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-002 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | HANTECH LTD | 018V0004 | HW19008-DOC-151 | 018-C-PQP-40026-001 | FABRICATION AND QUIALITY CONTROL PLAN FOR 018V0004 | B1002 | AXX | 2 | 2019-06-27 | CON-BMP-VTRA-012536 | 2019-06-27 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-002 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | HANTECH LTD | 018V0004 | HW19008-DOC-181 | 018-C-MCD-40043-001 | WPS AND PQR WITH WELD MAP (WELDER QUALIFICATION RECORD) FOR 018V0004 | B1103 | AX | 2 | 2019-03-12 | CON-BMP-VTRA-010657 | 2019-03-12 | FOR BAPCO REVIEW | 2019-03-26 | 2019-03-20 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000351 | CLASS 2
076551C-000R-MR-0811-002 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | HANTECH LTD | 018V0037 | HW19008-018V0037/38-CAL-001 | 018-C-CAL-40074-001 | STRENGTH CALCULATION 018V0037 018V0038 | A1003 | AXX | 2 | 2019-05-10 | CON-BMP-VTRA-011528 | 2019-05-10 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-002 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | HANTECH LTD | 018V0037 | HW19008-018V0037/38-DWG-001 | 018-C-GAD-40372-001 | CATALYST TRANSFER VESSEL GENERAL ASSEMBLY 018V0037 018V0038 | A1103 | AXX | 2 | 2019-05-30 | CON-BMP-VTRA-011862 | 2019-05-30 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-002 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | HANTECH LTD | 018V0037 | HW19008-018V0037/38-DWG-002 | 018-C-GAD-40373-001 | CATALYST TRANSFER VESSEL DETAIL OF BODY 018V0037/38 | A1109 | BX | 2 | 2019-07-08 | CON-BMP-VTRA-012722 | 2019-07-08 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-002 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | HANTECH LTD | 018V0037 | HW19008-018V0037/38-DWG-003 | 018-C-GAD-40374-001 | CATALYST TRANSFER VESSEL DETAIL OF MANHOLE 018V0037 018V0038 | A1109 | BX | 2 | 2019-07-08 | CON-BMP-VTRA-012722 | 2019-07-08 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-002 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | HANTECH LTD | 018V0037 | HW19008-018V0037/38-DWG-004 | 018-C-GAD-40375-001 | CATALYST TRANSFER VESSEL DETAIL OF NOZZLE (1/5) 018V0037 018V0038 | A1109 | BX | 2 | 2019-07-08 | CON-BMP-VTRA-012722 | 2019-07-08 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-002 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | HANTECH LTD | 018V0037 | HW19008-018V0037/38-DWG-005 | 018-C-GAD-40375-002 | CATALYST TRANSFER VESSEL DETAIL OF NOZZLE (2/5) 018V0037 018V0038 | A1109 | BX | 2 | 2019-07-08 | CON-BMP-VTRA-012722 | 2019-07-08 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-002 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | HANTECH LTD | 018V0037 | HW19008-018V0037/38-DWG-006 | 018-C-GAD-40375-003 | CATALYST TRANSFER VESSEL DETAIL OF NOZZLE (3/5) 018V0037 018V0038 | A1109 | BX | 2 | 2019-07-08 | CON-BMP-VTRA-012722 | 2019-07-08 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-002 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | HANTECH LTD | 018V0037 | HW19008-018V0037/38-DWG-008 | 018-C-DLB-40039-001 | CATALYST TRANSFER VESSEL DETAIL OF TEMPLATE 01V0037 018V0038 | A2010 | BX | 4 | 2019-07-04 | CON-BMP-VTRA-012668 | 2019-07-04 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-002 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | HANTECH LTD | 018V0037 | HW19008-018V0037/38-DWG-009 | 018-C-DLB-40040-001 | CATALYST TRANSFER VESSEL DETAIL OF NAME PLATE 018V0037 018V0038 | A1112 | AX | 2 | 2019-07-08 | CON-BMP-VTRA-012720 | 2019-07-08 | FOR BAPCO REVIEW | 2019-07-22 |  |  | CLASS 2
076551C-000R-MR-0811-002 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | HANTECH LTD | 018V0037 | HW19008-018V0037/38-DWG-010 | 018-C-GAD-40375-004 | CATALYST TRANSFER VESSEL DETAIL OF NOZZLE (4/5) 018V0037 018V0038 | A1109 | BX | 2 | 2019-07-08 | CON-BMP-VTRA-012722 | 2019-07-08 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-002 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | HANTECH LTD | 018V0037 | HW19008-018V0037/38-DWG-011 | 018-C-GAD-40375-005 | CATALYST TRANSFER VESSEL DETAIL OF NOZZLE (5/5) 018V0037 018V0038 | A1109 | BX | 2 | 2019-07-08 | CON-BMP-VTRA-012722 | 2019-07-08 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-002 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | HANTECH LTD | 018V0037 | HW19008-DOC-152 | 018-C-PQP-40027-001 | FABRICATION AND QUIALITY CONTROL PLAN FOR 018V0037 | B1002 | AXX | 2 | 2019-06-27 | CON-BMP-VTRA-012536 | 2019-06-27 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-002 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | HANTECH LTD | 018V0037 | HW19008-DOC-182 | 018-C-MCD-40044-001 | WPS AND PQR WITH WELD MAP (WELDER QUALIFICATION RECORD) FOR 018V0037 | B1103 | BX | 2 | 2019-05-23 | CON-BMP-VTRA-011761 | 2019-05-23 | FOR BAPCO REVIEW | 2019-06-07 | 2019-06-04 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000874 | CLASS 2
076551C-000R-MR-0811-002 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | HANTECH LTD | 018V0038 | HW19008-DOC-153 | 018-C-PQP-40028-001 | FABRICATION AND QUIALITY CONTROL PLAN FOR 018V0038 | B1002 | AXX | 2 | 2019-06-27 | CON-BMP-VTRA-012536 | 2019-06-27 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-002 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | HANTECH LTD | 018V0038 | HW19008-DOC-183 | 018-C-MCD-40045-001 | WPS AND PQR WITH WELD MAP (WELDER QUALIFICATION RECORD) FOR 018V0038 | B1103 | BX | 2 | 2019-05-23 | CON-BMP-VTRA-011761 | 2019-05-23 | FOR BAPCO REVIEW | 2019-06-07 | 2019-06-04 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000874 | CLASS 2
076551C-000R-MR-0811-002 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | HANTECH LTD | 018V0039 | HW19008-018V0039-CAL-001 | 018-C-CAL-40075-001 | STRENGTH CALCULATION 018V0039 | A1003 | AXX | 2 | 2019-05-10 | CON-BMP-VTRA-011528 | 2019-05-10 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-002 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | HANTECH LTD | 018V0039 | HW19008-018V0039-DWG-001 | 018-C-GAD-40376-001 | TRANSPORT OIL SURGE DRUM GENERAL ASSEMBLY 018V0039 | A1103 | AXX | 2 | 2019-05-30 | CON-BMP-VTRA-011862 | 2019-05-30 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-002 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | HANTECH LTD | 018V0039 | HW19008-018V0039-DWG-002 | 018-C-GAD-40377-001 | TRANSPORT OIL SURGE DRUM DETAIL OF BODY 018V0039 | A1109 | AXX | 2 | 2019-05-17 | CON-BMP-VTRA-011663 | 2019-05-17 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-002 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | HANTECH LTD | 018V0039 | HW19008-018V0039-DWG-003 | 018-C-GAD-40378-001 | TRANSPORT OIL SURGE DRUM DETAIL OF MANHOLE 018V0039 | A1109 | AX | 2 | 2019-04-26 | CON-BMP-VTRA-011281 | 2019-04-26 | FOR BAPCO REVIEW | 2019-05-14 | 2019-05-18 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000702 | CLASS 2
076551C-000R-MR-0811-002 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | HANTECH LTD | 018V0039 | HW19008-018V0039-DWG-004 | 018-C-GAD-40379-001 | TRANSPORT OIL SURGE DRUM DETAIL OF NOZZLE (1/3) 018V0039 | A1109 | AX | 2 | 2019-04-26 | CON-BMP-VTRA-011281 | 2019-04-26 | FOR BAPCO REVIEW | 2019-05-14 | 2019-05-18 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000702 | CLASS 2
076551C-000R-MR-0811-002 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | HANTECH LTD | 018V0039 | HW19008-018V0039-DWG-005 | 018-C-GAD-40379-002 | TRANSPORT OIL SURGE DRUM DETAIL OF NOZZLE (2/3) 018V0039 | A1109 | AX | 2 | 2019-04-26 | CON-BMP-VTRA-011281 | 2019-04-26 | FOR BAPCO REVIEW | 2019-05-14 | 2019-05-18 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000702 | CLASS 2
076551C-000R-MR-0811-002 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | HANTECH LTD | 018V0039 | HW19008-018V0039-DWG-006 | 018-C-GAD-40379-003 | TRANSPORT OIL SURGE DRUM DETAIL OF NOZZLE (3/3) 018V0039 | A1109 | AX | 2 | 2019-04-26 | CON-BMP-VTRA-011281 | 2019-04-26 | FOR BAPCO REVIEW | 2019-05-14 | 2019-05-18 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000702 | CLASS 2
076551C-000R-MR-0811-002 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | HANTECH LTD | 018V0039 | HW19008-DOC-154 | 018-C-PQP-40029-001 | FABRICATION AND QUIALITY CONTROL PLAN FOR 018V0039 | B1002 | AXX | 2 | 2019-06-27 | CON-BMP-VTRA-012536 | 2019-06-27 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-002 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | HANTECH LTD | 018V0039 | HW19008-DOC-184 | 018-C-MCD-40046-001 | WPS AND PQR WITH WELD MAP (WELDER QUALIFICATION RECORD) FOR 018V0039 | B1103 | AX | 2 | 2019-03-12 | CON-BMP-VTRA-010657 | 2019-03-12 | FOR BAPCO REVIEW | 2019-03-26 | 2019-03-20 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000351 | CLASS 2
076551C-000R-MR-0811-002 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | HANTECH LTD | 018V0050 | HW19008-018V0050-CAL-001 | 018-C-CAL-40076-001 | STRENGTH CALCULATION 018V0050 | A1003 | BX | 2 | 2019-07-09 | CON-BMP-VTRA-012754 | 2019-07-09 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-002 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | HANTECH LTD | 018V0050 | HW19008-018V0050-DWG-001 | 018-C-GAD-40380-001 | SHORT CIRCULATIUM DRUM GENERAL ASSEMBLY 018V0050 | A1103 | BX | 2 | 2019-07-09 | CON-BMP-VTRA-012755 | 2019-07-09 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-002 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | HANTECH LTD | 018V0050 | HW19008-018V0050-DWG-002 | 018-C-GAD-40381-001 | SHORT CIRCULATION DRUM DETAIL OF BODY 018V0050 | A1109 | BX | 2 | 2019-07-09 | CON-BMP-VTRA-012752 | 2019-07-09 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-002 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | HANTECH LTD | 018V0050 | HW19008-018V0050-DWG-003 | 018-C-GAD-40382-001 | SHORT CIRCULATION DRUM DETAIL OF MANHOLE 018V0050 | A1109 | BX | 2 | 2019-07-09 | CON-BMP-VTRA-012752 | 2019-07-09 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-002 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | HANTECH LTD | 018V0050 | HW19008-018V0050-DWG-004 | 018-C-GAD-40383-001 | SHORT CIRCULATION DRUM DETAIL OF NOZZLE (1/3) 018V0050 | A1109 | BX | 2 | 2019-07-09 | CON-BMP-VTRA-012752 | 2019-07-09 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-002 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | HANTECH LTD | 018V0050 | HW19008-018V0050-DWG-005 | 018-C-GAD-40383-002 | SHORT CIRCULATION DRUM DETAIL OF NOZZLE (2/3) 018V0050 | A1109 | BX | 2 | 2019-07-09 | CON-BMP-VTRA-012752 | 2019-07-09 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-002 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | HANTECH LTD | 018V0050 | HW19008-018V0050-DWG-006 | 018-C-GAD-40383-003 | SHORT CIRCULATION DRUM DETAIL OF NOZZLE (3/3) 018V0050 | A1109 | BX | 2 | 2019-07-09 | CON-BMP-VTRA-012752 | 2019-07-09 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-002 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | HANTECH LTD | 018V0050 | HW19008-018V0050-DWG-011 | 018-C-DLB-40042-001 | SHORT CIRCULATION DRUM DETAIL OF TEMPLATE 018V0050 | A2010 | BX | 2 | 2019-07-04 | CON-BMP-VTRA-012669 | 2019-07-04 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-002 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | HANTECH LTD | 018V0050 | HW19008-018V0050-DWG-012 | 018-C-DLB-40043-001 | SHORT CIRCULATION DRUM DETAIL OF NAME PLATE 018V0050 | A1112 | AX | 2 | 2019-07-09 | CON-BMP-VTRA-012751 | 2019-07-09 | FOR BAPCO REVIEW | 2019-07-23 |  |  | CLASS 2
076551C-000R-MR-0811-002 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | HANTECH LTD | 018V0050 | HW19008-018V0050-DWG-013 | 018-C-GAD-40769-001 | GENERAL NOTES SHORT CIRCULATION DRUM 018V0050 | A1109 | AX | 2 | 2019-07-09 | CON-BMP-VTRA-012753 | 2019-07-09 | FOR BAPCO REVIEW | 2019-07-23 |  |  | CLASS 2
076551C-000R-MR-0811-002 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | HANTECH LTD | 018V0050 | HW19008-DOC-155 | 018-C-PQP-40030-001 | FABRICATION AND QUIALITY CONTROL PLAN FOR 018V0050 | B1002 | AXX | 2 | 2019-06-27 | CON-BMP-VTRA-012536 | 2019-06-27 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-002 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | HANTECH LTD | 018V0050 | HW19008-DOC-185 | 018-C-MCD-40047-001 | WPS AND PQR WITH WELD MAP (WELDER QUALIFICATION RECORD) FOR 018V0050 | B1103 | AX | 2 | 2019-03-12 | CON-BMP-VTRA-010657 | 2019-03-12 | FOR BAPCO REVIEW | 2019-03-26 | 2019-03-20 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000351 | CLASS 2
076551C-000R-MR-0811-002 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | HANTECH LTD | 018V1048 | HW19008-018V1048/2048-CAL-001 | 018-C-CAL-40071-001 | STRENGTH CALCULATION 018V1048 018V2048 | A1003 | BX | 2 | 2019-07-09 | CON-BMP-VTRA-012754 | 2019-07-09 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-002 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | HANTECH LTD | 018V1048 | HW19008-018V1048V2048-DWG-001 | 018-C-GAD-40385-001 | TRAIN 1/2 SEAL OIL RESERVOIR GENERAL ASSEMBLY 018V1048 018V2048 | A1103 | BX | 2 | 2019-07-09 | CON-BMP-VTRA-012755 | 2019-07-09 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-002 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | HANTECH LTD | 018V1048 | HW19008-018V1048V2048-DWG-002 | 018-C-GAD-40386-001 | TRAIN 1/2 SEAL OIL RESEVOIR DETAIL OF BODY 018V1048/V2048 | A1109 | BX | 2 | 2019-07-09 | CON-BMP-VTRA-012752 | 2019-07-09 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-002 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | HANTECH LTD | 018V1048 | HW19008-018V1048V2048-DWG-003 | 018-C-GAD-40387-001 | TRAIN 1/2 SEAL OIL RESERVOIR DETAIL OF MANHOLE (1/2) 018V1048 018V2048 | A1109 | BX | 2 | 2019-07-09 | CON-BMP-VTRA-012752 | 2019-07-09 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-002 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | HANTECH LTD | 018V1048 | HW19008-018V1048V2048-DWG-004 | 018-C-GAD-40387-002 | TRAIN 1/2 SEAL OIL RESERVOIR DETAIL OF MANHOLE (2/2) 018V1048 018V2048 | A1109 | BX | 2 | 2019-07-09 | CON-BMP-VTRA-012752 | 2019-07-09 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-002 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | HANTECH LTD | 018V1048 | HW19008-018V1048V2048-DWG-005 | 018-C-GAD-40388-001 | TRAIN 1/2 SEAL OIL RESERVOIR DETAIL OF NOZZLE (1/2) 018V1048 018V2048 | A1109 | BX | 2 | 2019-07-09 | CON-BMP-VTRA-012752 | 2019-07-09 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-002 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | HANTECH LTD | 018V1048 | HW19008-018V1048V2048-DWG-006 | 018-C-GAD-40388-002 | TRAIN 1/2 SEAL OIL RESERVOIR DETAIL OF NOZZLE (2/2) 018V1048 018V2048 | A1109 | BX | 2 | 2019-07-09 | CON-BMP-VTRA-012752 | 2019-07-09 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-002 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | HANTECH LTD | 018V1048 | HW19008-018V1048V2048-DWG-009 | 018-C-PLD-40028-001 | TRAIN 1&2 SEAL OIL RESERVOIR DETAIL OF INSUL. & FIRE PROOF. CLIP 018V1048 018V2048 | A1105 | AX | 2 | 2019-07-08 | CON-BMP-VTRA-012747 | 2019-07-08 | FOR BAPCO REVIEW | 2019-07-23 |  |  | CLASS 2
076551C-000R-MR-0811-002 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | HANTECH LTD | 018V1048 | HW19008-018V1048V2048-DWG-010 | 018-C-DLB-40044-001 | TRAIN 1&2 SEAL OIL RESERVOIR DETAIL OF NAME PLATE 018V1048 018V2048 | A1112 | AX | 2 | 2019-07-09 | CON-BMP-VTRA-012751 | 2019-07-09 | FOR BAPCO REVIEW | 2019-07-23 |  |  | CLASS 2
076551C-000R-MR-0811-002 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | HANTECH LTD | 018V1048 | HW19008-018V1048V2048-DWG-011 | 018-C-GAD-40770-001 | GENERAL NOTES TRAIN 1/2 SEAL OIL RESERVOIR 018V1048 / 018V2048 | A1109 | AX | 2 | 2019-07-09 | CON-BMP-VTRA-012753 | 2019-07-09 | FOR BAPCO REVIEW | 2019-07-23 |  |  | CLASS 2
076551C-000R-MR-0811-002 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | HANTECH LTD | 018V1048 | HW19008-DOC-158 | 018-C-PQP-40031-001 | FABRICATION AND QUIALITY CONTROL PLAN FOR 018V1048 | B1002 | AXX | 2 | 2019-06-27 | CON-BMP-VTRA-012536 | 2019-06-27 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-002 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | HANTECH LTD | 018V1048 | HW19008-DOC-188 | 018-C-MCD-40048-001 | WPS AND PQR WITH WELD MAP (WELDER QUALIFICATION RECORD) FOR 018V104808 | B1103 | AX | 2 | 2019-03-12 | CON-BMP-VTRA-010657 | 2019-03-12 | FOR BAPCO REVIEW | 2019-03-26 | 2019-03-20 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000351 | CLASS 2
076551C-000R-MR-0811-002 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | HANTECH LTD | 018V2048 | HW19008-DOC-159 | 018-C-PQP-40032-001 | FABRICATION AND QUIALITY CONTROL PLAN FOR 018V2048 | B1002 | AXX | 2 | 2019-06-27 | CON-BMP-VTRA-012536 | 2019-06-27 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-002 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | HANTECH LTD | 018V2048 | HW19008-DOC-189 | 018-C-MCD-40049-001 | WPS AND PQR WITH WELD MAP (WELDER QUALIFICATION RECORD) FOR 018V2048 | B1103 | AX | 2 | 2019-03-12 | CON-BMP-VTRA-010657 | 2019-03-12 | FOR BAPCO REVIEW | 2019-03-26 | 2019-03-20 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000351 | CLASS 2
076551C-000R-MR-0811-002 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | HANTECH LTD | 021V0004 | HW19008-021V0004-CAL-001 | 021-C-CAL-40014-001 | STRENGTH CALCULATION 021V0004 | A1003 | AXX | 2 | 2019-05-10 | CON-BMP-VTRA-011528 | 2019-05-10 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-002 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | HANTECH LTD | 021V0004 | HW19008-021V0004-DWG-001 | 021-C-GAD-40077-001 | COLD HIGH PRESSURE SEPARATOR GENERAL ASSEMBLY 021V0004 | A1103 | AX | 2 | 2019-04-03 | CON-BMP-VTRA-010969 | 2019-04-03 | FOR BAPCO REVIEW | 2019-04-17 | 2019-04-24 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000560 | CLASS 2
076551C-000R-MR-0811-002 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | HANTECH LTD | 021V0004 | HW19008-021V0004-DWG-002 | 021-C-GAD-40078-001 | COLD HIGH PRESSURE SEPARATOR DETAIL OF BODY 021V0004 | A1109 | AXX | 2 | 2019-05-17 | CON-BMP-VTRA-011663 | 2019-05-17 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-002 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | HANTECH LTD | 021V0004 | HW19008-021V0004-DWG-003 | 021-C-GAD-40079-001 | COLD HIGH PRESSURE SEPARATOR DETAIL OF MANHOLE 021V0004 | A1109 | AX | 2 | 2019-04-29 | CON-BMP-VTRA-011310 | 2019-04-29 | FOR BAPCO REVIEW | 2019-05-15 | 2019-05-23 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000742 | CLASS 2
076551C-000R-MR-0811-002 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | HANTECH LTD | 021V0004 | HW19008-021V0004-DWG-004 | 021-C-GAD-40080-001 | COLD HIGH PRESSURE SEPARATOR DETAIL OF NOZZLE (1/2) 021V0004 | A1109 | AX | 2 | 2019-04-29 | CON-BMP-VTRA-011310 | 2019-04-29 | FOR BAPCO REVIEW | 2019-05-15 | 2019-05-23 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000742 | CLASS 2
076551C-000R-MR-0811-002 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | HANTECH LTD | 021V0004 | HW19008-021V0004-DWG-005 | 021-C-GAD-40080-002 | COLD HIGH PRESSURE SEPARATOR DETAIL OF NOZZLE (2/2) 021V0004 | A1109 | AX | 2 | 2019-04-29 | CON-BMP-VTRA-011310 | 2019-04-29 | FOR BAPCO REVIEW | 2019-05-15 | 2019-05-23 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000742 | CLASS 2
076551C-000R-MR-0811-002 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | HANTECH LTD | 021V0004 | HW19008-DOC-156 | 021-C-PQP-40005-001 | FABRICATION AND QUALITY CONTROL PLAN FOR 021V0004 | B1002 | AXX | 2 | 2019-05-03 | CON-BMP-VTRA-011395 | 2019-05-03 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-002 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | HANTECH LTD | 021V0004 | HW19008-DOC-186 | 021-C-MCD-40005-001 | WPS AND PQR WITH WELD MAP (WELDER QUALIFICATION RECORD) FOR 021V0004 | B1304 | BX | 2 | 2019-05-24 | CON-BMP-VTRA-011794 | 2019-05-24 | FOR BAPCO REVIEW | 2019-06-10 | 2019-06-04 | 5-RETAINED FOR INFORMATION BMP-ROC-TRE-000883 | CLASS 2
076551C-000R-MR-0811-002 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | HANTECH LTD | 021V0008 | HW19008-021V0008-CAL-001 | 021-C-CAL-40015-001 | STRENGTH CALCULATION 021V0008 | A1003 | BX | 2 | 2019-07-09 | CON-BMP-VTRA-012760 | 2019-07-09 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-002 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | HANTECH LTD | 021V0008 | HW19008-021V0008-DWG-001 | 021-C-GAD-40082-001 | HOT LOW PRESSURE SEPARATOR GENERAL ASSEMBLY 021V0008 | A1103 | BX | 2 | 2019-07-09 | CON-BMP-VTRA-012761 | 2019-07-09 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-002 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | HANTECH LTD | 021V0008 | HW19008-021V0008-DWG-002 | 021-C-GAD-40083-001 | HOT LOW PRESSURE SEPARATOR DETAIL OF BODY 021V0008 | A1109 | BX | 2 | 2019-07-09 | CON-BMP-VTRA-012756 | 2019-07-09 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-002 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | HANTECH LTD | 021V0008 | HW19008-021V0008-DWG-003 | 021-C-GAD-40084-001 | HOT LOW PRESSURE SEPARATOR DETAIL OF MANHOLE 021V0008 | A1109 | BX | 2 | 2019-07-09 | CON-BMP-VTRA-012756 | 2019-07-09 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-002 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | HANTECH LTD | 021V0008 | HW19008-021V0008-DWG-004 | 021-C-GAD-40085-001 | HOT LOW PRESSURE SEPARATOR DETAIL OF NOZZLE (1/2) 021V0008 | A1109 | BX | 2 | 2019-07-09 | CON-BMP-VTRA-012756 | 2019-07-09 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-002 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | HANTECH LTD | 021V0008 | HW19008-021V0008-DWG-005 | 021-C-GAD-40085-002 | HOT LOW PRESSURE SEPARATOR DETAIL OF NOZZLE (2/2) 021V0008 | A1109 | BX | 2 | 2019-07-09 | CON-BMP-VTRA-012756 | 2019-07-09 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-002 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | HANTECH LTD | 021V0008 | HW19008-021V0008-DWG-006 | 021-C-PLD-40011-001 | HOT LOW PRESSURE SEPARATOR (HLPS) DETAIL OF INSUL. & FIREPROOF. CLIP 021V0008 | A1105 | AX | 2 | 2019-07-09 | CON-BMP-VTRA-012759 | 2019-07-09 | FOR BAPCO REVIEW | 2019-07-23 |  |  | CLASS 2
076551C-000R-MR-0811-002 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | HANTECH LTD | 021V0008 | HW19008-021V0008-DWG-007 | 021-C-DLB-40010-001 | DETAIL OF TEMPLATE 021V0008 | A2010 | BX | 2 | 2019-07-03 | CON-BMP-VTRA-012641 | 2019-07-03 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-002 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | HANTECH LTD | 021V0008 | HW19008-021V0008-DWG-008 | 021-C-DLB-40011-001 | HOT LOW PRESSURE SEPARATOR (HLPS) DETAIL OF NAME PLATE 021V0008 | A1112 | AX | 2 | 2019-07-09 | CON-BMP-VTRA-012758 | 2019-07-09 | FOR BAPCO REVIEW | 2019-07-23 |  |  | CLASS 2
076551C-000R-MR-0811-002 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | HANTECH LTD | 021V0008 | HW19008-021V0008-DWG-009 | 021-C-GAD-40200-001 | GENERAL NOTES HOT LOW PRESSURESEPARATOR 021V0008 | A1109 | AX | 2 | 2019-07-09 | CON-BMP-VTRA-012757 | 2019-07-09 | FOR BAPCO REVIEW | 2019-07-23 |  |  | CLASS 2
076551C-000R-MR-0811-002 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | HANTECH LTD | 021V0008 | HW19008-DOC-157 | 021-C-PQP-40006-001 | FABRICATION AND QUALITY CONTROL PLAN FOR 021V0008 | B1002 | AXX | 2 | 2019-05-03 | CON-BMP-VTRA-011395 | 2019-05-03 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-002 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | HANTECH LTD | 021V0008 | HW19008-DOC-187 | 021-C-MCD-40006-001 | WPS AND PQR WITH WELD MAP (WELDER QUALIFICATION RECORD) FOR 021V0008 | B1103 | AX | 2 | 2019-03-12 | CON-BMP-VTRA-010657 | 2019-03-12 | FOR BAPCO REVIEW | 2019-03-26 | 2019-03-20 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000351 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V0001 | 4748-00-DDL-001 | 000-C-INX-40015-001 | LIST OF DOCUMENTS AND DRAWINGS CARBON STEEL PRESSURE VESSELS ALL ITEMS | A0001 | AX | 4 | 2019-05-06 | CON-BMP-VTRA-011424 | 2019-05-06 | FOR BAPCO REVIEW | 2019-05-21 | 2019-05-25 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000765 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V0001 | 4748-00-IE-001 | 000-C-PRO-40059-001 | HARDNESS TEST PROCEDURE ALL ITEMS | B1103 | AX | 2 | 2019-06-10 | CON-BMP-VTRA-012111 | 2019-06-10 | FOR BAPCO REVIEW | 2019-06-24 | 2019-06-21 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001010 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V0001 | 4748-00-MPR-001 | 000-C-MRS-40010-001 | MONTHLY PROGRESS REPORT CARBON STEEL PRESSURE VESSELS ALL ITEMS | C1002 | BX | 4 | 2019-06-06 | CON-BMP-VTRA-012086 | 2019-06-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V0001 | 4748-00-MS-001 | 000-C-SCH-40009-001 | ENGINEERING PROCUREMENT AND MANUFACTURING SCHEDULE CARBON STEEL PRESSURE VESSELS ALL ITEMS | C1001 | AX | 4 | 2019-05-06 | CON-BMP-VTRA-011478 | 2019-05-08 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V0001 | 4748-00-NDE-001 | 000-C-PRO-40061-001 | CARBON STEEL PRESSURE VESSELS NON-DESTRUCTIVE EXAMINATION PROCEDURE ALL ITEMS | B1202 | AX | 2 | 2019-06-06 | CON-BMP-VTRA-012085 | 2019-06-06 | FOR BAPCO REVIEW | 2019-06-21 | 2019-06-19 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-01002 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V0001 | 4748-00-PP-001 | 000-C-TSP-40018-001 | MATERIAL SPECIFICATION FOR MAIN ORDERS ALL ITEMS | B1203 | AX | 2 | 2019-05-22 | CON-BMP-VTRA-011725 | 2019-05-22 | FOR BAPCO REVIEW | 2019-06-06 | 2019-06-13 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000919 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V0001 | 4748-00-VL-001 | 000-C-PQS-40005-001 | SUB-VENDOR QUALIFICATION LIST ALL ITEMS | B1401 | AX | 2 | 2019-05-22 | CON-BMP-VTRA-011717 | 2019-05-22 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V0001 | 4748-01-200 | 018-C-DLB-40096-001 | SITE TEMPLATE DRAWING FOR SECOND-STAGE SUCTION DRUM 018V0001 | A2010 | AX | 2 | 2019-06-18 | CON-BMP-VTRA-012269 | 2019-06-18 | FOR BAPCO REVIEW | 2019-07-02 | 2019-07-09 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001236 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V0001 | 4748-01-900 | 018-C-GAD-40583-001 | GENERAL ARRANGEMENT DRAWING FOR SECOND STAGE SUCTION DRUM 018V0001 | A1103 | AX | 2 | 2019-06-12 | CON-BMP-VTRA-012173 | 2019-06-12 | FOR BAPCO REVIEW | 2019-06-26 | 2019-07-06 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001173 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V0001 | 4748-01-IT-001 | 018-C-PQP-40063-001 | FABRICATION AND QUALITY CONTROL PLAN 018V0001 | B1002 | AX | 2 | 2019-06-01 | CON-BMP-VTRA-011923 | 2019-06-01 | FOR BAPCO REVIEW | 2019-06-17 | 2019-06-10 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000910 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V0001 | 4748-01-SC-001 | 018-C-CAL-40166-001 | MECHANICAL DESIGN CALCULATION 018V0001 | A1003 | AX | 2 | 2019-06-01 | CON-BMP-VTRA-011927 | 2019-06-01 | FOR BAPCO REVIEW | 2019-06-17 | 2019-06-18 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000985 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V0001 | 4748-01-WB-001 | 018-C-MCD-40137-001 | WELDING BOOK (WELD MAP WPS & PQR) 018V0001 | B1304 | AX | 1 | 2019-05-22 | CON-BMP-VTRA-011728 | 2019-05-22 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V0002 | 4748-02-200 | 018-C-DLB-40097-001 | SITE TEMPLATE DRAWING FOR THIRD-STAGE SUCTION DRUM 018V0002 | A2010 | AX | 2 | 2019-06-24 | CON-BMP-VTRA-012410 | 2019-06-24 | FOR BAPCO REVIEW | 2019-07-09 |  |  | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V0002 | 4748-02-900 | 018-C-GAD-40584-001 | GENERAL ARRANGEMENT DRAWING FOR THIRD STAGE SUCTION DRUM 018V0002 | A1103 | AX | 2 | 2019-06-04 | CON-BMP-VTRA-011973 | 2019-06-04 | FOR BAPCO REVIEW | 2019-06-19 | 2019-06-29 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001071 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V0002 | 4748-02-IT-001 | 018-C-PQP-40064-001 | FABRICATION AND QUALITY CONTROL PLAN 018V0002 | B1002 | AX | 2 | 2019-06-01 | CON-BMP-VTRA-011923 | 2019-06-01 | FOR BAPCO REVIEW | 2019-06-17 | 2019-06-10 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000910 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V0002 | 4748-02-SC-001 | 018-C-CAL-40168-001 | MECHANICAL DESIGN CALCULATION CARBON STEELE PRESSURE VESSELS 018V0002 | A1003 | AX | 2 | 2019-05-22 | CON-BMP-VTRA-011726 | 2019-05-22 | FOR BAPCO REVIEW | 2019-06-06 | 2019-06-12 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000916 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V0002 | 4748-02-WB-001 | 018-C-MCD-40138-001 | WELDING BOOK (WELD MAP WPS & PQR) CARBON STEEL PRESSURE VESSELS 018V0002 | B1304 | AX | 1 | 2019-05-22 | CON-BMP-VTRA-011728 | 2019-05-22 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V0007 | 4748-03-900 | 018-C-GAD-40585-001 | GENERAL ARRANGEMENT DRAWING FOR LT/MT OIL SURGE DRUM 018V0007 | A1103 | AX | 2 | 2019-06-04 | CON-BMP-VTRA-011973 | 2019-06-04 | FOR BAPCO REVIEW | 2019-06-19 | 2019-06-29 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001071 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V0007 | 4748-03-IT-001 | 018-C-PQP-40065-001 | FABRICATION AND QUALITY CONTROL PLAN 018V0007 | B1002 | AX | 2 | 2019-06-01 | CON-BMP-VTRA-011923 | 2019-06-01 | FOR BAPCO REVIEW | 2019-06-17 | 2019-06-10 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000910 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V0007 | 4748-03-SC-001 | 018-C-CAL-40170-001 | MECHANICAL DESIGN CALCULATION CARBON STEELE PRESSURE VESSELS 018V0007 | A1003 | AX | 2 | 2019-05-22 | CON-BMP-VTRA-011726 | 2019-05-22 | FOR BAPCO REVIEW | 2019-06-06 | 2019-06-12 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000916 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V0007 | 4748-03-WB-001 | 018-C-MCD-40139-001 | WELDING BOOK (WELD MAP, WPS & PQR) CARBON STEEL PRESSURE VESSELS 018V0007 | B1304 | AX | 1 | 2019-05-22 | CON-BMP-VTRA-011728 | 2019-05-22 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V0009 | 4748-04-900 | 018-C-GAD-40586-001 | GENERAL ARRANGEMENT DRAWING FOR ATM COLUMN OVHD PRODUCT DRUM 018V0009 | A1103 | AX | 2 | 2019-06-04 | CON-BMP-VTRA-011973 | 2019-06-04 | FOR BAPCO REVIEW | 2019-06-19 | 2019-06-29 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001071 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V0009 | 4748-04-IT-001 | 018-C-PQP-40066-001 | FABRICATION AND QUALITY CONTROL PLAN CARBON STEEL PRESSURE VESSELS 018V0009 | B1002 | AX | 2 | 2019-06-01 | CON-BMP-VTRA-011923 | 2019-06-01 | FOR BAPCO REVIEW | 2019-06-17 | 2019-06-10 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000910 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V0009 | 4748-04-SC-001 | 018-C-CAL-40171-001 | MECHANICAL DESIGN CALCULATION CARBON STEEL PRESSURE VESSELS 018V0009 | A1003 | AX | 2 | 2019-05-24 | CON-BMP-VTRA-011799 | 2019-05-24 | FOR BAPCO REVIEW | 2019-06-10 | 2019-06-16 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000946 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V0009 | 4748-04-WB-001 | 018-C-MCD-40140-001 | WELDING BOOK (WELD MAP WPS & PQR) CARBON STEEL PRESSURE VESSELS 018V0009 | B1304 | AX | 1 | 2019-05-22 | CON-BMP-VTRA-011728 | 2019-05-22 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V0010A | 4748-05-200 | 018-C-DLB-40098-001 | SITE TEMPLATE DRAWING FOR SOURGAS COMPRESSOR 1ST STAGE SUCTION DRUMS 018V0010A/B | A2010 | AX | 2 | 2019-06-18 | CON-BMP-VTRA-012269 | 2019-06-18 | FOR BAPCO REVIEW | 2019-07-02 | 2019-07-09 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001236 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V0010A | 4748-05-900 | 018-C-GAD-40587-001 | GENERAL ARRANGEMENT DRAWING FOR SOUR GAS COMPRESSOR 1ST STAGE SUCTION DRUM 018V0010A/B | A1103 | AX | 2 | 2019-06-12 | CON-BMP-VTRA-012173 | 2019-06-12 | FOR BAPCO REVIEW | 2019-06-26 | 2019-07-06 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001173 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V0010A | 4748-05-IT-001 | 018-C-PQP-40067-001 | FABRICATION AND QUALITY CONTROL PLAN CARBON STEEL PRESSURE VESSELS 018V0010A/B | B1002 | AX | 2 | 2019-06-22 | CON-BMP-VTRA-012382 | 2019-06-22 | FOR BAPCO REVIEW | 2019-07-08 | 2019-07-06 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001174 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V0010A | 4748-05-SC-001 | 018-C-CAL-40173-001 | MECHANICAL DESIGN CALCULATION CARBON STEEL PRESSURE VESSELS 018V0010A/B | A1003 | AX | 2 | 2019-06-06 | CON-BMP-VTRA-012081 | 2019-06-06 | FOR BAPCO REVIEW | 2019-06-21 | 2019-07-07 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001184 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V0010A | 4748-05-WB-001 | 018-C-MCD-40141-001 | WELDING BOOK (WELD MAP WPS & PQR) CARBON STEEL PRESSURE VESSELS 018V0010A/B | B1304 | AX | 1 | 2019-05-22 | CON-BMP-VTRA-011728 | 2019-05-22 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V0011A | 4748-06-200 | 018-C-DLB-40099-001 | SITE TEMPLATE DRAWING FOR SOURGAS COMPRESSOR DISCHARGE KO DRUMS 018V0011A/B | A2010 | AX | 2 | 2019-06-18 | CON-BMP-VTRA-012269 | 2019-06-18 | FOR BAPCO REVIEW | 2019-07-02 | 2019-07-09 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001236 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V0011A | 4748-06-900 | 018-C-GAD-40588-001 | GENERAL ARRANGEMENT DRAWING FOR SOUR GAS COMPRESSOR DISCHARGE KO DRUMS 018V0011A/B | A1103 | AX | 2 | 2019-06-12 | CON-BMP-VTRA-012173 | 2019-06-12 | FOR BAPCO REVIEW | 2019-06-26 | 2019-07-06 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001173 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V0011A | 4748-06-IT-001 | 018-C-PQP-40068-001 | FABRICATION AND QUALITY CONTROL PLAN CARBON STEEL PRESSURE VESSELS 018V0011A/B | B1002 | AX | 2 | 2019-06-22 | CON-BMP-VTRA-012382 | 2019-06-22 | FOR BAPCO REVIEW | 2019-07-08 | 2019-07-06 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001174 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V0011A | 4748-06-SC-001 | 018-C-CAL-40175-001 | MECHANICAL DESIGN CALCULATION CARBON STEEL PRESSURE VESSELS 018V0011A/B | A1003 | AX | 2 | 2019-06-01 | CON-BMP-VTRA-011927 | 2019-06-01 | FOR BAPCO REVIEW | 2019-06-17 | 2019-06-18 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000985 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V0011A | 4748-06-WB-001 | 018-C-MCD-40142-001 | WELDING BOOK (WELD MAP WPS & PQR) CARBON STEEL PRESSURE VESSELS 018V0011A/B | B1304 | AX | 1 | 2019-05-22 | CON-BMP-VTRA-011728 | 2019-05-22 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V0013 | 4748-07-900 | 018-C-GAD-40589-001 | GENERAL ARRANGEMENT DRAWING FOR VACUUM COLUMN HOTWELL 018V0013 | A1103 | AX | 2 | 2019-06-04 | CON-BMP-VTRA-011973 | 2019-06-04 | FOR BAPCO REVIEW | 2019-06-19 | 2019-06-29 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001071 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V0013 | 4748-07-IT-001 | 018-C-PQP-40069-001 | FABRICATION AND QUALITY CONTROL PLAN CARBON STEEL PRESSURE VESSELS 018V0013 | B1002 | AX | 2 | 2019-06-01 | CON-BMP-VTRA-011923 | 2019-06-01 | FOR BAPCO REVIEW | 2019-06-17 | 2019-06-10 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000910 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V0013 | 4748-07-SC-001 | 018-C-CAL-40177-001 | MECHANICAL DESIGN CALCULATION CARBON STEEL PRESSURE VESSELS 018V0013 | A1003 | AX | 2 | 2019-05-22 | CON-BMP-VTRA-011726 | 2019-05-22 | FOR BAPCO REVIEW | 2019-06-06 | 2019-06-12 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000916 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V0013 | 4748-07-WB-001 | 018-C-MCD-40143-001 | WELDING BOOK (WELD MAP WPS & PQR) CARBON STEEL PRESSURE VESSELS 018V0013 | B1304 | AX | 1 | 2019-05-22 | CON-BMP-VTRA-011728 | 2019-05-22 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V0014 | 4748-08-900 | 018-C-GAD-40590-001 | GENERAL ARRANGEMENT DRAWING FOR HOTWELL VAPOR WATER SEAL DRUM 018V0014 | A1103 | AX | 2 | 2019-06-04 | CON-BMP-VTRA-011973 | 2019-06-04 | FOR BAPCO REVIEW | 2019-06-19 | 2019-06-29 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001071 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V0014 | 4748-08-IT-001 | 018-C-PQP-40070-001 | FABRICATION AND QUALITY CONTROL PLAN CARBON STEEL PRESSURE VESSELS 018V0014 | B1002 | AX | 2 | 2019-06-01 | CON-BMP-VTRA-011923 | 2019-06-01 | FOR BAPCO REVIEW | 2019-06-17 | 2019-06-10 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000910 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V0014 | 4748-08-SC-001 | 018-C-CAL-40178-001 | MECHANICAL DESIGN CALCULATION CARBON STEEL PRESSURE VESSELS 018V0014 | A1003 | AX | 2 | 2019-05-22 | CON-BMP-VTRA-011726 | 2019-05-22 | FOR BAPCO REVIEW | 2019-06-06 | 2019-06-12 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000916 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V0014 | 4748-08-WB-001 | 018-C-MCD-40144-001 | WELDING BOOK (WELD MAP WPS & PQR) CARBON STEEL PRESSURE VESSELS 018V0014 | B1304 | AX | 1 | 2019-05-22 | CON-BMP-VTRA-011730 | 2019-05-22 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V0014 | 4748-32-200 | 018-C-DLB-40114-001 | SITE TEMPLATE DRAWING FOR THIRD-STAGE SUCTION DRUM 018V1014 | A2010 | AX | 2 | 2019-06-24 | CON-BMP-VTRA-012410 | 2019-06-24 | FOR BAPCO REVIEW | 2019-07-09 |  |  | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V0023 | 4748-09-900 | 018-C-GAD-40591-001 | GENERAL ARRANGEMENT DRAWING FOR VACUUM COLUMN BTMS MP STEAM DRUM 018V0023 | A1103 | AX | 2 | 2019-06-04 | CON-BMP-VTRA-011973 | 2019-06-04 | FOR BAPCO REVIEW | 2019-06-19 | 2019-06-29 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001071 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V0023 | 4748-09-IT-001 | 018-C-PQP-40071-001 | FABRICATION AND QUALITY CONTROL PLAN CARBON STEEL PRESSURE VESSELS 018V0023 | B1002 | AX | 2 | 2019-06-01 | CON-BMP-VTRA-011923 | 2019-06-01 | FOR BAPCO REVIEW | 2019-06-17 | 2019-06-10 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000910 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V0023 | 4748-09-SC-001 | 018-C-CAL-40180-001 | MECHANICAL DESIGN CALCULATION CARBON STEEL PRESSURE VESSELS 018V0023 | A1003 | AX | 2 | 2019-06-01 | CON-BMP-VTRA-011922 | 2019-06-01 | FOR BAPCO REVIEW | 2019-06-17 | 2019-06-18 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000990 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V0023 | 4748-09-WB-001 | 018-C-MCD-40145-001 | WELDING BOOK (WELD MAP WPS & PQR) CARBON STEEL PRESSURE VESSELS 018V0023 | B1304 | AX | 1 | 2019-05-22 | CON-BMP-VTRA-011730 | 2019-05-22 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V0024 | 4748-10-200 | 018-C-DLB-40100-001 | SITE TEMPLATE DRAWING FOR CUTTER STOCK SURGE DRUM 018V0024 | A2010 | AX | 2 | 2019-06-24 | CON-BMP-VTRA-012410 | 2019-06-24 | FOR BAPCO REVIEW | 2019-07-09 |  |  | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V0024 | 4748-10-900 | 018-C-GAD-40592-001 | GENERAL ARRANGEMENT DRAWING FOR CUTTER STOCK SURGE DRUM 018V0024 | A1103 | AX | 2 | 2019-06-04 | CON-BMP-VTRA-011973 | 2019-06-04 | FOR BAPCO REVIEW | 2019-06-19 | 2019-06-29 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001071 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V0024 | 4748-10-IT-001 | 018-C-PQP-40072-001 | FABRICATION AND QUALITY CONTROL PLAN CARBON STEEL PRESSURE VESSELS 018V0024 | B1002 | AX | 2 | 2019-06-01 | CON-BMP-VTRA-011923 | 2019-06-01 | FOR BAPCO REVIEW | 2019-06-17 | 2019-06-10 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000910 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V0024 | 4748-10-SC-001 | 018-C-CAL-40182-001 | MECHANICAL DESIGN CALCULATION CARBON STEEL PRESSURE VESSELS 018V0024 | A1003 | AX | 2 | 2019-06-01 | CON-BMP-VTRA-011922 | 2019-06-01 | FOR BAPCO REVIEW | 2019-06-17 | 2019-06-18 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000990 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V0024 | 4748-10-WB-001 | 018-C-MCD-40146-001 | WELDING BOOK (WELD MAP WPS & PQR) CARBON STEEL PRESSURE VESSELS 018V0024 | B1304 | AX | 1 | 2019-05-22 | CON-BMP-VTRA-011729 | 2019-05-22 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V0025 | 4748-11-200 | 018-C-DLB-40101-001 | SITE TEMPLATE DRAWING FOR LEANAMINE SUCTION DRUM 018V0025 | A2010 | AX | 2 | 2019-06-24 | CON-BMP-VTRA-012410 | 2019-06-24 | FOR BAPCO REVIEW | 2019-07-09 |  |  | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V0025 | 4748-11-900 | 018-C-GAD-40593-001 | GENERAL ARRANGEMENT DRAWING FOR LEAN AMINE SURGE DRUM 018V0025 | A1103 | AX | 2 | 2019-06-24 | CON-BMP-VTRA-012402 | 2019-06-24 | FOR BAPCO REVIEW | 2019-07-08 |  |  | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V0025 | 4748-11-IT-001 | 018-C-PQP-40073-001 | FABRICATION AND QUALITY CONTROL PLAN CARBON STEEL PRESSURE VESSELS 018V0025 | B1002 | AX | 2 | 2019-06-01 | CON-BMP-VTRA-011923 | 2019-06-01 | FOR BAPCO REVIEW | 2019-06-17 | 2019-06-10 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000910 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V0025 | 4748-11-SC-001 | 018-C-CAL-40183-001 | MECHANICAL DESIGN CALCULATION CARBON STEEL PRESSURE VESSELS 018V0025 | A1003 | AX | 2 | 2019-06-18 | CON-BMP-VTRA-012263 | 2019-06-18 | FOR BAPCO REVIEW | 2019-07-02 | 2019-07-08 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001203 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V0025 | 4748-11-WB-001 | 018-C-MCD-40147-001 | WELDING BOOK (WELD MAP WPS & PQR) CARBON STEEL PRESSURE VESSELS 018V0025 | B1304 | AX | 1 | 2019-05-22 | CON-BMP-VTRA-011728 | 2019-05-22 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V0029 | 4748-12-200 | 018-C-DLB-40102-001 | SITE TEMPLATE DRAWING FOR INJECTION WATER DRUM 018V0029 | A2010 | AX | 2 | 2019-06-18 | CON-BMP-VTRA-012269 | 2019-06-18 | FOR BAPCO REVIEW | 2019-07-02 | 2019-07-09 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001236 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V0029 | 4748-12-900 | 018-C-GAD-40594-001 | GENERAL ARRANGEMENT DRAWING FOR INJECTION WATER DRUM 018V0029 | A1103 | AX | 2 | 2019-06-12 | CON-BMP-VTRA-012173 | 2019-06-12 | FOR BAPCO REVIEW | 2019-06-26 | 2019-07-06 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001173 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V0029 | 4748-12-IT-001 | 018-C-PQP-40074-001 | FABRICATION AND QUALITY CONTROL PLAN CARBON STEEL PRESSURE VESSELS 018V0029 | B1002 | AX | 2 | 2019-06-01 | CON-BMP-VTRA-011923 | 2019-06-01 | FOR BAPCO REVIEW | 2019-06-17 | 2019-06-10 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000910 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V0029 | 4748-12-SC-001 | 018-C-CAL-40184-001 | MECHANICAL DESIGN CALCULATION CARBON STEEL PRESSURE VESSELS 018V0029 | A1003 | AX | 2 | 2019-06-06 | CON-BMP-VTRA-012081 | 2019-06-06 | FOR BAPCO REVIEW | 2019-06-21 | 2019-07-07 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001184 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V0029 | 4748-12-WB-001 | 018-C-MCD-40148-001 | WELDING BOOK (WELD MAP WPS & PQR) CARBON STEEL PRESSURE VESSELS 018V0029 | B1304 | AX | 1 | 2019-05-22 | CON-BMP-VTRA-011727 | 2019-05-22 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V0030 | 4748-13-200 | 018-C-DLB-40103-001 | SITE TEMPLATE DRAWING FOR CONDENSATE SURGE DRUM 018V0030 | A2010 | AX | 2 | 2019-06-13 | CON-BMP-VTRA-012190 | 2019-06-13 | FOR BAPCO REVIEW | 2019-06-27 | 2019-07-04 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001169 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V0030 | 4748-13-900 | 018-C-GAD-40595-001 | GENERAL ARRANGEMENT DRAWING FOR CONDENSATE SURGE DRUM 018V0030 | A1103 | AX | 2 | 2019-06-12 | CON-BMP-VTRA-012173 | 2019-06-12 | FOR BAPCO REVIEW | 2019-06-26 | 2019-07-06 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001173 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V0030 | 4748-13-IT-001 | 018-C-PQP-40075-001 | FABRICATION AND QUALITY CONTROL PLAN CARBON STEEL PRESSURE VESSELS 018V0030 | B1002 | AX | 2 | 2019-06-22 | CON-BMP-VTRA-012382 | 2019-06-22 | FOR BAPCO REVIEW | 2019-07-08 | 2019-07-06 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001174 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V0030 | 4748-13-SC-001 | 018-C-CAL-40185-001 | MECHANICAL DESIGN CALCULATION CARBON STEEL PRESSURE VESSELS 018V0030 | A1003 | AX | 2 | 2019-06-01 | CON-BMP-VTRA-011927 | 2019-06-01 | FOR BAPCO REVIEW | 2019-06-17 | 2019-06-18 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000985 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V0030 | 4748-13-WB-001 | 018-C-MCD-40149-001 | WELDING BOOK (WELD MAP WPS & PQR) CARBON STEEL PRESSURE VESSELS 018V0030 | B1304 | AX | 1 | 2019-05-22 | CON-BMP-VTRA-011727 | 2019-05-22 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V0031 | 4748-14-900 | 018-C-GAD-40596-001 | GENERAL ARRANGEMENT DRAWING FOR FCTP LIQUID OVERFLOW POT 018V0031 | A1103 | AX | 2 | 2019-06-04 | CON-BMP-VTRA-011973 | 2019-06-04 | FOR BAPCO REVIEW | 2019-06-19 | 2019-06-29 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001071 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V0031 | 4748-14-IT-001 | 018-C-PQP-40076-001 | FABRICATION AND QUALITY CONTROL PLAN CARBON STEEL PRESSURE VESSELS 018V0031 | B1002 | AX | 2 | 2019-06-01 | CON-BMP-VTRA-011923 | 2019-06-01 | FOR BAPCO REVIEW | 2019-06-17 | 2019-06-10 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000910 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V0031 | 4748-14-SC-001 | 018-C-CAL-40186-001 | MECHANICAL DESIGN CALCULATION CARBON STEEL PRESSURE VESSELS 018V0031 | A1003 | AX | 2 | 2019-05-24 | CON-BMP-VTRA-011799 | 2019-05-24 | FOR BAPCO REVIEW | 2019-06-10 | 2019-06-16 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000946 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V0031 | 4748-14-WB-001 | 018-C-MCD-40150-001 | WELDING BOOK (WELD MAP WPS & PQR) CARBON STEEL PRESSURE VESSELS 018V0031 | B1304 | AX | 1 | 2019-05-22 | CON-BMP-VTRA-011728 | 2019-05-22 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V0040 | 4748-15-900 | 018-C-GAD-40597-001 | GENERAL ARRANGEMENT DRAWING FOR COOLING OIL SURGE DRUM 018V0040 | A1103 | AX | 2 | 2019-06-14 | CON-BMP-VTRA-012220 | 2019-06-14 | FOR BAPCO REVIEW | 2019-06-28 | 2019-07-08 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001226 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V0040 | 4748-15-IT-001 | 018-C-PQP-40077-001 | FABRICATION AND QUALITY CONTROL PLAN CARBON STEEL PRESSURE VESSELS 018V0040 VESSELS 372V0035 | B1002 | AX | 2 | 2019-06-06 | CON-BMP-VTRA-012084 | 2019-06-06 | FOR BAPCO REVIEW | 2019-06-21 | 2019-06-19 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001005 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V0040 | 4748-15-SC-001 | 018-C-CAL-40187-001 | MECHANICAL DESIGN CALCULATION CARBON STEEL PRESSURE VESSELS 018V0040 | A1003 | AX | 2 | 2019-06-11 | CON-BMP-VTRA-012156 | 2019-06-11 | FOR BAPCO REVIEW | 2019-06-26 | 2019-07-04 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001170 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V0040 | 4748-15-WB-001 | 018-C-MCD-40151-001 | WELDING BOOK (WELD MAP WPS & PQR) CARBON STEEL PRESSURE VESSELS 018V0040 | B1304 | AX | 1 | 2019-05-22 | CON-BMP-VTRA-011728 | 2019-05-22 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V0042 | 4748-16-200 | 018-C-DLB-40104-001 | SITE TEMPLATE DRAWING FOR SPENT CATALYST DE-OILING BIN 018V0042 | A2010 | AX | 2 | 2019-06-24 | CON-BMP-VTRA-012410 | 2019-06-24 | FOR BAPCO REVIEW | 2019-07-09 |  |  | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V0042 | 4748-16-900 | 018-C-GAD-40598-001 | GENERAL ARRANGEMENT DRAWING FOR SPENT CATALYST DE- OILING BIN 018V0042 | A1103 | AX | 2 | 2019-06-14 | CON-BMP-VTRA-012220 | 2019-06-14 | FOR BAPCO REVIEW | 2019-06-28 | 2019-07-08 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001226 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V0042 | 4748-16-IT-001 | 018-C-PQP-40078-001 | FABRICATION AND QUALITY CONTROL PLAN CARBON STEEL PRESSURE VESSELS 018V0042 | B1002 | AX | 2 | 2019-06-22 | CON-BMP-VTRA-012382 | 2019-06-22 | FOR BAPCO REVIEW | 2019-07-08 | 2019-07-06 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001174 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V0042 | 4748-16-SC-001 | 018-C-CAL-40188-001 | MECHANICAL DESIGN CALCULATION CARBON STEEL PRESSURE VESSELS 018V0042 | A1003 | AX | 2 | 2019-06-11 | CON-BMP-VTRA-012156 | 2019-06-11 | FOR BAPCO REVIEW | 2019-06-26 | 2019-07-04 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001170 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V0042 | 4748-16-WB-001 | 018-C-MCD-40152-001 | WELDING BOOK (WELD MAP WPS & PQR) CARBON STEEL PRESSURE VESSELS 018V0042 | B1304 | AX | 1 | 2019-05-22 | CON-BMP-VTRA-011728 | 2019-05-22 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V0043 | 4748-17-200 | 018-C-DLB-40105-001 | SITE TEMPLATE DRAWING FOR SPENT CATALYST DE-OILING BIN 018V0043 | A2010 | AX | 2 | 2019-06-24 | CON-BMP-VTRA-012410 | 2019-06-24 | FOR BAPCO REVIEW | 2019-07-09 |  |  | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V0043 | 4748-17-900 | 018-C-GAD-40599-001 | GENERAL ARRANGEMENT DRAWING FOR SPENT CATALYST DE-OILING BIN 018V0043 | A1103 | AX | 2 | 2019-06-14 | CON-BMP-VTRA-012220 | 2019-06-14 | FOR BAPCO REVIEW | 2019-06-28 | 2019-07-08 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001226 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V0043 | 4748-17-IT-001 | 018-C-PQP-40079-001 | FABRICATION AND QUALITY CONTROL PLAN CARBON STEEL PRESSURE VESSELS 018V00431 | B1002 | AX | 2 | 2019-06-01 | CON-BMP-VTRA-011923 | 2019-06-01 | FOR BAPCO REVIEW | 2019-06-17 | 2019-06-10 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000910 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V0043 | 4748-17-WB-001 | 018-C-MCD-40153-001 | WELDING BOOK (WELD MAP WPS & PQR) CARBON STEEL PRESSURE VESSELS 018V0043 | B1304 | AX | 1 | 2019-05-22 | CON-BMP-VTRA-011729 | 2019-05-22 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V0044 | 4748-18-200 | 018-C-DLB-40106-001 | SITE TEMPLATE DRAWING FOR OIL DRAIN SURGE DRUM 018V0044 | A2010 | AX | 2 | 2019-06-18 | CON-BMP-VTRA-012269 | 2019-06-18 | FOR BAPCO REVIEW | 2019-07-02 | 2019-07-09 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001236 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V0044 | 4748-18-900 | 018-C-GAD-40600-001 | GENERAL ARRANGEMENT DRAWING FOR OIL DRAIN SURGE DRUM 018V0044 | A1103 | AX | 2 | 2019-06-12 | CON-BMP-VTRA-012173 | 2019-06-12 | FOR BAPCO REVIEW | 2019-06-26 | 2019-07-06 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001173 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V0044 | 4748-18-IT-001 | 018-C-PQP-40080-001 | FABRICATION AND QUALITY CONTROL PLAN CARBON STEEL PRESSURE VESSELS 018V0044 | B1002 | AX | 2 | 2019-06-01 | CON-BMP-VTRA-011923 | 2019-06-01 | FOR BAPCO REVIEW | 2019-06-17 | 2019-06-10 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000910 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V0044 | 4748-18-SC-001 | 018-C-CAL-40192-001 | MECHANICAL DESIGN CALCULATION CARBON STEEL PRESSURE VESSELS 018V0044 | A1003 | AX | 2 | 2019-06-06 | CON-BMP-VTRA-012081 | 2019-06-06 | FOR BAPCO REVIEW | 2019-06-21 | 2019-07-07 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001184 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V0044 | 4748-18-WB-001 | 018-C-MCD-40154-001 | WELDING BOOK (WELD MAP WPS & PQR) CARBON STEEL PRESSURE VESSELS 018V0044 | B1304 | AX | 1 | 2019-05-22 | CON-BMP-VTRA-011729 | 2019-05-22 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V0053 | 4748-19-900 | 018-C-GAD-40601-001 | GENERAL ARRANGEMENT DRAWING FOR SWEET FUEL GAS KO DRUM 018V0053 | A1103 | AX | 2 | 2019-06-04 | CON-BMP-VTRA-011973 | 2019-06-04 | FOR BAPCO REVIEW | 2019-06-19 | 2019-06-29 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001071 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V0053 | 4748-19-IT-001 | 018-C-PQP-40081-001 | FABRICATION AND QUALITY CONTROL PLAN CARBON STEEL PRESSURE VESSELS 018V0053 | B1002 | AX | 2 | 2019-06-01 | CON-BMP-VTRA-011923 | 2019-06-01 | FOR BAPCO REVIEW | 2019-06-17 | 2019-06-10 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000910 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V0053 | 4748-19-SC-001 | 018-C-CAL-40193-001 | MECHANICAL DESIGN CALCULATION CARBON STEEL PRESSURE VESSELS 018V0053 | A1003 | AX | 2 | 2019-05-24 | CON-BMP-VTRA-011799 | 2019-05-24 | FOR BAPCO REVIEW | 2019-06-10 | 2019-06-16 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000946 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V0053 | 4748-19-WB-001 | 018-C-MCD-40155-001 | WELDING BOOK (WELD MAP WPS & PQR) CARBON STEEL PRESSURE VESSELS 018V0053 | B1304 | AX | 1 | 2019-05-22 | CON-BMP-VTRA-011728 | 2019-05-22 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V0054 | 4748-20-900 | 018-C-GAD-40602-001 | GENERAL ARRANGEMENT DRAWING FOR PROCESS FUEL GAS KO DRUM 018V0054 | A1103 | AX | 2 | 2019-06-04 | CON-BMP-VTRA-011973 | 2019-06-04 | FOR BAPCO REVIEW | 2019-06-19 | 2019-06-29 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001071 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V0054 | 4748-20-IT-001 | 018-C-PQP-40082-001 | FABRICATION AND QUALITY CONTROL PLAN CARBON STEEL PRESSURE VESSELS 018V0054 | B1002 | AX | 2 | 2019-06-01 | CON-BMP-VTRA-011923 | 2019-06-01 | FOR BAPCO REVIEW | 2019-06-17 | 2019-06-10 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000910 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V0054 | 4748-20-SC-001 | 018-C-CAL-40195-001 | MECHANICAL DESIGN CALCULATION CARBON STEEL PRESSURE VESSELS 018V0054 | A1003 | AX | 2 | 2019-06-01 | CON-BMP-VTRA-011922 | 2019-06-01 | FOR BAPCO REVIEW | 2019-06-17 | 2019-06-18 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000990 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V0054 | 4748-20-WB-001 | 018-C-MCD-40156-001 | WELDING BOOK (WELD MAP WPS & PQR) CARBON STEEL PRESSURE VESSELS 018V0054 | B1304 | AX | 1 | 2019-05-22 | CON-BMP-VTRA-011727 | 2019-05-22 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V0055 | 4748-21-200 | 018-C-DLB-40107-001 | SITE TEMPLATE DRAWING FOR TEMPERED WATER DRUM 018V0055 | A2010 | AX | 2 | 2019-06-18 | CON-BMP-VTRA-012269 | 2019-06-18 | FOR BAPCO REVIEW | 2019-07-02 | 2019-07-09 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001236 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V0055 | 4748-21-900 | 018-C-GAD-40603-001 | GENERAL ARRANGEMENT DRAWING FOR TEMPERED WATER DRUM 018V0055 | A1103 | AX | 2 | 2019-06-12 | CON-BMP-VTRA-012173 | 2019-06-12 | FOR BAPCO REVIEW | 2019-06-26 | 2019-07-06 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001173 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V0055 | 4748-21-IT-001 | 018-C-PQP-40083-001 | FABRICATION AND QUALITY CONTROL PLAN CARBON STEEL PRESSURE VESSELS 018V0055 | B1002 | AX | 2 | 2019-06-01 | CON-BMP-VTRA-011923 | 2019-06-01 | FOR BAPCO REVIEW | 2019-06-17 | 2019-06-10 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000910 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V0055 | 4748-21-SC-001 | 018-C-CAL-40197-001 | MECHANICAL DESIGN CALCULATION CARBON STEEL PRESSURE VESSELS 018V0055 | A1003 | AX | 2 | 2019-06-01 | CON-BMP-VTRA-011927 | 2019-06-01 | FOR BAPCO REVIEW | 2019-06-17 | 2019-06-18 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000985 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V0055 | 4748-21-WB-001 | 018-C-MCD-40157-001 | WELDING BOOK (WELD MAP WPS & PQR) CARBON STEEL PRESSURE VESSELS 018V0055 | B1304 | AX | 1 | 2019-05-22 | CON-BMP-VTRA-011729 | 2019-05-22 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V0056 | 4748-22-200 | 018-C-DLB-40108-001 | SITE TEMPLATE DRAWING FOR HOT PURGE OIL SURGE DRUM 018V0056 | A2010 | AX | 2 | 2019-06-18 | CON-BMP-VTRA-012269 | 2019-06-18 | FOR BAPCO REVIEW | 2019-07-02 | 2019-07-09 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001236 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V0056 | 4748-22-900 | 018-C-GAD-40604-001 | GENERAL ARRANGEMENT DRAWING FOR HOT PURGE OIL SURGE DRUM 018V0056 | A1103 | AX | 2 | 2019-06-12 | CON-BMP-VTRA-012173 | 2019-06-12 | FOR BAPCO REVIEW | 2019-06-26 | 2019-07-06 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001173 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V0056 | 4748-22-IT-001 | 018-C-PQP-40084-001 | FABRICATION AND QUALITY CONTROL PLAN CARBON STEEL PRESSURE VESSELS 018V0056 | B1002 | AX | 2 | 2019-06-01 | CON-BMP-VTRA-011923 | 2019-06-01 | FOR BAPCO REVIEW | 2019-06-17 | 2019-06-10 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000910 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V0056 | 4748-22-SC-001 | 018-C-CAL-40198-001 | MECHANICAL DESIGN CALCULATION CARBON STEEL PRESSURE VESSELS 018V0056 | A1003 | AX | 2 | 2019-06-06 | CON-BMP-VTRA-012081 | 2019-06-06 | FOR BAPCO REVIEW | 2019-06-21 | 2019-07-07 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001184 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V0056 | 4748-22-WB-001 | 018-C-MCD-40158-001 | WELDING BOOK (WELD MAP WPS & PQR) CARBON STEEL PRESSURE VESSELS 018V0056 | B1304 | AX | 1 | 2019-05-22 | CON-BMP-VTRA-011729 | 2019-05-22 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V0057 | 4748-23-900 | 018-C-GAD-40605-001 | GENERAL ARRANGEMENT DRAWING FOR SOUR WATER SUMP 018V0057 | A1103 | AX | 2 | 2019-06-12 | CON-BMP-VTRA-012173 | 2019-06-12 | FOR BAPCO REVIEW | 2019-06-26 | 2019-07-06 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001173 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V0057 | 4748-23-IT-001 | 018-C-PQP-40085-001 | FABRICATION AND QUALITY CONTROL PLAN CARBON STEEL PRESSURE VESSELS 018V0057 | B1002 | AX | 2 | 2019-06-22 | CON-BMP-VTRA-012382 | 2019-06-22 | FOR BAPCO REVIEW | 2019-07-08 | 2019-07-06 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001174 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V0057 | 4748-23-SC-001 | 018-C-CAL-40199-001 | MECHANICAL DESIGN CALCULATION CARBON STEEL PRESSURE VESSELS 018V0057 | A1003 | AX | 2 | 2019-06-06 | CON-BMP-VTRA-012081 | 2019-06-06 | FOR BAPCO REVIEW | 2019-06-21 | 2019-07-07 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001184 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V0057 | 4748-23-WB-001 | 018-C-MCD-40159-001 | WELDING BOOK (WELD MAP WPS & PQR) CARBON STEEL PRESSURE VESSELS 018V0057 | B1304 | AX | 1 | 2019-05-22 | CON-BMP-VTRA-011727 | 2019-05-22 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V0058 | 4748-24-900 | 018-C-GAD-40606-001 | GENERAL ARRANGEMENT DRAWING FOR AMINE SUMP 018V0058 | A1103 | AX | 2 | 2019-06-14 | CON-BMP-VTRA-012220 | 2019-06-14 | FOR BAPCO REVIEW | 2019-06-28 | 2019-07-08 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001226 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V0058 | 4748-24-IT-001 | 018-C-PQP-40086-001 | FABRICATION AND QUALITY CONTROL PLAN CARBON STEEL PRESSURE VESSELS 018V0058 | B1002 | AX | 2 | 2019-06-22 | CON-BMP-VTRA-012382 | 2019-06-22 | FOR BAPCO REVIEW | 2019-07-08 | 2019-07-06 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001174 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V0058 | 4748-24-SC-001 | 018-C-CAL-40200-001 | MECHANICAL DESIGN CALCULATION CARBON STEEL PRESSURE VESSELS 018V0058 | A1003 | AX | 2 | 2019-06-10 | CON-BMP-VTRA-012110 | 2019-06-10 | FOR BAPCO REVIEW | 2019-06-24 | 2019-07-02 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001141 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V0058 | 4748-24-WB-001 | 018-C-MCD-40160-001 | WELDING BOOK (WELD MAP WPS & PQR) CARBON STEEL PRESSURE VESSELS 018V0058 | B1304 | AX | 1 | 2019-05-22 | CON-BMP-VTRA-011729 | 2019-05-22 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V0068 | 4748-25-900 | 018-C-GAD-40607-001 | GENERAL ARRANGEMENT DRAWING FOR HP/MP BLOWDOWN FLASH DRUM 018V0068 | A1103 | AX | 2 | 2019-06-04 | CON-BMP-VTRA-011971 | 2019-06-04 | FOR BAPCO REVIEW | 2019-06-19 | 2019-06-26 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001042 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V0068 | 4748-25-IT-001 | 018-C-PQP-40087-001 | FABRICATION AND QUALITY CONTROL PLAN CARBON STEEL PRESSURE VESSELS 018V0068 | B1002 | AX | 2 | 2019-06-22 | CON-BMP-VTRA-012382 | 2019-06-22 | FOR BAPCO REVIEW | 2019-07-08 | 2019-07-06 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001174 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V0068 | 4748-25-SC-001 | 018-C-CAL-40201-001 | MECHANICAL DESIGN CALCULATION CARBON STEEL PRESSURE VESSELS 018V0068 | A1003 | AX | 2 | 2019-06-05 | CON-BMP-VTRA-011992 | 2019-06-05 | FOR BAPCO REVIEW | 2019-06-19 | 2019-06-29 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001082 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V0068 | 4748-25-WB-001 | 018-C-MCD-40161-001 | WELDING BOOK (WELD MAP WPS & PQR) CARBONE STEEL PRESSURE VESSELS 018V0068 | B1304 | AX | 1 | 2019-05-29 | CON-BMP-VTRA-011821 | 2019-05-29 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V0069 | 4748-26-900 | 018-C-GAD-40608-001 | GENERAL ARRANGEMENT DRAWING FOR LP BLOWDOWN FLASH DRUM 018V0069 | A1103 | AX | 2 | 2019-06-12 | CON-BMP-VTRA-012173 | 2019-06-12 | FOR BAPCO REVIEW | 2019-06-26 | 2019-07-06 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001173 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V0069 | 4748-26-IT-001 | 018-C-PQP-40088-001 | FABRICATION AND QUALITY CONTROL PLAN CARBON STEEL PRESSURE VESSELS 018V0069 | B1002 | AX | 2 | 2019-06-22 | CON-BMP-VTRA-012382 | 2019-06-22 | FOR BAPCO REVIEW | 2019-07-08 | 2019-07-06 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001174 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V0069 | 4748-26-SC-001 | 018-C-CAL-40202-001 | MECHANICAL DESIGN CALCULATION CARBON STEEL PRESSURE VESSELS 018V0069 | A1003 | AX | 2 | 2019-06-01 | CON-BMP-VTRA-011921 | 2019-06-01 | FOR BAPCO REVIEW | 2019-06-17 | 2019-06-18 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000966 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V0069 | 4748-26-WB-001 | 018-C-MCD-40162-001 | WELDING BOOK (WELD MAP WPS & PQR) CARBON STEEL PRESSURE VESSELS 018V0069 | B1304 | AX | 1 | 2019-05-29 | CON-BMP-VTRA-011821 | 2019-05-29 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V1001 | 4748-17-SC-001 | 018-C-CAL-40190-001 | MECHANICAL DESIGN CALCULATION CARBON STEEL PRESSURE VESSELS 018V0043 | A1003 | AX | 2 | 2019-06-11 | CON-BMP-VTRA-012156 | 2019-06-11 | FOR BAPCO REVIEW | 2019-06-26 | 2019-07-04 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001170 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V1001 | 4748-27-200 | 018-C-DLB-40109-001 | SITE TEMPLATE DRAWING FOR TRAIN 2 FEED SURGE DRUM 018V1001 | A2010 | AX | 2 | 2019-06-18 | CON-BMP-VTRA-012269 | 2019-06-18 | FOR BAPCO REVIEW | 2019-07-02 | 2019-07-09 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001236 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V1001 | 4748-27-IT-001 | 018-C-PQP-40089-001 | FABRICATION AND QUALITY CONTROL PLAN CARBON STEEL PRESSURE VESSELS 018V1001 | B1002 | AX | 2 | 2019-06-22 | CON-BMP-VTRA-012382 | 2019-06-22 | FOR BAPCO REVIEW | 2019-07-08 | 2019-07-06 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001174 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V1001 | 4748-27-SC-001 | 018-C-CAL-40203-001 | MECHANICAL DESIGN CALCULATION CARBON STEEL PRESSURE VESSELS 018V1001 | A1003 | AX | 2 | 2019-06-11 | CON-BMP-VTRA-012156 | 2019-06-11 | FOR BAPCO REVIEW | 2019-06-26 | 2019-07-04 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001170 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V1001 | 4748-27-WB-001 | 018-C-MCD-40163-001 | WELDING BOOK (WELD MAP WPS & PQR) CARBON STEEL PRESSURE VESSELS 018V1001 | B1304 | AX | 1 | 2019-05-22 | CON-BMP-VTRA-011729 | 2019-05-22 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V1010 | 4748-28-200 | 018-C-DLB-40110-001 | SITE TEMPLATE DRAWING FOR FIRST-STAGE SUCTION DRUM 018V1010 | A2010 | AX | 2 | 2019-06-18 | CON-BMP-VTRA-012269 | 2019-06-18 | FOR BAPCO REVIEW | 2019-07-02 | 2019-07-09 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001236 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V1010 | 4748-28-900 | 018-C-GAD-40610-001 | GENERAL ARRANGEMENT DRAWING FOR FIRST STAGE SUCTION DRUM 018V1010 | A1103 | AX | 2 | 2019-06-12 | CON-BMP-VTRA-012173 | 2019-06-12 | FOR BAPCO REVIEW | 2019-06-26 | 2019-07-06 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001173 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V1010 | 4748-28-IT-001 | 018-C-PQP-40090-001 | FABRICATION AND QUALITY CONTROL PLAN CARBON STEEL PRESSURE VESSELS 018V1010 | B1002 | AX | 2 | 2019-06-22 | CON-BMP-VTRA-012382 | 2019-06-22 | FOR BAPCO REVIEW | 2019-07-08 | 2019-07-06 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001174 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V1010 | 4748-28-SC-001 | 018-C-CAL-40204-001 | MECHANICAL DESIGN CALCULATION CARBON STEEL PRESSURE VESSELS 018V1010 | A1003 | AX | 2 | 2019-06-06 | CON-BMP-VTRA-012081 | 2019-06-06 | FOR BAPCO REVIEW | 2019-06-21 | 2019-07-07 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001184 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V1011 | 4748-29-200 | 018-C-DLB-40111-001 | SITE TEMPLATE DRAWING FOR SECOND-STAGE SUCTION DRUM 018V1011 | A2010 | AX | 2 | 2019-06-18 | CON-BMP-VTRA-012269 | 2019-06-18 | FOR BAPCO REVIEW | 2019-07-02 | 2019-07-09 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001236 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V1011 | 4748-29-900 | 018-C-GAD-40611-001 | GENERAL ARRANGEMENT DRAWING FOR SECOND STAGE SUCTION DRUM 018V1011 | A1103 | AX | 2 | 2019-06-04 | CON-BMP-VTRA-011971 | 2019-06-04 | FOR BAPCO REVIEW | 2019-06-19 | 2019-06-26 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001042 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V1011 | 4748-29-IT-001 | 018-C-PQP-40091-001 | FABRICATION AND QUALITY CONTROL PLAN CARBON STEEL PRESSURE VESSELS 018V1011 | B1002 | AX | 2 | 2019-06-22 | CON-BMP-VTRA-012382 | 2019-06-22 | FOR BAPCO REVIEW | 2019-07-08 | 2019-07-06 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001174 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V1011 | 4748-29-SC-001 | 018-C-CAL-40206-001 | MECHANICAL DESIGN CALCULATION CARBON STEEL PRESSURE VESSELS 018V1011 | A1003 | AX | 2 | 2019-06-01 | CON-BMP-VTRA-011922 | 2019-06-01 | FOR BAPCO REVIEW | 2019-06-17 | 2019-06-18 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000990 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V1011 | 4748-29-WB-001 | 018-C-MCD-40165-001 | WELDING BOOK (WELD MAP WPS & PQR) CARBON STEEL PRESSURE VESSELS 018V1011 | B1304 | AX | 1 | 2019-05-22 | CON-BMP-VTRA-011727 | 2019-05-22 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V1012 | 4748-30-200 | 018-C-DLB-40112-001 | SITE TEMPLATE DRAWING FOR THIRD-STAGE SUCTION DRUM 018V1012 | A2010 | AX | 2 | 2019-06-18 | CON-BMP-VTRA-012269 | 2019-06-18 | FOR BAPCO REVIEW | 2019-07-02 | 2019-07-09 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001236 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V1012 | 4748-30-900 | 018-C-GAD-40612-001 | GENERAL ARRANGEMENT DRAWING FOR THIRD STAGE SUCTION DRUM 018V1012 | A1103 | AX | 2 | 2019-06-12 | CON-BMP-VTRA-012173 | 2019-06-12 | FOR BAPCO REVIEW | 2019-06-26 | 2019-07-06 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001173 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V1012 | 4748-30-IT-001 | 018-C-PQP-40092-001 | FABRICATION AND QUALITY CONTROL PLAN CARBON STEEL PRESSURE VESSELS 018V1012 | B1002 | AX | 2 | 2019-06-22 | CON-BMP-VTRA-012382 | 2019-06-22 | FOR BAPCO REVIEW | 2019-07-08 | 2019-07-06 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001174 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V1012 | 4748-30-SC-001 | 018-C-CAL-40208-001 | MECHANICAL DESIGN CALCULATION CARBON STEEL PRESSURE VESSELS 018V1012 | A1003 | AX | 2 | 2019-06-06 | CON-BMP-VTRA-012081 | 2019-06-06 | FOR BAPCO REVIEW | 2019-06-21 | 2019-07-07 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001184 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V1012 | 4748-30-WB-001 | 018-C-MCD-40166-001 | WELDING BOOK (WELD MAP WPS & PQR) CARBON STEEL PRESSURE VESSELS 018V1012 | B1304 | AX | 1 | 2019-05-22 | CON-BMP-VTRA-011727 | 2019-05-22 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V1013 | 4748-31-200 | 018-C-DLB-40113-001 | SITE TEMPLATE DRAWING FOR SECOND-STAGE SUCTION DRUM 018V1013 | A2010 | AX | 2 | 2019-06-18 | CON-BMP-VTRA-012269 | 2019-06-18 | FOR BAPCO REVIEW | 2019-07-02 | 2019-07-09 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001236 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V1013 | 4748-31-900 | 018-C-GAD-40613-001 | GENERAL ARRANGEMENT DRAWING FOR SECOND STAGE SUCTION DRUM 018V1013 | A1103 | AX | 2 | 2019-06-04 | CON-BMP-VTRA-011971 | 2019-06-04 | FOR BAPCO REVIEW | 2019-06-19 | 2019-06-26 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001042 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V1013 | 4748-31-IT-001 | 018-C-PQP-40093-001 | FABRICATION AND QUALITY CONTROL PLAN CARBON STEEL PRESSURE VESSELS 018V1013 | B1002 | AX | 2 | 2019-06-22 | CON-BMP-VTRA-012382 | 2019-06-22 | FOR BAPCO REVIEW | 2019-07-08 | 2019-07-06 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001174 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V1013 | 4748-31-SC-001 | 018-C-CAL-40210-001 | MECHANICAL DESIGN CALCULATION CARBON STEEL PRESSURE VESSELS 018V1013 | A1003 | AX | 2 | 2019-06-01 | CON-BMP-VTRA-011922 | 2019-06-01 | FOR BAPCO REVIEW | 2019-06-17 | 2019-06-18 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000990 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V1013 | 4748-31-WB-001 | 018-C-MCD-40167-001 | WELDING BOOK (WELD MAP WPS & PQR) CARBON STEEL PRESSURE VESSELS 018V1013 | B1304 | AX | 1 | 2019-05-22 | CON-BMP-VTRA-011727 | 2019-05-22 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V1014 | 4748-27-900 | 018-C-GAD-40609-001 | GENERAL ARRANGEMENT DRAWING FOR TRAIN 1 FEED SURGE DRUM 018V1001 | A1103 | AX | 2 | 2019-06-14 | CON-BMP-VTRA-012220 | 2019-06-14 | FOR BAPCO REVIEW | 2019-06-28 | 2019-07-08 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001226 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V1014 | 4748-32-IT-001 | 018-C-PQP-40094-001 | FABRICATION AND QUALITY CONTROL PLAN CARBON STEEL PRESSURE VESSELS 018V1014 018V0040 VESSELS 372V0035 | B1002 | AX | 2 | 2019-06-06 | CON-BMP-VTRA-012084 | 2019-06-06 | FOR BAPCO REVIEW | 2019-06-21 | 2019-06-19 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001005 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V1014 | 4748-32-SC-001 | 018-C-CAL-40212-001 | MECHANICAL DESGN CLACULATION CARBON STEEL PRESSURE VESSELS 018V1014 | A1003 | AX | 2 | 2019-06-10 | CON-BMP-VTRA-012110 | 2019-06-10 | FOR BAPCO REVIEW | 2019-06-24 | 2019-07-02 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001141 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V1014 | 4748-32-WB-001 | 018-C-MCD-40168-001 | WELDING BOOK (WELD MAP WPS & PQR) CARBON STEEL PRESSURE VESSELS 018V1014 | B1304 | AX | 1 | 2019-05-22 | CON-BMP-VTRA-011729 | 2019-05-22 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V1018 | 4748-33-900 | 018-C-GAD-40615-001 | GENERAL ARRANGEMENT DRAWING FOR TRAIN 1 HP STEAM DRUM 018V1018 | A1103 | AX | 2 | 2019-06-04 | CON-BMP-VTRA-011971 | 2019-06-04 | FOR BAPCO REVIEW | 2019-06-19 | 2019-06-26 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001042 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V1018 | 4748-33-IT-001 | 018-C-PQP-40095-001 | FABRICATION AND QUALITY CONTROL PLAN CARBON STEEL PRESSURE VESSELS 018V1018 | B1002 | AX | 2 | 2019-06-06 | CON-BMP-VTRA-012084 | 2019-06-06 | FOR BAPCO REVIEW | 2019-06-21 | 2019-06-19 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001005 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V1018 | 4748-33-SC-001 | 018-C-CAL-40214-001 | MECHANICAL DESGN CLACULATION CARBON STEEL PRESSURE VESSELS 018V1018 | A1003 | AX | 2 | 2019-06-01 | CON-BMP-VTRA-011922 | 2019-06-01 | FOR BAPCO REVIEW | 2019-06-17 | 2019-06-18 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000990 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V1018 | 4748-33-WB-001 | 018-C-MCD-40169-001 | WELDING BOOK (WELD MAP WPS & PQR) CARBON STEEL PRESSURE VESSELS 018V1018 | B1304 | AX | 1 | 2019-05-22 | CON-BMP-VTRA-011729 | 2019-05-22 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V2001 | 4748-34-200 | 018-C-DLB-40115-001 | SITE TEMPLATE DRAWING FOR TRAIN 2 FEED SURGE DRUM 018V2001 | A2010 | AX | 2 | 2019-06-18 | CON-BMP-VTRA-012269 | 2019-06-18 | FOR BAPCO REVIEW | 2019-07-02 | 2019-07-09 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001236 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V2001 | 4748-34-900 | 018-C-GAD-40616-001 | GENERAL ARRANGEMENT DRAWING FOR TRAIN 2 FEED SURGE DRUM 018V2001 | A1103 | AX | 2 | 2019-06-14 | CON-BMP-VTRA-012220 | 2019-06-14 | FOR BAPCO REVIEW | 2019-06-28 | 2019-07-08 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001226 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V2001 | 4748-34-IT-001 | 018-C-PQP-40096-001 | FABRICATION AND QUALITY CONTROL PLAN CARBON STEEL PRESSURE VESSELS 018V2001 | B1002 | AX | 2 | 2019-06-06 | CON-BMP-VTRA-012084 | 2019-06-06 | FOR BAPCO REVIEW | 2019-06-21 | 2019-06-19 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001005 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V2001 | 4748-34-SC-001 | 018-C-CAL-40216-001 | MECHANICAL DESIGN CALCULATION CARBON STEEL PRESSURE VESSELS 018V2001 | A1003 | AX | 2 | 2019-06-11 | CON-BMP-VTRA-012156 | 2019-06-11 | FOR BAPCO REVIEW | 2019-06-26 | 2019-07-04 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001170 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V2001 | 4748-34-WB-001 | 018-C-MCD-40170-001 | WELDING BOOK (WELD MAP WPS & PQR) CARBON STEEL PRESSURE VESSELS 018V2001 | B1304 | AX | 1 | 2019-05-22 | CON-BMP-VTRA-011729 | 2019-05-22 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V2010 | 4748-35-200 | 018-C-DLB-40116-001 | SITE TEMPLATE DRAWING FOR FIRST-STAGE SUCTION DRUM 018V2010 | A2010 | AX | 2 | 2019-06-18 | CON-BMP-VTRA-012269 | 2019-06-18 | FOR BAPCO REVIEW | 2019-07-02 | 2019-07-09 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001236 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V2010 | 4748-35-900 | 018-C-GAD-40617-001 | GENERAL ARRANGEMENT DRAWING FOR FIRST STAGE SUCTION DRUM 018V2010 | A1103 | AX | 2 | 2019-06-12 | CON-BMP-VTRA-012173 | 2019-06-12 | FOR BAPCO REVIEW | 2019-06-26 | 2019-07-06 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001173 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V2010 | 4748-35-IT-001 | 018-C-PQP-40097-001 | FABRICATION AND QUALITY CONTROL PLAN CARBON STEEL PRESSURE VESSELS 018V2010 | B1002 | AX | 2 | 2019-06-06 | CON-BMP-VTRA-012084 | 2019-06-06 | FOR BAPCO REVIEW | 2019-06-21 | 2019-06-19 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001005 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V2010 | 4748-35-SC-001 | 018-C-CAL-40217-001 | MECHANICAL DESIGN CALCULATION CARBON STEEL PRESSURE VESSELS 018V2010 | A1003 | AX | 2 | 2019-06-06 | CON-BMP-VTRA-012081 | 2019-06-06 | FOR BAPCO REVIEW | 2019-06-21 | 2019-07-07 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001184 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V2010 | 4748-35-WB-001 | 018-C-MCD-40171-001 | WELDING BOOK (WELD MAP WPS & PQR) CARBON STEEL PRESSURE VESSELS 018V2010 | B1304 | AX | 1 | 2019-05-22 | CON-BMP-VTRA-011727 | 2019-05-22 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V2011 | 4748-36-200 | 018-C-DLB-40117-001 | SITE TEMPLATE DRAWING FOR SECOUND-STAGE SUCTION DRUM 018V2011 | A2010 | AX | 2 | 2019-06-18 | CON-BMP-VTRA-012269 | 2019-06-18 | FOR BAPCO REVIEW | 2019-07-02 | 2019-07-09 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001236 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V2011 | 4748-36-900 | 018-C-GAD-40618-001 | GENERAL ARRANGEMENT DRAWING FOR SECOND STAGE SUCTION DRUM 018V2011 | A1103 | AX | 2 | 2019-06-04 | CON-BMP-VTRA-011971 | 2019-06-04 | FOR BAPCO REVIEW | 2019-06-19 | 2019-06-26 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001042 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V2011 | 4748-36-IT-001 | 018-C-PQP-40098-001 | FABRICATION AND QUALITY CONTROL PLAN CARBON STEEL PRESSURE VESSELS 018V2011 | B1002 | AX | 2 | 2019-06-06 | CON-BMP-VTRA-012084 | 2019-06-06 | FOR BAPCO REVIEW | 2019-06-21 | 2019-06-19 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001005 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V2011 | 4748-36-SC-001 | 018-C-CAL-40219-001 | MECHANICAL DESIGN CALCULATION CARBON STEEL PRESSURE VESSELS 018V2011 | A1003 | AX | 2 | 2019-06-01 | CON-BMP-VTRA-011922 | 2019-06-01 | FOR BAPCO REVIEW | 2019-06-17 | 2019-06-18 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000990 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V2011 | 4748-36-WB-001 | 018-C-MCD-40172-001 | WELDING BOOK (WELD MAP WPS & PQR) CARBON STEEL PRESSURE VESSELS 018V2011 | B1304 | AX | 1 | 2019-05-22 | CON-BMP-VTRA-011727 | 2019-05-22 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V2012 | 4748-37-200 | 018-C-DLB-40118-001 | SITE TEMPLATE DRAWING FOR THIRD-STAGE SUCTION DRUM 018V2012 | A2010 | AX | 2 | 2019-06-18 | CON-BMP-VTRA-012269 | 2019-06-18 | FOR BAPCO REVIEW | 2019-07-02 | 2019-07-09 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001236 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V2012 | 4748-37-900 | 018-C-GAD-40619-001 | GENERAL ARRANGEMENT DRAWING FOR THIRD STAGE SUCTION DRUM 018V2012 | A1103 | AX | 2 | 2019-06-12 | CON-BMP-VTRA-012173 | 2019-06-12 | FOR BAPCO REVIEW | 2019-06-26 | 2019-07-06 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001173 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V2012 | 4748-37-IT-001 | 018-C-PQP-40099-001 | FABRICATION AND QUALITY CONTROL PLAN CARBON STEEL PRESSURE VESSELS 018V2012 | B1002 | AX | 2 | 2019-06-22 | CON-BMP-VTRA-012382 | 2019-06-22 | FOR BAPCO REVIEW | 2019-07-08 | 2019-07-06 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001174 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V2012 | 4748-37-SC-001 | 018-C-CAL-40221-001 | MECHANICAL DESIGN CALCULATION CARBON STEEL PRESSURE VESSELS 018V2012 | A1003 | AX | 2 | 2019-06-06 | CON-BMP-VTRA-012081 | 2019-06-06 | FOR BAPCO REVIEW | 2019-06-21 | 2019-07-07 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001184 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V2012 | 4748-37-WB-001 | 018-C-MCD-40173-001 | WELDING BOOK (WELD MAP WPS & PQR) CARBON STEEL PRESSURE VESSELS 018V2012 | B1304 | AX | 1 | 2019-05-22 | CON-BMP-VTRA-011727 | 2019-05-22 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V2013 | 4748-38-200 | 018-C-DLB-40119-001 | SITE TEMPLATE DRAWING FOR SECOUND-STAGE SUCTION DRUM 018V2013 | A2010 | AX | 2 | 2019-06-18 | CON-BMP-VTRA-012269 | 2019-06-18 | FOR BAPCO REVIEW | 2019-07-02 | 2019-07-09 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001236 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V2013 | 4748-38-900 | 018-C-GAD-40620-001 | GENERAL ARRANGEMENT DRAWING FOR SECOND STAGE SUCTION DRUM 018V2013 | A1103 | AX | 2 | 2019-06-04 | CON-BMP-VTRA-011971 | 2019-06-04 | FOR BAPCO REVIEW | 2019-06-19 | 2019-06-26 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001042 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V2013 | 4748-38-IT-001 | 018-C-PQP-40100-001 | FABRICATION AND QUALITY CONTROL PLAN CARBON STEEL PRESSURE VESSELS 018V2013 | B1002 | AX | 2 | 2019-06-22 | CON-BMP-VTRA-012382 | 2019-06-22 | FOR BAPCO REVIEW | 2019-07-08 | 2019-07-06 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001174 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V2013 | 4748-38-SC-001 | 018-C-CAL-40223-001 | MECHANICAL DESIGN CALCULATION CARBON STEEL PRESSURE VESSELS 018V2013 | A1003 | AX | 2 | 2019-06-01 | CON-BMP-VTRA-011922 | 2019-06-01 | FOR BAPCO REVIEW | 2019-06-17 | 2019-06-18 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000990 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V2013 | 4748-38-WB-001 | 018-C-MCD-40174-001 | WELDING BOOK (WELD MAP WPS & PQR) CARBON STEEL PRESSURE VESSELS 018V2013 | B1304 | AX | 1 | 2019-05-22 | CON-BMP-VTRA-011728 | 2019-05-22 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V2014 | 4748-39-900 | 018-C-GAD-40621-001 | GENERAL ARRANGEMENT DRAWING FOR THIRD STAGE SUCTION DRUM 018V2014 | A1103 | AX | 2 | 2019-06-14 | CON-BMP-VTRA-012220 | 2019-06-14 | FOR BAPCO REVIEW | 2019-06-28 | 2019-07-08 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001226 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V2014 | 4748-39-IT-001 | 018-C-PQP-40101-001 | FABRICATION AND QUALITY CONTROL PLAN CARBON STEEL PRESSURE VESSELS 018V2014 | B1002 | AX | 2 | 2019-06-22 | CON-BMP-VTRA-012382 | 2019-06-22 | FOR BAPCO REVIEW | 2019-07-08 | 2019-07-06 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001174 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V2014 | 4748-39-SC-001 | 018-C-CAL-40225-001 | MECHANICAL DESIGN CALCULATION CARBON STEEL PRESSURE VESSELS 018V2014 | A1003 | AX | 2 | 2019-06-10 | CON-BMP-VTRA-012110 | 2019-06-10 | FOR BAPCO REVIEW | 2019-06-24 | 2019-07-02 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001141 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V2014 | 4748-39-WB-001 | 018-C-MCD-40175-001 | WELDING BOOK (WELD MAP WPS & PQR) CARBON STEEL PRESSURE VESSELS 018V2014 | B1304 | AX | 1 | 2019-05-22 | CON-BMP-VTRA-011728 | 2019-05-22 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V2018 | 4748-40-900 | 018-C-GAD-40622-001 | GENERAL ARRANGEMENT DRAWING FOR TRAIN 2 HP STEAM DRUM 018V2018 | A1103 | AX | 2 | 2019-06-04 | CON-BMP-VTRA-011971 | 2019-06-04 | FOR BAPCO REVIEW | 2019-06-19 | 2019-06-26 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001042 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V2018 | 4748-40-IT-001 | 018-C-PQP-40102-001 | FABRICATION AND QUALITY CONTROL PLAN CARBON STEEL PRESSURE VESSELS 018V2018 | B1002 | AX | 2 | 2019-06-22 | CON-BMP-VTRA-012382 | 2019-06-22 | FOR BAPCO REVIEW | 2019-07-08 | 2019-07-06 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001174 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V2018 | 4748-40-SC-001 | 018-C-CAL-40227-001 | MECHANICAL DESIGN CALCULATION CARBON STEEL PRESSURE VESSELS 018V2018 | A1003 | AX | 2 | 2019-06-01 | CON-BMP-VTRA-011922 | 2019-06-01 | FOR BAPCO REVIEW | 2019-06-17 | 2019-06-18 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000990 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 018V2018 | 4748-40-WB-001 | 018-C-MCD-40176-001 | WELDING BOOK (WELD MAP WPS & PQR) CARBONE STEEL PRESSURE VESSELS 018V2018 | B1304 | AX | 1 | 2019-05-22 | CON-BMP-VTRA-011728 | 2019-05-22 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 021V0006 | 4748-41-200 | 021-C-DLB-40024-001 | SITE TEMPLATE DRAWING FOR RECYCLE GAS COMPRESSOR SUCTIONDRUM 021V0006 | A2010 | AX | 2 | 2019-06-18 | CON-BMP-VTRA-012266 | 2019-06-18 | FOR BAPCO REVIEW | 2019-07-02 | 2019-06-30 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001113 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 021V0006 | 4748-41-900 | 021-C-GAD-40146-001 | GENERAL ARRANGEMENT DRAWING FOR RECYCLE GAS COMPRESSOR SUCTION DRUM 021V0006 | A1103 | AX | 2 | 2019-06-04 | CON-BMP-VTRA-011971 | 2019-06-04 | FOR BAPCO REVIEW | 2019-06-19 | 2019-06-26 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001042 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 021V0006 | 4748-41-IT-001 | 021-C-PQP-40017-001 | FABRICATION AND QUALITY CONTROL PLAN CARBON STEEL PRESSURE VESSELS 021V0006 | B1002 | AX | 2 | 2019-06-06 | CON-BMP-VTRA-012084 | 2019-06-06 | FOR BAPCO REVIEW | 2019-06-21 | 2019-06-19 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001005 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 021V0006 | 4748-41-SC-001 | 021-C-CAL-40038-001 | MECHANICAL DESIGN CALCULATION CARBON STEEL PRESSURE VESSELS 021V0006 | A1003 | AX | 2 | 2019-05-24 | CON-BMP-VTRA-011799 | 2019-05-24 | FOR BAPCO REVIEW | 2019-06-10 | 2019-06-16 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000946 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 021V0006 | 4748-41-WB-001 | 021-C-MCD-40036-001 | WELDING BOOK (WELD MAP WPS & PQR) CARBON STEEL PRESSURE VESSELS 021V0006 | B1304 | AX | 1 | 2019-05-22 | CON-BMP-VTRA-011728 | 2019-05-22 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 021V0007 | 4748-42-200 | 021-C-DLB-40025-001 | SITE TEMPLATE DRAWING FOR INJECTION WATER BREAK TANK 021V0007 | A2010 | AX | 2 | 2019-06-18 | CON-BMP-VTRA-012266 | 2019-06-18 | FOR BAPCO REVIEW | 2019-07-02 | 2019-06-30 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001113 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 021V0007 | 4748-42-900 | 021-C-GAD-40147-001 | GENERAL ARRANGEMENT DRAWING FOR INJECTION WATER BREAK TANK021V0007 | A1103 | AX | 2 | 2019-06-12 | CON-BMP-VTRA-012174 | 2019-06-12 | FOR BAPCO REVIEW | 2019-06-26 | 2019-07-07 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001178 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 021V0007 | 4748-42-IT-001 | 021-C-PQP-40018-001 | FABRICATION AND QUALITY CONTROL PLAN CARBON STEEL PRESSURE VESSELS 021V0007 | B1002 | AX | 2 | 2019-06-22 | CON-BMP-VTRA-012385 | 2019-06-22 | FOR BAPCO REVIEW | 2019-07-08 | 2019-07-11 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001302 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 021V0007 | 4748-42-SC-001 | 021-C-CAL-40040-001 | MECHANICAL DESIGN CALCULATION CARBON STEEL PRESSURE VESSELS 021V0007 | A1003 | AX | 2 | 2019-06-06 | CON-BMP-VTRA-012081 | 2019-06-06 | FOR BAPCO REVIEW | 2019-06-21 | 2019-07-07 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001184 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 021V0007 | 4748-42-WB-001 | 021-C-MCD-40037-001 | WELDING BOOK (WELD MAP WPS & PQR) CARBONE STEEL PRESSURE VESSELS 021V0007 | B1304 | AX | 1 | 2019-05-22 | CON-BMP-VTRA-011727 | 2019-05-22 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 021V0010 | 4748-43-900 | 021-C-GAD-40148-001 | GENERAL ARRANGEMENT DRAWING FOR STRIPPER REFLUX DRUM 021V0010 | A1103 | AX | 2 | 2019-06-04 | CON-BMP-VTRA-011971 | 2019-06-04 | FOR BAPCO REVIEW | 2019-06-19 | 2019-06-26 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001042 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 021V0010 | 4748-43-IT-001 | 021-C-PQP-40019-001 | FABRICATION AND QUALITY CONTROL PLAN CARBON STEEL PRESSURE VESSELS 021V0010 | B1002 | AX | 2 | 2019-06-06 | CON-BMP-VTRA-012084 | 2019-06-06 | FOR BAPCO REVIEW | 2019-06-21 | 2019-06-19 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001005 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 021V0010 | 4748-43-SC-001 | 021-C-CAL-40041-001 | MECHANICAL DESIGN CALCULATION CARBON STEEL PRESSURE VESSELS 021V0010 | A1003 | AX | 2 | 2019-05-24 | CON-BMP-VTRA-011799 | 2019-05-24 | FOR BAPCO REVIEW | 2019-06-10 | 2019-06-16 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000946 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 021V0010 | 4748-43-WB-001 | 021-C-MCD-40038-001 | WELDING BOOK (WELD MAP WPS & PQR) CARBONE STEEL PRESSURE VESSELS 021V0010 | B1304 | AX | 1 | 2019-05-22 | CON-BMP-VTRA-011728 | 2019-05-22 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 021V0013 | 4748-44-900 | 021-C-GAD-40149-001 | GENERAL ARRANGEMENT DRAWING FOR EJECTOR RECEIVER 021V0013 | A1103 | AX | 2 | 2019-06-12 | CON-BMP-VTRA-012174 | 2019-06-12 | FOR BAPCO REVIEW | 2019-06-26 | 2019-07-07 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001178 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 021V0013 | 4748-44-IT-001 | 021-C-PQP-40020-001 | FABRICATION AND QUALITY CONTROL PLAN CARBON STEEL PRESSURE VESSELS 021V0013 | B1002 | AX | 2 | 2019-06-22 | CON-BMP-VTRA-012385 | 2019-06-22 | FOR BAPCO REVIEW | 2019-07-08 | 2019-07-11 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001302 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 021V0013 | 4748-44-SC-001 | 021-C-CAL-40042-001 | MECHANICAL DESIGN CALCULATION CARBON STEEL PRESSURE VESSELS 021V0013 | A1003 | AX | 2 | 2019-06-06 | CON-BMP-VTRA-012081 | 2019-06-06 | FOR BAPCO REVIEW | 2019-06-21 | 2019-07-07 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001184 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 021V0013 | 4748-44-WB-001 | 021-C-MCD-40039-001 | WELDING BOOK (WELD MAP WPS & PQR) CARBONE STEEL PRESSURE VESSELS 021V0013 | B1304 | AX | 1 | 2019-05-22 | CON-BMP-VTRA-011728 | 2019-05-22 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 021V0014 | 4748-45-900 | 021-C-GAD-40150-001 | GENERAL ARRANGEMENT DRAWING FOR WATER SEAL POT 021V0014 | A1103 | AX | 2 | 2019-06-04 | CON-BMP-VTRA-011971 | 2019-06-04 | FOR BAPCO REVIEW | 2019-06-19 | 2019-06-26 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001042 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 021V0014 | 4748-45-IT-001 | 021-C-PQP-40021-001 | FABRICATION AND QUALITY CONTROL PLAN CARBON STEEL PRESSURE VESSELS 021V0014 | B1002 | AX | 2 | 2019-06-22 | CON-BMP-VTRA-012385 | 2019-06-22 | FOR BAPCO REVIEW | 2019-07-08 | 2019-07-11 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001302 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 021V0014 | 4748-45-SC-001 | 021-C-CAL-40043-001 | MECHANICAL DESIGN CALCULATION CARBON STEEL PRESSURE VESSELS 021V0014 | A1003 | AX | 2 | 2019-06-01 | CON-BMP-VTRA-011922 | 2019-06-01 | FOR BAPCO REVIEW | 2019-06-17 | 2019-06-18 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000990 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 021V0014 | 4748-45-WB-001 | 021-C-MCD-40040-001 | WELDING BOOK (WELD MAP WPS & PQR) CARBONE STEEL PRESSURE VESSELS 021V0014 | B1304 | AX | 1 | 2019-05-22 | CON-BMP-VTRA-011728 | 2019-05-22 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 021V0016 | 4748-46-200 | 021-C-DLB-40026-001 | SITE TEMPLATE DRAWING FOR SOURWATER DEGASSING DRUM 021V0016 | A2010 | AX | 2 | 2019-06-18 | CON-BMP-VTRA-012266 | 2019-06-18 | FOR BAPCO REVIEW | 2019-07-02 | 2019-06-30 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001113 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 021V0016 | 4748-46-900 | 021-C-GAD-40151-001 | GENERAL ARRANGEMENT DRAWING FOR SOUR WATER DEGASSING DRUM 021V0016 | A1103 | AX | 2 | 2019-06-04 | CON-BMP-VTRA-011971 | 2019-06-04 | FOR BAPCO REVIEW | 2019-06-19 | 2019-06-26 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001042 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 021V0016 | 4748-46-IT-001 | 021-C-PQP-40022-001 | FABRICATION AND QUALITY CONTROL PLAN CARBON STEEL PRESSURE VESSELS 021V0016 | B1002 | AX | 2 | 2019-06-22 | CON-BMP-VTRA-012385 | 2019-06-22 | FOR BAPCO REVIEW | 2019-07-08 | 2019-07-11 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001302 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 021V0016 | 4748-46-SC-001 | 021-C-CAL-40044-001 | MECHANICAL DESIGN CALCULATION CARBON STEEL PRESSURE VESSELS 021V0016 | A1003 | AX | 2 | 2019-06-01 | CON-BMP-VTRA-011922 | 2019-06-01 | FOR BAPCO REVIEW | 2019-06-17 | 2019-06-18 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000990 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 021V0016 | 4748-46-WB-001 | 021-C-MCD-40041-001 | WELDING BOOK (WELD MAP WPS & PQR) CARBONE STEEL PRESSURE VESSELS 021V0016 | B1304 | AX | 1 | 2019-05-22 | CON-BMP-VTRA-011727 | 2019-05-22 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 021V0017 | 4748-47-200 | 021-C-DLB-40027-001 | SITE TEMPLATE DRAWING FOR LEANAMINE SURGE DRUM 021V0017 | A2010 | AX | 2 | 2019-06-18 | CON-BMP-VTRA-012266 | 2019-06-18 | FOR BAPCO REVIEW | 2019-07-02 | 2019-06-30 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001113 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 021V0017 | 4748-47-900 | 021-C-GAD-40152-001 | GENERAL ARRANGEMENT DRAWING FOR LEAN AMINE SURGE DRUM 021V0017 | A1103 | AX | 2 | 2019-06-14 | CON-BMP-VTRA-012221 | 2019-06-14 | FOR BAPCO REVIEW | 2019-06-28 | 2019-07-07 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001180 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 021V0017 | 4748-47-IT-001 | 021-C-PQP-40023-001 | FABRICATION AND QUALITY CONTROL PLAN CARBON STEEL PRESSURE VESSELS 021V0017 | B1002 | AX | 2 | 2019-06-25 | CON-BMP-VTRA-012428 | 2019-06-25 | FOR BAPCO REVIEW | 2019-07-09 | 2019-07-08 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001220 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 021V0017 | 4748-47-SC-001 | 021-C-CAL-40045-001 | MECHANICAL DESIGN CALCULATION CARBON STEEL PRESSURE VESSELS 021V0017 | A1003 | AX | 2 | 2019-06-11 | CON-BMP-VTRA-012157 | 2019-06-11 | FOR BAPCO REVIEW | 2019-06-26 | 2019-07-02 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001142 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 021V0017 | 4748-47-WB-001 | 021-C-MCD-40042-001 | WELDING BOOK (WELD MAP WPS & PQR) CARBONE STEEL PRESSURE VESSELS 021V0017 | B1304 | AX | 1 | 2019-05-22 | CON-BMP-VTRA-011727 | 2019-05-22 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 021V0018 | 4748-48-200 | 021-C-DLB-40028-001 | SITE TEMPLATE DRAWING FOR BACKWASH SURGE DRUM 021V0018 | A2010 | AX | 2 | 2019-06-18 | CON-BMP-VTRA-012266 | 2019-06-18 | FOR BAPCO REVIEW | 2019-07-02 | 2019-06-30 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001113 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 021V0018 | 4748-48-900 | 021-C-GAD-40153-001 | GENERAL ARRANGEMENT DRAWING FOR BACKWASH SURGE DRUM 021V0018 | A1103 | AX | 2 | 2019-06-04 | CON-BMP-VTRA-011971 | 2019-06-04 | FOR BAPCO REVIEW | 2019-06-19 | 2019-06-26 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001042 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 021V0018 | 4748-48-IT-001 | 021-C-PQP-40024-001 | FABRICATION AND QUALITY CONTROL PLAN CARBON STEEL PRESSURE VESSELS 021V0018 | B1002 | AX | 2 | 2019-06-25 | CON-BMP-VTRA-012428 | 2019-06-25 | FOR BAPCO REVIEW | 2019-07-09 | 2019-07-08 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001220 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 021V0018 | 4748-48-SC-001 | 021-C-CAL-40046-001 | MECHANICAL DESIGN CALCULATION CARBON STEEL PRESSURE VESSELS 021V0018 | A1003 | AX | 2 | 2019-05-22 | CON-BMP-VTRA-011726 | 2019-05-22 | FOR BAPCO REVIEW | 2019-06-06 | 2019-06-12 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000916 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 021V0018 | 4748-48-WB-001 | 021-C-MCD-40043-001 | WELDING BOOK (WELD MAP WPS & PQR) CARBONE STEEL PRESSURE VESSELS 021V0018 | B1304 | AX | 1 | 2019-05-22 | CON-BMP-VTRA-011727 | 2019-05-22 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 021V0019 | 4748-49-900 | 021-C-GAD-40154-001 | GENERAL ARRANGEMENT DRAWING FOR FUEL GAS KO DRUM 021V0019 | A1103 | AX | 2 | 2019-06-04 | CON-BMP-VTRA-011971 | 2019-06-04 | FOR BAPCO REVIEW | 2019-06-19 | 2019-06-26 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001042 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 021V0019 | 4748-49-IT-001 | 021-C-PQP-40025-001 | FABRICATION AND QUALITY CONTROL PLAN CARBON STEEL PRESSURE VESSELS 021V0019 | B1002 | AX | 2 | 2019-06-25 | CON-BMP-VTRA-012428 | 2019-06-25 | FOR BAPCO REVIEW | 2019-07-09 | 2019-07-08 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001220 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 021V0019 | 4748-49-SC-001 | 021-C-CAL-40047-001 | MECHANICAL DESIGN CALCULATION CARBON STEEL PRESSURE VESSELS 021V0019 | A1003 | AX | 2 | 2019-05-22 | CON-BMP-VTRA-011718 | 2019-05-22 | FOR BAPCO REVIEW | 2019-06-05 | 2019-06-12 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000918 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 021V0019 | 4748-49-WB-001 | 021-C-MCD-40044-001 | WELDING BOOK (WELD MAP WPS & PQR) CARBONE STEEL PRESSURE VESSELS 021V0019 | B1304 | AX | 1 | 2019-05-22 | CON-BMP-VTRA-011727 | 2019-05-22 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 021V0020 | 4748-50-900 | 021-C-GAD-40155-001 | GENERAL ARRANGEMENT DRAWING FOR RECOVERED PROCESS SLOP OILSUMP 021V0020 | A1103 | AXX | 2 | 2019-07-08 | CON-BMP-VTRA-012725 | 2019-07-08 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 021V0020 | 4748-50-IT-001 | 021-C-PQP-40026-001 | FABRICATION AND QUALITY CONTROL PLAN CARBON STEEL PRESSURE VESSELS 021V0020 | B1002 | AX | 2 | 2019-06-22 | CON-BMP-VTRA-012385 | 2019-06-22 | FOR BAPCO REVIEW | 2019-07-08 | 2019-07-11 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001302 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 021V0020 | 4748-50-SC-001 | 021-C-CAL-40049-001 | MECHANICAL DESIGN CALCULATION CARBON STEEL PRESSURE VESSELS 021V0020 | A1003 | AX | 2 | 2019-06-18 | CON-BMP-VTRA-012264 | 2019-06-18 | FOR BAPCO REVIEW | 2019-07-02 | 2019-07-08 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001206 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 021V0020 | 4748-50-WB-001 | 021-C-MCD-40045-001 | WELDING BOOK (WELD MAP WPS & PQR) CARBONE STEEL PRESSURE VESSELS 021V0020 | B1304 | AX | 1 | 2019-05-22 | CON-BMP-VTRA-011727 | 2019-05-22 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 021V0021 | 4748-51-900 | 021-C-GAD-40156-001 | GENERAL ARRANGEMENT DRAWING FOR AMINE SUMP TANK 021V0021 | A1103 | AX | 2 | 2019-06-12 | CON-BMP-VTRA-012174 | 2019-06-12 | FOR BAPCO REVIEW | 2019-06-26 | 2019-07-07 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001178 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 021V0021 | 4748-51-IT-001 | 021-C-PQP-40027-001 | FABRICATION AND QUALITY CONTROL PLAN CARBON STEEL PRESSURE VESSELS 021V0021 | B1002 | AX | 2 | 2019-06-22 | CON-BMP-VTRA-012385 | 2019-06-22 | FOR BAPCO REVIEW | 2019-07-08 | 2019-07-11 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001302 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 021V0021 | 4748-51-SC-001 | 021-C-CAL-40050-001 | MECHANICAL DESIGN CALCULATION CARBON STEEL PRESSURE VESSELS 021V0021 | A1003 | AX | 2 | 2019-06-01 | CON-BMP-VTRA-011927 | 2019-06-01 | FOR BAPCO REVIEW | 2019-06-17 | 2019-06-18 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000985 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 021V0021 | 4748-51-WB-001 | 021-C-MCD-40046-001 | WELDING BOOK (WELD MAP WPS & PQR) CARBONE STEEL PRESSURE VESSELS 021V0021 | B1304 | AX | 1 | 2019-05-22 | CON-BMP-VTRA-011729 | 2019-05-22 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 021V0022 | 4748-52-900 | 021-C-GAD-40157-001 | GENERAL ARRANGEMENT DRAWING FOR SOUR WATER SUMP 021V0022 | A1103 | AX | 2 | 2019-06-04 | CON-BMP-VTRA-011971 | 2019-06-04 | FOR BAPCO REVIEW | 2019-06-19 | 2019-06-26 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001042 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 021V0022 | 4748-52-IT-001 | 021-C-PQP-40028-001 | FABRICATION AND QUALITY CONTROL PLAN CARBON STEEL PRESSURE VESSELS 021V0022 | B1002 | AX | 2 | 2019-06-22 | CON-BMP-VTRA-012385 | 2019-06-22 | FOR BAPCO REVIEW | 2019-07-08 | 2019-07-11 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001302 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 021V0022 | 4748-52-SC-001 | 021-C-CAL-40051-001 | MECHANICAL DESIGN CALCULATION CARBON STEEL PRESSURE VESSELS 021V0022 | A1003 | AX | 2 | 2019-06-01 | CON-BMP-VTRA-011922 | 2019-06-01 | FOR BAPCO REVIEW | 2019-06-17 | 2019-06-18 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000990 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 021V0022 | 4748-52-WB-001 | 021-C-MCD-40047-001 | WELDING BOOK (WELD MAP WPS & PQR) CARBONE STEEL PRESSURE VESSELS 021V0022 | B1304 | AX | 1 | 2019-05-22 | CON-BMP-VTRA-011729 | 2019-05-22 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 021V0024 | 4748-53-900 | 021-C-GAD-40158-001 | GENERAL ARRANGEMENT DRAWING FOR STEAM BLOWDOWN DRUM 021V0024 | A1103 | AX | 2 | 2019-06-04 | CON-BMP-VTRA-011971 | 2019-06-04 | FOR BAPCO REVIEW | 2019-06-19 | 2019-06-26 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001042 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 021V0024 | 4748-53-IT-001 | 021-C-PQP-40029-001 | FABRICATION AND QUALITY CONTROL PLAN CARBON STEEL PRESSURE VESSELS 021V0024 | B1002 | AX | 2 | 2019-06-25 | CON-BMP-VTRA-012428 | 2019-06-25 | FOR BAPCO REVIEW | 2019-07-09 | 2019-07-08 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001220 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 021V0024 | 4748-53-SC-001 | 021-C-CAL-40052-001 | MECHANICAL DESIGN CALCULATION CARBON STEEL PRESSURE VESSELS 021V0024 | A1003 | AX | 2 | 2019-05-22 | CON-BMP-VTRA-011726 | 2019-05-22 | FOR BAPCO REVIEW | 2019-06-06 | 2019-06-12 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000916 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 021V0024 | 4748-53-WB-001 | 021-C-MCD-40048-001 | WELDING BOOK (WELD MAP WPS & PQR) CARBONE STEEL PRESSURE VESSELS 021V0024 | B1304 | AX | 1 | 2019-05-22 | CON-BMP-VTRA-011729 | 2019-05-22 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 023V0001 | 4748-54-200 | 023-C-DLB-40005-001 | SITE TEMPLATE DRAWING FOR FEEDGAS K.O. DRUM 023V0001 | A2010 | AX | 2 | 2019-06-18 | CON-BMP-VTRA-012268 | 2019-06-18 | FOR BAPCO REVIEW | 2019-07-02 | 2019-07-09 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001238 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 023V0001 | 4748-54-900 | 023-C-GAD-40031-001 | GENERAL ARRANGEMENT DRAWING FOR FEED GAS K.O. DRUM 023V0001 | A1103 | AX | 2 | 2019-06-12 | CON-BMP-VTRA-012175 | 2019-06-12 | FOR BAPCO REVIEW | 2019-06-26 | 2019-07-04 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001172 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 023V0001 | 4748-54-IT-001 | 023-C-PQP-40004-001 | FABRICATION AND QUALITY CONTROL PLAN CARBON STEEL PRESSURE VESSELS 023V0001 | B1002 | AX | 2 | 2019-06-22 | CON-BMP-VTRA-012387 | 2019-06-22 | FOR BAPCO REVIEW | 2019-07-08 | 2019-07-07 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001183 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 023V0001 | 4748-54-SC-001 | 023-C-CAL-40008-001 | MECHANICAL DESIGN CALCULATION CARBON STEEL PRESSURE VESSELS 023V0001 | A1003 | AX | 2 | 2019-06-06 | CON-BMP-VTRA-012081 | 2019-06-06 | FOR BAPCO REVIEW | 2019-06-21 | 2019-07-07 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001184 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 023V0001 | 4748-54-WB-001 | 023-C-MCD-40007-001 | WELDING BOOK (WELD MAP WPS & PQR) CARBONE STEEL PRESSURE VESSELS 023V0001 | B1304 | AX | 1 | 2019-05-22 | CON-BMP-VTRA-011729 | 2019-05-22 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 023V0002 | 4748-55-200 | 023-C-DLB-40006-001 | SITE TEMPLATE DRAWING FOR COMPRESSED GAS K.O. DRUM 023V0002 | A2010 | AX | 2 | 2019-06-18 | CON-BMP-VTRA-012268 | 2019-06-18 | FOR BAPCO REVIEW | 2019-07-02 | 2019-07-09 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001238 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 023V0002 | 4748-55-900 | 023-C-GAD-40032-001 | GENERAL ARRANGEMENT DRAWING FOR COMPRESSED GAS K.O. DRUM 023V0002 | A1103 | AX | 2 | 2019-06-04 | CON-BMP-VTRA-011971 | 2019-06-04 | FOR BAPCO REVIEW | 2019-06-19 | 2019-06-26 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001042 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 023V0002 | 4748-55-IT-001 | 023-C-PQP-40005-001 | FABRICATION AND QUALITY CONTROL PLAN CARBON STEEL PRESSURE VESSELS 023V0002 | B1002 | AX | 2 | 2019-06-25 | CON-BMP-VTRA-012429 | 2019-06-25 | FOR BAPCO REVIEW | 2019-07-09 |  |  | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 023V0002 | 4748-55-SC-001 | 023-C-CAL-40006-001 | MECHANICAL DESIGN CALCULATION CARBON STEEL PRESSURE VESSELS 023V0002 | A1003 | AX | 2 | 2019-06-01 | CON-BMP-VTRA-011922 | 2019-06-01 | FOR BAPCO REVIEW | 2019-06-17 | 2019-06-18 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000990 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 023V0002 | 4748-55-WB-001 | 023-C-MCD-40008-001 | WELDING BOOK (WELD MAP WPS & PQR) CARBONE STEEL PRESSURE VESSELS 023V0002 | B1304 | AX | 1 | 2019-05-22 | CON-BMP-VTRA-011727 | 2019-05-22 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 023V0003 | 4748-56-200 | 023-C-DLB-40007-001 | SITE TEMPLATE DRAWING FOR LEANAMINE SURGE DRUM 023V0003 | A2010 | AX | 2 | 2019-06-24 | CON-BMP-VTRA-012411 | 2019-06-24 | FOR BAPCO REVIEW | 2019-07-09 |  |  | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 023V0003 | 4748-56-900 | 023-C-GAD-40033-001 | GENERAL ARRANGEMENT DRAWING FOR LEAN AMINE SURGE DRUM 023V0003 | A1103 | AX | 2 | 2019-06-24 | CON-BMP-VTRA-012405 | 2019-06-24 | FOR BAPCO REVIEW | 2019-07-08 |  |  | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 023V0003 | 4748-56-IT-001 | 023-C-PQP-40006-001 | FABRICATION AND QUALITY CONTROL PLAN CARBON STEEL PRESSURE VESSELS 023V0003 | B1002 | AX | 2 | 2019-06-25 | CON-BMP-VTRA-012429 | 2019-06-25 | FOR BAPCO REVIEW | 2019-07-09 |  |  | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 023V0003 | 4748-56-WB-001 | 023-C-MCD-40009-001 | WELDING BOOK (WELD MAP WPS & PQR) CARBON STEEL PRESSURE VESSELS 023V0003 | B1304 | AX | 1 | 2019-05-22 | CON-BMP-VTRA-011727 | 2019-05-22 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 051V0001A | 4748-57-200 | 051-C-DLB-40004-001 | SITE TEMPLATE DRAWING FOR INSTRUMENT AIR HOLD-UP RECEIVERS 051V0001A/B | A2010 | AX | 2 | 2019-06-13 | CON-BMP-VTRA-012191 | 2019-06-13 | FOR BAPCO REVIEW | 2019-06-27 | 2019-06-25 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001028 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 051V0001A | 4748-57-900 | 051-C-GAD-40022-001 | GENERAL ARRANGEMENT DRAWING FOR INSTRUMENT AIR HOLD-UP RECEIVERS 051V0001A/B | A1103 | AX | 2 | 2019-06-04 | CON-BMP-VTRA-011971 | 2019-06-04 | FOR BAPCO REVIEW | 2019-06-19 | 2019-06-26 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001042 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 051V0001A | 4748-57-IT-001 | 051-C-PQP-40003-001 | FABRICATION AND QUALITY CONTROL PLAN CARBON STEEL PRESSURE VESSELS 051V0001A/B | B1002 | AX | 2 | 2019-06-22 | CON-BMP-VTRA-012389 | 2019-06-22 | FOR BAPCO REVIEW | 2019-07-08 | 2019-07-07 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001195 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 051V0001A | 4748-57-SC-001 | 051-C-CAL-40018-001 | MECHANICAL DESIGN CALCULATION CARBON STEEL PRESSURE VESSELS 051V0001A/B | A1003 | AX | 2 | 2019-05-22 | CON-BMP-VTRA-011726 | 2019-05-22 | FOR BAPCO REVIEW | 2019-06-06 | 2019-06-12 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000916 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 051V0001A | 4748-57-WB-001 | 051-C-MCD-40009-001 | WELDING BOOK (WELD MAP WPS & PQR) CARBONE STEEL PRESSURE VESSELS 051V0001A/B | B1304 | AX | 1 | 2019-05-22 | CON-BMP-VTRA-011727 | 2019-05-22 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 051V0002A | 4748-58-200 | 051-C-DLB-40005-001 | SITE TEMPLATE DRAWING FOR PROPANE COMPRESSOR 1ST STAGE SUCTION DRUMS 051V0002A/B | A2010 | AX | 2 | 2019-06-13 | CON-BMP-VTRA-012191 | 2019-06-13 | FOR BAPCO REVIEW | 2019-06-27 | 2019-06-25 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001028 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 051V0002A | 4748-58-900 | 051-C-GAD-40023-001 | GENERAL ARRANGEMENT DRAWING FOR PROPANE COMPRESSOR 1ST STAGE SUCTION DRUMS 051V0002A/B | A1103 | AX | 2 | 2019-06-04 | CON-BMP-VTRA-011971 | 2019-06-04 | FOR BAPCO REVIEW | 2019-06-19 | 2019-06-26 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001042 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 051V0002A | 4748-58-IT-001 | 051-C-PQP-40004-001 | FABRICATION AND QUALITY CONTROL PLAN CARBON STEEL PRESSURE VESSELS 051V0002A/B | B1002 | AX | 2 | 2019-06-22 | CON-BMP-VTRA-012389 | 2019-06-22 | FOR BAPCO REVIEW | 2019-07-08 | 2019-07-07 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001195 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 051V0002A | 4748-58-SC-001 | 051-C-CAL-40019-001 | MECHANICAL DESIGN CALCULATION CARBON STEEL PRESSURE VESSELS 051V0002A/B | A1003 | AX | 2 | 2019-05-24 | CON-BMP-VTRA-011799 | 2019-05-24 | FOR BAPCO REVIEW | 2019-06-10 | 2019-06-16 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000946 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 051V0002A | 4748-58-WB-001 | 051-C-MCD-40010-001 | WELDING BOOK (WELD MAP WPS & PQR) CARBON STEEL PRESSURE VESSELS 051V0002A/B | B1304 | AX | 1 | 2019-05-22 | CON-BMP-VTRA-011729 | 2019-05-22 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 058V5817 | 4748-59-200 | 058-C-DLB-40003-001 | SITE TEMPLATE DRAWING FOR PROCESS GAS MIXING DRUM 058V5817 | A2010 | AX | 2 | 2019-06-18 | CON-BMP-VTRA-012267 | 2019-06-18 | FOR BAPCO REVIEW | 2019-07-02 | 2019-07-01 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001132 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 058V5817 | 4748-59-900 | 058-C-GAD-40016-001 | GENERAL ARRANGEMENT DRAWING FOR PROCESS GAS MIXING DRUM 058V5817 | A1103 | AXX | 2 | 2019-07-01 | CON-BMP-VTRA-012592 | 2019-07-01 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 058V5817 | 4748-59-IT-001 | 058-C-PQP-40002-001 | FABRICATION AND QUALITY CONTROL PLAN CARBON STEEL PRESSURE VESSELS 058V5817 | B1002 | AX | 2 | 2019-06-22 | CON-BMP-VTRA-012390 | 2019-06-22 | FOR BAPCO REVIEW | 2019-07-08 | 2019-07-07 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001185 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 058V5817 | 4748-59-SC-001 | 058-C-CAL-40007-001 | MECHANICAL DESIGN CALCULATION CARBON STEEL PRESSURE VESSELS 058V5817 | A1003 | AX | 2 | 2019-06-01 | CON-BMP-VTRA-011922 | 2019-06-01 | FOR BAPCO REVIEW | 2019-06-17 | 2019-06-18 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000990 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 058V5817 | 4748-59-WB-001 | 058-C-MCD-40005-001 | WELDING BOOK (WELD MAP WPS & PQR) CARBON STEEL PRESSURE VESSELS 058V5817 | B1304 | AX | 1 | 2019-05-22 | CON-BMP-VTRA-011727 | 2019-05-22 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 058V5820 | 4748-60-200 | 058-C-DLB-40004-001 | SITE TEMPLATE DRAWING FOR SWEET KHUFF GAS KO DRUM 058V5820 | A2010 | AX | 2 | 2019-06-18 | CON-BMP-VTRA-012267 | 2019-06-18 | FOR BAPCO REVIEW | 2019-07-02 | 2019-07-01 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001132 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 058V5820 | 4748-60-900 | 058-C-GAD-40017-001 | GENERAL ARRANGEMENT DRAWING FOR SWEET KHUFF GAS KO DRUM 058V5820 | A1103 | AXX | 2 | 2019-07-01 | CON-BMP-VTRA-012592 | 2019-07-01 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 058V5820 | 4748-60-IT-001 | 058-C-PQP-40003-001 | FABRICATION AND QUALITY CONTROL PLAN CARBON STEEL PRESSURE VESSELS 058V5820 | B1002 | AX | 2 | 2019-06-22 | CON-BMP-VTRA-012390 | 2019-06-22 | FOR BAPCO REVIEW | 2019-07-08 | 2019-07-07 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001185 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 058V5820 | 4748-60-SC-001 | 058-C-CAL-40009-001 | MECHANICAL DESIGN CALCULATION CARBON STEEL PRESSURE VESSELS 058V5820 | A1003 | AX | 2 | 2019-06-01 | CON-BMP-VTRA-011927 | 2019-06-01 | FOR BAPCO REVIEW | 2019-06-17 | 2019-06-18 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000985 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 058V5820 | 4748-60-WB-001 | 058-C-MCD-40006-001 | WELDING BOOK (WELD MAP WPS & PQR) CARBON STEEL PRESSURE VESSELS 058V5820 | B1304 | AX | 1 | 2019-05-22 | CON-BMP-VTRA-011729 | 2019-05-22 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 081V8104 | 4748-61-900 | 081-C-GAD-40004-001 | GENERAL ARRANGEMENT DRAWING FOR LSDP FLARE K.O DRUM FOR BMP UNITS 081V8104 | A1103 | AX | 2 | 2019-06-04 | CON-BMP-VTRA-011971 | 2019-06-04 | FOR BAPCO REVIEW | 2019-06-19 | 2019-06-26 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001042 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 081V8104 | 4748-61-IT-001 | 081-C-PQP-40001-001 | FABRICATION AND QUALITY CONTROL PLAN CARBON STEEL PRESSURE VESSELS 081V8104 | B1002 | AX | 2 | 2019-06-22 | CON-BMP-VTRA-012391 | 2019-06-22 | FOR BAPCO REVIEW | 2019-07-08 | 2019-07-07 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001188 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 081V8104 | 4748-61-SC-001 | 081-C-CAL-40001-001 | MECHANICAL DESIGN CALCULATION CARBON STEEL PRESSURE VESSELS 081V8104 | A1003 | AX | 2 | 2019-06-01 | CON-BMP-VTRA-011922 | 2019-06-01 | FOR BAPCO REVIEW | 2019-06-17 | 2019-06-18 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000990 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 081V8104 | 4748-61-WB-001 | 081-C-MCD-40002-001 | WELDING BOOK (WELD MAP WPS & PQR) CARBON STEEL PRESSURE VESSELS 081V8104 | B1304 | AX | 1 | 2019-05-22 | CON-BMP-VTRA-011729 | 2019-05-22 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 371V0005 | 4748-62-200 | 371-C-DLB-40001-001 | SITE TEMPLATE DRAWING FOR 20 PSIG EXCESS STEAM CONDENSATE DRUM 371V0005 | A2010 | AX | 2 | 2019-06-13 | CON-BMP-VTRA-012192 | 2019-06-13 | FOR BAPCO REVIEW | 2019-06-27 | 2019-06-27 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001055 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 371V0005 | 4748-62-900 | 371-C-GAD-40002-001 | GENERAL ARRANGEMENT DRAWING FOR 20 PSIG EXCESS STEAM CONDENSATE DRUM 371V0005 | A1103 | AXX | 2 | 2019-07-01 | CON-BMP-VTRA-012598 | 2019-07-01 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 371V0005 | 4748-62-IT-001 | 371-C-PQP-40001-001 | FABRICATION AND QUALITY CONTROL PLAN CARBON STEEL PRESSURE VESSELS 371V0005 | B1002 | AX | 2 | 2019-06-22 | CON-BMP-VTRA-012392 | 2019-06-22 | FOR BAPCO REVIEW | 2019-07-08 | 2019-07-07 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001190 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 371V0005 | 4748-62-SC-001 | 371-C-CAL-40001-001 | MECHANICAL DESIGN CALCULATION CARBON STEEL PRESSURE VESSELS 371V0005 | A1003 | AX | 2 | 2019-06-06 | CON-BMP-VTRA-012081 | 2019-06-06 | FOR BAPCO REVIEW | 2019-06-21 | 2019-07-07 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001184 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 371V0005 | 4748-62-WB-001 | 371-C-MCD-40002-001 | WELDING BOOK (WELD MAP WPS & PQR) CARBON STEEL PRESSURE VESSELS 371V0005 | B1304 | AX | 1 | 2019-05-22 | CON-BMP-VTRA-011729 | 2019-05-22 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 372V0035 | 4748-63-200 | 372-C-DLB-40001-001 | SITE TEMPLATE DRAWING FOR HG CONDENSATE FLASH DRUM 372V0035 | A2010 | AX | 2 | 2019-06-13 | CON-BMP-VTRA-012193 | 2019-06-13 | FOR BAPCO REVIEW | 2019-06-27 | 2019-06-27 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001056 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 372V0035 | 4748-63-900 | 372-C-GAD-40002-001 | GENERAL ARRANGEMENT DRAWING FOR HG CONDENSATE FLASH DRUM 372V0035 | A1103 | AXX | 2 | 2019-07-01 | CON-BMP-VTRA-012599 | 2019-07-01 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 372V0035 | 4748-63-IT-001 | 372-C-PQP-40001-001 | FABRICATION AND QUALITY CONTROL PLAN CARBON STEEL PRESSURE VESSELS 372V0035 | B1002 | AX | 2 | 2019-06-24 | CON-BMP-VTRA-012395 | 2019-06-24 | FOR BAPCO REVIEW | 2019-07-08 | 2019-07-08 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001218 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 372V0035 | 4748-63-SC-001 | 372-C-CAL-40001-001 | MECHANICAL DESIGN CALCULATION CARBON STEEL PRESSURE VESSELS 372V0035 | A1003 | AX | 2 | 2019-06-11 | CON-BMP-VTRA-012158 | 2019-06-11 | FOR BAPCO REVIEW | 2019-06-26 | 2019-06-27 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001057 | CLASS 2
076551C-000R-MR-0811-003 | MATERIAL REQUISITION FOR CARBON STEEL PRESSURE VESSELS | FBM-KNM FZCO | 372V0035 | 4748-63-WB-001 | 372-C-MCD-40002-001 | WELDING BOOK (WELD MAP WPS & PQR) CARBON STEEL PRESSURE VESSELS 372V0035 | B1304 | AX | 1 | 2019-05-22 | CON-BMP-VTRA-011728 | 2019-05-22 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-004 | MATERIAL REQUISITION FOR LARGE CARBON STEEL PRESSURE VESSELS | KNM PROCESS SYSTEMS SND BHD | 018V0008 | K1808007-E-C-12-001 | 018-C-CAL-40084-001 | MECHANICAL DESIGN CALCULATION FOR ATM COLUMN REFLUX DRUM 018V0008 | A1003 | AXX | 2 | 2019-05-29 | CON-BMP-VTRA-011832 | 2019-05-29 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-004 | MATERIAL REQUISITION FOR LARGE CARBON STEEL PRESSURE VESSELS | KNM PROCESS SYSTEMS SND BHD | 018V0008 | K1808007-E-D-12-001 | 018-C-GAD-40396-001 | GENERAL ARRANGEMENT FOR ATM COLUMN REFLUX DRUM 018V0008 | A1103 | AXX | 2 | 2019-05-24 | CON-BMP-VTRA-011803 | 2019-05-24 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-004 | MATERIAL REQUISITION FOR LARGE CARBON STEEL PRESSURE VESSELS | KNM PROCESS SYSTEMS SND BHD | 018V0008 | K1808007-E-D-12-002 | 018-C-GAD-40406-001 | BODY SADDLE & ACCESSORIES DETAIL FOR ATM COLUMN REFLUX DRUM 018V0008 | A1109 | AX | 2 | 2019-05-15 | CON-BMP-VTRA-011620 | 2019-05-15 | FOR BAPCO REVIEW | 2019-05-30 | 2019-05-28 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000849 | CLASS 2
076551C-000R-MR-0811-004 | MATERIAL REQUISITION FOR LARGE CARBON STEEL PRESSURE VESSELS | KNM PROCESS SYSTEMS SND BHD | 018V0008 | K1808007-E-D-12-003 | 018-C-GAD-40416-001 | NOZZLE DETAIL FOR ATM COLUMN REFLUX DRUM 018V0008 | A1109 | AX | 2 | 2019-05-15 | CON-BMP-VTRA-011620 | 2019-05-15 | FOR BAPCO REVIEW | 2019-05-30 | 2019-05-28 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000849 | CLASS 2
076551C-000R-MR-0811-004 | MATERIAL REQUISITION FOR LARGE CARBON STEEL PRESSURE VESSELS | KNM PROCESS SYSTEMS SND BHD | 018V0008 | K1808007-E-D-12-004 | 018-C-GAD-40426-001 | MANHOLE DETAIL DRAWING FOR ATM COLUMN REFLUX DRUM 018V0008 | A1109 | AX | 2 | 2019-05-15 | CON-BMP-VTRA-011620 | 2019-05-15 | FOR BAPCO REVIEW | 2019-05-30 | 2019-05-28 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000849 | CLASS 2
076551C-000R-MR-0811-004 | MATERIAL REQUISITION FOR LARGE CARBON STEEL PRESSURE VESSELS | KNM PROCESS SYSTEMS SND BHD | 018V0008 | K1808007-E-D-12-010 | 018-C-DLB-40059-001 | NAMEPLATE DETAIL DRAWING FOR ATM COLUMN REFLUX DRUM 018V0008 | A1112 | AX | 2 | 2019-04-26 | CON-BMP-VTRA-011289 | 2019-04-26 | FOR BAPCO REVIEW | 2019-05-14 | 2019-05-23 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000743 | CLASS 2
076551C-000R-MR-0811-004 | MATERIAL REQUISITION FOR LARGE CARBON STEEL PRESSURE VESSELS | KNM PROCESS SYSTEMS SND BHD | 018V0008 | K1808007-E-G-001 | 000-C-TSP-40010-001 | MATERIAL SPECIFICATION OR MAINSUB FORDER ALL ITEMS | B1203 | AX | 2 | 2019-02-28 | CON-BMP-VTRA-010545 | 2019-02-28 | FOR BAPCO REVIEW | 2019-03-15 | 2019-03-17 | 4-NOT APPROVED BMP-ROC-VTRE-000329 | CLASS 2
076551C-000R-MR-0811-004 | MATERIAL REQUISITION FOR LARGE CARBON STEEL PRESSURE VESSELS | KNM PROCESS SYSTEMS SND BHD | 018V0008 | K1808007-P-G-001 | 000-C-INX-40009-001 | LIST OF VENDOR DOCUMENTS AND DRAWING ALL ITEMS | A0001 | BX | 4 | 2019-05-22 | CON-BMP-VTRA-011711 | 2019-05-22 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-004 | MATERIAL REQUISITION FOR LARGE CARBON STEEL PRESSURE VESSELS | KNM PROCESS SYSTEMS SND BHD | 018V0008 | K1808007-P-G-002 | 000-C-MRS-40007-001 | MONTHLY PROGRESS REPORT -002 ALL ITEMS | C1002 | AX | 4 | 2019-05-08 | CON-BMP-VTRA-011483 | 2019-05-08 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-0811-004 | MATERIAL REQUISITION FOR LARGE CARBON STEEL PRESSURE VESSELS | KNM PROCESS SYSTEMS SND BHD | 018V0008 | K1808007-P-G-005 | 000-C-INV-40005-001 | UNPRICED COPY OF MAIN SUBORDER ALL ITEMS | C1005 | BX | 4 | 2019-06-04 | CON-BMP-VTRA-011946 | 2019-06-04 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-004 | MATERIAL REQUISITION FOR LARGE CARBON STEEL PRESSURE VESSELS | KNM PROCESS SYSTEMS SND BHD | 018V0008 | K1808007-P-G-006 | 000-C-SCH-40006-001 | ENGINEERING, PROCUREMENT MANUFACTURING AND TEST SCHEDULE ALL ITEMS | C1001 | AX | 4 | 2019-05-03 | CON-BMP-VTRA-011364 | 2019-05-03 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-0811-004 | MATERIAL REQUISITION FOR LARGE CARBON STEEL PRESSURE VESSELS | KNM PROCESS SYSTEMS SND BHD | 018V0008 | K1808007-P-G-010 | 000-C-PQS-40004-001 | SUB-VENDOR QUALIFICATION RECORD ALL ITEMS | B1401 | AX | 2 | 2019-05-22 | CON-BMP-VTRA-011712 | 2019-05-22 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-0811-004 | MATERIAL REQUISITION FOR LARGE CARBON STEEL PRESSURE VESSELS | KNM PROCESS SYSTEMS SND BHD | 018V0008 | K1808007-Q-P-001 | 000-C-PQP-40010-001 | PROJECT QUALITY PLAN ALL ITEMS | B1001 | AXX | 4 | 2019-06-06 | CON-BMP-VTRA-012067 | 2019-06-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-004 | MATERIAL REQUISITION FOR LARGE CARBON STEEL PRESSURE VESSELS | KNM PROCESS SYSTEMS SND BHD | 018V0008 | K1808007-Q-P-002L | 018-C-PQP-40042-001 | FABRICATION AND QUALITY CONTROL PLAN 018V0008 | B1002 | AX | 2 | 2019-04-16 | CON-BMP-VTRA-011205 | 2019-04-16 | FOR BAPCO REVIEW | 2019-05-02 | 2019-04-28 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000611 | CLASS 2
076551C-000R-MR-0811-004 | MATERIAL REQUISITION FOR LARGE CARBON STEEL PRESSURE VESSELS | KNM PROCESS SYSTEMS SND BHD | 018V0008 | K1808007-Q-P-003L | 018-C-MCD-40068-001 | WPS & PQR AND WELD MAP FOR CARBON STEEL WITH PWHT (018V0008) | B1304 | BX | 2 | 2019-06-29 | CON-BMP-VTRA-012564 | 2019-06-29 | FOR BAPCO REVIEW | 2019-07-15 |  |  | CLASS 2
076551C-000R-MR-0811-004 | MATERIAL REQUISITION FOR LARGE CARBON STEEL PRESSURE VESSELS | KNM PROCESS SYSTEMS SND BHD | 018V0008 | K1808007-Q-P-004A | 000-C-PRO-40043-001 | LIQUID PENETRANT EXAMINATION PROCEDURE (PT) ALL ITEMS | B1202 | AXX | 2 | 2019-06-01 | CON-BMP-VTRA-011918 | 2019-06-01 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-004 | MATERIAL REQUISITION FOR LARGE CARBON STEEL PRESSURE VESSELS | KNM PROCESS SYSTEMS SND BHD | 018V0008 | K1808007-Q-P-004B | 000-C-PRO-40044-001 | MAGNETIC PARTICLE EXAMINATION PROCEDURE (MT) ALL ITEMS | B1202 | AXX | 2 | 2019-06-01 | CON-BMP-VTRA-011918 | 2019-06-01 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-004 | MATERIAL REQUISITION FOR LARGE CARBON STEEL PRESSURE VESSELS | KNM PROCESS SYSTEMS SND BHD | 018V0008 | K1808007-Q-P-004C | 000-C-PRO-40045-001 | RADIOGRAPHIC EXAMINATION PROCEDURE ALL ITEMS | B1202 | AXX | 2 | 2019-06-01 | CON-BMP-VTRA-011918 | 2019-06-01 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-004 | MATERIAL REQUISITION FOR LARGE CARBON STEEL PRESSURE VESSELS | KNM PROCESS SYSTEMS SND BHD | 018V0008 | K1808007-Q-P-004D | 000-C-PRO-40046-001 | ULTRASONIC EXAMINATION PROCEDURE ALL ITEMS | B1202 | AXX | 2 | 2019-06-01 | CON-BMP-VTRA-011918 | 2019-06-01 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-004 | MATERIAL REQUISITION FOR LARGE CARBON STEEL PRESSURE VESSELS | KNM PROCESS SYSTEMS SND BHD | 018V0008 | K1808007-Q-P-004F | 000-C-PRO-40047-001 | TIME OF FLIGHT DIFFRACTION (TOFD) PROCEDURE ALL ITEMS | B1202 | AXX | 2 | 2019-06-01 | CON-BMP-VTRA-011920 | 2019-06-01 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-004 | MATERIAL REQUISITION FOR LARGE CARBON STEEL PRESSURE VESSELS | KNM PROCESS SYSTEMS SND BHD | 018V0008 | K1808007-Q-P-011 | 000-C-PRO-40048-001 | HARDNESS TEST PROCEDURE ALL ITEMS | B1202 | AXX | 2 | 2019-06-01 | CON-BMP-VTRA-011920 | 2019-06-01 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-004 | MATERIAL REQUISITION FOR LARGE CARBON STEEL PRESSURE VESSELS | KNM PROCESS SYSTEMS SND BHD | 018V0008 | K1808007-Q-P-013 | 000-C-MCD-40015-001 | WELD REPAIR PROCEDURE ALL ITEMS | B1304 | AXX | 2 | 2019-05-22 | CON-BMP-VTRA-011732 | 2019-05-22 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-004 | MATERIAL REQUISITION FOR LARGE CARBON STEEL PRESSURE VESSELS | KNM PROCESS SYSTEMS SND BHD | 018V0032 | K1808007-E-C-01-001 | 018-C-CAL-40077-001 | MECHANICAL DESIGN CALCULATION FOR FRESH CATALYST TRANSPORT POT 018V0032 | A1003 | AXX | 2 | 2019-05-29 | CON-BMP-VTRA-011832 | 2019-05-29 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-004 | MATERIAL REQUISITION FOR LARGE CARBON STEEL PRESSURE VESSELS | KNM PROCESS SYSTEMS SND BHD | 018V0032 | K1808007-E-D-01-001 | 018-C-GAD-40389-001 | GENERAL ARRANGEMENT FOR FRESH CATALYST TRANSPORT POT 018V0032 | A1103 | AXX | 2 | 2019-07-09 | CON-BMP-VTRA-012765 | 2019-07-09 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-004 | MATERIAL REQUISITION FOR LARGE CARBON STEEL PRESSURE VESSELS | KNM PROCESS SYSTEMS SND BHD | 018V0032 | K1808007-E-D-01-002 | 018-C-GAD-40399-001 | BODY SUPPORT & ACCESSORIES DETAIL DRAWING FOR FRESH CATALYST TRANSPORT POT 018V0032 | A1109 | AX | 2 | 2019-05-03 | CON-BMP-VTRA-011366 | 2019-05-03 | FOR BAPCO REVIEW | 2019-05-17 | 2019-05-26 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000792 | CLASS 2
076551C-000R-MR-0811-004 | MATERIAL REQUISITION FOR LARGE CARBON STEEL PRESSURE VESSELS | KNM PROCESS SYSTEMS SND BHD | 018V0032 | K1808007-E-D-01-003 | 018-C-GAD-40409-001 | NOZZLE DETAIL DRAWING FOR FRESH CATALYST TRANSPORT POT 018V0032 | A1109 | AX | 2 | 2019-05-14 | CON-BMP-VTRA-011565 | 2019-05-14 | FOR BAPCO REVIEW | 2019-05-29 | 2019-05-30 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000852 | CLASS 2
076551C-000R-MR-0811-004 | MATERIAL REQUISITION FOR LARGE CARBON STEEL PRESSURE VESSELS | KNM PROCESS SYSTEMS SND BHD | 018V0032 | K1808007-E-D-01-004 | 018-C-GAD-40419-001 | MANHOLE DETAIL DRAWING FOR FRESH CATALYST TRANSPORT POT 018V0032 | A1109 | AX | 2 | 2019-05-14 | CON-BMP-VTRA-011565 | 2019-05-14 | FOR BAPCO REVIEW | 2019-05-29 | 2019-05-30 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000852 | CLASS 2
076551C-000R-MR-0811-004 | MATERIAL REQUISITION FOR LARGE CARBON STEEL PRESSURE VESSELS | KNM PROCESS SYSTEMS SND BHD | 018V0032 | K1808007-E-D-01-006 | 018-C-DLB-40045-001 | TEMPLATE DRAWING FOR FRESH CATALYST TRANSPORT POT 018V0032 | A2010 | 0X | 2 | 2019-05-28 | CON-BMP-VTRA-011818 | 2019-05-29 | FOR BAPCO REVIEW | 2019-06-12 | 2019-06-17 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000951 | CLASS 2
076551C-000R-MR-0811-004 | MATERIAL REQUISITION FOR LARGE CARBON STEEL PRESSURE VESSELS | KNM PROCESS SYSTEMS SND BHD | 018V0032 | K1808007-E-D-01-012 | 018-C-DLB-40052-001 | NAMEPLATE DETAIL DRAWING FOR FRESH CATALYST TRANSPORT POT 018V0032 | A1112 | AXX | 2 | 2019-07-09 | CON-BMP-VTRA-012763 | 2019-07-09 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-004 | MATERIAL REQUISITION FOR LARGE CARBON STEEL PRESSURE VESSELS | KNM PROCESS SYSTEMS SND BHD | 018V0032 | K1808007-Q-P-002A | 018-C-PQP-40035-001 | FABRICATION AND QUALITY CONTROL PLAN 018V0032 | B1002 | AXX | 2 | 2019-05-13 | CON-BMP-VTRA-011533 | 2019-05-13 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-004 | MATERIAL REQUISITION FOR LARGE CARBON STEEL PRESSURE VESSELS | KNM PROCESS SYSTEMS SND BHD | 018V0032 | K1808007-Q-P-002B | 018-C-PQP-40036-001 | FABRICATION AND QUALITY CONTROL PLAN 018V0033 | A1109 | AXX | 2 | 2019-05-14 | CON-BMP-VTRA-011564 | 2019-05-14 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-004 | MATERIAL REQUISITION FOR LARGE CARBON STEEL PRESSURE VESSELS | KNM PROCESS SYSTEMS SND BHD | 018V0032 | K1808007-Q-P-003A | 018-C-MCD-40061-001 | WPS & PWR AND WELD MAP FOR LARGE CARBON STEEL PRESSURE WITH PWHT 018V0032 | B1304 | BX | 2 | 2019-06-29 | CON-BMP-VTRA-012563 | 2019-06-29 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-004 | MATERIAL REQUISITION FOR LARGE CARBON STEEL PRESSURE VESSELS | KNM PROCESS SYSTEMS SND BHD | 018V0033 | K1808007-E-C-02-001 | 018-C-CAL-40078-001 | MECHANICAL DESIGN CALCULATION FOR FRESH CATALYST INVENTORY HOLDING BIN 018V0033 | A1003 | AXX | 2 | 2019-05-29 | CON-BMP-VTRA-011832 | 2019-05-29 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-004 | MATERIAL REQUISITION FOR LARGE CARBON STEEL PRESSURE VESSELS | KNM PROCESS SYSTEMS SND BHD | 018V0033 | K1808007-E-D-02-001 | 018-C-GAD-40390-001 | GENERAL ARRANGEMENT FOR CATALYST INVENTORY HOLDING BIN 018V0033 | A1103 | AXX | 2 | 2019-05-24 | CON-BMP-VTRA-011803 | 2019-05-24 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-004 | MATERIAL REQUISITION FOR LARGE CARBON STEEL PRESSURE VESSELS | KNM PROCESS SYSTEMS SND BHD | 018V0033 | K1808007-E-D-02-002 | 018-C-GAD-40400-001 | BODY SUPPORT & ACCESSORIES DETAIL DRAWING FOR CATALYST INVENTORY HOLDING BIN 018V0033 | A1109 | AX | 2 | 2019-05-03 | CON-BMP-VTRA-011366 | 2019-05-03 | FOR BAPCO REVIEW | 2019-05-17 | 2019-05-26 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000792 | CLASS 2
076551C-000R-MR-0811-004 | MATERIAL REQUISITION FOR LARGE CARBON STEEL PRESSURE VESSELS | KNM PROCESS SYSTEMS SND BHD | 018V0033 | K1808007-E-D-02-003 | 018-C-GAD-40410-001 | NOZZLE DETAIL DRAWING FOR CATALYST INVENTORY HOLDING BIN 018V0033 | A1109 | AX | 2 | 2019-05-14 | CON-BMP-VTRA-011565 | 2019-05-14 | FOR BAPCO REVIEW | 2019-05-29 | 2019-05-20 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000852 | CLASS 2
076551C-000R-MR-0811-004 | MATERIAL REQUISITION FOR LARGE CARBON STEEL PRESSURE VESSELS | KNM PROCESS SYSTEMS SND BHD | 018V0033 | K1808007-E-D-02-004 | 018-C-GAD-40420-001 | MANHOLE DETAIL DRAWING FOR CATALYST INVENTORY HOLDING BIN 018V0033 | A1109 | AX | 2 | 2019-05-14 | CON-BMP-VTRA-011565 | 2019-05-14 | FOR BAPCO REVIEW | 2019-05-29 | 2019-05-30 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000852 | CLASS 2
076551C-000R-MR-0811-004 | MATERIAL REQUISITION FOR LARGE CARBON STEEL PRESSURE VESSELS | KNM PROCESS SYSTEMS SND BHD | 018V0033 | K1808007-E-D-02-006 | 018-C-DLB-40046-001 | TEMPLATE DRAWING FOR CATALYST INVENTORY HOLDING BIN 018V0033 | A2010 | 0X | 2 | 2019-05-28 | CON-BMP-VTRA-011818 | 2019-05-29 | FOR BAPCO REVIEW | 2019-06-12 | 2019-06-17 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000951 | CLASS 2
076551C-000R-MR-0811-004 | MATERIAL REQUISITION FOR LARGE CARBON STEEL PRESSURE VESSELS | KNM PROCESS SYSTEMS SND BHD | 018V0033 | K1808007-E-D-02-012 | 018-C-DLB-40053-001 | NAMEPLATE DETAIL DRAWING FOR CATALYST INVENTORY HOLDING BIN 018V0033 | A1112 | AXX | 2 | 2019-07-09 | CON-BMP-VTRA-012763 | 2019-07-09 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-004 | MATERIAL REQUISITION FOR LARGE CARBON STEEL PRESSURE VESSELS | KNM PROCESS SYSTEMS SND BHD | 018V0033 | K1808007-Q-P-003B | 018-C-MCD-40062-001 | WPS & PWR AND WELD MAP FOR CARBON STEEL WITH PWHT 018V0033 | B1304 | BX | 2 | 2019-06-29 | CON-BMP-VTRA-012564 | 2019-06-29 | FOR BAPCO REVIEW | 2019-07-15 |  |  | CLASS 2
076551C-000R-MR-0811-004 | MATERIAL REQUISITION FOR LARGE CARBON STEEL PRESSURE VESSELS | KNM PROCESS SYSTEMS SND BHD | 018V0034 | K1808007-E-C-03-001 | 018-C-CAL-40079-001 | MECHANICAL DESIGN CALCULATION FOR FRESH CATALYST INVENTORY HOLDING BIN 018V0034 | A1003 | AX | 2 | 2019-04-12 | CON-BMP-VTRA-011149 | 2019-04-12 | FOR BAPCO REVIEW | 2019-04-29 | 2019-05-09 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000653 | CLASS 2
076551C-000R-MR-0811-004 | MATERIAL REQUISITION FOR LARGE CARBON STEEL PRESSURE VESSELS | KNM PROCESS SYSTEMS SND BHD | 018V0034 | K1808007-E-D-03-001 | 018-C-GAD-40391-001 | GENERAL ARRANGEMENT CATALYST INVENTORY HOLDING BIN 018V0034 | A1103 | AXX | 2 | 2019-05-24 | CON-BMP-VTRA-011803 | 2019-05-24 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-004 | MATERIAL REQUISITION FOR LARGE CARBON STEEL PRESSURE VESSELS | KNM PROCESS SYSTEMS SND BHD | 018V0034 | K1808007-E-D-03-002 | 018-C-GAD-40401-001 | BODY SUPPORT & ACCESSORIES DETAIL DRAWING FOR CATALYST INVENTORY HOLDING BIN 018V0034 | A1109 | AX | 2 | 2019-05-03 | CON-BMP-VTRA-011366 | 2019-05-03 | FOR BAPCO REVIEW | 2019-05-17 | 2019-05-26 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000792 | CLASS 2
076551C-000R-MR-0811-004 | MATERIAL REQUISITION FOR LARGE CARBON STEEL PRESSURE VESSELS | KNM PROCESS SYSTEMS SND BHD | 018V0034 | K1808007-E-D-03-003 | 018-C-GAD-40411-001 | NOZZLE DETAIL DRAWING FOR CATALYST INVENTORY HOLDING BIN 018V0034 | A1109 | AX | 2 | 2019-05-14 | CON-BMP-VTRA-011565 | 2019-05-14 | FOR BAPCO REVIEW | 2019-05-29 | 2019-05-30 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000852 | CLASS 2
076551C-000R-MR-0811-004 | MATERIAL REQUISITION FOR LARGE CARBON STEEL PRESSURE VESSELS | KNM PROCESS SYSTEMS SND BHD | 018V0034 | K1808007-E-D-03-004 | 018-C-GAD-40421-001 | MANHOLE DETAIL DRAWING FOR CATALYST INVENTORY HOLDING BIN 018V0034 | A1109 | AX | 2 | 2019-05-14 | CON-BMP-VTRA-011565 | 2019-05-14 | FOR BAPCO REVIEW | 2019-05-29 | 2019-05-30 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000852 | CLASS 2
076551C-000R-MR-0811-004 | MATERIAL REQUISITION FOR LARGE CARBON STEEL PRESSURE VESSELS | KNM PROCESS SYSTEMS SND BHD | 018V0034 | K1808007-E-D-03-006 | 018-C-DLB-40047-001 | TEMPLATE DRAWING FOR CATALYST INVENTORY HOLDING BIN 018V0034 | A2010 | 0X | 2 | 2019-05-28 | CON-BMP-VTRA-011818 | 2019-05-29 | FOR BAPCO REVIEW | 2019-06-12 | 2019-06-17 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000951 | CLASS 2
076551C-000R-MR-0811-004 | MATERIAL REQUISITION FOR LARGE CARBON STEEL PRESSURE VESSELS | KNM PROCESS SYSTEMS SND BHD | 018V0034 | K1808007-E-D-03-012 | 018-C-DLB-40054-001 | NAMEPLATE DETAIL DRAWING FOR CATALYST INVENTORY HOLDING BIN 018V0034 | A1112 | AXX | 2 | 2019-07-09 | CON-BMP-VTRA-012763 | 2019-07-09 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-004 | MATERIAL REQUISITION FOR LARGE CARBON STEEL PRESSURE VESSELS | KNM PROCESS SYSTEMS SND BHD | 018V0034 | K1808007-Q-P-002C | 018-C-PQP-40037-001 | FABRICATION AND QUALITY CONTROL PLAN 018V0034 | B1002 | AXX | 2 | 2019-05-14 | CON-BMP-VTRA-011564 | 2019-05-14 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-004 | MATERIAL REQUISITION FOR LARGE CARBON STEEL PRESSURE VESSELS | KNM PROCESS SYSTEMS SND BHD | 018V0034 | K1808007-Q-P-003C | 018-C-MCD-40063-001 | WPS & PWR AND WELD MAP FOR CARBON STEEL WITH PWHT 018V0034 | B1304 | BX | 2 | 2019-06-29 | CON-BMP-VTRA-012564 | 2019-06-29 | FOR BAPCO REVIEW | 2019-07-15 |  |  | CLASS 2
076551C-000R-MR-0811-004 | MATERIAL REQUISITION FOR LARGE CARBON STEEL PRESSURE VESSELS | KNM PROCESS SYSTEMS SND BHD | 018V0035 | K1808007-E-C-04-001 | 018-C-CAL-40080-001 | MECHANICAL DESIGN CALCULATION FOR FRESH CATALYST INVENTORY HOLDING BIN 018V0035 | A1003 | AX | 2 | 2019-04-12 | CON-BMP-VTRA-011149 | 2019-04-12 | FOR BAPCO REVIEW | 2019-04-29 | 2019-05-09 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000653 | CLASS 2
076551C-000R-MR-0811-004 | MATERIAL REQUISITION FOR LARGE CARBON STEEL PRESSURE VESSELS | KNM PROCESS SYSTEMS SND BHD | 018V0035 | K1808007-E-D-04-001 | 018-C-GAD-40392-001 | GENERAL ARRANGEMENT CATALYST INVENTORY HOLDING BIN 018V0035 | A1103 | AXX | 2 | 2019-05-24 | CON-BMP-VTRA-011803 | 2019-05-24 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-004 | MATERIAL REQUISITION FOR LARGE CARBON STEEL PRESSURE VESSELS | KNM PROCESS SYSTEMS SND BHD | 018V0035 | K1808007-E-D-04-002 | 018-C-GAD-40402-001 | BODY SUPPORT & ACCESSORIES DETAIL DRAWING FOR CATALYST INVENTORY HOLDING BIN 018V0035 | A1109 | AX | 2 | 2019-05-03 | CON-BMP-VTRA-011366 | 2019-05-03 | FOR BAPCO REVIEW | 2019-05-17 | 2019-05-26 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000792 | CLASS 2
076551C-000R-MR-0811-004 | MATERIAL REQUISITION FOR LARGE CARBON STEEL PRESSURE VESSELS | KNM PROCESS SYSTEMS SND BHD | 018V0035 | K1808007-E-D-04-003 | 018-C-GAD-40412-001 | NOZZLE DETAIL DRAWING FOR CATALYST INVENTORY HOLDING BIN 018V0035 | A1109 | AX | 2 | 2019-05-14 | CON-BMP-VTRA-011565 | 2019-05-14 | FOR BAPCO REVIEW | 2019-05-29 | 2019-05-30 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000852 | CLASS 2
076551C-000R-MR-0811-004 | MATERIAL REQUISITION FOR LARGE CARBON STEEL PRESSURE VESSELS | KNM PROCESS SYSTEMS SND BHD | 018V0035 | K1808007-E-D-04-004 | 018-C-GAD-40422-001 | MANHOLE DETAIL DRAWING FOR CATALYST INVENTORY HOLDING BIN 018V0035 | A1109 | AX | 2 | 2019-05-14 | CON-BMP-VTRA-011565 | 2019-05-14 | FOR BAPCO REVIEW | 2019-05-29 | 2019-05-30 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000852 | CLASS 2
076551C-000R-MR-0811-004 | MATERIAL REQUISITION FOR LARGE CARBON STEEL PRESSURE VESSELS | KNM PROCESS SYSTEMS SND BHD | 018V0035 | K1808007-E-D-04-006 | 018-C-DLB-40048-001 | TEMPLATE DRAWING FOR CATALYST INVENTORY HOLDING BIN 018V0035 | A2010 | 0X | 2 | 2019-05-28 | CON-BMP-VTRA-011818 | 2019-05-29 | FOR BAPCO REVIEW | 2019-06-12 | 2019-06-17 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000951 | CLASS 2
076551C-000R-MR-0811-004 | MATERIAL REQUISITION FOR LARGE CARBON STEEL PRESSURE VESSELS | KNM PROCESS SYSTEMS SND BHD | 018V0035 | K1808007-E-D-04-012 | 018-C-DLB-40055-001 | NAMEPLATE DETAIL DRAWING FOR CATALYST INVENTORY HOLDING BIN 018V0035 | A1112 | AX | 2 | 2019-04-26 | CON-BMP-VTRA-011254 | 2019-04-26 | FOR BAPCO REVIEW | 2019-05-10 | 2019-05-15 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000689 | CLASS 2
076551C-000R-MR-0811-004 | MATERIAL REQUISITION FOR LARGE CARBON STEEL PRESSURE VESSELS | KNM PROCESS SYSTEMS SND BHD | 018V0035 | K1808007-Q-P-002D | 018-C-PQP-40038-001 | FABRICATION AND QUALITY CONTROL PLAN 018V0035 | B1002 | AXX | 2 | 2019-05-14 | CON-BMP-VTRA-011564 | 2019-05-14 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-004 | MATERIAL REQUISITION FOR LARGE CARBON STEEL PRESSURE VESSELS | KNM PROCESS SYSTEMS SND BHD | 018V0035 | K1808007-Q-P-003D | 018-C-MCD-40064-001 | WPS & PQR AND WELD MAP FOR CARBON STEEL WITH PWHT 018V0035 | B1304 | BX | 2 | 2019-06-29 | CON-BMP-VTRA-012564 | 2019-06-29 | FOR BAPCO REVIEW | 2019-07-15 |  |  | CLASS 2
076551C-000R-MR-0811-004 | MATERIAL REQUISITION FOR LARGE CARBON STEEL PRESSURE VESSELS | KNM PROCESS SYSTEMS SND BHD | 018V0036 | K1808007-E-C-05-001 | 018-C-CAL-40081-001 | MECHANICAL DESIGN CALCULATION FOR FRESH CATALYST INVENTORY HOLDING BIN 018V0036 | A1003 | AX | 2 | 2019-04-12 | CON-BMP-VTRA-011149 | 2019-04-12 | FOR BAPCO REVIEW | 2019-04-29 | 2019-05-09 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000653 | CLASS 2
076551C-000R-MR-0811-004 | MATERIAL REQUISITION FOR LARGE CARBON STEEL PRESSURE VESSELS | KNM PROCESS SYSTEMS SND BHD | 018V0036 | K1808007-E-D-05-001 | 018-C-GAD-40393-001 | GENERAL ARRANGEMENT CATALYST INVENTORY HOLDING BIN 018V0036 | A1103 | AXX | 2 | 2019-05-24 | CON-BMP-VTRA-011803 | 2019-05-24 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-004 | MATERIAL REQUISITION FOR LARGE CARBON STEEL PRESSURE VESSELS | KNM PROCESS SYSTEMS SND BHD | 018V0036 | K1808007-E-D-05-002 | 018-C-GAD-40403-001 | BODY SUPPORT & ACCESSORIES DETAIL DRAWING FOR CATALYST INVENTORY HOLDING BIN 018V0036 | A1109 | AX | 2 | 2019-05-03 | CON-BMP-VTRA-011366 | 2019-05-03 | FOR BAPCO REVIEW | 2019-05-17 | 2019-05-26 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000792 | CLASS 2
076551C-000R-MR-0811-004 | MATERIAL REQUISITION FOR LARGE CARBON STEEL PRESSURE VESSELS | KNM PROCESS SYSTEMS SND BHD | 018V0036 | K1808007-E-D-05-003 | 018-C-GAD-40413-001 | NOZZLE DETAIL DRAWING FOR CATALYST INVENTORY HOLDING BIN 018V0036 | A1109 | AX | 2 | 2019-05-14 | CON-BMP-VTRA-011565 | 2019-05-14 | FOR BAPCO REVIEW | 2019-05-29 | 2019-05-30 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000852 | CLASS 2
076551C-000R-MR-0811-004 | MATERIAL REQUISITION FOR LARGE CARBON STEEL PRESSURE VESSELS | KNM PROCESS SYSTEMS SND BHD | 018V0036 | K1808007-E-D-05-004 | 018-C-GAD-40423-001 | MANHOLE DETAIL DRAWING FOR CATALYST INVENTORY HOLDING BIN 018V0036 | A1109 | AX | 2 | 2019-05-14 | CON-BMP-VTRA-011565 | 2019-05-14 | FOR BAPCO REVIEW | 2019-05-29 | 2019-05-30 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000852 | CLASS 2
076551C-000R-MR-0811-004 | MATERIAL REQUISITION FOR LARGE CARBON STEEL PRESSURE VESSELS | KNM PROCESS SYSTEMS SND BHD | 018V0036 | K1808007-E-D-05-006 | 018-C-DLB-40049-001 | TEMPLATE DRAWING FOR CATALYST INVENTORY HOLDING BIN 018V0036 | A2010 | 0X | 2 | 2019-05-28 | CON-BMP-VTRA-011818 | 2019-05-29 | FOR BAPCO REVIEW | 2019-06-12 | 2019-06-17 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000951 | CLASS 2
076551C-000R-MR-0811-004 | MATERIAL REQUISITION FOR LARGE CARBON STEEL PRESSURE VESSELS | KNM PROCESS SYSTEMS SND BHD | 018V0036 | K1808007-E-D-05-012 | 018-C-DLB-40056-001 | NAMEPLATE DETAIL DRAWING FOR CATALYST INVENTORY HOLDING BIN 018V0036 | A1112 | AXX | 2 | 2019-07-09 | CON-BMP-VTRA-012763 | 2019-07-09 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-004 | MATERIAL REQUISITION FOR LARGE CARBON STEEL PRESSURE VESSELS | KNM PROCESS SYSTEMS SND BHD | 018V0036 | K1808007-Q-P-002E | 018-C-PQP-40039-001 | FABRICATION AND QUALITY CONTROL PLAN 018V0036 | B1002 | AXX | 2 | 2019-05-14 | CON-BMP-VTRA-011564 | 2019-05-14 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-004 | MATERIAL REQUISITION FOR LARGE CARBON STEEL PRESSURE VESSELS | KNM PROCESS SYSTEMS SND BHD | 018V0036 | K1808007-Q-P-003E | 018-C-MCD-40065-001 | WPS & PWR AND WELD MAP FOR CARBON STEEL WITH PWHT 018V0036 | B1304 | BX | 2 | 2019-06-29 | CON-BMP-VTRA-012564 | 2019-06-29 | FOR BAPCO REVIEW | 2019-07-15 |  |  | CLASS 2
076551C-000R-MR-0811-004 | MATERIAL REQUISITION FOR LARGE CARBON STEEL PRESSURE VESSELS | KNM PROCESS SYSTEMS SND BHD | 018V0060 | K1808007-E-C-13-001 | 018-C-CAL-40085-001 | MECHANICAL DESIGN CALCULATION FOR FLARE KO DRUM 018V0060 | A1003 | AXX | 2 | 2019-05-29 | CON-BMP-VTRA-011832 | 2019-05-29 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-004 | MATERIAL REQUISITION FOR LARGE CARBON STEEL PRESSURE VESSELS | KNM PROCESS SYSTEMS SND BHD | 018V0060 | K1808007-E-D-13-001 | 018-C-GAD-40397-001 | GENERAL ARRANGEMENT FOR FLARE KO DRUM 018V0060 | A1103 | AX | 2 | 2019-05-03 | CON-BMP-VTRA-011391 | 2019-05-03 | FOR BAPCO REVIEW | 2019-05-20 | 2019-05-26 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000776 | CLASS 2
076551C-000R-MR-0811-004 | MATERIAL REQUISITION FOR LARGE CARBON STEEL PRESSURE VESSELS | KNM PROCESS SYSTEMS SND BHD | 018V0060 | K1808007-E-D-13-002 | 018-C-GAD-40407-001 | BODY SUPPORT & ACCESSORIES DETAIL DRAWING FLARE KO DRUM 018V0060 | A1109 | AX | 2 | 2019-05-03 | CON-BMP-VTRA-011366 | 2019-05-03 | FOR BAPCO REVIEW | 2019-05-17 | 2019-05-26 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000792 | CLASS 2
076551C-000R-MR-0811-004 | MATERIAL REQUISITION FOR LARGE CARBON STEEL PRESSURE VESSELS | KNM PROCESS SYSTEMS SND BHD | 018V0060 | K1808007-E-D-13-003 | 018-C-GAD-40417-001 | NOZZLE DETAIL FOR FLARE KO DRUM 018V0060 | A1109 | AX | 2 | 2019-05-03 | CON-BMP-VTRA-011366 | 2019-05-03 | FOR BAPCO REVIEW | 2019-05-17 | 2019-05-26 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000792 | CLASS 2
076551C-000R-MR-0811-004 | MATERIAL REQUISITION FOR LARGE CARBON STEEL PRESSURE VESSELS | KNM PROCESS SYSTEMS SND BHD | 018V0060 | K1808007-E-D-13-004 | 018-C-GAD-40427-001 | MANHOLE DETAIL DRAWING FIR FLARE K.O. DRUM 018V0060 | A1109 | AX | 2 | 2019-05-03 | CON-BMP-VTRA-011366 | 2019-05-03 | FOR BAPCO REVIEW | 2019-05-17 | 2019-05-26 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000792 | CLASS 2
076551C-000R-MR-0811-004 | MATERIAL REQUISITION FOR LARGE CARBON STEEL PRESSURE VESSELS | KNM PROCESS SYSTEMS SND BHD | 018V0060 | K1808007-E-D-13-010 | 018-C-DLB-40060-001 | NAMEPLATE DETAIL DRAWING FOR FLARE KO DRUM 018V0060 | A1112 | AX | 2 | 2019-04-26 | CON-BMP-VTRA-011289 | 2019-04-26 | FOR BAPCO REVIEW | 2019-05-14 | 2019-05-23 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000743 | CLASS 2
076551C-000R-MR-0811-004 | MATERIAL REQUISITION FOR LARGE CARBON STEEL PRESSURE VESSELS | KNM PROCESS SYSTEMS SND BHD | 018V0060 | K1808007-Q-P-002M | 018-C-PQP-40043-001 | FABRICATION AND QUALITY CONTROL PLAN 018V0060 | B1002 | AX | 2 | 2019-04-16 | CON-BMP-VTRA-011205 | 2019-04-16 | FOR BAPCO REVIEW | 2019-05-02 | 2019-04-28 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000611 | CLASS 2
076551C-000R-MR-0811-004 | MATERIAL REQUISITION FOR LARGE CARBON STEEL PRESSURE VESSELS | KNM PROCESS SYSTEMS SND BHD | 018V0060 | K1808007-Q-P-003M | 018-C-MCD-40069-001 | WPS & PQR AND WELD MAP FOR CARBON STEEL WITH PWHT 018V0060 | B1304 | BX | 2 | 2019-06-29 | CON-BMP-VTRA-012564 | 2019-06-29 | FOR BAPCO REVIEW | 2019-07-15 |  |  | CLASS 2
076551C-000R-MR-0811-004 | MATERIAL REQUISITION FOR LARGE CARBON STEEL PRESSURE VESSELS | KNM PROCESS SYSTEMS SND BHD | 018V1008 | K1808007-E-C-06-001 | 018-C-CAL-40082-001 | MECHANICAL DESIGN CALCULATION FOR TRAIN 1 MEMBRANE KO DRUM 018V1008 | A1003 | AX | 2 | 2019-04-19 | CON-BMP-VTRA-011234 | 2019-04-19 | FOR BAPCO REVIEW | 2019-05-07 | 2019-05-18 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000698 | CLASS 2
076551C-000R-MR-0811-004 | MATERIAL REQUISITION FOR LARGE CARBON STEEL PRESSURE VESSELS | KNM PROCESS SYSTEMS SND BHD | 018V1008 | K1808007-E-D-06-001 | 018-C-GAD-40394-001 | GENERAL ARRANGEMENT FOR TRAIN 1 MEMBRANE KO DRUM 018V1008 | A1103 | AX | 2 | 2019-05-03 | CON-BMP-VTRA-011391 | 2019-05-03 | FOR BAPCO REVIEW | 2019-05-20 | 2019-05-26 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000776 | CLASS 2
076551C-000R-MR-0811-004 | MATERIAL REQUISITION FOR LARGE CARBON STEEL PRESSURE VESSELS | KNM PROCESS SYSTEMS SND BHD | 018V1008 | K1808007-E-D-06-002 | 018-C-GAD-40404-001 | BODY SKIRT & ACCESSORIES DETAIL DRAWING FOR TRAIN 1 MEMBRANE KO DRUM 018V1008 | A1109 | AX | 2 | 2019-05-03 | CON-BMP-VTRA-011366 | 2019-05-03 | FOR BAPCO REVIEW | 2019-05-17 | 2019-05-26 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000792 | CLASS 2
076551C-000R-MR-0811-004 | MATERIAL REQUISITION FOR LARGE CARBON STEEL PRESSURE VESSELS | KNM PROCESS SYSTEMS SND BHD | 018V1008 | K1808007-E-D-06-003 | 018-C-GAD-40414-001 | NOZZLE DETAIL DRAWING FOR TRAIN 1 MEMBRANE KO DRUM 018V1008 | A1109 | AX | 2 | 2019-05-03 | CON-BMP-VTRA-011366 | 2019-05-03 | FOR BAPCO REVIEW | 2019-05-17 | 2019-05-26 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000792 | CLASS 2
076551C-000R-MR-0811-004 | MATERIAL REQUISITION FOR LARGE CARBON STEEL PRESSURE VESSELS | KNM PROCESS SYSTEMS SND BHD | 018V1008 | K1808007-E-D-06-004 | 018-C-GAD-40424-001 | MANHOLE DETAIL DRAWING FOR MEMBRANE KO DRUM 018V1008 | A1109 | AX | 2 | 2019-05-03 | CON-BMP-VTRA-011366 | 2019-05-03 | FOR BAPCO REVIEW | 2019-05-17 | 2019-05-26 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000792 | CLASS 2
076551C-000R-MR-0811-004 | MATERIAL REQUISITION FOR LARGE CARBON STEEL PRESSURE VESSELS | KNM PROCESS SYSTEMS SND BHD | 018V1008 | K1808007-E-D-06-008 | 018-C-DLB-40050-001 | TEMPLATE ARRANGEMENT FOR TRAIN 1 MEMBRANE KO DRUM 018V1008 | A2010 | 0X | 2 | 2019-05-28 | CON-BMP-VTRA-011818 | 2019-05-29 | FOR BAPCO REVIEW | 2019-06-12 | 2019-06-17 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000951 | CLASS 2
076551C-000R-MR-0811-004 | MATERIAL REQUISITION FOR LARGE CARBON STEEL PRESSURE VESSELS | KNM PROCESS SYSTEMS SND BHD | 018V1008 | K1808007-E-D-06-014 | 018-C-DLB-40057-001 | NAMEPLATE DETAIL DRAWING FOR TRAIN 1 MEMBRANE K.O. DRUM 018V1008 | A1112 | AX | 2 | 2019-04-26 | CON-BMP-VTRA-011289 | 2019-04-26 | FOR BAPCO REVIEW | 2019-05-14 | 2019-05-23 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000743 | CLASS 2
076551C-000R-MR-0811-004 | MATERIAL REQUISITION FOR LARGE CARBON STEEL PRESSURE VESSELS | KNM PROCESS SYSTEMS SND BHD | 018V1008 | K1808007-Q-P-002F | 018-C-PQP-40040-001 | FABRICATION AND QUALITY CONTROL PLAN 018V1008 | B1002 | AXX | 2 | 2019-05-21 | CON-BMP-VTRA-011708 | 2019-05-21 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-004 | MATERIAL REQUISITION FOR LARGE CARBON STEEL PRESSURE VESSELS | KNM PROCESS SYSTEMS SND BHD | 018V1008 | K1808007-Q-P-003F | 018-C-MCD-40066-001 | WPS & PWR AND WELD MAP FOR CARBON STEEL WITH PWHT 018V1008 | B1304 | BX | 2 | 2019-06-29 | CON-BMP-VTRA-012564 | 2019-06-29 | FOR BAPCO REVIEW | 2019-07-15 |  |  | CLASS 2
076551C-000R-MR-0811-004 | MATERIAL REQUISITION FOR LARGE CARBON STEEL PRESSURE VESSELS | KNM PROCESS SYSTEMS SND BHD | 018V2008 | K1808007-E-C-07-001 | 018-C-CAL-40083-001 | MECHANICAL DESIGN CALCULATION FOR TRAIN 2 MEMBRANE KO DRUM 018V2008 | A1003 | AXX | 2 | 2019-06-22 | CON-BMP-VTRA-012378 | 2019-06-22 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-004 | MATERIAL REQUISITION FOR LARGE CARBON STEEL PRESSURE VESSELS | KNM PROCESS SYSTEMS SND BHD | 018V2008 | K1808007-E-D-07-001 | 018-C-GAD-40395-001 | GENERAL ARRANGEMENT FOR TRAIN 2 MEMBRANE KO DRUM 018V2008 | A1103 | AX | 2 | 2019-05-03 | CON-BMP-VTRA-011391 | 2019-05-03 | FOR BAPCO REVIEW | 2019-05-20 | 2019-05-26 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000776 | CLASS 2
076551C-000R-MR-0811-004 | MATERIAL REQUISITION FOR LARGE CARBON STEEL PRESSURE VESSELS | KNM PROCESS SYSTEMS SND BHD | 018V2008 | K1808007-E-D-07-002 | 018-C-GAD-40405-001 | BODY, SKIRT & ACCESSORIES DETAIL DRAWING FOR TRAIN 2 MEMBRANE KO DRUM 018V2008 | A1109 | AX | 2 | 2019-05-03 | CON-BMP-VTRA-011366 | 2019-05-03 | FOR BAPCO REVIEW | 2019-05-17 | 2019-05-26 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000792 | CLASS 2
076551C-000R-MR-0811-004 | MATERIAL REQUISITION FOR LARGE CARBON STEEL PRESSURE VESSELS | KNM PROCESS SYSTEMS SND BHD | 018V2008 | K1808007-E-D-07-003 | 018-C-GAD-40415-001 | NOZZLE DETAIL FOR TRAIN 2 MEMBRANE KO DRUM 018V2008 | A1109 | AX | 2 | 2019-05-03 | CON-BMP-VTRA-011366 | 2019-05-03 | FOR BAPCO REVIEW | 2019-05-17 | 2019-05-26 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000792 | CLASS 2
076551C-000R-MR-0811-004 | MATERIAL REQUISITION FOR LARGE CARBON STEEL PRESSURE VESSELS | KNM PROCESS SYSTEMS SND BHD | 018V2008 | K1808007-E-D-07-004 | 018-C-GAD-40425-001 | MANHOLE DETAIL DRAWING FOR MEMBRANE KO DRUM 018V2008 | A1109 | AX | 2 | 2019-05-03 | CON-BMP-VTRA-011366 | 2019-05-03 | FOR BAPCO REVIEW | 2019-05-17 | 2019-05-26 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000792 | CLASS 2
076551C-000R-MR-0811-004 | MATERIAL REQUISITION FOR LARGE CARBON STEEL PRESSURE VESSELS | KNM PROCESS SYSTEMS SND BHD | 018V2008 | K1808007-E-D-07-008 | 018-C-DLB-40051-001 | TEMPLATE ARRANGEMENT FOR TRAIN 2 MEMBRANE KO DRUM 018V2008 | A2010 | 0X | 2 | 2019-05-28 | CON-BMP-VTRA-011818 | 2019-05-29 | FOR BAPCO REVIEW | 2019-06-12 | 2019-06-17 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000951 | CLASS 2
076551C-000R-MR-0811-004 | MATERIAL REQUISITION FOR LARGE CARBON STEEL PRESSURE VESSELS | KNM PROCESS SYSTEMS SND BHD | 018V2008 | K1808007-E-D-07-014 | 018-C-DLB-40058-001 | NAMEPLATE DETAIL DRAWING FOR TRAIN 2 MEMBRANE K.O. DRUM 018V2008 | A1112 | AX | 2 | 2019-04-26 | CON-BMP-VTRA-011289 | 2019-04-26 | FOR BAPCO REVIEW | 2019-05-14 | 2019-05-23 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000743 | CLASS 2
076551C-000R-MR-0811-004 | MATERIAL REQUISITION FOR LARGE CARBON STEEL PRESSURE VESSELS | KNM PROCESS SYSTEMS SND BHD | 018V2008 | K1808007-Q-P-002G | 018-C-PQP-40041-001 | FABRICATION AND QUALITY CONTROL PLAN 018V2008 | B1002 | AX | 2 | 2019-04-16 | CON-BMP-VTRA-011205 | 2019-04-16 | FOR BAPCO REVIEW | 2019-05-02 | 2019-04-28 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000611 | CLASS 2
076551C-000R-MR-0811-004 | MATERIAL REQUISITION FOR LARGE CARBON STEEL PRESSURE VESSELS | KNM PROCESS SYSTEMS SND BHD | 018V2008 | K1808007-Q-P-003G | 018-C-MCD-40067-001 | WPS & PWR AND WELD MAP FOR CARBON STEEL WITH PWHT 018V2008 | B1304 | BX | 2 | 2019-06-29 | CON-BMP-VTRA-012564 | 2019-06-29 | FOR BAPCO REVIEW | 2019-07-15 |  |  | CLASS 2
076551C-000R-MR-0811-004 | MATERIAL REQUISITION FOR LARGE CARBON STEEL PRESSURE VESSELS | KNM PROCESS SYSTEMS SND BHD | 021V0002 | K1808007-E-C-08-001 | 021-C-CAL-40016-001 | MECHANICAL DESIGN CALCULATION FOR FEED SURGE DRUM 021V0002 | A1003 | AX | 2 | 2019-04-19 | CON-BMP-VTRA-011234 | 2019-04-19 | FOR BAPCO REVIEW | 2019-05-07 | 2019-05-18 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000698 | CLASS 2
076551C-000R-MR-0811-004 | MATERIAL REQUISITION FOR LARGE CARBON STEEL PRESSURE VESSELS | KNM PROCESS SYSTEMS SND BHD | 021V0002 | K1808007-E-D-08-001 | 021-C-GAD-40086-001 | GENERAL ARRANGEMENT FOR FEED SURGE DRUM 021V0002 | A1103 | AX | 2 | 2019-05-14 | CON-BMP-VTRA-011545 | 2019-05-14 | FOR BAPCO REVIEW | 2019-05-28 | 2019-05-28 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000819 | CLASS 2
076551C-000R-MR-0811-004 | MATERIAL REQUISITION FOR LARGE CARBON STEEL PRESSURE VESSELS | KNM PROCESS SYSTEMS SND BHD | 021V0002 | K1808007-E-D-08-002 | 021-C-GAD-40088-001 | BODY SUPPORT & ACCESSORIES DETAIL DRAWING FOR FEED SURGE DRUM 021V0002 | A1109 | AXX | 2 | 2019-07-08 | CON-BMP-VTRA-012711 | 2019-07-08 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-004 | MATERIAL REQUISITION FOR LARGE CARBON STEEL PRESSURE VESSELS | KNM PROCESS SYSTEMS SND BHD | 021V0002 | K1808007-E-D-08-003 | 021-C-GAD-40090-001 | NOZZLE DETAIL DRAWING FOR FEED SURGE DRUM 021V0002 | A1109 | AXX | 2 | 2019-07-08 | CON-BMP-VTRA-012711 | 2019-07-08 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-004 | MATERIAL REQUISITION FOR LARGE CARBON STEEL PRESSURE VESSELS | KNM PROCESS SYSTEMS SND BHD | 021V0002 | K1808007-E-D-08-004 | 021-C-GAD-40092-001 | MANHOLE DETAIL DRAWING FOR FEED SURGE DRUM 021V0002 | A1109 | AXX | 2 | 2019-07-08 | CON-BMP-VTRA-012711 | 2019-07-08 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-004 | MATERIAL REQUISITION FOR LARGE CARBON STEEL PRESSURE VESSELS | KNM PROCESS SYSTEMS SND BHD | 021V0002 | K1808007-E-D-08-006 | 021-C-DLB-40012-001 | TEMPLATE DETAIL DRAWING FOR FEED SURGE DRUM 021V0002 | A2010 | 0X | 2 | 2019-05-28 | CON-BMP-VTRA-011818 | 2019-05-29 | FOR BAPCO REVIEW | 2019-06-12 | 2019-06-17 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000951 | CLASS 2
076551C-000R-MR-0811-004 | MATERIAL REQUISITION FOR LARGE CARBON STEEL PRESSURE VESSELS | KNM PROCESS SYSTEMS SND BHD | 021V0002 | K1808007-E-D-08-012 | 021-C-DLB-40013-001 | NAMEPLATE DETAIL DRAWING FOR FEED SURGE DRUM 021V0002 | A1112 | AX | 2 | 2019-04-26 | CON-BMP-VTRA-011289 | 2019-04-26 | FOR BAPCO REVIEW | 2019-05-14 | 2019-05-23 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000743 | CLASS 2
076551C-000R-MR-0811-004 | MATERIAL REQUISITION FOR LARGE CARBON STEEL PRESSURE VESSELS | KNM PROCESS SYSTEMS SND BHD | 021V0002 | K1808007-Q-P-002H | 021-C-PQP-40011-001 | FABRICATION AND QUALITY CONTROL PLAN 021V0002 | B1002 | AX | 2 | 2019-04-16 | CON-BMP-VTRA-011205 | 2019-04-16 | FOR BAPCO REVIEW | 2019-05-02 | 2019-04-28 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000611 | CLASS 2
076551C-000R-MR-0811-004 | MATERIAL REQUISITION FOR LARGE CARBON STEEL PRESSURE VESSELS | KNM PROCESS SYSTEMS SND BHD | 021V0002 | K1808007-Q-P-003H | 021-C-MCD-40013-001 | WPS & PWR AND WELD MAP FOR CARBON STEEL WITH PWHT 021V0002 | B1304 | BX | 2 | 2019-06-29 | CON-BMP-VTRA-012567 | 2019-06-29 | FOR BAPCO REVIEW | 2019-07-15 |  |  | CLASS 2
076551C-000R-MR-0811-004 | MATERIAL REQUISITION FOR LARGE CARBON STEEL PRESSURE VESSELS | KNM PROCESS SYSTEMS SND BHD | 021V0023 | K1808007-E-C-14-001 | 021-C-CAL-40017-001 | MECHANICAL DESIGN CALCULATION FOR FLARE KO DRUM 021V0023 | A1003 | AX | 2 | 2019-05-03 | CON-BMP-VTRA-011367 | 2019-05-03 | FOR BAPCO REVIEW | 2019-05-17 | 2019-05-21 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000716 | CLASS 2
076551C-000R-MR-0811-004 | MATERIAL REQUISITION FOR LARGE CARBON STEEL PRESSURE VESSELS | KNM PROCESS SYSTEMS SND BHD | 021V0023 | K1808007-E-D-14-001 | 021-C-GAD-40087-001 | GENERAL ARRANGEMENT FOR FLARE KO DRUM 021V0023 | A1103 | AX | 2 | 2019-05-03 | CON-BMP-VTRA-011391 | 2019-05-03 | FOR BAPCO REVIEW | 2019-05-20 | 2019-05-26 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000776 | CLASS 2
076551C-000R-MR-0811-004 | MATERIAL REQUISITION FOR LARGE CARBON STEEL PRESSURE VESSELS | KNM PROCESS SYSTEMS SND BHD | 021V0023 | K1808007-E-D-14-002 | 021-C-GAD-40089-001 | BODY SADDLE & ACCESSORIES DETAIL FOR FLARE KO DRUM 021V0023 | A1109 | AX | 2 | 2019-05-14 | CON-BMP-VTRA-011565 | 2019-05-14 | FOR BAPCO REVIEW | 2019-05-29 | 2019-05-30 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000852 | CLASS 2
076551C-000R-MR-0811-004 | MATERIAL REQUISITION FOR LARGE CARBON STEEL PRESSURE VESSELS | KNM PROCESS SYSTEMS SND BHD | 021V0023 | K1808007-E-D-14-003 | 021-C-GAD-40091-001 | NOZZLE DETAIL DRAWING FOR FLARE KO DRUM 021V0023 | A1109 | AX | 2 | 2019-05-14 | CON-BMP-VTRA-011565 | 2019-05-14 | FOR BAPCO REVIEW | 2019-05-29 | 2019-05-30 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000852 | CLASS 2
076551C-000R-MR-0811-004 | MATERIAL REQUISITION FOR LARGE CARBON STEEL PRESSURE VESSELS | KNM PROCESS SYSTEMS SND BHD | 021V0023 | K1808007-E-D-14-004 | 021-C-GAD-40093-001 | MANHOLE DETAIL DRAWING FOR FLARE KO DRUM 021V0023 | A1109 | AX | 2 | 2019-05-14 | CON-BMP-VTRA-011565 | 2019-05-14 | FOR BAPCO REVIEW | 2019-05-29 | 2019-05-30 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000852 | CLASS 2
076551C-000R-MR-0811-004 | MATERIAL REQUISITION FOR LARGE CARBON STEEL PRESSURE VESSELS | KNM PROCESS SYSTEMS SND BHD | 021V0023 | K1808007-E-D-14-009 | 021-C-DLB-40014-001 | NAMEPLATE DETAIL DRAWING FOR FLARE KO DRUM 021V0023 | A1112 | AX | 2 | 2019-04-26 | CON-BMP-VTRA-011289 | 2019-04-26 | FOR BAPCO REVIEW | 2019-05-14 | 2019-05-23 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000743 | CLASS 2
076551C-000R-MR-0811-004 | MATERIAL REQUISITION FOR LARGE CARBON STEEL PRESSURE VESSELS | KNM PROCESS SYSTEMS SND BHD | 021V0023 | K1808007-Q-P-002N | 021-C-PQP-40012-001 | FABRICATION AND QUALITY CONTROL PLAN 021V0023 | B1002 | AX | 2 | 2019-04-16 | CON-BMP-VTRA-011205 | 2019-04-16 | FOR BAPCO REVIEW | 2019-05-02 | 2019-04-28 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000611 | CLASS 2
076551C-000R-MR-0811-004 | MATERIAL REQUISITION FOR LARGE CARBON STEEL PRESSURE VESSELS | KNM PROCESS SYSTEMS SND BHD | 021V0023 | K1808007-Q-P-003N | 021-C-MCD-40014-001 | WPS & PQR AND WELD MAP FOR CARBON STEEL WITH PWHT (021V0023) | B1304 | BX | 2 | 2019-06-29 | CON-BMP-VTRA-012567 | 2019-06-29 | FOR BAPCO REVIEW | 2019-07-15 |  |  | CLASS 2
076551C-000R-MR-0811-004 | MATERIAL REQUISITION FOR LARGE CARBON STEEL PRESSURE VESSELS | KNM PROCESS SYSTEMS SND BHD | 051V0003A | K1808007-E-C-09-001 | 051-C-CAL-40006-001 | MECHANICAL DESIGN CALCULATION FOR PROPANE COMPRESSOR 2ND STAGE SUCTION DRUM 051V0003A/B | A1003 | AX | 2 | 2019-05-03 | CON-BMP-VTRA-011367 | 2019-05-03 | FOR BAPCO REVIEW | 2019-05-17 | 2019-05-21 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000716 | CLASS 2
076551C-000R-MR-0811-004 | MATERIAL REQUISITION FOR LARGE CARBON STEEL PRESSURE VESSELS | KNM PROCESS SYSTEMS SND BHD | 051V0003A | K1808007-E-D-09-001 | 051-C-GAD-40005-001 | GENERAL ARRANGEMENT FOR PROPANE COMPRESSOR 2ND STAGE SUCTION DRUMS 051V0003A/B | A1103 | AX | 2 | 2019-05-03 | CON-BMP-VTRA-011391 | 2019-05-03 | FOR BAPCO REVIEW | 2019-05-20 | 2019-05-26 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000776 | CLASS 2
076551C-000R-MR-0811-004 | MATERIAL REQUISITION FOR LARGE CARBON STEEL PRESSURE VESSELS | KNM PROCESS SYSTEMS SND BHD | 051V0003A | K1808007-E-D-09-002 | 051-C-GAD-40007-001 | BODY,SKIRT & ACCESSORIES DETAIL DRAWING FOR PROPANE COMPRESSOR 2ND STAGE SUCTION DRUMS 051V0003A/B | A1109 | AX | 2 | 2019-05-03 | CON-BMP-VTRA-011366 | 2019-05-03 | FOR BAPCO REVIEW | 2019-05-17 | 2019-05-26 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000792 | CLASS 2
076551C-000R-MR-0811-004 | MATERIAL REQUISITION FOR LARGE CARBON STEEL PRESSURE VESSELS | KNM PROCESS SYSTEMS SND BHD | 051V0003A | K1808007-E-D-09-003 | 051-C-GAD-40009-001 | NOZZLE DETAIL DRAWING FOR PROPANE COMPRESSOR 2ND STAGE SUCTION DRUMS 051V0003A/B | A1109 | AX | 2 | 2019-05-03 | CON-BMP-VTRA-011366 | 2019-05-03 | FOR BAPCO REVIEW | 2019-05-17 | 2019-05-26 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000792 | CLASS 2
076551C-000R-MR-0811-004 | MATERIAL REQUISITION FOR LARGE CARBON STEEL PRESSURE VESSELS | KNM PROCESS SYSTEMS SND BHD | 051V0003A | K1808007-E-D-09-004 | 051-C-GAD-40011-001 | MANHOLE DETAIL DRAWING FOR PROPANE COMPRESSOR 2ND STAGE SUCTION DRUMS 051V0003A/B | A1109 | AX | 2 | 2019-05-14 | CON-BMP-VTRA-011565 | 2019-05-14 | FOR BAPCO REVIEW | 2019-05-29 | 2019-05-30 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000852 | CLASS 2
076551C-000R-MR-0811-004 | MATERIAL REQUISITION FOR LARGE CARBON STEEL PRESSURE VESSELS | KNM PROCESS SYSTEMS SND BHD | 051V0003A | K1808007-E-D-09-007 | 051-C-DLB-40001-001 | TEMPLATE DETAIL DRAWING FOR PROPANE COMPRESSOR 2ND STAGE SUCTION DRUM (TRAIN A/B) 051V0003A/B | A2010 | 0X | 2 | 2019-05-28 | CON-BMP-VTRA-011818 | 2019-05-29 | FOR BAPCO REVIEW | 2019-06-12 | 2019-06-17 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000951 | CLASS 2
076551C-000R-MR-0811-004 | MATERIAL REQUISITION FOR LARGE CARBON STEEL PRESSURE VESSELS | KNM PROCESS SYSTEMS SND BHD | 051V0003A | K1808007-E-D-09-014 | 051-C-DLB-40002-001 | NAMEPLATE DETAIL DRAWING FOR PROPANE COMPRESSOR 2ND STAGE SUCTION DRUM 051V0003A/B | A1112 | AX | 2 | 2019-04-26 | CON-BMP-VTRA-011289 | 2019-04-26 | FOR BAPCO REVIEW | 2019-05-14 | 2019-05-23 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000743 | CLASS 2
076551C-000R-MR-0811-004 | MATERIAL REQUISITION FOR LARGE CARBON STEEL PRESSURE VESSELS | KNM PROCESS SYSTEMS SND BHD | 051V0003A | K1808007-Q-P-002I | 051-C-PQP-40001-001 | FABRICATION ND QUALITY CONTROL PLAN 051V0003A/B | B1002 | AX | 2 | 2019-04-16 | CON-BMP-VTRA-011205 | 2019-04-16 | FOR BAPCO REVIEW | 2019-05-02 | 2019-04-28 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000611 | CLASS 2
076551C-000R-MR-0811-004 | MATERIAL REQUISITION FOR LARGE CARBON STEEL PRESSURE VESSELS | KNM PROCESS SYSTEMS SND BHD | 051V0003A | K1808007-Q-P-003I | 051-C-MCD-40003-001 | WPS & PWR AND WELD MAP FOR CARBON STEEL WITH PWHT 051V0003A/B | B1304 | BX | 2 | 2019-06-29 | CON-BMP-VTRA-012566 | 2019-06-29 | FOR BAPCO REVIEW | 2019-07-15 |  |  | CLASS 2
076551C-000R-MR-0811-004 | MATERIAL REQUISITION FOR LARGE CARBON STEEL PRESSURE VESSELS | KNM PROCESS SYSTEMS SND BHD | 051V0004A | K1808007-E-C-10-001 | 051-A-CAL-40007-001 | MECHANICAL DESIGN CALCULATION 051V0004A/B | A1003 | AXX | 2 | 2019-05-29 | CON-BMP-VTRA-011832 | 2019-05-29 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-004 | MATERIAL REQUISITION FOR LARGE CARBON STEEL PRESSURE VESSELS | KNM PROCESS SYSTEMS SND BHD | 051V0004A | K1808007-E-D-10-001 | 051-C-GAD-40006-001 | GENERAL ARRANGEMENT FOR PROPANE CONDENSER ACCUMULATORS 051V0004A/B | A1103 | AXX | 2 | 2019-05-24 | CON-BMP-VTRA-011803 | 2019-05-24 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-004 | MATERIAL REQUISITION FOR LARGE CARBON STEEL PRESSURE VESSELS | KNM PROCESS SYSTEMS SND BHD | 051V0004A | K1808007-E-D-10-002 | 051-C-GAD-40008-001 | BODY SADDLE & ACCESSORIES DETAIL DRAWING FOR PROPANE CONDENSER ACCUMULATORS 051V0004A/B | A1109 | AX | 2 | 2019-05-06 | CON-BMP-VTRA-011398 | 2019-05-06 | FOR BAPCO REVIEW | 2019-05-20 | 2019-05-21 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000720 | CLASS 2
076551C-000R-MR-0811-004 | MATERIAL REQUISITION FOR LARGE CARBON STEEL PRESSURE VESSELS | KNM PROCESS SYSTEMS SND BHD | 051V0004A | K1808007-E-D-10-003 | 051-C-GAD-40010-001 | NOZZLE DETAIL FOR PROPANE CONDENSER ACCUMULATORS 051V0004A/B | A1109 | AX | 2 | 2019-05-06 | CON-BMP-VTRA-011398 | 2019-05-06 | FOR BAPCO REVIEW | 2019-05-20 | 2019-05-21 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000720 | CLASS 2
076551C-000R-MR-0811-004 | MATERIAL REQUISITION FOR LARGE CARBON STEEL PRESSURE VESSELS | KNM PROCESS SYSTEMS SND BHD | 051V0004A | K1808007-E-D-10-004 | 051-C-GAD-40012-001 | MANHOLE DETAIL DRAWING FOR PROPANE CONDENSER ACCUMULATORS 051V0004A/B | A1109 | AXX | 2 | 2019-07-08 | CON-BMP-VTRA-012712 | 2019-07-08 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-004 | MATERIAL REQUISITION FOR LARGE CARBON STEEL PRESSURE VESSELS | KNM PROCESS SYSTEMS SND BHD | 051V0004A | K1808007-E-D-10-010 | 051-C-DLB-40003-001 | NAMEPLATE DETAIL DRAWING FOR PROPANE CONDENSER ACCUMULATOR 051V0004A/B | A1112 | AX | 2 | 2019-04-26 | CON-BMP-VTRA-011289 | 2019-04-26 | FOR BAPCO REVIEW | 2019-05-14 | 2019-05-23 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000743 | CLASS 2
076551C-000R-MR-0811-004 | MATERIAL REQUISITION FOR LARGE CARBON STEEL PRESSURE VESSELS | KNM PROCESS SYSTEMS SND BHD | 051V0004A | K1808007-Q-P-002J | 051-C-PQP-40002-001 | FABRICATION AND QUALITY CONTROL PLAN 051V0004A/B | B1002 | AX | 2 | 2019-04-16 | CON-BMP-VTRA-011205 | 2019-04-16 | FOR BAPCO REVIEW | 2019-05-02 | 2019-04-28 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000611 | CLASS 2
076551C-000R-MR-0811-004 | MATERIAL REQUISITION FOR LARGE CARBON STEEL PRESSURE VESSELS | KNM PROCESS SYSTEMS SND BHD | 051V0004A | K1808007-Q-P-003J | 051-C-MCD-40004-001 | WPS & PQR AND WELD MAP FOR CARBON STEEL WITH PWHT (051V0004A/B) | B1304 | BX | 2 | 2019-06-29 | CON-BMP-VTRA-012566 | 2019-06-29 | FOR BAPCO REVIEW | 2019-07-15 |  |  | CLASS 2
076551C-000R-MR-0811-004 | MATERIAL REQUISITION FOR LARGE CARBON STEEL PRESSURE VESSELS | KNM PROCESS SYSTEMS SND BHD | 058C5807 | K1808007-E-C-11-001 | 058-C-CAL-40001-001 | MECHANICAL DESIGN CALCULATION 058C5807/058C5808 | A1003 | AX | 2 | 2019-04-23 | CON-BMP-VTRA-011239 | 2019-04-23 | FOR BAPCO REVIEW | 2019-05-08 | 2019-05-12 | 3-REVIEWED WITH COMMENTS BMP-ROC-VTRE-000662 | CLASS 2
076551C-000R-MR-0811-004 | MATERIAL REQUISITION FOR LARGE CARBON STEEL PRESSURE VESSELS | KNM PROCESS SYSTEMS SND BHD | 058C5807 | K1808007-E-D-11-001 | 058-C-GAD-40006-001 | GENERAL ARRANGEMENT FOR FERINERY SOUTH MICROSCRUBBER 058C5807/058C5808 | A1103 | AX | 2 | 2019-05-03 | CON-BMP-VTRA-011391 | 2019-05-03 | FOR BAPCO REVIEW | 2019-05-20 | 2019-05-26 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000776 | CLASS 2
076551C-000R-MR-0811-004 | MATERIAL REQUISITION FOR LARGE CARBON STEEL PRESSURE VESSELS | KNM PROCESS SYSTEMS SND BHD | 058C5807 | K1808007-E-D-11-002 | 058-C-GAD-40007-001 | BODY SKIRT & ACCESSORIES DETAIL DRAWING REFINERY SOUTH MICROSCRUBBER 058C5807 /058C5808 | A1109 | AXX | 2 | 2019-07-08 | CON-BMP-VTRA-012713 | 2019-07-08 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-004 | MATERIAL REQUISITION FOR LARGE CARBON STEEL PRESSURE VESSELS | KNM PROCESS SYSTEMS SND BHD | 058C5807 | K1808007-E-D-11-003 | 058-C-GAD-40008-001 | NOZZLE DETAIL DRAWING REFINERY SOUTH MICROSCRUBBER 058C5807 058C5808 | A1109 | AXX | 2 | 2019-07-08 | CON-BMP-VTRA-012713 | 2019-07-08 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-004 | MATERIAL REQUISITION FOR LARGE CARBON STEEL PRESSURE VESSELS | KNM PROCESS SYSTEMS SND BHD | 058C5807 | K1808007-E-D-11-004 | 058-C-GAD-40009-001 | MANHOLE DETAIL DRAWING FOR REFINERY SOUTH MICROSCRUBBER 058C5807/058C5808 | A1109 | AXX | 2 | 2019-07-08 | CON-BMP-VTRA-012713 | 2019-07-08 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-004 | MATERIAL REQUISITION FOR LARGE CARBON STEEL PRESSURE VESSELS | KNM PROCESS SYSTEMS SND BHD | 058C5807 | K1808007-E-D-11-014 | 058-C-DLB-40002-001 | NAMEPLATE DETAIL DRAWING FOR REFINERY SOUTH MICROSCRUBBER 058C5807/058C5808 | A1112 | AX | 2 | 2019-04-26 | CON-BMP-VTRA-011289 | 2019-04-26 | FOR BAPCO REVIEW | 2019-05-14 | 2019-05-23 | 3-REVIEWED WITH COMMENTS BMP-ROC-VTRE-000743 | CLASS 2
076551C-000R-MR-0811-004 | MATERIAL REQUISITION FOR LARGE CARBON STEEL PRESSURE VESSELS | KNM PROCESS SYSTEMS SND BHD | 058C5807 | K1808007-Q-P-002K | 058-C-PQP-40001-001 | FABRICATION AND QUALITY CONTROL PLAN 058C5807 058C5808 | B1002 | AX | 2 | 2019-04-16 | CON-BMP-VTRA-011205 | 2019-04-16 | FOR BAPCO REVIEW | 2019-05-02 | 2019-04-28 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000611 | CLASS 2
076551C-000R-MR-0811-004 | MATERIAL REQUISITION FOR LARGE CARBON STEEL PRESSURE VESSELS | KNM PROCESS SYSTEMS SND BHD | 058C5807 | K1808007-Q-P-003K | 058-C-MCD-40002-001 | WPS & PQR AND WELD MAP FOR CARBON STEEL WITH PWHT (058C5807/ 058C5808) | B1304 | BX | 2 | 2019-06-29 | CON-BMP-VTRA-012565 | 2019-06-29 | FOR BAPCO REVIEW | 2019-07-15 | 2019-07-10 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001281 | CLASS 2
076551C-000R-MR-0811-004 | MATERIAL REQUISITION FOR LARGE CARBON STEEL PRESSURE VESSELS | KNM PROCESS SYSTEMS SND BHD | 058C5807 | K1808019-E-D-11-007 | 058-C-DLB-40001-001 | TEMPLATE DRAWING FOR KHUFF GAS MICROSCRUBBER 058C5807/058C5808 | A2010 | 0X | 2 | 2019-05-28 | CON-BMP-VTRA-011818 | 2019-05-29 | FOR BAPCO REVIEW | 2019-06-12 | 2019-06-17 | 3-REVIEWED WITH COMMENTS BMP-ROC-VTRE-000951 | CLASS 2
076551C-000R-MR-0811-004 | MATERIAL REQUISITION FOR LARGE CARBON STEEL PRESSURE VESSELS | KNM PROCESS SYSTEMS SND BHD | 082V0001A | K1808007-E-C-15-001 | 082-C-CAL-40001-001 | MECHANICAL DESIGN CALCULATION FOR REFINERY SOUTH FLARE MAIN KO DRUMS (082V0001 A/B) | A1003 | AXX | 2 | 2019-05-29 | CON-BMP-VTRA-011832 | 2019-05-29 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-004 | MATERIAL REQUISITION FOR LARGE CARBON STEEL PRESSURE VESSELS | KNM PROCESS SYSTEMS SND BHD | 082V0001A | K1808007-E-D-15-001 | 082-C-GAD-40003-001 | GENERAL ARRANGEMENT FOR REFINERY SOUTH FLARE MAIN K.O DRUM 082V0001A/B | A1103 | AX | 2 | 2019-05-14 | CON-BMP-VTRA-011545 | 2019-05-14 | FOR BAPCO REVIEW | 2019-05-28 | 2019-05-28 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000819 | CLASS 2
076551C-000R-MR-0811-004 | MATERIAL REQUISITION FOR LARGE CARBON STEEL PRESSURE VESSELS | KNM PROCESS SYSTEMS SND BHD | 082V0001A | K1808007-E-D-15-002 | 082-C-GAD-40004-001 | BODY SADDLE & ACCESSORIES DETAIL DRAWING FOR REFINERY SOUTH FLARE MAIN K.O. DRUM 082V0001A/B | A1109 | AX | 2 | 2019-05-03 | CON-BMP-VTRA-011366 | 2019-05-03 | FOR BAPCO REVIEW | 2019-05-17 | 2019-05-26 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000792 | CLASS 2
076551C-000R-MR-0811-004 | MATERIAL REQUISITION FOR LARGE CARBON STEEL PRESSURE VESSELS | KNM PROCESS SYSTEMS SND BHD | 082V0001A | K1808007-E-D-15-003 | 082-C-GAD-40005-001 | NOZZLE DETAIL DRAWING FOR REFINERY SOUTH FLARE MAIN KO DRUM 082V0001A/B | A1109 | AX | 2 | 2019-05-03 | CON-BMP-VTRA-011366 | 2019-05-03 | FOR BAPCO REVIEW | 2019-05-17 | 2019-05-26 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000792 | CLASS 2
076551C-000R-MR-0811-004 | MATERIAL REQUISITION FOR LARGE CARBON STEEL PRESSURE VESSELS | KNM PROCESS SYSTEMS SND BHD | 082V0001A | K1808007-E-D-15-004 | 082-C-GAD-40006-001 | MANHOLE DETAIL DRAWING FOR REFINERY SOUTH FLARE MAIN K.O. DRUM 082V0001A/B | A1109 | AX | 2 | 2019-05-03 | CON-BMP-VTRA-011366 | 2019-05-03 | FOR BAPCO REVIEW | 2019-05-17 | 2019-05-26 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000792 | CLASS 2
076551C-000R-MR-0811-004 | MATERIAL REQUISITION FOR LARGE CARBON STEEL PRESSURE VESSELS | KNM PROCESS SYSTEMS SND BHD | 082V0001A | K1808007-E-D-15-010 | 082-C-DLB-40001-001 | NAMEPLATE DETAIL DRAWING FOR REFINERY SOUTH FLARE MAIN KO DRUM 082V0001A/B | A1112 | AXX | 2 | 2019-07-09 | CON-BMP-VTRA-012764 | 2019-07-09 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-004 | MATERIAL REQUISITION FOR LARGE CARBON STEEL PRESSURE VESSELS | KNM PROCESS SYSTEMS SND BHD | 082V0001A | K1808007-Q-P-002O | 082-C-PQP-40001-001 | FABRICATION AND QUALITY CONTROL PLAN 082V0001A/B | B1002 | AX | 2 | 2019-04-16 | CON-BMP-VTRA-011205 | 2019-04-16 | FOR BAPCO REVIEW | 2019-05-02 | 2019-04-28 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000611 | CLASS 2
076551C-000R-MR-0811-004 | MATERIAL REQUISITION FOR LARGE CARBON STEEL PRESSURE VESSELS | KNM PROCESS SYSTEMS SND BHD | 082V0001A | K1808007-Q-P-003O | 082-C-MCD-40001-001 | WPS & PQR AND WELD MAP FOR CARBON STEEL WITH PWHT 082V0001A/B | B1304 | BX | 2 | 2019-06-29 | CON-BMP-VTRA-012568 | 2019-06-29 | FOR BAPCO REVIEW | 2019-07-15 |  |  | CLASS 2
076551C-000R-MR-0811-005 | MATERIAL REQUISITION FOR HP CENTRIFUGAL SEPARATOR | FORAIN S.r.l. | 018V1007 | 48A519-QCP_001 | 018-C-PQP-40061-001 | FABRICATION AND QUALITY CONTROL PLAN 018V1007 | B1002 | BX | 2 | 2019-06-13 | CON-BMP-VTRA-012194 | 2019-06-13 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-005 | MATERIAL REQUISITION FOR HP CENTRIFUGAL SEPARATOR | FORAIN S.r.l. | 018V1007 | 48A519_AAA-002 | 018-C-INX-40024-001 | LIST OF VENDOR'S DOCUMENTS AND DRAWINGS ALL ITEMS | A0001 | BXX | 4 | 2019-07-08 | CON-BMP-VTRA-012734 | 2019-07-08 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-005 | MATERIAL REQUISITION FOR HP CENTRIFUGAL SEPARATOR | FORAIN S.r.l. | 018V1007 | 48A519_CFC-001 | 018-C-GAD-40545-001 | N.1 RESIDUE HYDROCRACKING UNIT CENTRIFUGAL SEPARATOR MAIN DRAWING 018V1007 | A2001 | BX | 2 | 2019-06-21 | CON-BMP-VTRA-012365 | 2019-06-21 | FOR BAPCO REVIEW | 2019-07-05 |  |  | CLASS 2
076551C-000R-MR-0811-005 | MATERIAL REQUISITION FOR HP CENTRIFUGAL SEPARATOR | FORAIN S.r.l. | 018V1007 | 48A519_FMC-001 | 018-C-CAL-40164-001 | MECHANICAL CLACULATION HP CENTRIFUGAL SEPARATOR CH8 018V1007 | A1003 | BX | 2 | 2019-06-21 | CON-BMP-VTRA-012364 | 2019-06-21 | FOR BAPCO REVIEW | 2019-07-05 |  |  | CLASS 2
076551C-000R-MR-0811-005 | MATERIAL REQUISITION FOR HP CENTRIFUGAL SEPARATOR | FORAIN S.r.l. | 018V1007 | 48A519_PBH-001 | 018-C-PRO-40032-001 | POSTWELD HEAT TREATMENT PROCEDURE ALL ITEMS | B1201 | AX | 1 | 2019-05-16 | CON-BMP-VTRA-011640 | 2019-05-16 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-005 | MATERIAL REQUISITION FOR HP CENTRIFUGAL SEPARATOR | FORAIN S.r.l. | 018V1007 | 48A519_PBP-001 | 018-C-TSP-40026-001 | PAINTING SPECIFICATION ALL ITEMS | A0106 | AX | 1 | 2019-05-16 | CON-BMP-VTRA-011641 | 2019-05-16 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-005 | MATERIAL REQUISITION FOR HP CENTRIFUGAL SEPARATOR | FORAIN S.r.l. | 018V1007 | 48A519_PBT-001 | 018-C-PRO-40031-001 | NDT PROCEDURE ALL ITEMS | B1202 | AX | 2 | 2019-05-16 | CON-BMP-VTRA-011638 | 2019-05-16 | FOR BAPCO REVIEW | 2019-05-30 | 2019-05-26 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000782 | CLASS 2
076551C-000R-MR-0811-005 | MATERIAL REQUISITION FOR HP CENTRIFUGAL SEPARATOR | FORAIN S.r.l. | 018V1007 | 48A519_PFF-001 | 018-C-PRO-40033-001 | TESTING PROCEDURE ALL ITEMS | B1103 | BX | 3 | 2019-06-21 | CON-BMP-VTRA-012366 | 2019-06-21 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-005 | MATERIAL REQUISITION FOR HP CENTRIFUGAL SEPARATOR | FORAIN S.r.l. | 018V1007 | 48A519_PZA-002 | 018-C-TSP-40032-001 | MATERIAL SECIFICATION FOR MAIN SUB-ORDER ALL ITEMS | B1203 | AXX | 2 | 2019-07-08 | CON-BMP-VTRA-012735 | 2019-07-08 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-005 | MATERIAL REQUISITION FOR HP CENTRIFUGAL SEPARATOR | FORAIN S.r.l. | 018V1007 | 48A519_PZA-003 | 018-C-PRO-40034-001 | HEAD FORMING PROCEDURE 018V1007 / 018V2007 | B1202 | AX | 2 | 2019-05-16 | CON-BMP-VTRA-011638 | 2019-05-16 | FOR BAPCO REVIEW | 2019-05-30 | 2019-05-26 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000782 | CLASS 2
076551C-000R-MR-0811-005 | MATERIAL REQUISITION FOR HP CENTRIFUGAL SEPARATOR | FORAIN S.r.l. | 018V1007 | 48A519_PZA_001 | 018-C-PQS-40002-001 | SUB-VENDOR QUALIFICATION 018V1007 018V2007 | B1401 | AX | 4 | 2019-05-16 | CON-BMP-VTRA-011635 | 2019-05-16 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-0811-005 | MATERIAL REQUISITION FOR HP CENTRIFUGAL SEPARATOR | FORAIN S.r.l. | 018V1007 | 48A519_QFP-001 | 018-C-SCH-40004-001 | ENGINEERING PROCUREMENT MANUFACTURING AND TEST SCHEDULE 018V1007 018V2007 | C1001 | BX | 4 | 2019-05-16 | CON-BMP-VTRA-011642 | 2019-05-16 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-0811-005 | MATERIAL REQUISITION FOR HP CENTRIFUGAL SEPARATOR | FORAIN S.r.l. | 018V1007 | 48A519_QMR-001 | 018-C-MRS-40004-001 | MONTHLY PROGRESS REPORT 018V1007 018V2007018V2007 | C1002 | BX | 4 | 2019-05-23 | CON-BMP-VTRA-011759 | 2019-05-23 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-0811-005 | MATERIAL REQUISITION FOR HP CENTRIFUGAL SEPARATOR | FORAIN S.r.l. | 018V1007 | 48A519_QWB-001 | 018-C-MCD-40091-001 | WELDING BOOK 018V1007 | B1304 | AX | 1 | 2019-05-16 | CON-BMP-VTRA-011633 | 2019-05-16 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-005 | MATERIAL REQUISITION FOR HP CENTRIFUGAL SEPARATOR | FORAIN S.r.l. | 018V1007 | 48A519_TLO_001 | 018-C-INV-40004-001 | SUB-ORDER LIST AND UNPRICED COPY 018V1007 018V2007 | C1005 | BX | 4 | 2019-05-23 | CON-BMP-VTRA-011760 | 2019-05-23 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-005 | MATERIAL REQUISITION FOR HP CENTRIFUGAL SEPARATOR | FORAIN S.r.l. | 018V2007 | 48A519-QCP_002 | 018-C-PQP-40062-001 | FABRICATION AND QUALITY CONTROL PLAN 018V2007 | B1002 | BX | 2 | 2019-06-13 | CON-BMP-VTRA-012194 | 2019-06-13 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-005 | MATERIAL REQUISITION FOR HP CENTRIFUGAL SEPARATOR | FORAIN S.r.l. | 018V2007 | 48A519_CFC-002 | 018-C-GAD-40546-001 | N.1 RESIDUE HYDROCRACKING UNIT CENTRIFUGAL SEPARATOR MAIN DRAWING 018V2007 | A2001 | BX | 2 | 2019-06-21 | CON-BMP-VTRA-012365 | 2019-06-21 | FOR BAPCO REVIEW | 2019-07-05 |  |  | CLASS 2
076551C-000R-MR-0811-005 | MATERIAL REQUISITION FOR HP CENTRIFUGAL SEPARATOR | FORAIN S.r.l. | 018V2007 | 48A519_FMC-002 | 018-C-CAL-40165-001 | MECHANICAL CLACULATION HP CENTRIFUGAL SEPARATOR CH8 018V2007 | A1003 | BX | 2 | 2019-06-21 | CON-BMP-VTRA-012364 | 2019-06-21 | FOR BAPCO REVIEW | 2019-07-05 |  |  | CLASS 2
076551C-000R-MR-0811-005 | MATERIAL REQUISITION FOR HP CENTRIFUGAL SEPARATOR | FORAIN S.r.l. | 018V2007 | 48A519_QWB-002 | 018-C-MCD-40094-001 | WELDING BOOK 018V2007 | B1304 | AX | 1 | 2019-05-16 | CON-BMP-VTRA-011633 | 2019-05-16 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-102 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | DOOSAN MECATEC CO.LTD | 018V0006 | 18C0090-01-01 | 018-C-GAD-40468-001 | LT OIL FLASH DRUM GENERAL ASSEMBLY 018V0006 | A1103 | AX | 2 | 2019-04-10 | CON-BMP-VTRA-011086 | 2019-04-10 | FOR BAPCO REVIEW | 2019-04-24 | 2019-04-27 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000603 | CLASS 2
076551C-000R-MR-0811-102 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | DOOSAN MECATEC CO.LTD | 018V0006 | 18C0090-01-02 | 018-C-GAD-40469-001 | BODY DETAIL LT OIL FLASH DRUM 018V0006 | A1109 | AX | 2 | 2019-04-08 | CON-BMP-VTRA-011032 | 2019-04-08 | FOR BAPCO REVIEW | 2019-04-22 | 2019-04-25 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000577 | CLASS 2
076551C-000R-MR-0811-102 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | DOOSAN MECATEC CO.LTD | 018V0006 | 18C0090-01-03 | 018-C-GAD-40470-001 | 018V0006 LT OIL FLASH DRUM MANHOLE DETAIL | A1109 | AX | 2 | 2019-04-17 | CON-BMP-VTRA-011209 | 2019-04-17 | FOR BAPCO REVIEW | 2019-05-02 | 2019-05-11 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000658 | CLASS 2
076551C-000R-MR-0811-102 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | DOOSAN MECATEC CO.LTD | 018V0006 | 18C0090-01-04 | 018-C-GAD-40471-001 | 018V0006 LT OIL FLASH DRUM NOZZLE DETAIL (1) | A1109 | AX | 2 | 2019-04-17 | CON-BMP-VTRA-011209 | 2019-04-17 | FOR BAPCO REVIEW | 2019-05-02 | 2019-05-11 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000658 | CLASS 2
076551C-000R-MR-0811-102 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | DOOSAN MECATEC CO.LTD | 018V0006 | 18C0090-01-05 | 018-C-GAD-40472-001 | 018V0006 LT OIL FLASH DRUM NOZZLE DETAIL (2) | A1109 | AX | 2 | 2019-04-17 | CON-BMP-VTRA-011209 | 2019-04-17 | FOR BAPCO REVIEW | 2019-05-02 | 2019-05-11 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000658 | CLASS 2
076551C-000R-MR-0811-102 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | DOOSAN MECATEC CO.LTD | 018V0006 | 18C0090-01-08 | 018-C-DLB-40062-001 | TEMPLATE DETAIL LT OIL FLASH DRUM 018V0006 | A2010 | BX | 2 | 2019-06-07 | CON-BMP-VTRA-012087 | 2019-06-07 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-102 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | DOOSAN MECATEC CO.LTD | 018V0006 | 18C0090-CAL-01 | 018-C-CAL-40153-001 | STRENGTH CALCULATION FOR LT OIL FLASH DRUM 018V0006 | A1003 | AX | 2 | 2019-04-08 | CON-BMP-VTRA-011033 | 2019-04-08 | FOR BAPCO REVIEW | 2019-04-22 | 2019-04-25 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000575 | CLASS 2
076551C-000R-MR-0811-102 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | DOOSAN MECATEC CO.LTD | 018V0006 | 18C0090-FQCP-01 | 018-C-PQP-40049-001 | FABRICATION AND QUALITY CONTROL PLAN FOR 018V0006 | B1002 | AXX | 2 | 2019-05-06 | CON-BMP-VTRA-011397 | 2019-05-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-102 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | DOOSAN MECATEC CO.LTD | 018V0006 | 18C0090-MPR | 000-C-MRS-40008-001 | MONTHLY PROGRESS REPORT ALL ITEMS | C1002 | AX | 4 | 2019-05-22 | CON-BMP-VTRA-011714 | 2019-05-22 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-0811-102 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | DOOSAN MECATEC CO.LTD | 018V0006 | 18C0090-MPS | 000-C-TSP-40013-001 | MATERIAL PURCHASE SPECIFICATION ALL ITEMS | B1203 | AXX | 2 | 2019-05-23 | CON-BMP-VTRA-011752 | 2019-05-23 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-102 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | DOOSAN MECATEC CO.LTD | 018V0006 | 18C0090-NDE | 000-C-PRO-40052-001 | NDE PROCEDURE ALL ITEMS | B1202 | AX | 2 | 2019-05-23 | CON-BMP-VTRA-011755 | 2019-05-23 | FOR BAPCO REVIEW | 2019-06-07 | 2019-06-04 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000875 | CLASS 2
076551C-000R-MR-0811-102 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | DOOSAN MECATEC CO.LTD | 018V0006 | 18C0090-PWHT | 000-C-PRO-40051-001 | PWHT PROCEDURE ALL ITEMS | B1201 | AX | 2 | 2019-04-08 | CON-BMP-VTRA-011031 | 2019-04-08 | FOR BAPCO REVIEW | 2019-04-22 | 2019-04-18 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-TRE-002323 | CLASS 2
076551C-000R-MR-0811-102 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | DOOSAN MECATEC CO.LTD | 018V0006 | 18C0090-UPO | 000-C-INV-40006-001 | UNPRICED COPY OF MAIN SUBORDERS (MAJOR MATERIALS) ALL ITEMS | C1005 | AX | 4 | 2019-05-08 | CON-BMP-VTRA-011497 | 2019-05-08 | FOR BAPCO REVIEW | 2019-05-23 | 2019-05-21 | 3-REVIEWED WITH COMMENTS BMP-ROC-VTRE-000717 | CLASS 2
076551C-000R-MR-0811-102 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | DOOSAN MECATEC CO.LTD | 018V0006 | 18C0090-VDDL | 000-C-INX-40011-001 | LIST OF VENDOR'S DOCUMENTS AND DRAWINGS ALL ITEMS | A0001 | AXX | 2 | 2019-07-08 | CON-BMP-VTRA-012733 | 2019-07-08 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-102 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | DOOSAN MECATEC CO.LTD | 018V0006 | 18C0090-WPS-01 | 018-C-MCD-40083-001 | WELDING BOOK 018V0006 | B1304 | AXX | 2 | 2019-04-08 | CON-BMP-VTRA-011037 | 2019-04-08 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-102 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | DOOSAN MECATEC CO.LTD | 018V0027 | 18C0090-02-01 | 018-C-GAD-40477-001 | GENERAL ASSEMBLY 018V0027 | A1103 | AXX | 2 | 2019-05-23 | CON-BMP-VTRA-011754 | 2019-05-23 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-102 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | DOOSAN MECATEC CO.LTD | 018V0027 | 18C0090-02-02 | 018-C-GAD-40478-001 | BODY DETAIL 018V0027 | A1109 | AX | 2 | 2019-04-01 | CON-BMP-VTRA-010956 | 2019-04-01 | FOR BAPCO REVIEW | 2019-04-16 | 2019-04-24 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000554 | CLASS 2
076551C-000R-MR-0811-102 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | DOOSAN MECATEC CO.LTD | 018V0027 | 18C0090-02-03 | 018-C-GAD-40479-001 | 018V0027 SOUR WATER DEGASSER MANHOLE DETAIL | A1109 | AX | 2 | 2019-04-11 | CON-BMP-VTRA-011118 | 2019-04-11 | FOR BAPCO REVIEW | 2019-04-26 | 2019-06-26 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001040 | CLASS 2
076551C-000R-MR-0811-102 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | DOOSAN MECATEC CO.LTD | 018V0027 | 18C0090-02-04 | 018-C-GAD-40480-001 | 018V0027 SOUR WATER DEGASSER NOZZLE DETAIL (1) | A1109 | AX | 2 | 2019-04-11 | CON-BMP-VTRA-011118 | 2019-04-11 | FOR BAPCO REVIEW | 2019-04-26 | 2019-06-26 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001040 | CLASS 2
076551C-000R-MR-0811-102 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | DOOSAN MECATEC CO.LTD | 018V0027 | 18C0090-02-05 | 018-C-GAD-40481-001 | 018V0027 SOUR WATER DEGASSER NOZZLE DETAIL (2) | A1109 | AX | 2 | 2019-04-11 | CON-BMP-VTRA-011118 | 2019-04-11 | FOR BAPCO REVIEW | 2019-04-26 | 2019-06-26 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001040 | CLASS 2
076551C-000R-MR-0811-102 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | DOOSAN MECATEC CO.LTD | 018V0027 | 18C0090-02-06 | 018-C-GAD-40482-001 | 018V0027 SOUR WATER DEGASSER NOZZLE DETAIL (3) | A1109 | AX | 2 | 2019-04-11 | CON-BMP-VTRA-011118 | 2019-04-11 | FOR BAPCO REVIEW | 2019-04-26 | 2019-06-26 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001040 | CLASS 2
076551C-000R-MR-0811-102 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | DOOSAN MECATEC CO.LTD | 018V0027 | 18C0090-02-10 | 018-C-DLB-40064-001 | TEMPLATE DETAIL 018V0027 | A2010 | BX | 2 | 2019-06-07 | CON-BMP-VTRA-012087 | 2019-06-07 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-102 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | DOOSAN MECATEC CO.LTD | 018V0027 | 18C0090-CAL-02 | 018-C-CAL-40154-001 | STRENGTH CALCULATION FOR 018V0027 | A1003 | AX | 2 | 2019-04-01 | CON-BMP-VTRA-010957 | 2019-04-01 | FOR BAPCO REVIEW | 2019-04-16 | 2019-04-24 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000558 | CLASS 2
076551C-000R-MR-0811-102 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | DOOSAN MECATEC CO.LTD | 018V0027 | 18C0090-FQCP-02 | 018-C-PQP-40050-001 | FABRICATION AND QUALITY CONTROL PLAN FOR 018V0027 | B1002 | AXX | 2 | 2019-05-06 | CON-BMP-VTRA-011397 | 2019-05-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-102 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | DOOSAN MECATEC CO.LTD | 018V0027 | 18C0090-WPS-02 | 018-C-MCD-40084-001 | WELDING BOOK 018V0027 | B1304 | AXX | 2 | 2019-04-08 | CON-BMP-VTRA-011037 | 2019-04-08 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-102 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | DOOSAN MECATEC CO.LTD | 018V0028 | 18C0090-03-01 | 018-C-GAD-40488-001 | RICH AMINE FLASH DRUM GENERAL ASSEMBLY 018V0028 | A1103 | AXX | 2 | 2019-05-17 | CON-BMP-VTRA-011665 | 2019-05-17 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-102 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | DOOSAN MECATEC CO.LTD | 018V0028 | 18C0090-03-02 | 018-C-GAD-40489-001 | BODY DETAIL 018V0028 | A1109 | AX | 2 | 2019-04-01 | CON-BMP-VTRA-010956 | 2019-04-01 | FOR BAPCO REVIEW | 2019-04-16 | 2019-04-24 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000554 | CLASS 2
076551C-000R-MR-0811-102 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | DOOSAN MECATEC CO.LTD | 018V0028 | 18C0090-03-03 | 018-C-GAD-40490-001 | 018V0028 RICH AMINE FLASH DRUM MANHOLE DETAIL | A1109 | AX | 2 | 2019-04-16 | CON-BMP-VTRA-011188 | 2019-04-16 | FOR BAPCO REVIEW | 2019-04-30 | 2019-05-09 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000648 | CLASS 2
076551C-000R-MR-0811-102 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | DOOSAN MECATEC CO.LTD | 018V0028 | 18C0090-03-04 | 018-C-GAD-40491-001 | 018V0028 RICH AMINE FLASH DRUM NOZZLE DETAIL (1) | A1109 | AX | 2 | 2019-04-16 | CON-BMP-VTRA-011188 | 2019-04-16 | FOR BAPCO REVIEW | 2019-04-30 | 2019-05-09 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000648 | CLASS 2
076551C-000R-MR-0811-102 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | DOOSAN MECATEC CO.LTD | 018V0028 | 18C0090-03-05 | 018-C-GAD-40492-001 | 018V0028 RICH AMINE FLASH DRUM NOZZLE DETAIL (2) | A1109 | AX | 2 | 2019-04-16 | CON-BMP-VTRA-011188 | 2019-04-16 | FOR BAPCO REVIEW | 2019-04-30 | 2019-05-09 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000648 | CLASS 2
076551C-000R-MR-0811-102 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | DOOSAN MECATEC CO.LTD | 018V0028 | 18C0090-03-06 | 018-C-GAD-40493-001 | 018V0028 RICH AMINE FLASH DRUM NOZZLE DETAIL (3) | A1109 | AX | 2 | 2019-04-16 | CON-BMP-VTRA-011188 | 2019-04-16 | FOR BAPCO REVIEW | 2019-04-30 | 2019-05-09 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000648 | CLASS 2
076551C-000R-MR-0811-102 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | DOOSAN MECATEC CO.LTD | 018V0028 | 18C0090-03-06A | 018-C-GAD-40544-001 | 018V0028 RICH AMINE FLASH DRUM NOZZLE DETAIL (4) | A1109 | AX | 2 | 2019-04-16 | CON-BMP-VTRA-011188 | 2019-04-16 | FOR BAPCO REVIEW | 2019-04-30 | 2019-05-09 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000648 | CLASS 2
076551C-000R-MR-0811-102 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | DOOSAN MECATEC CO.LTD | 018V0028 | 18C0090-CAL-03 | 018-C-CAL-40155-001 | STRENGTH CALCULATION FOR 018V0028 | A1003 | AX | 2 | 2019-04-01 | CON-BMP-VTRA-010957 | 2019-04-01 | FOR BAPCO REVIEW | 2019-04-16 | 2019-04-24 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000558 | CLASS 2
076551C-000R-MR-0811-102 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | DOOSAN MECATEC CO.LTD | 018V0028 | 18C0090-FQCP-03 | 018-C-PQP-40051-001 | FABRICATION AND QUALITY CONTROL PLAN FOR 018V0028 | B1002 | AXX | 2 | 2019-05-06 | CON-BMP-VTRA-011397 | 2019-05-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-102 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | DOOSAN MECATEC CO.LTD | 018V0028 | 18C0090-WPS-03 | 018-C-MCD-40085-001 | WELDING BOOK 018V0028 | B1304 | AXX | 2 | 2019-04-08 | CON-BMP-VTRA-011037 | 2019-04-08 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-102 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | DOOSAN MECATEC CO.LTD | 018V0041 | 18C0090-04-01 | 018-C-GAD-40497-001 | CATALYST SLOP OIL DRUM GENERAL ASSEMBLY 018V0041 | A1103 | AXX | 2 | 2019-05-17 | CON-BMP-VTRA-011665 | 2019-05-17 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-102 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | DOOSAN MECATEC CO.LTD | 018V0041 | 18C0090-04-02 | 018-C-GAD-40498-001 | BODY DETAIL 018V0041 | A1109 | AX | 2 | 2019-04-01 | CON-BMP-VTRA-010956 | 2019-04-01 | FOR BAPCO REVIEW | 2019-04-16 | 2019-04-24 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000554 | CLASS 2
076551C-000R-MR-0811-102 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | DOOSAN MECATEC CO.LTD | 018V0041 | 18C0090-04-03 | 018-C-GAD-40499-001 | 018V0041 CATALYST SLOP OIL DRUM MANHOLE DETAIL | A1109 | AX | 2 | 2019-04-11 | CON-BMP-VTRA-011118 | 2019-04-11 | FOR BAPCO REVIEW | 2019-04-26 | 2019-06-26 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001040 | CLASS 2
076551C-000R-MR-0811-102 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | DOOSAN MECATEC CO.LTD | 018V0041 | 18C0090-04-04 | 018-C-GAD-40500-001 | 018V0041 CATALYST SLOP OIL DRUM NOZZLE DETAIL (1) | A1109 | AX | 2 | 2019-04-11 | CON-BMP-VTRA-011118 | 2019-04-11 | FOR BAPCO REVIEW | 2019-04-26 | 2019-06-26 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001040 | CLASS 2
076551C-000R-MR-0811-102 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | DOOSAN MECATEC CO.LTD | 018V0041 | 18C0090-04-05 | 018-C-GAD-40501-001 | 018V0041 CATALYST SLOP OIL DRUM NOZZLE DETAIL (2) | A1109 | AX | 2 | 2019-04-11 | CON-BMP-VTRA-011118 | 2019-04-11 | FOR BAPCO REVIEW | 2019-04-26 | 2019-06-26 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001040 | CLASS 2
076551C-000R-MR-0811-102 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | DOOSAN MECATEC CO.LTD | 018V0041 | 18C0090-04-08 | 018-C-DLB-40067-001 | TEMPLATE DETAIL 018V0041 | A2010 | BX | 2 | 2019-06-07 | CON-BMP-VTRA-012087 | 2019-06-07 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-102 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | DOOSAN MECATEC CO.LTD | 018V0041 | 18C0090-CAL-04 | 018-C-CAL-40156-001 | STRENGTH CALCULATION FOR 018V0041 | A1003 | AX | 2 | 2019-04-01 | CON-BMP-VTRA-010957 | 2019-04-01 | FOR BAPCO REVIEW | 2019-04-16 | 2019-04-24 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000558 | CLASS 2
076551C-000R-MR-0811-102 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | DOOSAN MECATEC CO.LTD | 018V0041 | 18C0090-FQCP-04 | 018-C-PQP-40052-001 | FABRICATION AND QUALITY CONTROL PLAN FOR 018V0041 | B1002 | AXX | 2 | 2019-05-06 | CON-BMP-VTRA-011397 | 2019-05-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-102 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | DOOSAN MECATEC CO.LTD | 018V0041 | 18C0090-WPS-04 | 018-C-MCD-40086-001 | WELDING BOOK 018V0041 | B1304 | AXX | 2 | 2019-04-08 | CON-BMP-VTRA-011037 | 2019-04-08 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-102 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | DOOSAN MECATEC CO.LTD | 018V1004 | 18C0090-05-01 | 018-C-GAD-40506-001 | TRAIN 1 MP/HT SEPARATOR GENERAL ASSEMBLY 018V1004 | A1103 | AXX | 2 | 2019-05-23 | CON-BMP-VTRA-011757 | 2019-05-23 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-102 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | DOOSAN MECATEC CO.LTD | 018V1004 | 18C0090-05-02 | 018-C-GAD-40507-001 | TRAIN 1 MP/HT SEPARATOR BODY DETAIL 018V1004 | A1109 | AXX | 2 | 2019-05-17 | CON-BMP-VTRA-011664 | 2019-05-17 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-102 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | DOOSAN MECATEC CO.LTD | 018V1004 | 18C0090-05-03 | 018-C-GAD-40508-001 | 018V1004 TRAIN 1 MP/HT SEPARATOR MANHOLE DETAIL | A1109 | AX | 2 | 2019-04-12 | CON-BMP-VTRA-011140 | 2019-04-12 | FOR BAPCO REVIEW | 2019-04-26 | 2019-05-09 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000654 | CLASS 2
076551C-000R-MR-0811-102 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | DOOSAN MECATEC CO.LTD | 018V1004 | 18C0090-05-04 | 018-C-GAD-40509-001 | 018V1004 TRAIN 1 MP/HT SEPARATOR NOZZLE DETAIL (1) | A1109 | AXX | 2 | 2019-06-01 | CON-BMP-VTRA-011926 | 2019-06-01 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-102 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | DOOSAN MECATEC CO.LTD | 018V1004 | 18C0090-05-05 | 018-C-GAD-40510-001 | 018V1004 TRAIN 1 MP/HT SEPARATOR NOZZLE DETAIL (2) | A1109 | AXX | 2 | 2019-06-01 | CON-BMP-VTRA-011926 | 2019-06-01 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-102 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | DOOSAN MECATEC CO.LTD | 018V1004 | 18C0090-05-06 | 018-C-GAD-40511-001 | 018V1004 TRAIN 1 MP/HT SEPARATOR NOZZLE DETAIL (3) | A1109 | AX | 2 | 2019-04-12 | CON-BMP-VTRA-011140 | 2019-04-12 | FOR BAPCO REVIEW | 2019-04-26 | 2019-05-09 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000654 | CLASS 2
076551C-000R-MR-0811-102 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | DOOSAN MECATEC CO.LTD | 018V1004 | 18C0090-05-07 | 018-C-GAD-40512-001 | 018V1004 TRAIN 1 MP/HT SEPARATOR NOZZLE DETAIL (4) | A1109 | AX | 2 | 2019-04-12 | CON-BMP-VTRA-011140 | 2019-04-12 | FOR BAPCO REVIEW | 2019-04-26 | 2019-05-09 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000654 | CLASS 2
076551C-000R-MR-0811-102 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | DOOSAN MECATEC CO.LTD | 018V1004 | 18C0090-05-10 | 018-C-DLB-40069-001 | TEMPLATE DETAIL 018V1004 | A2010 | BX | 2 | 2019-06-13 | CON-BMP-VTRA-012179 | 2019-06-13 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-102 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | DOOSAN MECATEC CO.LTD | 018V1004 | 18C0090-CAL-05 | 018-C-CAL-40157-001 | STRENGTH CALCULATION FOR 018V1004 | A1003 | AX | 2 | 2019-04-03 | CON-BMP-VTRA-010979 | 2019-04-03 | FOR BAPCO REVIEW | 2019-04-18 | 2019-04-24 | 5-RETAIED FOR INFORMATION BMP-ROC-VTRE-000553 | CLASS 2
076551C-000R-MR-0811-102 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | DOOSAN MECATEC CO.LTD | 018V1004 | 18C0090-FQCP-05 | 018-C-PQP-40053-001 | FABRICATION AND QUALITY CONTROL PLAN FOR 018V1004 | B1002 | AXX | 2 | 2019-05-06 | CON-BMP-VTRA-011397 | 2019-05-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-102 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | DOOSAN MECATEC CO.LTD | 018V1004 | 18C0090-WPS-05 | 018-C-MCD-40087-001 | WELDING BOOK 018V1004 | B1304 | AXX | 2 | 2019-04-08 | CON-BMP-VTRA-011037 | 2019-04-08 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-102 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | DOOSAN MECATEC CO.LTD | 018V1006 | 18C0090-06-01 | 018-C-GAD-40516-001 | TRAIN 1 HP/LT SEPARATOR GENERAL ASSEMBLY 018V1006 | A1103 | AXX | 2 | 2019-05-23 | CON-BMP-VTRA-011757 | 2019-05-23 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-102 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | DOOSAN MECATEC CO.LTD | 018V1006 | 18C0090-06-02 | 018-C-GAD-40517-001 | 018V1006 TRAIN 1 HP-LT SEPARATOR BODY DETAIL | A1109 | AX | 2 | 2019-04-04 | CON-BMP-VTRA-010997 | 2019-04-04 | FOR BAPCO REVIEW | 2019-04-18 | 2019-04-24 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000563 | CLASS 2
076551C-000R-MR-0811-102 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | DOOSAN MECATEC CO.LTD | 018V1006 | 18C0090-06-03 | 018-C-GAD-40518-001 | 018V1006 TRAIN 1 HP/LT SEPARATOR MANHOLE DETAIL | A1109 | AX | 2 | 2019-04-15 | CON-BMP-VTRA-011184 | 2019-04-15 | FOR BAPCO REVIEW | 2019-04-30 | 2019-05-10 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000642 | CLASS 2
076551C-000R-MR-0811-102 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | DOOSAN MECATEC CO.LTD | 018V1006 | 18C0090-06-04 | 018-C-GAD-40519-001 | 018V1006 TRAIN 1 HP/LT SEPARATOR NOZZLE DETAIL (1) | A1109 | AX | 2 | 2019-04-15 | CON-BMP-VTRA-011184 | 2019-04-15 | FOR BAPCO REVIEW | 2019-04-30 | 2019-05-10 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000642 | CLASS 2
076551C-000R-MR-0811-102 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | DOOSAN MECATEC CO.LTD | 018V1006 | 18C0090-06-05 | 018-C-GAD-40520-001 | 018V1006 TRAIN 1 HP/LT SEPARATOR NOZZLE DETAIL (2) | A1109 | AX | 2 | 2019-04-15 | CON-BMP-VTRA-011184 | 2019-04-15 | FOR BAPCO REVIEW | 2019-04-30 | 2019-05-10 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000642 | CLASS 2
076551C-000R-MR-0811-102 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | DOOSAN MECATEC CO.LTD | 018V1006 | 18C0090-06-08 | 018-C-DLB-40071-001 | TEMPLATE DETAIL TRAIN 1 HP/LT SEPARATOR 018V1006 | A2010 | BX | 2 | 2019-06-07 | CON-BMP-VTRA-012087 | 2019-06-07 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-102 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | DOOSAN MECATEC CO.LTD | 018V1006 | 18C0090-CAL-06 | 018-C-CAL-40158-001 | STRENGTH CALCULATION FOR TRAIN 1 HP/LT SEPARATOR 018V1006 | A1003 | AXX | 2 | 2019-05-22 | CON-BMP-VTRA-011713 | 2019-05-22 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-102 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | DOOSAN MECATEC CO.LTD | 018V1006 | 18C0090-FQCP-06 | 018-C-PQP-40054-001 | FABRICATION AND QUALITY CONTROL PLAN FOR 018V1006 | B1002 | AXX | 2 | 2019-05-06 | CON-BMP-VTRA-011397 | 2019-05-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-102 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | DOOSAN MECATEC CO.LTD | 018V1006 | 18C0090-WPS-06 | 018-C-MCD-40088-001 | WELDING BOOK 018V1006 | B1304 | AXX | 2 | 2019-04-08 | CON-BMP-VTRA-011037 | 2019-04-08 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-102 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | DOOSAN MECATEC CO.LTD | 018V2004 | 18C0090-07-01 | 018-C-GAD-40525-001 | TRAIN 2 MP/HT SEPARATOR GENERAL ASSEMBLY 018V2004 | A1103 | AXX | 2 | 2019-05-23 | CON-BMP-VTRA-011757 | 2019-05-23 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-102 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | DOOSAN MECATEC CO.LTD | 018V2004 | 18C0090-07-02 | 018-C-GAD-40526-001 | 018V2004 TRAIN 2 MP-HT SEPARATOR BODY DETAIL | A1109 | AX | 2 | 2019-04-04 | CON-BMP-VTRA-010997 | 2019-04-04 | FOR BAPCO REVIEW | 2019-04-18 | 2019-04-24 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000563 | CLASS 2
076551C-000R-MR-0811-102 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | DOOSAN MECATEC CO.LTD | 018V2004 | 18C0090-07-03 | 018-C-GAD-40527-001 | 018V2004 TRAIN 2 MP/HT SEPARATOR MANHOLE DETAIL | A1109 | AX | 2 | 2019-04-12 | CON-BMP-VTRA-011140 | 2019-04-12 | FOR BAPCO REVIEW | 2019-04-26 | 2019-05-09 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000654 | CLASS 2
076551C-000R-MR-0811-102 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | DOOSAN MECATEC CO.LTD | 018V2004 | 18C0090-07-04 | 018-C-GAD-40528-001 | 018V2004 TRAIN 2 MP/HT SEPARATOR NOZZLE DETAIL (1) | A1109 | AXX | 2 | 2019-06-01 | CON-BMP-VTRA-011926 | 2019-06-01 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-102 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | DOOSAN MECATEC CO.LTD | 018V2004 | 18C0090-07-05 | 018-C-GAD-40529-001 | 018V2004 TRAIN 2 MP/HT SEPARATOR NOZZLE DETAIL (2) | A1109 | AXX | 2 | 2019-06-01 | CON-BMP-VTRA-011926 | 2019-06-01 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-102 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | DOOSAN MECATEC CO.LTD | 018V2004 | 18C0090-07-06 | 018-C-GAD-40530-001 | 018V2004 TRAIN 2 MP/HP SEPARATOR NOZZLE DETAIL (3) | A1109 | AX | 2 | 2019-04-12 | CON-BMP-VTRA-011140 | 2019-04-12 | FOR BAPCO REVIEW | 2019-04-26 | 2019-05-09 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000654 | CLASS 2
076551C-000R-MR-0811-102 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | DOOSAN MECATEC CO.LTD | 018V2004 | 18C0090-07-07 | 018-C-GAD-40531-001 | 018V2004 TRAIN 2 MP/HT SEPARATOR NOZZLE DETAIL (4) | A1109 | AX | 2 | 2019-04-12 | CON-BMP-VTRA-011140 | 2019-04-12 | FOR BAPCO REVIEW | 2019-04-26 | 2019-05-09 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000654 | CLASS 2
076551C-000R-MR-0811-102 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | DOOSAN MECATEC CO.LTD | 018V2004 | 18C0090-07-10 | 018-C-DLB-40073-001 | TEMPLATE DETAIL TRAIN 2 MP/HT SEPARATOR 018V2004 | A2010 | BX | 2 | 2019-06-07 | CON-BMP-VTRA-012087 | 2019-06-07 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-102 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | DOOSAN MECATEC CO.LTD | 018V2004 | 18C0090-CAL-07 | 018-C-CAL-40159-001 | STRENGTH CALCULATION FOR TRAIN 2 MP/HT SEPARATOR 018V2004 | A1003 | AX | 2 | 2019-04-04 | CON-BMP-VTRA-011001 | 2019-04-04 | FOR BAPCO REVIEW | 2019-04-19 | 2019-04-24 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000551 | CLASS 2
076551C-000R-MR-0811-102 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | DOOSAN MECATEC CO.LTD | 018V2004 | 18C0090-FQCP-07 | 018-C-PQP-40055-001 | FABRICATION AND QUALITY CONTROL PLAN FOR 018V2004 | B1002 | AXX | 2 | 2019-05-06 | CON-BMP-VTRA-011397 | 2019-05-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-102 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | DOOSAN MECATEC CO.LTD | 018V2004 | 18C0090-WPS-07 | 018-C-MCD-40089-001 | WELDING BOOK 018V2004 | B1304 | AXX | 2 | 2019-04-09 | CON-BMP-VTRA-011079 | 2019-04-09 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-102 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | DOOSAN MECATEC CO.LTD | 018V2006 | 18C0090-08-01 | 018-C-GAD-40535-001 | TRAIN 2 HP/LT SEPARATOR GENERAL ASSEMBLY 018V2006 | A1103 | AXX | 2 | 2019-05-23 | CON-BMP-VTRA-011757 | 2019-05-23 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-102 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | DOOSAN MECATEC CO.LTD | 018V2006 | 18C0090-08-02 | 018-C-GAD-40536-001 | 018V2006 TRAIN 2 HP-LT SEPARATOR BODY DETAIL | A1109 | AX | 2 | 2019-04-04 | CON-BMP-VTRA-010997 | 2019-04-04 | FOR BAPCO REVIEW | 2019-04-18 | 2019-04-24 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000563 | CLASS 2
076551C-000R-MR-0811-102 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | DOOSAN MECATEC CO.LTD | 018V2006 | 18C0090-08-03 | 018-C-GAD-40537-001 | 018V2006 TRAIN 2 HP/LT SEPARATOR MANHOLE DETAIL | A1109 | AX | 2 | 2019-04-15 | CON-BMP-VTRA-011184 | 2019-04-15 | FOR BAPCO REVIEW | 2019-04-30 | 2019-05-10 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000642 | CLASS 2
076551C-000R-MR-0811-102 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | DOOSAN MECATEC CO.LTD | 018V2006 | 18C0090-08-04 | 018-C-GAD-40538-001 | 018V2006 TRAIN 2 HP/LT SEPARATOR NOZZLE DETAIL (1) | A1109 | AX | 2 | 2019-04-15 | CON-BMP-VTRA-011184 | 2019-04-15 | FOR BAPCO REVIEW | 2019-04-30 | 2019-05-10 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000642 | CLASS 2
076551C-000R-MR-0811-102 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | DOOSAN MECATEC CO.LTD | 018V2006 | 18C0090-08-05 | 018-C-GAD-40539-001 | 018V2006 TRAIN 2 HP/LT SEPARATOR NOZZLE DETAIL (2) | A1109 | AX | 2 | 2019-04-15 | CON-BMP-VTRA-011184 | 2019-04-15 | FOR BAPCO REVIEW | 2019-04-30 | 2019-05-10 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000642 | CLASS 2
076551C-000R-MR-0811-102 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | DOOSAN MECATEC CO.LTD | 018V2006 | 18C0090-08-08 | 018-C-DLB-40075-001 | TEMPLATE DETAIL TRAIN 2 HP/LT SEPARATOR 018V2006 | A2010 | BX | 2 | 2019-06-07 | CON-BMP-VTRA-012087 | 2019-06-07 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-102 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | DOOSAN MECATEC CO.LTD | 018V2006 | 18C0090-CAL-08 | 018-C-CAL-40160-001 | STRENGTH CALCULATION FOR TRAIN 2 HP/LT SEPARATOR 018V2006 | A1003 | AXX | 2 | 2019-05-22 | CON-BMP-VTRA-011713 | 2019-05-22 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-102 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | DOOSAN MECATEC CO.LTD | 018V2006 | 18C0090-FQCP-08 | 018-C-PQP-40056-001 | FABRICATION AND QUALITY CONTROL PLAN FOR 018V2006 | B1002 | AXX | 2 | 2019-05-06 | CON-BMP-VTRA-011397 | 2019-05-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-102 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | DOOSAN MECATEC CO.LTD | 018V2006 | 18C0090-WPS-08 | 018-C-MCD-40090-001 | WELDING BOOK 018V2006 | B1304 | AXX | 2 | 2019-04-09 | CON-BMP-VTRA-011079 | 2019-04-09 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-102 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | DOOSAN MECATEC CO.LTD | 021V0003 | 18C0090-09-01 | 021-C-GAD-40099-001 | HOT HIGH PRESSURE SEPARATOR GENERAL ASSEMBLY 021V0003 | A1103 | AXX | 2 | 2019-06-01 | CON-BMP-VTRA-011925 | 2019-06-01 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-102 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | DOOSAN MECATEC CO.LTD | 021V0003 | 18C0090-09-02 | 021-C-GAD-40100-001 | 021V0003 HOT HIGH PRESSURE SEPARATOR BODY DETAIL | A1109 | AX | 2 | 2019-04-04 | CON-BMP-VTRA-010997 | 2019-04-04 | FOR BAPCO REVIEW | 2019-04-18 | 2019-04-24 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000563 | CLASS 2
076551C-000R-MR-0811-102 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | DOOSAN MECATEC CO.LTD | 021V0003 | 18C0090-09-03 | 021-C-GAD-40101-001 | 021V0003 HOT HIGH PRESSURE SEPARATOR MANHOLE DETAIL | A1109 | AX | 2 | 2019-04-15 | CON-BMP-VTRA-011184 | 2019-04-15 | FOR BAPCO REVIEW | 2019-04-30 | 2019-05-10 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000642 | CLASS 2
076551C-000R-MR-0811-102 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | DOOSAN MECATEC CO.LTD | 021V0003 | 18C0090-09-04 | 021-C-GAD-40102-001 | 021V0003 HOT HIGH PRESSURE SEPARATOR NOZZLE DETAIL (1) | A1109 | AX | 2 | 2019-04-15 | CON-BMP-VTRA-011184 | 2019-04-15 | FOR BAPCO REVIEW | 2019-04-30 | 2019-05-10 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000642 | CLASS 2
076551C-000R-MR-0811-102 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | DOOSAN MECATEC CO.LTD | 021V0003 | 18C0090-09-05 | 021-C-GAD-40103-001 | 021V0003 HOT HIGH PRESSURE SEPARATOR NOZZLE DETAIL (2) | A1109 | AX | 2 | 2019-04-15 | CON-BMP-VTRA-011184 | 2019-04-15 | FOR BAPCO REVIEW | 2019-04-30 | 2019-05-10 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000642 | CLASS 2
076551C-000R-MR-0811-102 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | DOOSAN MECATEC CO.LTD | 021V0003 | 18C0090-09-07 | 021-C-DLB-40015-001 | TEMPLATE DETAIL HOT HIGH PRESSURE SEPARATOR 021V0003 | A2010 | BX | 2 | 2019-06-07 | CON-BMP-VTRA-012087 | 2019-06-07 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-102 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | DOOSAN MECATEC CO.LTD | 021V0003 | 18C0090-CAL-09 | 021-C-CAL-40026-001 | STRENGTH CALCULATION FOR HOT HIGH PRESSURE SEPARATOR 021V0003 | A1003 | AX | 2 | 2019-04-04 | CON-BMP-VTRA-011001 | 2019-04-04 | FOR BAPCO REVIEW | 2019-04-19 | 2019-04-24 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000551 | CLASS 2
076551C-000R-MR-0811-102 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | DOOSAN MECATEC CO.LTD | 021V0003 | 18C0090-FQCP-09 | 021-C-PQP-40013-001 | FABRICATION AND QUALITY CONTROL PLAN FOR 021V0003 | B1002 | AXX | 2 | 2019-05-06 | CON-BMP-VTRA-011397 | 2019-05-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-102 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | DOOSAN MECATEC CO.LTD | 021V0003 | 18C0090-WPS-09 | 021-C-MCD-40018-001 | WELDING BOOK 021V0003 | B1304 | AXX | 2 | 2019-04-09 | CON-BMP-VTRA-011079 | 2019-04-09 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-102 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | DOOSAN MECATEC CO.LTD | 021V0009 | 18C0090-10-01 | 021-C-GAD-40107-001 | COLD LOW PRESSURE SEPARATOR GENERAL ASSEMBLY 021V0009 | A1103 | AX | 2 | 2019-04-10 | CON-BMP-VTRA-011085 | 2019-04-10 | FOR BAPCO REVIEW | 2019-04-24 | 2019-04-25 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-vTRE-000580 | CLASS 2
076551C-000R-MR-0811-102 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | DOOSAN MECATEC CO.LTD | 021V0009 | 18C0090-10-02 | 021-C-GAD-40108-001 | COLD LOW PRESSURE SEPARATOR BODY DETAIL 021V0009 | A1109 | AXX | 2 | 2019-05-17 | CON-BMP-VTRA-011664 | 2019-05-17 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-102 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | DOOSAN MECATEC CO.LTD | 021V0009 | 18C0090-10-03 | 021-C-GAD-40109-001 | 021V0009 COLD LOW PRESSURE SEPARATOR MANHOLE DETAIL | A1109 | AX | 2 | 2019-04-16 | CON-BMP-VTRA-011196 | 2019-04-16 | FOR BAPCO REVIEW | 2019-04-30 | 2019-05-20 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000715 | CLASS 2
076551C-000R-MR-0811-102 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | DOOSAN MECATEC CO.LTD | 021V0009 | 18C0090-10-04 | 021-C-GAD-40110-001 | 021V0009 COLD LOW PRESSURE SEPARATOR NOZZLE DETAIL (1) | A1109 | AX | 2 | 2019-04-16 | CON-BMP-VTRA-011196 | 2019-04-16 | FOR BAPCO REVIEW | 2019-04-30 | 2019-05-20 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000715 | CLASS 2
076551C-000R-MR-0811-102 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | DOOSAN MECATEC CO.LTD | 021V0009 | 18C0090-10-05 | 021-C-GAD-40111-001 | 021V0009 COLD LOW PRESSURE SEPARATOR NOZZLE DETAIL (2) | A1109 | AX | 2 | 2019-04-16 | CON-BMP-VTRA-011196 | 2019-04-16 | FOR BAPCO REVIEW | 2019-04-30 | 2019-05-20 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000715 | CLASS 2
076551C-000R-MR-0811-102 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | DOOSAN MECATEC CO.LTD | 021V0009 | 18C0090-10-05A | 021-C-GAD-40144-001 | 021V0009 COLD LOW PRESSURE SEPARATOR NOZZLE DETAIL (3) | A1109 | AX | 2 | 2019-04-16 | CON-BMP-VTRA-011196 | 2019-04-16 | FOR BAPCO REVIEW | 2019-04-30 | 2019-05-20 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000715 | CLASS 2
076551C-000R-MR-0811-102 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | DOOSAN MECATEC CO.LTD | 021V0009 | 18C0090-CAL-10 | 021-C-CAL-40027-001 | STRENGTH CALCULATION FOR 021V0009 | A1003 | AX | 2 | 2019-04-03 | CON-BMP-VTRA-010979 | 2019-04-03 | FOR BAPCO REVIEW | 2019-04-18 | 2019-04-24 | 5-RETAIED FOR INFORMATION BMP-ROC-VTRE-000553 | CLASS 2
076551C-000R-MR-0811-102 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | DOOSAN MECATEC CO.LTD | 021V0009 | 18C0090-FQCP-10 | 021-C-PQP-40014-001 | FABRICATION AND QUALITY CONTROL PLAN FOR 021V0009 | B1002 | AXX | 2 | 2019-05-06 | CON-BMP-VTRA-011397 | 2019-05-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-102 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | DOOSAN MECATEC CO.LTD | 021V0009 | 18C0090-WPS-10 | 021-C-MCD-40019-001 | WELDING BOOK 021V0009 | B1304 | AXX | 2 | 2019-04-09 | CON-BMP-VTRA-011079 | 2019-04-09 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-102 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | DOOSAN MECATEC CO.LTD | 021V0015 | 18C0090-11-01 | 021-C-GAD-40115-001 | RICH AMINE FLASH DRUM GENERAL ASSEMBLY 021V0015 | A1103 | AXX | 2 | 2019-06-01 | CON-BMP-VTRA-011925 | 2019-06-01 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-102 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | DOOSAN MECATEC CO.LTD | 021V0015 | 18C0090-11-02 | 021-C-GAD-40116-001 | 021V0015 RICH AMINE FLASH DRUM BODY DETAIL | A1109 | AX | 2 | 2019-04-04 | CON-BMP-VTRA-010997 | 2019-04-04 | FOR BAPCO REVIEW | 2019-04-18 | 2019-04-24 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000563 | CLASS 2
076551C-000R-MR-0811-102 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | DOOSAN MECATEC CO.LTD | 021V0015 | 18C0090-11-03 | 021-C-GAD-40117-001 | 021V0015 RICH AMINE FLASH DRUM MANHOLE DETAIL (1) | A1109 | AX | 2 | 2019-04-16 | CON-BMP-VTRA-011196 | 2019-04-16 | FOR BAPCO REVIEW | 2019-04-30 |  |  | CLASS 2
076551C-000R-MR-0811-102 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | DOOSAN MECATEC CO.LTD | 021V0015 | 18C0090-11-03A | 021-C-GAD-40145-001 | 021V0015 RICH AMINE FLASH DRUM MANHOLE DETAIL (2) | A1109 | AX | 2 | 2019-04-16 | CON-BMP-VTRA-011196 | 2019-04-16 | FOR BAPCO REVIEW | 2019-04-30 | 2019-05-20 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000715 | CLASS 2
076551C-000R-MR-0811-102 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | DOOSAN MECATEC CO.LTD | 021V0015 | 18C0090-11-04 | 021-C-GAD-40118-001 | 021V0015 RICH AMINE FLASH DRUM NOZZLE DETAIL (1) | A1109 | AX | 2 | 2019-04-16 | CON-BMP-VTRA-011196 | 2019-04-16 | FOR BAPCO REVIEW | 2019-04-30 | 2019-05-20 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000715 | CLASS 2
076551C-000R-MR-0811-102 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | DOOSAN MECATEC CO.LTD | 021V0015 | 18C0090-11-05 | 021-C-GAD-40119-001 | 021V0015 RICH AMINE FLASH DRUM NOZZLE DETAIL (2) | A1109 | AX | 2 | 2019-04-16 | CON-BMP-VTRA-011196 | 2019-04-16 | FOR BAPCO REVIEW | 2019-04-30 | 2019-05-20 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000715 | CLASS 2
076551C-000R-MR-0811-102 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | DOOSAN MECATEC CO.LTD | 021V0015 | 18C0090-CAL-11 | 021-C-CAL-40028-001 | STRENGTH CALCULATION FOR RICH AMINE FLASH DRUM 021V0015 | A1003 | AX | 2 | 2019-04-04 | CON-BMP-VTRA-011001 | 2019-04-04 | FOR BAPCO REVIEW | 2019-04-19 | 2019-04-24 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000551 | CLASS 2
076551C-000R-MR-0811-102 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | DOOSAN MECATEC CO.LTD | 021V0015 | 18C0090-FQCP-11 | 021-C-PQP-40015-001 | FABRICATION AND QUALITY CONTROL PLAN FOR 21V0015 | B1002 | AXX | 2 | 2019-05-06 | CON-BMP-VTRA-011397 | 2019-05-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-102 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | DOOSAN MECATEC CO.LTD | 021V0015 | 18C0090-WPS-11 | 021-C-MCD-40020-001 | WELDING BOOK 021V0015 | B1304 | AXX | 2 | 2019-04-09 | CON-BMP-VTRA-011079 | 2019-04-09 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-102 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | DOOSAN MECATEC CO.LTD | 023V0005 | 18C0090-12-01 | 023-C-GAD-40021-001 | RICH AMINE ACCUMULATOR GENERAL ASSEMBLY 023V0005 | A1103 | AX | 2 | 2019-04-10 | CON-BMP-VTRA-011084 | 2019-04-10 | FOR BAPCO REVIEW | 2019-04-24 | 2019-04-27 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000601 | CLASS 2
076551C-000R-MR-0811-102 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | DOOSAN MECATEC CO.LTD | 023V0005 | 18C0090-12-02 | 023-C-GAD-40022-001 | 023V0005 RICH AMINE ACCUMULATOR BODY DETAIL | A1109 | AX | 2 | 2019-04-04 | CON-BMP-VTRA-010997 | 2019-04-04 | FOR BAPCO REVIEW | 2019-04-18 | 2019-04-24 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000563 | CLASS 2
076551C-000R-MR-0811-102 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | DOOSAN MECATEC CO.LTD | 023V0005 | 18C0090-12-03 | 023-C-GAD-40023-001 | 023V0005 RICH AMINE ACCUMULATOR MANHOLE DETAIL | A1109 | AX | 2 | 2019-04-17 | CON-BMP-VTRA-011209 | 2019-04-17 | FOR BAPCO REVIEW | 2019-05-02 | 2019-05-11 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000658 | CLASS 2
076551C-000R-MR-0811-102 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | DOOSAN MECATEC CO.LTD | 023V0005 | 18C0090-12-04 | 023-C-GAD-40024-001 | 023V0005 RICH AMINE ACCUMULATOR NOZZLE DETAIL (1) | A1109 | AX | 2 | 2019-04-17 | CON-BMP-VTRA-011209 | 2019-04-17 | FOR BAPCO REVIEW | 2019-05-02 | 2019-05-11 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000658 | CLASS 2
076551C-000R-MR-0811-102 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | DOOSAN MECATEC CO.LTD | 023V0005 | 18C0090-12-05 | 023-C-GAD-40025-001 | 023V0005 RICH AMINE ACCUMULATOR NOZZLE DETAIL (2) | A1109 | AX | 2 | 2019-05-06 | CON-BMP-VTRA-011446 | 2019-05-06 | FOR BAPCO REVIEW | 2019-05-21 | 2019-05-29 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000832 | CLASS 2
076551C-000R-MR-0811-102 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | DOOSAN MECATEC CO.LTD | 023V0005 | 18C0090-CAL-12 | 023-C-CAL-40004-001 | STRENGTH CALCULATION FOR RICH AMINE ACCUMULATOR 023V0005 | A1003 | AX | 2 | 2019-04-04 | CON-BMP-VTRA-011001 | 2019-04-04 | FOR BAPCO REVIEW | 2019-04-19 | 2019-04-24 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000551 | CLASS 2
076551C-000R-MR-0811-102 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | DOOSAN MECATEC CO.LTD | 023V0005 | 18C0090-FQCP-12 | 023-C-PQP-40003-001 | FABRICATION AND QUALITY CONTROL PLAN FOR 023V0005 | B1002 | AXX | 2 | 2019-05-06 | CON-BMP-VTRA-011397 | 2019-05-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-102 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | DOOSAN MECATEC CO.LTD | 023V0005 | 18C0090-WPS-12 | 023-C-MCD-40003-001 | WELDING BOOK 023V0005 | B1304 | AXX | 2 | 2019-04-09 | CON-BMP-VTRA-011079 | 2019-04-09 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-102 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | DOOSAN MECATEC CO.LTD | 082V0002 | 18C0090-13-01 | 082-C-GAD-40010-001 | REFINERY SOUTH FLARE SEAL DRUM GENERAL ASSEMBLY 082V0002 | A1103 | AX | 2 | 2019-04-15 | CON-BMP-VTRA-011164 | 2019-04-15 | FOR BAPCO REVIEW | 2019-04-29 | 2019-05-21 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000719 | CLASS 2
076551C-000R-MR-0811-102 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | DOOSAN MECATEC CO.LTD | 082V0002 | 18C0090-13-02 | 082-C-GAD-40011-001 | BODY DETAIL REFINERY SOUTH FLARE SEAL DRUM 082V0002 | A1109 | AX | 2 | 2019-04-08 | CON-BMP-VTRA-011032 | 2019-04-08 | FOR BAPCO REVIEW | 2019-04-22 | 2019-04-25 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000577 | CLASS 2
076551C-000R-MR-0811-102 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | DOOSAN MECATEC CO.LTD | 082V0002 | 18C0090-13-03 | 082-C-GAD-40012-001 | 082V0002 REFINERY SOUTH FLARE SEAL DRUM MANHOLE DETAIL (1) | A1109 | AX | 2 | 2019-04-16 | CON-BMP-VTRA-011196 | 2019-04-16 | FOR BAPCO REVIEW | 2019-04-30 | 2019-05-20 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000715 | CLASS 2
076551C-000R-MR-0811-102 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | DOOSAN MECATEC CO.LTD | 082V0002 | 18C0090-13-03A | 082-C-GAD-40145-001 | 082V0002 REFINERY SOUTH FLARE SEAL DRUM MANHOLE DETAIL (2) | A1109 | AX | 2 | 2019-04-16 | CON-BMP-VTRA-011196 | 2019-04-16 | FOR BAPCO REVIEW | 2019-04-30 | 2019-05-20 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000715 | CLASS 2
076551C-000R-MR-0811-102 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | DOOSAN MECATEC CO.LTD | 082V0002 | 18C0090-13-04 | 082-C-GAD-40013-001 | 082V0002 REFINERY SOUTH FLARE SEAL DRUM NOZZLE DETAIL (1) | A1109 | AX | 2 | 2019-04-16 | CON-BMP-VTRA-011196 | 2019-04-16 | FOR BAPCO REVIEW | 2019-04-30 | 2019-05-20 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000715 | CLASS 2
076551C-000R-MR-0811-102 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | DOOSAN MECATEC CO.LTD | 082V0002 | 18C0090-13-05 | 082-C-GAD-40014-001 | 082V0002 REFINERY SOUTH FLARE SEAL DRUM NOZZLE DETAIL (2) | A1109 | AX | 2 | 2019-04-16 | CON-BMP-VTRA-011196 | 2019-04-16 | FOR BAPCO REVIEW | 2019-04-30 | 2019-05-20 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000715 | CLASS 2
076551C-000R-MR-0811-102 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | DOOSAN MECATEC CO.LTD | 082V0002 | 18C0090-13-06 | 082-C-GAD-40015-001 | 082V0002 REFINERY SOUTH FLARE SEAL DRUM NOZZLE DETAIL (3) | A1109 | AX | 2 | 2019-04-16 | CON-BMP-VTRA-011196 | 2019-04-16 | FOR BAPCO REVIEW | 2019-04-30 | 2019-05-20 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000715 | CLASS 2
076551C-000R-MR-0811-102 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | DOOSAN MECATEC CO.LTD | 082V0002 | 18C0090-13-07 | 082-C-GAD-40016-001 | 082V0002 REFINERY SOUTH FLARE SEAL DRUM NOZZLE DETAIL (4) | A1109 | AX | 2 | 2019-04-16 | CON-BMP-VTRA-011196 | 2019-04-16 | FOR BAPCO REVIEW | 2019-04-30 | 2019-05-20 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000715 | CLASS 2
076551C-000R-MR-0811-102 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | DOOSAN MECATEC CO.LTD | 082V0002 | 18C0090-13-10 | 082-C-DLB-40002-001 | TEMPLATE DETAIL REFINERY SOUTH FLARE SEAL DRUM 082V0002 | A2010 | BX | 2 | 2019-06-07 | CON-BMP-VTRA-012087 | 2019-06-07 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-102 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | DOOSAN MECATEC CO.LTD | 082V0002 | 18C0090-CAL-13 | 082-C-CAL-40006-001 | STRENGTH CALCULATION FOR REFINERY SOUTH FLARE SEAL DRUM 082V0002 | A1003 | AX | 2 | 2019-04-08 | CON-BMP-VTRA-011033 | 2019-04-08 | FOR BAPCO REVIEW | 2019-04-22 | 2019-04-25 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000575 | CLASS 2
076551C-000R-MR-0811-102 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | DOOSAN MECATEC CO.LTD | 082V0002 | 18C0090-FQCP-13 | 082-C-PQP-40003-001 | FABRICATION AND QUALITY CONTROL PLAN FOR 082V0002 | B1002 | AXX | 2 | 2019-05-06 | CON-BMP-VTRA-011397 | 2019-05-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0811-102 | MATERIAL REQUISITION FOR CLADDED AND ALLOY/SS VESSEL | DOOSAN MECATEC CO.LTD | 082V0002 | 18C0090-WPS-13 | 082-C-MCD-40004-001 | WELDING BOOK 082V0002 | B1304 | AXX | 2 | 2019-04-09 | CON-BMP-VTRA-011079 | 2019-04-09 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0841-001 | MATERIAL REQUISITION FOR FILTER | FILTERS | 018V0005A | 190134_DS-001 | 018-C-DAT-40121-001 | FILTER DATA SHEET QUENCH OIL PUMP STRAINERS 018V0005A/B | A1001 | AX | 2 | 2019-06-06 | CON-BMP-VTRA-012031 | 2019-06-06 | FOR BAPCO REVIEW | 2019-06-20 | 2019-06-30 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001112 | CLASS 2
076551C-000R-MR-0841-001 | MATERIAL REQUISITION FOR FILTER | FILTERS | 018V0005A | 190134_DWG-037 | 018-C-GAD-40566-001 | GENERAL ARRANGEMENT DRAWING QUENCH OIL PUMP STRAINER ITEM 018V0005A/B | A2001 | AX | 1 | 2019-05-23 | CON-BMP-VTRA-011734 | 2019-05-23 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0841-001 | MATERIAL REQUISITION FOR FILTER | FILTERS | 018V0005A | 190134_DWG-057 | 018-C-S3D-40001-001 | 3D MODEL FOR ITEM 018V0005A/B | A2013 | AX | 1 | 2019-06-24 | CON-BMP-VTRA-012406 | 2019-06-24 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0841-001 | MATERIAL REQUISITION FOR FILTER | FILTERS | 018V0005A | 190134_MPR-001 | 000-C-MRS-40009-001 | VENDOR MONTHLY PROGRESS REPORTAS OF FEBRUARY 2019 ALL ITEMS | C1002 | BX | 4 | 2019-07-08 | CON-BMP-VTRA-012726 | 2019-07-08 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-0841-001 | MATERIAL REQUISITION FOR FILTER | FILTERS | 018V0005A | 190134_QCP-001 | 000-C-PQP-40012-001 | FABRICATION AND QUALITY CONTROL PLAN ALL ITEMS | B1002 | BX | 2 | 2019-07-08 | CON-BMP-VTRA-012724 | 2019-07-08 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0841-001 | MATERIAL REQUISITION FOR FILTER | FILTERS | 018V0005A | 190134_VDL-001 | 000-C-INX-40013-001 | LIST OF VENDOR¿S DOCUMENTS AND DRAWINGS | A0001 | AX | 2 | 2019-05-17 | CON-BMP-VTRA-011666 | 2019-05-17 | FOR BAPCO REVIEW | 2019-06-03 | 2019-06-01 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000865 | CLASS 2
076551C-000R-MR-0841-001 | MATERIAL REQUISITION FOR FILTER | FILTERS | 018V0005A | 19134_SCH-001 | 000-C-SCH-40008-001 | ENGINEERING,PROCUREMENT,MANUFACTURING & TEST SCHEDULE ALL ITEMS | C1001 | AX | 1 | 2019-05-15 | CON-BMP-VTRA-011621 | 2019-05-15 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-0841-001 | MATERIAL REQUISITION FOR FILTER | FILTERS | 018V0012A | 190134_DS-002 | 018-C-DAT-40122-001 | FILTER DATA SHEET ATMOSPHERIC COLUMN BOTTOMS STRAINERS 018V0012A/B | A1001 | AX | 2 | 2019-06-04 | CON-BMP-VTRA-011967 | 2019-06-04 | FOR BAPCO REVIEW | 2019-06-19 | 2019-06-26 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001046 | CLASS 2
076551C-000R-MR-0841-001 | MATERIAL REQUISITION FOR FILTER | FILTERS | 018V0012A | 190134_DWG-038 | 018-C-GAD-40567-001 | GENERAL ARRANGEMENT DRAWING ATMOSPHERIC COLUMN BOTTOMS STRAINER ITEM 018V0012A/B | A2001 | AX | 1 | 2019-05-23 | CON-BMP-VTRA-011734 | 2019-05-23 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0841-001 | MATERIAL REQUISITION FOR FILTER | FILTERS | 018V0012A | 190134_DWG-058 | 018-C-S3D-40002-001 | 3D MODEL FOR ITEM 018V0012A/B | A2013 | AX | 1 | 2019-06-24 | CON-BMP-VTRA-012406 | 2019-06-24 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0841-001 | MATERIAL REQUISITION FOR FILTER | FILTERS | 018V0015A | 190134_DS-003 | 018-C-DAT-40123-001 | FILTER DATA SHEET LVGO CIRCULATING REFLUX STRAINERS 018V0015A/B | A1001 | AX | 2 | 2019-06-04 | CON-BMP-VTRA-011967 | 2019-06-04 | FOR BAPCO REVIEW | 2019-06-19 | 2019-06-26 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001046 | CLASS 2
076551C-000R-MR-0841-001 | MATERIAL REQUISITION FOR FILTER | FILTERS | 018V0015A | 190134_DWG-039 | 018-C-GAD-40568-001 | GENERAL ARRANGEMENT DRAWING BASKET FILTER ITEM 018V0015A/B | A2001 | AX | 1 | 2019-05-23 | CON-BMP-VTRA-011734 | 2019-05-23 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0841-001 | MATERIAL REQUISITION FOR FILTER | FILTERS | 018V0015A | 190134_DWG-059 | 018-C-S3D-40003-001 | 3D MODEL FOR ITEM 018V0015A/B | A2013 | AX | 1 | 2019-06-24 | CON-BMP-VTRA-012406 | 2019-06-24 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0841-001 | MATERIAL REQUISITION FOR FILTER | FILTERS | 018V0016A | 190134_DS-004 | 018-C-DAT-40124-001 | FILTER DATA SHEET MVGO CIRCULATING REFLUX STRAINER 018V0016A/B | A1001 | AX | 2 | 2019-06-04 | CON-BMP-VTRA-011967 | 2019-06-04 | FOR BAPCO REVIEW | 2019-06-19 | 2019-06-26 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001046 | CLASS 2
076551C-000R-MR-0841-001 | MATERIAL REQUISITION FOR FILTER | FILTERS | 018V0016A | 190134_DWG-040 | 018-C-GAD-40569-001 | GENERAL ARRANGEMENT DRAWING MVGO CIRCULATING REFLUX STRAINER ITEM 018V0016A/B | A2001 | AX | 1 | 2019-05-23 | CON-BMP-VTRA-011734 | 2019-05-23 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0841-001 | MATERIAL REQUISITION FOR FILTER | FILTERS | 018V0016A | 190134_DWG-060 | 018-C-S3D-40004-001 | 3D MODEL FOR ITEM 018V0016A/B | A2013 | AX | 1 | 2019-06-24 | CON-BMP-VTRA-012406 | 2019-06-24 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0841-001 | MATERIAL REQUISITION FOR FILTER | FILTERS | 018V0017A | 190134_DS-005 | 018-C-DAT-40125-001 | FILTER DATA SHEET MVGO PUMPBACK STRAINERS 018V0017A/B | A1001 | AX | 2 | 2019-06-04 | CON-BMP-VTRA-011967 | 2019-06-04 | FOR BAPCO REVIEW | 2019-06-19 | 2019-06-26 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001046 | CLASS 2
076551C-000R-MR-0841-001 | MATERIAL REQUISITION FOR FILTER | FILTERS | 018V0017A | 190134_DWG-041 | 018-C-GAD-40570-001 | GENERAL ARRANGEMENT DRAWING MVGO PUMPBACK STRAINER ITEM 018V0017A/B | A2001 | AX | 1 | 2019-05-23 | CON-BMP-VTRA-011734 | 2019-05-23 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0841-001 | MATERIAL REQUISITION FOR FILTER | FILTERS | 018V0017A | 190134_DWG-061 | 018-C-S3D-40005-001 | 3D MODEL FOR ITEM 018V0017A/B | A2013 | AX | 1 | 2019-06-24 | CON-BMP-VTRA-012406 | 2019-06-24 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0841-001 | MATERIAL REQUISITION FOR FILTER | FILTERS | 018V0018A | 190134_DS-006 | 018-C-DAT-40126-001 | FILTER DATA SHEET HVGO CIRCULATING REFLUX STRAINERS 018V0018A/B | A1001 | AX | 2 | 2019-06-04 | CON-BMP-VTRA-011967 | 2019-06-04 | FOR BAPCO REVIEW | 2019-06-19 | 2019-06-26 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001046 | CLASS 2
076551C-000R-MR-0841-001 | MATERIAL REQUISITION FOR FILTER | FILTERS | 018V0018A | 190134_DWG-042 | 018-C-GAD-40571-001 | GENERAL ARRAGEMENT DRAWING HVGO CIRCULATING REFLUX STRAINER ITEM 018V0018A/B | A2001 | AX | 1 | 2019-05-23 | CON-BMP-VTRA-011734 | 2019-05-23 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0841-001 | MATERIAL REQUISITION FOR FILTER | FILTERS | 018V0018A | 190134_DWG-062 | 018-C-S3D-40006-001 | 3D MODEL FOR ITEM 018V0018A/B | A2013 | AX | 1 | 2019-06-24 | CON-BMP-VTRA-012406 | 2019-06-24 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0841-001 | MATERIAL REQUISITION FOR FILTER | FILTERS | 018V0019A | 190134_DS-007 | 018-C-DAT-40127-001 | FILTER DATA SHEET SECOND STAGE WASH OIL STRAINERS 018V0019A/B | A1001 | AX | 2 | 2019-06-05 | CON-BMP-VTRA-011987 | 2019-06-05 | FOR BAPCO REVIEW | 2019-06-19 | 2019-06-29 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001079 | CLASS 2
076551C-000R-MR-0841-001 | MATERIAL REQUISITION FOR FILTER | FILTERS | 018V0019A | 190134_DWG-043 | 018-C-GAD-40572-001 | GENERAL ARRANGEMENT DRAWING SECOND STAGE WASH OIL STRAINER ITEM 018V0019A/B | A2001 | AX | 1 | 2019-05-23 | CON-BMP-VTRA-011734 | 2019-05-23 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0841-001 | MATERIAL REQUISITION FOR FILTER | FILTERS | 018V0019A | 190134_DWG-063 | 018-C-S3D-40007-001 | 3D MODEL FOR ITEM 018V0019A/B | A2013 | AX | 1 | 2019-06-24 | CON-BMP-VTRA-012406 | 2019-06-24 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0841-001 | MATERIAL REQUISITION FOR FILTER | FILTERS | 018V0020A | 190134_DS-008 | 018-C-DAT-40128-001 | FILTER DATA SHEET FIRST STAGE WASH OIL STRAINERS 018V0020A/B | A1001 | AX | 2 | 2019-06-05 | CON-BMP-VTRA-011987 | 2019-06-05 | FOR BAPCO REVIEW | 2019-06-19 | 2019-06-29 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001079 | CLASS 2
076551C-000R-MR-0841-001 | MATERIAL REQUISITION FOR FILTER | FILTERS | 018V0020A | 190134_DWG-044 | 018-C-GAD-40573-001 | GENERAL ARRANGEMENT DRAWING FIRST STAGE WASH OIL STRAINER ITEM 018V0020A/B | A2001 | AX | 1 | 2019-05-23 | CON-BMP-VTRA-011734 | 2019-05-23 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0841-001 | MATERIAL REQUISITION FOR FILTER | FILTERS | 018V0020A | 190134_DWG-064 | 018-C-S3D-40008-001 | 3D MODEL FOR ITEM 018V0020A/B | A2013 | AX | 1 | 2019-06-24 | CON-BMP-VTRA-012406 | 2019-06-24 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0841-001 | MATERIAL REQUISITION FOR FILTER | FILTERS | 018V0021A | 190134_DS-009 | 018-C-DAT-40129-001 | FILTER DATA SHEET WASH OIL PUMP SUCTION STRAINERS 018V0021A/B | A1001 | AX | 2 | 2019-06-05 | CON-BMP-VTRA-011987 | 2019-06-05 | FOR BAPCO REVIEW | 2019-06-19 | 2019-06-29 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001079 | CLASS 2
076551C-000R-MR-0841-001 | MATERIAL REQUISITION FOR FILTER | FILTERS | 018V0021A | 190134_DWG-045 | 018-C-GAD-40574-001 | GENERAL ARRANGEMENT DRAWING WASH OIL PUMP SUCTION STRAINER ITEM 018V0021A/B | A2001 | AX | 1 | 2019-05-23 | CON-BMP-VTRA-011734 | 2019-05-23 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0841-001 | MATERIAL REQUISITION FOR FILTER | FILTERS | 018V0021A | 190134_DWG-065 | 018-C-S3D-40009-001 | 3D MODEL FOR ITEM 018V0021A/B | A2013 | AX | 1 | 2019-06-24 | CON-BMP-VTRA-012406 | 2019-06-24 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0841-001 | MATERIAL REQUISITION FOR FILTER | FILTERS | 018V0022A | 190134_DS-010 | 018-C-DAT-40130-001 | FILTER DATA SHEET VACUUM COLUMN BOTTOMS STRAINERS 018V0022A/B | A1001 | AX | 2 | 2019-06-05 | CON-BMP-VTRA-011987 | 2019-06-05 | FOR BAPCO REVIEW | 2019-06-19 | 2019-06-29 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001079 | CLASS 2
076551C-000R-MR-0841-001 | MATERIAL REQUISITION FOR FILTER | FILTERS | 018V0022A | 190134_DWG-046 | 018-C-GAD-40575-001 | GENERAL ARRANGEMENT DRAWING VACUUM COLUMN BOTTOMS STRAINER ITEM 018V0022A/B | A2001 | AX | 1 | 2019-05-23 | CON-BMP-VTRA-011734 | 2019-05-23 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0841-001 | MATERIAL REQUISITION FOR FILTER | FILTERS | 018V0022A | 190134_DWG-066 | 018-C-S3D-40010-001 | 3D MODEL FOR ITEM 018V0022A/B | A2013 | AX | 1 | 2019-06-24 | CON-BMP-VTRA-012406 | 2019-06-24 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0841-001 | MATERIAL REQUISITION FOR FILTER | FILTERS | 018V0045A | 190134_DS-011 | 018-C-DAT-40131-001 | FILTER DATA SHEET CIRCULATION OIL FILTERS 018V0045A/B | A1001 | AX | 2 | 2019-06-04 | CON-BMP-VTRA-011967 | 2019-06-04 | FOR BAPCO REVIEW | 2019-06-19 | 2019-06-26 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001046 | CLASS 2
076551C-000R-MR-0841-001 | MATERIAL REQUISITION FOR FILTER | FILTERS | 018V0045A | 190134_DWG-047 | 018-C-GAD-40576-001 | GENERAL ARRANGEMENT DRAWING CIRCULATING OIL FILTERS ITEM 018V0045A/B | A2001 | AX | 1 | 2019-05-23 | CON-BMP-VTRA-011734 | 2019-05-23 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0841-001 | MATERIAL REQUISITION FOR FILTER | FILTERS | 018V0045A | 190134_DWG-067 | 018-C-S3D-40011-001 | 3D MODEL FOR ITEM 018V0045A/B | A2013 | AX | 1 | 2019-06-24 | CON-BMP-VTRA-012406 | 2019-06-24 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0841-001 | MATERIAL REQUISITION FOR FILTER | FILTERS | 018V0046 | 190134_DS-012 | 018-C-DAT-40132-001 | FILTER DATA SHEET EMERGENCY QUENCH OIL FILTER 018V0046 | A1001 | AX | 2 | 2019-06-06 | CON-BMP-VTRA-012031 | 2019-06-06 | FOR BAPCO REVIEW | 2019-06-20 | 2019-06-30 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001112 | CLASS 2
076551C-000R-MR-0841-001 | MATERIAL REQUISITION FOR FILTER | FILTERS | 018V0046 | 190134_DWG-048 | 018-C-GAD-40577-001 | GENERAL ARRANGEMENT DRAWING EMERGENCY QUENCH OIL FILTER ITEM 018V0046 | A2001 | AX | 1 | 2019-05-23 | CON-BMP-VTRA-011734 | 2019-05-23 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0841-001 | MATERIAL REQUISITION FOR FILTER | FILTERS | 018V0046 | 190134_DWG-068 | 018-C-S3D-40012-001 | 3D MODEL FOR ITEM 018V0046 | A2013 | AX | 1 | 2019-06-24 | CON-BMP-VTRA-012406 | 2019-06-24 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0841-001 | MATERIAL REQUISITION FOR FILTER | FILTERS | 018V0048A | 190134_DS-013 | 018-C-DAT-40133-001 | FILTER DATA SHEET CATALYST SLOP OIL FILTERS 018V0048A/B | A1001 | AX | 2 | 2019-06-04 | CON-BMP-VTRA-011967 | 2019-06-04 | FOR BAPCO REVIEW | 2019-06-19 | 2019-06-26 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001046 | CLASS 2
076551C-000R-MR-0841-001 | MATERIAL REQUISITION FOR FILTER | FILTERS | 018V0048A | 190134_DWG-049 | 018-C-GAD-40578-001 | GENERAL ARRANGEMENT DRAWING CATALYST SLOP OIL FILTERS ITEM 018V0048A/B | A2001 | AX | 1 | 2019-05-23 | CON-BMP-VTRA-011734 | 2019-05-23 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0841-001 | MATERIAL REQUISITION FOR FILTER | FILTERS | 018V0048A | 190134_DWG-069 | 018-C-S3D-40013-001 | 3D MODEL FOR ITEM 018V0048A/B | A2013 | AX | 1 | 2019-06-24 | CON-BMP-VTRA-012406 | 2019-06-24 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0841-001 | MATERIAL REQUISITION FOR FILTER | FILTERS | 018V0051A | 190134_DS-014 | 018-C-DAT-40134-001 | FILTER DATA SHEET SHORT CIRCULATION FILTERS 018V0051A/B | A1001 | AX | 2 | 2019-06-04 | CON-BMP-VTRA-011967 | 2019-06-04 | FOR BAPCO REVIEW | 2019-06-19 | 2019-06-26 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001046 | CLASS 2
076551C-000R-MR-0841-001 | MATERIAL REQUISITION FOR FILTER | FILTERS | 018V0051A | 190134_DWG-050 | 018-C-GAD-40579-001 | GENERAL ARRANGEMENT DRAWING SHORT CIRCULATION FILTERS ITEM 018V0051A/B | A2001 | AX | 1 | 2019-05-23 | CON-BMP-VTRA-011734 | 2019-05-23 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0841-001 | MATERIAL REQUISITION FOR FILTER | FILTERS | 018V0051A | 190134_DWG-070 | 018-C-S3D-40014-001 | 3D MODEL FOR ITEM 018V0051A/B | A2013 | AX | 1 | 2019-06-24 | CON-BMP-VTRA-012406 | 2019-06-24 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0841-001 | MATERIAL REQUISITION FOR FILTER | FILTERS | 018V0063 | 190134_DWG-051 | 018-C-GAD-40580-001 | GENERAL ARRANGEMENT DRAWING INSTRUMENT AIR FILTERS ITEM 018V0063 | A2001 | AX | 1 | 2019-05-23 | CON-BMP-VTRA-011734 | 2019-05-23 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0841-001 | MATERIAL REQUISITION FOR FILTER | FILTERS | 018V0063 | 190134_DWG-071 | 018-C-S3D-40015-001 | 3D MODEL FOR ITEM 018V0063 | A2013 | AX | 1 | 2019-06-24 | CON-BMP-VTRA-012406 | 2019-06-24 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0841-001 | MATERIAL REQUISITION FOR FILTER | FILTERS | 018V1015A | 190134_DS-016 | 018-C-DAT-40136-001 | FILTER DATA SHEET TRAIN 1 FEED PUMP STRAINERS 018V1015A/B | A1001 | AX | 2 | 2019-06-04 | CON-BMP-VTRA-011967 | 2019-06-04 | FOR BAPCO REVIEW | 2019-06-19 | 2019-06-26 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001046 | CLASS 2
076551C-000R-MR-0841-001 | MATERIAL REQUISITION FOR FILTER | FILTERS | 018V1015A | 190134_DWG-052 | 018-C-GAD-40581-001 | GENERAL ARRANGEMENT DRAWING TRAIN 1 FEED PUMP STRAINERS ITEM 018V1015A/B | A2001 | AX | 1 | 2019-05-23 | CON-BMP-VTRA-011734 | 2019-05-23 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0841-001 | MATERIAL REQUISITION FOR FILTER | FILTERS | 018V1015A | 190134_DWG-072 | 018-C-S3D-40016-001 | 3D MODEL FOR ITEM 018V1015A/B | A2013 | AX | 1 | 2019-06-24 | CON-BMP-VTRA-012406 | 2019-06-24 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0841-001 | MATERIAL REQUISITION FOR FILTER | FILTERS | 018V2015A | 190134_DS-017 | 018-C-DAT-40137-001 | FILTER DATA SHEET TRAIN 2 FEED PUMP STRAINERS 018V2015A/B | A1001 | AX | 2 | 2019-06-04 | CON-BMP-VTRA-011967 | 2019-06-04 | FOR BAPCO REVIEW | 2019-06-19 | 2019-06-26 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001046 | CLASS 2
076551C-000R-MR-0841-001 | MATERIAL REQUISITION FOR FILTER | FILTERS | 018V2015A | 190134_DWG-053 | 018-C-GAD-40582-001 | GENERAL ARRANGEMENT DRAWING TRAIN 2 FEED PUMP STRAINERS ITEM 018V2015A/B | A2001 | AX | 1 | 2019-05-23 | CON-BMP-VTRA-011734 | 2019-05-23 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0841-001 | MATERIAL REQUISITION FOR FILTER | FILTERS | 018V2015A | 190134_DWG-073 | 018-C-S3D-40017-001 | 3D MODEL FOR ITEM 018V2015A/B | A2013 | AX | 1 | 2019-06-24 | CON-BMP-VTRA-012406 | 2019-06-24 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0841-001 | MATERIAL REQUISITION FOR FILTER | FILTERS | 023V0006 | 190134_DS-018 | 023-C-DAT-40013-001 | FILTER DATA SHEET 1HRU PSA PRODUCT FILTER 023V0006 | A1001 | AX | 2 | 2019-05-10 | CON-BMP-VTRA-011522 | 2019-05-10 | FOR BAPCO REVIEW | 2019-05-27 | 2019-05-27 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000804 | CLASS 2
076551C-000R-MR-0841-001 | MATERIAL REQUISITION FOR FILTER | FILTERS | 023V0006 | 190134_DWG-054 | 023-C-GAD-40030-001 | GENERAL ARRANGEMENT DRAWING HRU PSA PRODUCT FILTER ITEM 023V0006 | A2001 | AX | 1 | 2019-05-23 | CON-BMP-VTRA-011734 | 2019-05-23 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0841-001 | MATERIAL REQUISITION FOR FILTER | FILTERS | 023V0006 | 190134_DWG-074 | 023-C-S3D-40001-001 | 3D MODEL FOR ITEM 023V0006 | A2013 | AX | 1 | 2019-06-24 | CON-BMP-VTRA-012407 | 2019-06-24 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0841-001 | MATERIAL REQUISITION FOR FILTER | FILTERS | 061V6102A | 190134_DS-019 | 061-C-DAT-40006-001 | FILTER DATA SHEET INSTRUMENT AIR FILTERS 061V6102A/B | A1001 | AX | 2 | 2019-06-13 | CON-BMP-VTRA-012202 | 2019-06-13 | FOR BAPCO REVIEW | 2019-06-28 | 2019-06-26 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001039 | CLASS 2
076551C-000R-MR-0841-001 | MATERIAL REQUISITION FOR FILTER | FILTERS | 061V6102A | 190134_DWG-055 | 061-C-GAD-40004-001 | GENERAL ARRANGEMENT DRAWING INSTRUMENT AIR FILTERS ITEM 061V6102A/B | A2001 | AX | 1 | 2019-07-08 | CON-BMP-VTRA-012723 | 2019-07-08 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0841-001 | MATERIAL REQUISITION FOR FILTER | FILTERS | 061V6102A | 190134_DWG-075 | 061-C-S3D-40001-001 | 3D MODEL FOR ITEM 061V6102A/B | A2013 | AX | 1 | 2019-06-24 | CON-BMP-VTRA-012408 | 2019-06-24 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0841-001 | MATERIAL REQUISITION FOR FILTER | FILTERS | 081V8105A | 190134_DS-020 | 081-C-DAT-40004-001 | FILTER DATA SHEET INSTRUMENT AIR FILTERS 081V8105A/B | A1001 | AX | 2 | 2019-06-13 | CON-BMP-VTRA-012203 | 2019-06-13 | FOR BAPCO REVIEW | 2019-06-28 | 2019-06-27 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001059 | CLASS 2
076551C-000R-MR-0841-001 | MATERIAL REQUISITION FOR FILTER | FILTERS | 081V8105A | 190134_DWG-056 | 081-C-GAD-40003-001 | GENERAL ARRANGEMENT DRAWING INSTRUMENT AIR FILTERS ITEM 081V8105A/B | A2001 | AX | 1 | 2019-05-23 | CON-BMP-VTRA-011734 | 2019-05-23 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0841-001 | MATERIAL REQUISITION FOR FILTER | FILTERS | 081V8105A | 190134_DWG-076 | 081-C-S3D-40001-001 | 3D MODEL FOR ITEM 081V8105A/B | A2013 | AX | 1 | 2019-06-24 | CON-BMP-VTRA-012409 | 2019-06-24 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0841-002 | MATERIAL REQUISITION FOR COALESCERS | PARKER KOREA | 021V0001 | PK-BMP-CAL-001 | 021-C-CAL-40032-001 | STRENGTH CALCULATION FOR 021V0001 | A1003 | AX | 2 | 2019-05-20 | CON-BMP-VTRA-011919 | 2019-06-01 | FOR BAPCO REVIEW | 2019-06-17 | 2019-06-18 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000982 | CLASS 2
076551C-000R-MR-0841-002 | MATERIAL REQUISITION FOR COALESCERS | PARKER KOREA | 021V0001 | PK-BMP-DAT-001 | 021-C-DAT-40033-001 | EQUIPMENT FILLED-IN DATA SHEET FOR 021V0001 | A1001 | AX | 2 | 2019-06-04 | CON-BMP-VTRA-011976 | 2019-06-04 | FOR BAPCO REVIEW | 2019-06-19 | 2019-06-27 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001066 | CLASS 2
076551C-000R-MR-0841-002 | MATERIAL REQUISITION FOR COALESCERS | PARKER KOREA | 021V0001 | PK-BMP-GAD-001 | 021-C-GAD-40124-001 | GENERAL ARRANGEMENT DWGS FOR 021V0001 | A1103 | AX | 2 | 2019-06-13 | CON-BMP-VTRA-012180 | 2019-06-13 | FOR BAPCO REVIEW | 2019-06-27 | 2019-07-07 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001179 | CLASS 2
076551C-000R-MR-0841-002 | MATERIAL REQUISITION FOR COALESCERS | PARKER KOREA | 021V0001 | PK-BMP-INX-001 | 021-C-INX-40004-001 | LIST OF VENDOR'S DOCUMENTS AND DWGS ALL ITEMS | A0001 | BX | 2 | 2019-05-15 | CON-BMP-VTRA-011616 | 2019-05-15 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0841-002 | MATERIAL REQUISITION FOR COALESCERS | PARKER KOREA | 021V0001 | PK-BMP-PQP-001 | 021-C-PQP-40016-001 | FABRICATION AND QUALITY CONTROL PLAN ALL ITEMS | B1002 | AX | 2 | 2019-05-22 | CON-BMP-VTRA-011731 | 2019-05-22 | FOR BAPCO REVIEW | 2019-06-06 | 2019-06-03 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000878 | CLASS 2
076551C-000R-MR-0841-002 | MATERIAL REQUISITION FOR COALESCERS | PARKER KOREA | 021V0001 | PK-BMP-PRO-001 | 021-C-PRO-40001-001 | NON DESTRUCTIVE PROCEDURE ALL ITEMS | B1202 | AX | 2 | 2019-05-24 | CON-BMP-VTRA-011796 | 2019-05-24 | FOR BAPCO REVIEW | 2019-06-10 | 2019-06-04 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000884 | CLASS 2
076551C-000R-MR-0841-002 | MATERIAL REQUISITION FOR COALESCERS | PARKER KOREA | 021V0001 | PK-BMP-PRO-002 | 021-C-PRO-40002-001 | HYDRO TEST PROCEDURE ALL ITEM | B1103 | BX | 2 | 2019-07-08 | CON-BMP-VTRA-012728 | 2019-07-08 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0841-002 | MATERIAL REQUISITION FOR COALESCERS | PARKER KOREA | 021V0001 | PK-BMP-PRO-003 | 021-C-TSP-40005-001 | PAINTING SPECIFICATION AND PROCEDURE ALL ITEMS | A0106 | AX | 1 | 2019-05-15 | CON-BMP-VTRA-011618 | 2019-05-15 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0841-002 | MATERIAL REQUISITION FOR COALESCERS | PARKER KOREA | 021V0001 | PK-BMP-SCH-001 | 021-C-SCH-40002-001 | ENGINEERING PROCUREMENT MANUFACTURING & TEST SCHEDULE FOR COALESCER ALL ITEMS | C1001 | AX | 4 | 2019-07-08 | CON-BMP-VTRA-012730 | 2019-07-08 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-0841-002 | MATERIAL REQUISITION FOR COALESCERS | PARKER KOREA | 021V0001 | PK-BMP-SCH-002 | 021-C-MRS-40001-001 | MONTHLY PROGRESS REPORT ALL ITEMS | C1002 | CX | 1 | 2019-06-27 | CON-BMP-VTRA-012537 | 2019-06-27 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-0841-002 | MATERIAL REQUISITION FOR COALESCERS | PARKER KOREA | 021V0011 | PK-BMP-CAL-002 | 021-C-CAL-40033-001 | STRENGTH CALCULATION FOR 021V0011 | A1003 | AX | 2 | 2019-05-20 | CON-BMP-VTRA-011919 | 2019-06-01 | FOR BAPCO REVIEW | 2019-06-17 | 2019-06-18 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000982 | CLASS 2
076551C-000R-MR-0841-002 | MATERIAL REQUISITION FOR COALESCERS | PARKER KOREA | 021V0011 | PK-BMP-DAT-002 | 021-C-DAT-40034-001 | EQUIPMENT FILLED-IN DATA SHEET FOR 021V0011 | A1001 | AX | 2 | 2019-06-04 | CON-BMP-VTRA-011976 | 2019-06-04 | FOR BAPCO REVIEW | 2019-06-19 | 2019-06-27 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001066 | CLASS 2
076551C-000R-MR-0841-002 | MATERIAL REQUISITION FOR COALESCERS | PARKER KOREA | 021V0011 | PK-BMP-GAD-002 | 021-C-GAD-40128-001 | GENERAL ARRANGEMENT DWGS FOR 021V0011 | A1103 | AX | 2 | 2019-06-13 | CON-BMP-VTRA-012180 | 2019-06-13 | FOR BAPCO REVIEW | 2019-06-27 | 2019-07-07 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001179 | CLASS 2
076551C-000R-MR-0841-002 | MATERIAL REQUISITION FOR COALESCERS | PARKER KOREA | 021V0012 | PK-BMP-CAL-003 | 021-C-CAL-40034-001 | STRENGTH CALCULATION FOR 021V0012 | A1003 | AX | 2 | 2019-06-07 | CON-BMP-VTRA-012088 | 2019-06-07 | FOR BAPCO REVIEW | 2019-06-21 | 2019-07-02 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001136 | CLASS 2
076551C-000R-MR-0841-002 | MATERIAL REQUISITION FOR COALESCERS | PARKER KOREA | 021V0012 | PK-BMP-DAT-003 | 021-C-DAT-40035-001 | EQUIPMENT FILLED-IN DATA SHEET FOR 021V0012 | A1001 | AX | 2 | 2019-06-04 | CON-BMP-VTRA-011976 | 2019-06-04 | FOR BAPCO REVIEW | 2019-06-19 | 2019-06-27 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001066 | CLASS 2
076551C-000R-MR-0841-002 | MATERIAL REQUISITION FOR COALESCERS | PARKER KOREA | 021V0012 | PK-BMP-GAD-003 | 021-C-GAD-40132-001 | GENERAL ARRANGEMENT DWGS FOR 021V0012 | A1103 | AX | 2 | 2019-06-13 | CON-BMP-VTRA-012180 | 2019-06-13 | FOR BAPCO REVIEW | 2019-06-27 | 2019-07-07 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001179 | CLASS 2
076551C-000R-MR-0841-002 | MATERIAL REQUISITION FOR COALESCERS | PARKER KOREA | 021V0051A | PK-BMP-CAL-004 | 021-C-CAL-40035-001 | STRENGTH CALCULATION FOR 021V0051 A/B | A1003 | AX | 2 | 2019-06-07 | CON-BMP-VTRA-012088 | 2019-06-07 | FOR BAPCO REVIEW | 2019-06-21 | 2019-07-02 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001136 | CLASS 2
076551C-000R-MR-0841-002 | MATERIAL REQUISITION FOR COALESCERS | PARKER KOREA | 021V0051A | PK-BMP-DAT-004 | 021-C-DAT-40036-001 | EQUIPMENT FILLED-IN DATA SHEET FOR 021V0051A/B | A1001 | AX | 2 | 2019-06-04 | CON-BMP-VTRA-011977 | 2019-06-04 | FOR BAPCO REVIEW | 2019-06-19 | 2019-06-27 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001054 | CLASS 2
076551C-000R-MR-0841-002 | MATERIAL REQUISITION FOR COALESCERS | PARKER KOREA | 021V0051A | PK-BMP-GAD-004 | 021-C-GAD-40136-001 | GENERAL ARRANGEMENT DWGS FOR 021V0051A/B | A1103 | AX | 2 | 2019-06-13 | CON-BMP-VTRA-012180 | 2019-06-13 | FOR BAPCO REVIEW | 2019-06-27 | 2019-07-07 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001179 | CLASS 2
076551C-000R-MR-0841-002 | MATERIAL REQUISITION FOR COALESCERS | PARKER KOREA | 021V0052A | PK-BMP-CAL-005 | 021-C-CAL-40036-001 | STRENGTH CALCULATION FOR 021V0052A/B | A1003 | AX | 2 | 2019-06-07 | CON-BMP-VTRA-012088 | 2019-06-07 | FOR BAPCO REVIEW | 2019-06-21 | 2019-07-02 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001136 | CLASS 2
076551C-000R-MR-0841-002 | MATERIAL REQUISITION FOR COALESCERS | PARKER KOREA | 021V0052A | PK-BMP-DAT-005 | 021-C-DAT-40037-001 | EQUIPMENT FILLED-IN DATA SHEET FOR 021V0052A/B | A1001 | AX | 2 | 2019-06-04 | CON-BMP-VTRA-011977 | 2019-06-04 | FOR BAPCO REVIEW | 2019-06-19 | 2019-06-27 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001054 | CLASS 2
076551C-000R-MR-0841-002 | MATERIAL REQUISITION FOR COALESCERS | PARKER KOREA | 021V0052A | PK-BMP-GAD-005 | 021-C-GAD-40140-001 | GENERAL ARRANGEMENT DWGS FOR 021V0052A/B | A1103 | AX | 2 | 2019-06-13 | CON-BMP-VTRA-012180 | 2019-06-13 | FOR BAPCO REVIEW | 2019-06-27 | 2019-07-07 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001179 | CLASS 2
076551C-000R-MR-0846-001 | MATERIAL REQUISITION FOR FEED FILTERS | FILTRATION GROUP PROCESS INC | 021U0001 | 021-S-CAL-00001-001 | 021-S-CAL-00004-001 | CALCULATION NOTES 021U0001 | A1003 | AX | 2 | 2018-11-23 | CON-BMP-VTRA-010068 | 2018-11-23 | FOR BAPCO REVIEW | 2018-12-08 | 2018-12-06 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000052 | CLASS 2
076551C-000R-MR-0846-001 | MATERIAL REQUISITION FOR FEED FILTERS | FILTRATION GROUP PROCESS INC | 021U0001 | 021-S-CWD-00001-001 | 021-S-CWD-40001-001 | WIRING DWGS (INTERNAL AND/OR INTERPANEL) 021U0001 | A4211 | AX | 1 | 2019-02-28 | CON-BMP-VTRA-010546 | 2019-02-28 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0846-001 | MATERIAL REQUISITION FOR FEED FILTERS | FILTRATION GROUP PROCESS INC | 021U0001 | 021-S-DAT-00001-001 | 021-S-DAT-40006-001 | NOISE DATA SHEET 021U0001 (EX BAPCO DOC N. 021-S-DAT-00006-001) | A0105 | 0X | 2 | 2019-06-26 | CON-BMP-VTRA-012464 | 2019-06-26 | FOR BAPCO REVIEW | 2019-07-10 |  |  | CLASS 2
076551C-000R-MR-0846-001 | MATERIAL REQUISITION FOR FEED FILTERS | FILTRATION GROUP PROCESS INC | 021U0001 | 021-S-DAT-00002-001 | 021-S-DAT-40007-001 | EQPT FILLED-IN DATA SHEETS 021U0001 (EX BAPCO DOC. N. 021-S-DAT-00007-001) | A1001 | BX | 2 | 2019-04-30 | CON-BMP-VTRA-011328 | 2019-04-30 | FOR BAPCO REVIEW | 2019-05-16 | 2019-05-23 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000747 | CLASS 2
076551C-000R-MR-0846-001 | MATERIAL REQUISITION FOR FEED FILTERS | FILTRATION GROUP PROCESS INC | 021U0001 | 021-S-DAT-00005-001 | 021-S-RPT-40001-001 | UTILITY BALANCE 021U0001 (EX BAPCO N.021-S-INX-00003-001) | A1014 | 0X | 2 | 2019-04-30 | CON-BMP-VTRA-011327 | 2019-04-30 | FOR BAPCO REVIEW | 2019-05-16 | 2019-05-23 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000730 | CLASS 2
076551C-000R-MR-0846-001 | MATERIAL REQUISITION FOR FEED FILTERS | FILTRATION GROUP PROCESS INC | 021U0001 | 021-S-GAD-00001-001 | 021-S-GAD-40007-001 | GENERAL ARRANGEMENT & FOUNDATION LAYOUT 021U001 (EX BAPO CODE N. 021-S-GAD-00007- 001) | A2001 | BX | 2 | 2019-03-25 | CON-BMP-VTRA-010829 | 2019-03-25 | FOR BAPCO REVIEW | 2019-04-08 | 2019-04-09 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000489 | CLASS 2
076551C-000R-MR-0846-001 | MATERIAL REQUISITION FOR FEED FILTERS | FILTRATION GROUP PROCESS INC | 021U0001 | 021-S-GAD-00008-001 | 021-S-GAD-40008-001 | TERMINAL BOX DETAIL DWG WITH TERMINATION DETAILS 021U0001 | A4206 | AX | 1 | 2019-05-02 | CON-BMP-VTRA-011332 | 2019-05-02 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0846-001 | MATERIAL REQUISITION FOR FEED FILTERS | FILTRATION GROUP PROCESS INC | 021U0001 | 021-S-GEN-00001-001 | 021-S-TSP-40001-001 | PAINTING SPECIFICATION 021U0001 (EX BAPCO DOC N. 021- S-TSP-00001-001) | A0106 | CX | 1 | 2019-05-02 | CON-BMP-VTRA-011334 | 2019-05-02 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0846-001 | MATERIAL REQUISITION FOR FEED FILTERS | FILTRATION GROUP PROCESS INC | 021U0001 | 021-S-GEN-00002-001 | 021-S-TSP-40002-001 | INSULATION SPECIFICATION 021U0001 | A0107 | AX | 2 | 2019-03-27 | CON-BMP-VTRA-010876 | 2019-03-27 | FOR BAPCO REVIEW | 2019-04-10 | 2019-04-14 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000511 | CLASS 2
076551C-000R-MR-0846-001 | MATERIAL REQUISITION FOR FEED FILTERS | FILTRATION GROUP PROCESS INC | 021U0001 | 021-S-GUI-00001-001 | 021-S-TSP-40003-001 | CONTROL SYSTEM DESCR OPER PRINCIPLES FUNCT DESIGN SPEC 021U001 (EX BAPCO DOC N. 021-S-TSP-00003-001) | A3501 | BX | 2 | 2019-06-22 | CON-BMP-VTRA-012373 | 2019-06-22 | FOR BAPCO REVIEW | 2019-07-08 |  |  | CLASS 2
076551C-000R-MR-0846-001 | MATERIAL REQUISITION FOR FEED FILTERS | FILTRATION GROUP PROCESS INC | 021U0001 | 021-S-INX-00001-001 | 021-S-INX-40001-001 | LIST OF VENDORS DOCUMENTS AND DWGS 021U001 (EX BAPCO DOC. N. 021-S-INX-00001-001) | A0001 | CX | 2 | 2019-04-29 | CON-BMP-VTRA-011322 | 2019-04-29 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0846-001 | MATERIAL REQUISITION FOR FEED FILTERS | FILTRATION GROUP PROCESS INC | 021U0001 | 021-S-MRS-00001-001 | 021-S-MRS-40001-001 | MONTHLY PROGRESS REPORT 021U001 (EX BAPCO N. 021-S-MRS-00001-001) | C1002 | DX | 2 | 2019-05-02 | CON-BMP-VTRA-011336 | 2019-05-02 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-0846-001 | MATERIAL REQUISITION FOR FEED FILTERS | FILTRATION GROUP PROCESS INC | 021U0001 | 021-S-PID-00001-001 | 021-S-PID-40001-001 | PIPING AND INSTRUMENT DIAGRAMS 021U001 (EX BAPCO DOC N. 021-S-PID-00001-001) | A0103 | BX | 2 | 2019-02-28 | CON-BMP-VTRA-010547 | 2019-02-28 | FOR BAPCO REVIEW | 2019-03-15 | 2019-03-20 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000352 | CLASS 2
076551C-000R-MR-0846-001 | MATERIAL REQUISITION FOR FEED FILTERS | FILTRATION GROUP PROCESS INC | 021U0001 | 021-S-PQP-00001-001 | 021-S-PQP-00001-001 | INSPECTION AND TEST PLAN 021U0001 | B1002 | AX | 2 | 2018-11-23 | CON-BMP-VTRA-010077 | 2018-11-23 | FOR BAPCO REVIEW | 2018-12-08 | 2018-12-13 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000060 | CLASS 2
076551C-000R-MR-0846-001 | MATERIAL REQUISITION FOR FEED FILTERS | FILTRATION GROUP PROCESS INC | 021U0001 | 021-S-PRO-00001-001 | 021-S-PRO-40001-001 | TESTING PROCEDURES 021U0001 | B1103 | AX | 2 | 2019-04-12 | CON-BMP-VTRA-011153 | 2019-04-12 | FOR BAPCO REVIEW | 2019-04-29 | 2019-04-25 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000570 | CLASS 2
076551C-000R-MR-0846-001 | MATERIAL REQUISITION FOR FEED FILTERS | FILTRATION GROUP PROCESS INC | 021U0001 | 021-S-PRO-00002-001 | 021-S-PRO-40002-001 | PWHT PROCEDURE 021U0001 | B1201 | AX | 1 | 2019-05-02 | CON-BMP-VTRA-011333 | 2019-05-02 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0846-001 | MATERIAL REQUISITION FOR FEED FILTERS | FILTRATION GROUP PROCESS INC | 021U0001 | 021-S-PRO-00003-001 | 021-S-PRO-40003-001 | NDT PROCEDURE 021U0001 | B1202 | AX | 2 | 2019-05-02 | CON-BMP-VTRA-011335 | 2019-05-02 | FOR BAPCO REVIEW | 2019-05-16 | 2019-05-13 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000665 | CLASS 2
076551C-000R-MR-0846-001 | MATERIAL REQUISITION FOR FEED FILTERS | FILTRATION GROUP PROCESS INC | 021U0001 | 021-S-QDR-00001-001 | 021-S-MCD-40004-001 | WELDING BOOK (MAP PROCEDURE QUALIFICATION REPORT) 021U0001 | B1304 | AX | 2 | 2019-01-21 | CON-BMP-VTRA-010256 | 2019-01-21 | FOR BAPCO REVIEW | 2019-02-04 | 2019-01-27 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000131 | CLASS 2
076551C-000R-MR-0846-001 | MATERIAL REQUISITION FOR FEED FILTERS | FILTRATION GROUP PROCESS INC | 021U0001 | 021-S-S3D-00001-001 | 021-S-S3D-40001-001 | 3D EQUIPMENT MODEL 021U0001 (EX BAPCO N. 021-S-S3D-00001-001) | A2013 | BX | 2 | 2019-04-26 | CON-BMP-VTRA-011256 | 2019-04-26 | FOR BAPCO REVIEW | 2019-05-10 | 2019-05-15 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000673 | CLASS 2
076551C-000R-MR-0846-001 | MATERIAL REQUISITION FOR FEED FILTERS | FILTRATION GROUP PROCESS INC | 021U0001 | 021-S-SCH-00001-001 | 021-S-SCH-40001-001 | ENGINEERING PROCUREMENT MANUFACTURING & TEST SCHEDULE 021U0001 (EX BAPCO CODE 021-S-SCH-00001-001) | C1001 | CX | 4 | 2019-05-02 | CON-BMP-VTRA-011338 | 2019-05-02 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-0846-001 | MATERIAL REQUISITION FOR FEED FILTERS | FILTRATION GROUP PROCESS INC | 021U0001 | C4049 | 021-S-GAD-40005-001 | CROSS SECT. ASSEMBLY DRAWINGS AND PRESSURE VESSEL CONSTR. DRAWINGS 021U0001 (EX BAPCO DOC N. 021-S-GAD-00005-001) | A1101 | CX | 2 | 2019-04-30 | CON-BMP-VTRA-011330 | 2019-04-30 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0851-001 | MATERIAL REQUISITION FOR VACUUM UNIT PACKAGE | GRAHAM CORPORATION | 018E0016A | 69431-0071 | 018-H-DAT-40004-001 | 018E0016A/B/C 1ST INTERSTAGE VACUUM CONDENSERS EQUIPMENT DATA SHEET (EX BAPCO DOC N¿018-H-DAT-00004-001) | A1001 | BX | 2 | 2019-06-17 | CON-BMP-VTRA-012242 | 2019-06-17 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0851-001 | MATERIAL REQUISITION FOR VACUUM UNIT PACKAGE | GRAHAM CORPORATION | 018E0016A | 69431-0400 | 018-H-GAD-40002-001 | 018E00016A/B/C 60X324 AXS 1ST INTERSTAGE VACUUM CONDENSER GENERAL ARRANGEMENT & CROSS SECTIONAL DRAWING | A1101 | BX | 2 | 2019-06-21 | CON-BMP-VTRA-012346 | 2019-06-21 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0851-001 | MATERIAL REQUISITION FOR VACUUM UNIT PACKAGE | GRAHAM CORPORATION | 018E0016A | 69431-0401 | 018-H-CAL-40002-001 | 018E0016A/B/C 60X324 AXS 1ST INTERSTAGE VACUUM CONDENSER MECHANICAL CALCULATIONS | A1003 | AX | 2 | 2019-03-29 | CON-BMP-VTRA-010904 | 2019-03-29 | FOR BAPCO REVIEW | 2019-04-15 | 2019-04-16 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000523 | CLASS 2
076551C-000R-MR-0851-001 | MATERIAL REQUISITION FOR VACUUM UNIT PACKAGE | GRAHAM CORPORATION | 018E0017 | 69431-0072 | 018-H-DAT-40005-001 | 018E00017 2ND INTERSTAGE VACUUM CONDENSER EQUIPMENT DATA SHEET (EX BAPCO DOC N¿ 018-H-DAT-00005-001) | A1001 | BX | 2 | 2019-06-17 | CON-BMP-VTRA-012242 | 2019-06-17 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0851-001 | MATERIAL REQUISITION FOR VACUUM UNIT PACKAGE | GRAHAM CORPORATION | 018E0017 | 69431-1000 | 018-H-GAD-40004-001 | 018E0017 37X 252 AXS 2ND INTERSTAGE VACUUM CONDENSER GENERAL ARRANGEMENT & CROSS SECTIONAL DRAWING | A1101 | BX | 2 | 2019-06-21 | CON-BMP-VTRA-012346 | 2019-06-21 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0851-001 | MATERIAL REQUISITION FOR VACUUM UNIT PACKAGE | GRAHAM CORPORATION | 018E0017 | 69431-1001 | 018-H-CAL-40004-001 | 018E0017 37X 252 AXS 2ND INTERSTAGE VACUUM CONDENSER MECHANICAL CALCULATIONS | A1003 | AX | 2 | 2019-03-29 | CON-BMP-VTRA-010904 | 2019-03-29 | FOR BAPCO REVIEW | 2019-04-15 | 2019-04-16 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000523 | CLASS 2
076551C-000R-MR-0851-001 | MATERIAL REQUISITION FOR VACUUM UNIT PACKAGE | GRAHAM CORPORATION | 018E0018 | 69431-0073 | 018-H-DAT-40006-001 | 018E0018 3RD STAGE VACUUM CONDENSER EQUIPMENT DATA SHEET (EX BAPCO DOC N¿ 018-H-DAT-00006-001) | A1001 | BX | 2 | 2019-06-17 | CON-BMP-VTRA-012242 | 2019-06-17 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0851-001 | MATERIAL REQUISITION FOR VACUUM UNIT PACKAGE | GRAHAM CORPORATION | 018E0018 | 69431-1400 | 018-H-GAD-40006-001 | 018E0018 28X 240 AES 3RD STAGE VACUUM CONDENSER GENERAL ARRANGEMENT & CROSS SECTIONAL DRAWING | A1101 | BX | 2 | 2019-06-21 | CON-BMP-VTRA-012346 | 2019-06-21 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0851-001 | MATERIAL REQUISITION FOR VACUUM UNIT PACKAGE | GRAHAM CORPORATION | 018E0018 | 69431-1401 | 018-H-CAL-40006-001 | 018E0018 28X 240 AES 3RD STAGE VACUUM CONDENSER MECHANICAL CALCULATIONS | A1003 | AX | 2 | 2019-03-29 | CON-BMP-VTRA-010904 | 2019-03-29 | FOR BAPCO REVIEW | 2019-04-15 | 2019-04-16 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000523 | CLASS 2
076551C-000R-MR-0851-001 | MATERIAL REQUISITION FOR VACUUM UNIT PACKAGE | GRAHAM CORPORATION | 018H0001A | 69431-0070 | 018-H-DAT-40003-001 | 018H1801A/B/C 018H1802A/B/C 018H1803A/B/C EJECTOR EQUIPMENT DATA SHEET (ALL STAGES) (EX BAPCO DOC N¿018-H-DAT-00003) | A1001 | BX | 2 | 2019-06-17 | CON-BMP-VTRA-012242 | 2019-06-17 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0851-001 | MATERIAL REQUISITION FOR VACUUM UNIT PACKAGE | GRAHAM CORPORATION | 018H0001A | 69431-0100 | 018-H-GAD-40001-001 | 018H0001A/B/C 1ST STAGE VACUUM EJECTOR GENERAL ARRANGEMENT & CROSS SECTIONAL DRAWING | A1101 | BX | 2 | 2019-06-21 | CON-BMP-VTRA-012346 | 2019-06-21 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0851-001 | MATERIAL REQUISITION FOR VACUUM UNIT PACKAGE | GRAHAM CORPORATION | 018H0001A | 69431-0101 | 018-H-CAL-40001-001 | 018H1801A/B/C 1ST STAGE VACUUM EJECTOR MECHANICAL CALCULATIONS | A1003 | AX | 2 | 2019-03-29 | CON-BMP-VTRA-010904 | 2019-03-29 | FOR BAPCO REVIEW | 2019-04-15 | 2019-04-16 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000523 | CLASS 2
076551C-000R-MR-0851-001 | MATERIAL REQUISITION FOR VACUUM UNIT PACKAGE | GRAHAM CORPORATION | 018H0002A | 69431-0700 | 018-H-GAD-40003-001 | 018H0002A/B/C 2ND STAGE VACUUM EJECTOR GENERAL ARRANGEMENT & CROSS SECTIONAL DRAWING | A1101 | BX | 2 | 2019-06-21 | CON-BMP-VTRA-012346 | 2019-06-21 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0851-001 | MATERIAL REQUISITION FOR VACUUM UNIT PACKAGE | GRAHAM CORPORATION | 018H0002A | 69431-0701 | 018-H-CAL-40003-001 | 018H0002A/B/C 2ND STAGE VACUUM EJECTOR MECHANICAL CALCULATIONS | A1003 | AX | 2 | 2019-03-29 | CON-BMP-VTRA-010904 | 2019-03-29 | FOR BAPCO REVIEW | 2019-04-15 | 2019-04-16 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000523 | CLASS 2
076551C-000R-MR-0851-001 | MATERIAL REQUISITION FOR VACUUM UNIT PACKAGE | GRAHAM CORPORATION | 018H0003A | 69431-1100 | 018-H-GAD-40005-001 | 018H0003A/B/C 3RD STAGE VACUUM EJECTOR GENERAL ARRANGEMENT & CROSS SECTIONAL DRAWING | A1101 | BX | 2 | 2019-06-21 | CON-BMP-VTRA-012346 | 2019-06-21 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0851-001 | MATERIAL REQUISITION FOR VACUUM UNIT PACKAGE | GRAHAM CORPORATION | 018H0003A | 69431-1101 | 018-H-CAL-40005-001 | 018H0003A/B/C 3RD STAGE VACUUM EJECTOR MECHANICAL CALCULATIONS | A1003 | AX | 2 | 2019-03-29 | CON-BMP-VTRA-010904 | 2019-03-29 | FOR BAPCO REVIEW | 2019-04-15 | 2019-04-16 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000523 | CLASS 2
076551C-000R-MR-0851-001 | MATERIAL REQUISITION FOR VACUUM UNIT PACKAGE | GRAHAM CORPORATION | 018U0001 | 17177-78-NDEPROCEDURES | 000-H-PRO-60003-001 | NDE PROCEDURES 018U0001 021U0002 | B1202 | BX | 2 | 2019-06-01 | CON-BMP-VTRA-011913 | 2019-06-01 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0851-001 | MATERIAL REQUISITION FOR VACUUM UNIT PACKAGE | GRAHAM CORPORATION | 018U0001 | 17177-QATESTING | 000-H-PRO-60001-001 | QA TESTING PROCEDURES 018U0001 021U0002 | B1103 | BX | 2 | 2019-06-01 | CON-BMP-VTRA-011915 | 2019-06-01 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0851-001 | MATERIAL REQUISITION FOR VACUUM UNIT PACKAGE | GRAHAM CORPORATION | 018U0001 | 17177-QIP | 018-H-PQP-40001-001 | 018U0001 QUAILITY INSPECTION AND TEST PLAN | B1002 | BX | 2 | 2019-06-01 | CON-BMP-VTRA-011914 | 2019-06-01 | FOR BAPCO REVIEW | 2019-06-17 | 2019-06-10 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000911 | CLASS 2
076551C-000R-MR-0851-001 | MATERIAL REQUISITION FOR VACUUM UNIT PACKAGE | GRAHAM CORPORATION | 018U0001 | 17177-WELD BOOK | 018-H-MCD-40003-001 | 018U0001 WELD BOOK (WELD MAPS/WPS/PQR) 17177 | B1304 | AX | 2 | 2019-06-14 | CON-BMP-VTRA-012217 | 2019-06-14 | FOR BAPCO REVIEW | 2019-06-28 | 2019-06-29 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001070 | CLASS 2
076551C-000R-MR-0851-001 | MATERIAL REQUISITION FOR VACUUM UNIT PACKAGE | GRAHAM CORPORATION | 018U0001 | 69431-0010 | 018-H-PID-00001-001 | 018U0001 PIPING & INSTRUMENTATION DIAGRAM COMMON VACUUM SYSTEM EJECTOR/CONDENSER | A0103 | BX | 2 | 2019-06-10 | CON-BMP-VTRA-012112 | 2019-06-10 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0851-001 | MATERIAL REQUISITION FOR VACUUM UNIT PACKAGE | GRAHAM CORPORATION | 018U0001 | 69431-0074 | 018-H-INX-40001-001 | 018U0001 UTILITY BALANCE (EX BAPCO DOC N. 018-H-INX-00001-001) | A1014 | BX | 2 | 2019-06-17 | CON-BMP-VTRA-012243 | 2019-06-17 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0851-001 | MATERIAL REQUISITION FOR VACUUM UNIT PACKAGE | GRAHAM CORPORATION | 021E0020 | 69432-0071 | 021-H-DAT-40004-001 | 021E00020 WATER COOLED PRECONDENSER | A1001 | AX | 2 | 2019-04-03 | CON-BMP-VTRA-010968 | 2019-04-03 | FOR BAPCO REVIEW | 2019-04-17 | 2019-04-30 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000618 | CLASS 2
076551C-000R-MR-0851-001 | MATERIAL REQUISITION FOR VACUUM UNIT PACKAGE | GRAHAM CORPORATION | 021E0020 | 69432-0100 | 021-H-GAD-40001-001 | 60X 288 AXS 021E0020 WATER COOLED PRECONDENSER GENERAL ARRANGEMENT & CROSS SECTIONAL DRAWING | A1101 | BX | 2 | 2019-06-21 | CON-BMP-VTRA-012347 | 2019-06-21 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0851-001 | MATERIAL REQUISITION FOR VACUUM UNIT PACKAGE | GRAHAM CORPORATION | 021E0020 | 69432-0101 | 021-H-CAL-40001-001 | 60X 288 AES 021E00020 WATER COOLED PRECONDENSER MECHANICAL CALCULATIONS | A1003 | AX | 2 | 2019-03-29 | CON-BMP-VTRA-010904 | 2019-03-29 | FOR BAPCO REVIEW | 2019-04-15 | 2019-04-16 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000523 | CLASS 2
076551C-000R-MR-0851-001 | MATERIAL REQUISITION FOR VACUUM UNIT PACKAGE | GRAHAM CORPORATION | 021E0021 | 69432-0072 | 021-H-DAT-40005-001 | 021E0021 INTER WATER COOLED CONDENSER | A1001 | AX | 2 | 2019-04-03 | CON-BMP-VTRA-010968 | 2019-04-03 | FOR BAPCO REVIEW | 2019-04-17 | 2019-04-30 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000618 | CLASS 2
076551C-000R-MR-0851-001 | MATERIAL REQUISITION FOR VACUUM UNIT PACKAGE | GRAHAM CORPORATION | 021E0021 | 69432-0400 | 021-H-GAD-40003-001 | 44X 228 AXS 021E0021 INTERWATER COOLED CONDENSER GENERAL ARRANGEMENT & CROSS SECTIONAL DRAWING | A1101 | BX | 2 | 2019-06-21 | CON-BMP-VTRA-012347 | 2019-06-21 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0851-001 | MATERIAL REQUISITION FOR VACUUM UNIT PACKAGE | GRAHAM CORPORATION | 021E0021 | 69432-0401 | 021-H-CAL-40003-001 | 44X 228 AES 021E0021 INTERWATER COOLED CONDENSER MECHANICAL CALCULATIONS | A1003 | AX | 2 | 2019-03-29 | CON-BMP-VTRA-010904 | 2019-03-29 | FOR BAPCO REVIEW | 2019-04-15 | 2019-04-16 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000523 | CLASS 2
076551C-000R-MR-0851-001 | MATERIAL REQUISITION FOR VACUUM UNIT PACKAGE | GRAHAM CORPORATION | 021E0022 | 69432-0073 | 021-H-DAT-40006-001 | 021E0022 AFTER WATER COOLED CONDENSER | A1001 | AX | 2 | 2019-04-03 | CON-BMP-VTRA-010968 | 2019-04-03 | FOR BAPCO REVIEW | 2019-04-17 | 2019-04-30 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000618 | CLASS 2
076551C-000R-MR-0851-001 | MATERIAL REQUISITION FOR VACUUM UNIT PACKAGE | GRAHAM CORPORATION | 021E0022 | 69432-0700 | 021-H-GAD-40005-001 | 28X 168 AES 021E0022 AFTER WATER COOLED CONDENSER GENERAL ARRANGEMENT & CROSS SECTIONAL DRAWING | A1101 | BX | 2 | 2019-06-21 | CON-BMP-VTRA-012347 | 2019-06-21 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0851-001 | MATERIAL REQUISITION FOR VACUUM UNIT PACKAGE | GRAHAM CORPORATION | 021E0022 | 69432-0701 | 021-H-CAL-40005-001 | 28X 168 AES 021E0022 AFTER WATER COOLED CONDENSER MECHANICAL CALCULATIONS | A1003 | AX | 2 | 2019-03-29 | CON-BMP-VTRA-010904 | 2019-03-29 | FOR BAPCO REVIEW | 2019-04-15 | 2019-04-16 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000523 | CLASS 2
076551C-000R-MR-0851-001 | MATERIAL REQUISITION FOR VACUUM UNIT PACKAGE | GRAHAM CORPORATION | 021H0001A | 69432-0070 | 021-H-DAT-00003-001 | 021H0001A/B 021H0002A/B EJECTOR EQUIPMENT DATA SHEET | A1001 | AX | 3 | 2018-12-03 | CON-BMP-VTRA-010112 | 2018-12-03 | FOR BAPCO REVIEW | 2018-12-18 | 2018-12-19 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000072 | CLASS 2
076551C-000R-MR-0851-001 | MATERIAL REQUISITION FOR VACUUM UNIT PACKAGE | GRAHAM CORPORATION | 021H0001A | 69432-0200 | 021-H-GAD-40002-001 | 021H0001A 1ST STAGE STEAM EJECTOR GENERAL ARRANGEMENT & CROSS SECTIONAL DRAWING | A1101 | BX | 2 | 2019-06-21 | CON-BMP-VTRA-012347 | 2019-06-21 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0851-001 | MATERIAL REQUISITION FOR VACUUM UNIT PACKAGE | GRAHAM CORPORATION | 021H0001A | 69432-0201 | 021-H-CAL-40002-001 | 021H0001A 1ST STAGE STEAM EJECTOR MECHANICAL CALCULATIONS | A1003 | AX | 2 | 2019-03-29 | CON-BMP-VTRA-010904 | 2019-03-29 | FOR BAPCO REVIEW | 2019-04-15 | 2019-04-16 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000523 | CLASS 2
076551C-000R-MR-0851-001 | MATERIAL REQUISITION FOR VACUUM UNIT PACKAGE | GRAHAM CORPORATION | 021H0001B | 69432-0300 | 021-H-GAD-40011-001 | 021H0001B 1ST STAGE STEAM EJECTOR GENERAL ARRANGEMENT & CROSS SECTIONAL DRAWING (50%) | A1101 | BX | 2 | 2019-06-21 | CON-BMP-VTRA-012347 | 2019-06-21 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0851-001 | MATERIAL REQUISITION FOR VACUUM UNIT PACKAGE | GRAHAM CORPORATION | 021H0001B | 69432-0301 | 021-H-CAL-40009-001 | 021H0001B 1ST STAGE STEAM EJECTOR MECHANICAL CALCULATIONS (50%) | A1003 | AX | 2 | 2019-03-29 | CON-BMP-VTRA-010904 | 2019-03-29 | FOR BAPCO REVIEW | 2019-04-15 | 2019-04-16 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000523 | CLASS 2
076551C-000R-MR-0851-001 | MATERIAL REQUISITION FOR VACUUM UNIT PACKAGE | GRAHAM CORPORATION | 021H0002A | 69432-0500 | 021-H-GAD-40004-001 | 021H0002A 2ND STAGE STEAM EJECTOR GENERAL ARRANGEMENT & CROSS SECTIONAL DRAWING | A1101 | BX | 2 | 2019-06-21 | CON-BMP-VTRA-012347 | 2019-06-21 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0851-001 | MATERIAL REQUISITION FOR VACUUM UNIT PACKAGE | GRAHAM CORPORATION | 021H0002A | 69432-0501 | 021-H-CAL-40004-001 | 021H0002A 2ND STAGE STEAM EJECTOR MECHANICAL CALCULATIONS | A1003 | AX | 2 | 2019-03-29 | CON-BMP-VTRA-010904 | 2019-03-29 | FOR BAPCO REVIEW | 2019-04-15 | 2019-04-16 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000523 | CLASS 2
076551C-000R-MR-0851-001 | MATERIAL REQUISITION FOR VACUUM UNIT PACKAGE | GRAHAM CORPORATION | 021H0002B | 69432-0600 | 021-H-GAD-40012-001 | 021H0002B 2ND STAGE STEAM EJECTOR GENERAL ARRANGEMENT & CROSS SECTIONAL DRAWING (50%) | A1101 | BX | 2 | 2019-06-21 | CON-BMP-VTRA-012347 | 2019-06-21 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0851-001 | MATERIAL REQUISITION FOR VACUUM UNIT PACKAGE | GRAHAM CORPORATION | 021H0002B | 69432-0601 | 021-H-CAL-40010-001 | 021H0002B 2ND STAGE STEAM EJECTOR MECHANICAL CALCULATIONS (50%) | A1003 | AX | 2 | 2019-03-29 | CON-BMP-VTRA-010904 | 2019-03-29 | FOR BAPCO REVIEW | 2019-04-15 | 2019-04-16 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000523 | CLASS 2
076551C-000R-MR-0851-001 | MATERIAL REQUISITION FOR VACUUM UNIT PACKAGE | GRAHAM CORPORATION | 021U0002 | 17178-QIP | 021-H-PQP-40001-001 | 021U0002 QUAILITY INSPECTION AND TEST PLAN | B1002 | BX | 2 | 2019-06-01 | CON-BMP-VTRA-011914 | 2019-06-01 | FOR BAPCO REVIEW | 2019-06-17 | 2019-06-10 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000911 | CLASS 2
076551C-000R-MR-0851-001 | MATERIAL REQUISITION FOR VACUUM UNIT PACKAGE | GRAHAM CORPORATION | 021U0002 | 17178-WELD BOOK | 021-H-MCD-40003-001 | 021U0002 WELD BOOK (WELD MAPS/WPS/PQR) 17178 | B1304 | AX | 2 | 2019-06-14 | CON-BMP-VTRA-012218 | 2019-06-14 | FOR BAPCO REVIEW | 2019-06-28 | 2019-06-29 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001084 | CLASS 2
076551C-000R-MR-0851-001 | MATERIAL REQUISITION FOR VACUUM UNIT PACKAGE | GRAHAM CORPORATION | 021U0002 | 69432-0010 | 021-H-PID-00001-001 | 021U0002 PIPING & INSTRUMENTATION DIAGRAM EJECTOR RECEIVER | A0103 | AX | 2 | 2018-12-03 | CON-BMP-VTRA-010108 | 2018-12-03 | FOR BAPCO REVIEW | 2018-12-18 | 2018-12-19 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000071 | CLASS 2
076551C-000R-MR-0851-001 | MATERIAL REQUISITION FOR VACUUM UNIT PACKAGE | GRAHAM CORPORATION | 021U0002 | 69432-0074 | 021-H-INX-00001-001 | 021U0002 UTILITY BALANCE | A1014 | AX | 2 | 2018-12-03 | CON-BMP-VTRA-010106 | 2018-12-03 | FOR BAPCO REVIEW | 2018-12-18 | 2018-12-19 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000076 | CLASS 2
076551C-000R-MR-0910-004 | MATERIAL REQUISITION FOR BB5 PUMPS | WORTHINGTON S.r.l. | 018E0038A | MPR-5237601 | 000-G-MRS-40001-001 | MONTHLY PROGRESS REPORT ALL ITEMS | C1002 | AX | 2 | 2019-04-26 | CON-BMP-VTRA-011291 | 2019-04-26 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-0910-004 | MATERIAL REQUISITION FOR BB5 PUMPS | WORTHINGTON S.r.l. | 018E0038A | PPL -5237601 | 000-G-TSP-40001-001 | PAINTING SPECIFICATION ALL ITEMS | A0106 | BX | 1 | 2019-07-10 | CON-BMP-VTRA-012798 | 2019-07-10 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0910-004 | MATERIAL REQUISITION FOR BB5 PUMPS | WORTHINGTON S.r.l. | 018E0038A | PQ06E | 000-G-PRO-40001-001 | FINAL INSPECTION PROCEDURE ALLITEMS | B1103 | AX | 2 | 2019-06-10 | CON-BMP-VTRA-012114 | 2019-06-10 | FOR BAPCO REVIEW | 2019-06-24 | 2019-06-21 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001011 | CLASS 2
076551C-000R-MR-0910-004 | MATERIAL REQUISITION FOR BB5 PUMPS | WORTHINGTON S.r.l. | 018E0038A | SQ 14E | 000-G-PRO-40007-001 | NOISE MEASURING SPECIFICATION ALL ITEMS | B1103 | AX | 2 | 2019-05-23 | CON-BMP-VTRA-011737 | 2019-05-23 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0910-004 | MATERIAL REQUISITION FOR BB5 PUMPS | WORTHINGTON S.r.l. | 018E0038A | SQ 91E | 000-G-PRO-40039-001 | BASEPLATE RIGIDITY TEST ALL ITEMS | B1103 | AX | 2 | 2019-05-23 | CON-BMP-VTRA-011737 | 2019-05-23 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0910-004 | MATERIAL REQUISITION FOR BB5 PUMPS | WORTHINGTON S.r.l. | 018E0038A | SQ-76/E | 000-G-SIN-40001-001 | RECOMMENDATIONS FOR STORAGE PRIOR AND AFTER ERECTION ALL ITEMS | A5002 | AX | 2 | 2019-05-23 | CON-BMP-VTRA-011738 | 2019-05-23 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0910-004 | MATERIAL REQUISITION FOR BB5 PUMPS | WORTHINGTON S.r.l. | 018E0038A | SQ-87E | 000-G-PRO-40016-001 | HARDNESS TEST PROCEDURE ALL ITEMS | B1202 | BX | 2 | 2019-06-01 | CON-BMP-VTRA-011911 | 2019-06-01 | FOR BAPCO REVIEW | 2019-06-17 | 2019-06-11 | 1-APPROVED BMP-ROC-VTRE-000907 | CLASS 3
076551C-000R-MR-0910-004 | MATERIAL REQUISITION FOR BB5 PUMPS | WORTHINGTON S.r.l. | 018E0038A | SQ55E | 000-G-PRO-40021-001 | POSITIVE MATERIAL IDENTIFICATION PROCEDURE ALL ITEMS | B1204 | BX | 2 | 2019-06-18 | CON-BMP-VTRA-012271 | 2019-06-18 | FOR BAPCO REVIEW | 2019-07-02 | 2019-06-30 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001120 | CLASS 2
076551C-000R-MR-0910-004 | MATERIAL REQUISITION FOR BB5 PUMPS | WORTHINGTON S.r.l. | 018E0038A | SQ75/E | 000-G-PRO-40019-001 | RADIOGRAPHIC EXAMINATION OF CASTINGS ALL ITEMS | B1202 | BX | 2 | 2019-06-01 | CON-BMP-VTRA-011911 | 2019-06-01 | FOR BAPCO REVIEW | 2019-06-17 | 2019-06-11 | 1-APPROVED BMP-ROC-VTRE-000907 | CLASS 3
076551C-000R-MR-0910-004 | MATERIAL REQUISITION FOR BB5 PUMPS | WORTHINGTON S.r.l. | 018E0038A | SSAWB-5237601 | 000-G-MCD-40001-001 | SEAL SYSTEM & ATU WELDING BOOK (MAP PROCEDUDRE QUALIFICATION REPORT) ALL ITEMS | B1304 | AX | 2 | 2019-05-23 | CON-BMP-VTRA-011744 | 2019-05-23 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0910-004 | MATERIAL REQUISITION FOR BB5 PUMPS | WORTHINGTON S.r.l. | 018E0038A | SSTP-5237601 | 000-G-PRO-40040-001 | SEAL SYSTEM TEST PROCEDURE ALLITEMS | B1103 | AX | 2 | 2019-06-25 | CON-BMP-VTRA-012440 | 2019-06-25 | FOR BAPCO REVIEW | 2019-07-09 | 2019-07-09 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001231 | CLASS 2
076551C-000R-MR-0910-004 | MATERIAL REQUISITION FOR BB5 PUMPS | WORTHINGTON S.r.l. | 018E0038A | VDL-5237601 | 000-G-INX-40001-001 | LIST OF VENDOR'S DOCUMENT AND DRAWING ALL ITEMS | A0001 | BX | 2 | 2019-06-03 | CON-BMP-VTRA-011938 | 2019-06-03 | FOR BAPCO REVIEW | 2019-06-18 |  |  | CLASS 2
076551C-000R-MR-0910-004 | MATERIAL REQUISITION FOR BB5 PUMPS | WORTHINGTON S.r.l. | 018E0050 | SCD -5237611 | 018-G-GAD-40091-001 | QUENCH OIL PUMPS 018P0001AB SEAL COOLER DWGS 018E0050/52 | A1103 | AX | 2 | 2019-05-10 | CON-BMP-VTRA-011531 | 2019-05-10 | FOR BAPCO INFORMATION |  | 2019-06-26 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001049 | CLASS 2
076551C-000R-MR-0910-004 | MATERIAL REQUISITION FOR BB5 PUMPS | WORTHINGTON S.r.l. | 018E1020A | EPMTS-5237601 | 000-G-SCH-40001-001 | ENGINEERING PROCUREMENT MANUFACTURING & TEST SCHEDULE 018P0001A/B 018P0019A/B 018P1001A/B 018P2001A/B 021P0001A/B | C1001 | AX | 2 | 2019-04-29 | CON-BMP-VTRA-011293 | 2019-04-29 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-0910-004 | MATERIAL REQUISITION FOR BB5 PUMPS | WORTHINGTON S.r.l. | 018M0001B | MDS-5237611 | 018-G-DAT-40197-001 | MOTOR DATA SHEET 018M0001B | A4102 | AX | 1 | 2019-04-26 | CON-BMP-VTRA-011288 | 2019-04-26 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0910-004 | MATERIAL REQUISITION FOR BB5 PUMPS | WORTHINGTON S.r.l. | 018M0001B | MND-5237611 | 018-G-DLB-40032-001 | QUENCH OIL PUMP 018P0001B MOTOR NAMEPLATE DRAWING 018M0001B | A4205 | AX | 1 | 2019-07-10 | CON-BMP-VTRA-012801 | 2019-07-10 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0910-004 | MATERIAL REQUISITION FOR BB5 PUMPS | WORTHINGTON S.r.l. | 018M0001B | MOD-5237611 | 018-G-GAD-40086-001 | QUENCH OIL PUMP 018P0001B ELECTRIC MOTOR DRAWING | A4207 | AX | 1 | 2019-05-10 | CON-BMP-VTRA-011529 | 2019-05-10 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0910-004 | MATERIAL REQUISITION FOR BB5 PUMPS | WORTHINGTON S.r.l. | 018M0001B | MPC-5237611 | 018-G-DAT-40201-001 | MOTOR TORQUE VS SPEED, CURRENT, POWER FACTOR CURVES 018M0001B | A4104 | AX | 2 | 2019-03-28 | CON-BMP-VTRA-010898 | 2019-03-28 | FOR BAPCO REVIEW | 2019-04-12 | 2019-04-15 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000519 | CLASS 2
076551C-000R-MR-0910-004 | MATERIAL REQUISITION FOR BB5 PUMPS | WORTHINGTON S.r.l. | 018M0019A | MDS-5036631 | 018-G-DAT-40198-001 | MOTOR DATA SHEET 018M0019A/B | A4102 | AX | 2 | 2019-04-26 | CON-BMP-VTRA-011290 | 2019-04-26 | FOR BAPCO INFORMATION |  | 2019-05-30 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000838 | CLASS 2
076551C-000R-MR-0910-004 | MATERIAL REQUISITION FOR BB5 PUMPS | WORTHINGTON S.r.l. | 018M0019A | MPC-5036631 | 018-G-DAT-40202-001 | MOTOR TORQUE VS SPEED, CURRENT, POWER FACTOR CURVES 018M0019A/B | A4104 | AX | 2 | 2019-03-28 | CON-BMP-VTRA-010898 | 2019-03-28 | FOR BAPCO REVIEW | 2019-04-12 | 2019-04-15 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000519 | CLASS 2
076551C-000R-MR-0910-004 | MATERIAL REQUISITION FOR BB5 PUMPS | WORTHINGTON S.r.l. | 018M1001B | MDS-4834611 | 018-G-DAT-40195-001 | MOTOR DATA SHEET 018M1001B | A4102 | AX | 2 | 2019-04-26 | CON-BMP-VTRA-011290 | 2019-04-26 | FOR BAPCO INFORMATION |  | 2019-05-30 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000838 | CLASS 2
076551C-000R-MR-0910-004 | MATERIAL REQUISITION FOR BB5 PUMPS | WORTHINGTON S.r.l. | 018M1001B | MND-4834611 | 018-G-DLB-40030-001 | TRAIN 1 FEED PUMP 018P1001B MOTOR NAMEPLATE DRAWING 018M1001B | A4205 | AX | 2 | 2019-07-10 | CON-BMP-VTRA-012799 | 2019-07-10 | FOR BAPCO REVIEW | 2019-07-25 |  |  | CLASS 2
076551C-000R-MR-0910-004 | MATERIAL REQUISITION FOR BB5 PUMPS | WORTHINGTON S.r.l. | 018M1001B | MPC-4834611 | 018-G-DAT-40199-001 | MOTOR TORQUE VS SPEED, CURRENT, POWER FACTOR CURVES 018M1001B | A4104 | AX | 2 | 2019-03-28 | CON-BMP-VTRA-010898 | 2019-03-28 | FOR BAPCO REVIEW | 2019-04-12 | 2019-04-15 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000519 | CLASS 2
076551C-000R-MR-0910-004 | MATERIAL REQUISITION FOR BB5 PUMPS | WORTHINGTON S.r.l. | 018M2001B | MDS-4834601 | 018-G-DAT-40196-001 | MOTOR DATA SHEET 018M2001B | A4102 | AX | 2 | 2019-04-26 | CON-BMP-VTRA-011290 | 2019-04-26 | FOR BAPCO INFORMATION |  | 2019-05-30 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000838 | CLASS 2
076551C-000R-MR-0910-004 | MATERIAL REQUISITION FOR BB5 PUMPS | WORTHINGTON S.r.l. | 018M2001B | MND-4834601 | 018-G-DLB-40031-001 | TRAIN 2 FEED PUMP 018P2001B MOTOR NAMEPLATE DRAWING 018M2001B | A4205 | AX | 2 | 2019-07-10 | CON-BMP-VTRA-012799 | 2019-07-10 | FOR BAPCO REVIEW | 2019-07-25 |  |  | CLASS 2
076551C-000R-MR-0910-004 | MATERIAL REQUISITION FOR BB5 PUMPS | WORTHINGTON S.r.l. | 018M2001B | MPC-4834601 | 018-G-DAT-40200-001 | MOTOR TORQUE VS SPEED, CURRENT, POWER FACTOR CURVES 018M2001B | A4104 | AX | 2 | 2019-03-28 | CON-BMP-VTRA-010898 | 2019-03-28 | FOR BAPCO REVIEW | 2019-04-12 | 2019-04-15 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000519 | CLASS 2
076551C-000R-MR-0910-004 | MATERIAL REQUISITION FOR BB5 PUMPS | WORTHINGTON S.r.l. | 018P0001A | ATUDS-5237601 | 018-G-DAT-40239-001 | AUTOMATIC TOP UP UNIT DATASHEET 018P0001A/B | A1006 | AX | 2 | 2019-05-06 | CON-BMP-VTRA-011400 | 2019-05-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0910-004 | MATERIAL REQUISITION FOR BB5 PUMPS | WORTHINGTON S.r.l. | 018P0001A | DEK046368 | 018-G-GAD-40053-001 | CENTRIFUGAL PUMP GENERAL ARRANGEMENT 018P0001A | A2001 | AX | 1 | 2019-05-15 | CON-BMP-VTRA-011607 | 2019-05-15 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0910-004 | MATERIAL REQUISITION FOR BB5 PUMPS | WORTHINGTON S.r.l. | 018P0001A | GA-225677 | 018-G-GAD-40342-001 | REFILLING UNIT 018P0001A/B | A2001 | AX | 2 | 2019-06-22 | CON-BMP-VTRA-012372 | 2019-06-22 | FOR BAPCO REVIEW | 2019-07-08 |  |  | CLASS 2
076551C-000R-MR-0910-004 | MATERIAL REQUISITION FOR BB5 PUMPS | WORTHINGTON S.r.l. | 018P0001A | MSAITP-5237601 | 000-G-PQP-40001-001 | MECHANICAL SEALS, SEAL SYSTEMS & ATU FABRICATION AND QUALITY CONTROL PLAN ALL ITEMS | B1002 | BX | 2 | 2019-06-07 | CON-BMP-VTRA-012089 | 2019-06-07 | FOR BAPCO REVIEW | 2019-06-21 | 2019-06-22 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001015 | CLASS 2
076551C-000R-MR-0910-004 | MATERIAL REQUISITION FOR BB5 PUMPS | WORTHINGTON S.r.l. | 018P0001A | MSDS-5237601 | 018-G-DAT-40236-001 | MECHANICAL SEAL DATA SHEET 018P0001A | A1006 | AX | 2 | 2019-05-06 | CON-BMP-VTRA-011400 | 2019-05-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0910-004 | MATERIAL REQUISITION FOR BB5 PUMPS | WORTHINGTON S.r.l. | 018P0001A | PDS-5237601 | 018-G-DAT-40101-001 | PUMP DATA SHEET 018P0001A/B | A1001 | AX | 2 | 2019-03-29 | CON-BMP-VTRA-010899 | 2019-03-29 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0910-004 | MATERIAL REQUISITION FOR BB5 PUMPS | WORTHINGTON S.r.l. | 018P0001A | PID-5237601 | 018-G-PID-40010-001 | CENTRIFUGAL PUMPS P&I DIAGRAM 018P0001A | A0106 | AX | 1 | 2019-04-15 | CON-BMP-VTRA-011167 | 2019-04-15 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0910-004 | MATERIAL REQUISITION FOR BB5 PUMPS | WORTHINGTON S.r.l. | 018P0001A | PIT-5237601 | 018-G-PQP-40014-001 | PUMP FABRICATION AND QUALITY CONTROL PLAN 018P0001A/B | B1002 | AX | 2 | 2019-03-29 | CON-BMP-VTRA-010902 | 2019-03-29 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0910-004 | MATERIAL REQUISITION FOR BB5 PUMPS | WORTHINGTON S.r.l. | 018P0001A | PPC-5237601 | 018-G-DAT-40132-001 | PUMP PERFORMANCE CURVES 018P0001A/B | A1002 | BX | 2 | 2019-06-07 | CON-BMP-VTRA-012090 | 2019-06-07 | FOR BAPCO REVIEW | 2019-06-21 | 2019-06-25 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001026 | CLASS 2
076551C-000R-MR-0910-004 | MATERIAL REQUISITION FOR BB5 PUMPS | WORTHINGTON S.r.l. | 018P0001A | PQ42E | 000-G-PRO-40002-001 | DYNAMIC BALANCING OF IMPELLER AND ROTORS ALL ITEMS | B1103 | BX | 2 | 2019-06-25 | CON-BMP-VTRA-012439 | 2019-06-25 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0910-004 | MATERIAL REQUISITION FOR BB5 PUMPS | WORTHINGTON S.r.l. | 018P0001A | SQ-02E | 000-G-PRO-40010-001 | PERFORMANCE TEST PROCEDURE & MECHANICAL RUNNING TEST ALL ITEMS | B1103 | BX | 2 | 2019-06-25 | CON-BMP-VTRA-012439 | 2019-06-25 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0910-004 | MATERIAL REQUISITION FOR BB5 PUMPS | WORTHINGTON S.r.l. | 018P0001A | SQ-22E | 000-G-PRO-40014-001 | PWHT PROCEDURE ALL ITEMS | B1201 | BX | 1 | 2019-06-25 | CON-BMP-VTRA-012437 | 2019-06-25 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-0910-004 | MATERIAL REQUISITION FOR BB5 PUMPS | WORTHINGTON S.r.l. | 018P0001A | SQ-38E | 000-G-PRO-40005-001 | HYDROSTATIC TEST PROCEDURE ALL ITEMS | B1103 | BX | 2 | 2019-06-18 | CON-BMP-VTRA-012270 | 2019-06-18 | FOR BAPCO REVIEW | 2019-07-02 |  |  | CLASS 2
076551C-000R-MR-0910-004 | MATERIAL REQUISITION FOR BB5 PUMPS | WORTHINGTON S.r.l. | 018P0001A | SQ23E | 000-G-PRO-40020-001 | ULTRASONIC EXAMINATION PROCEDURE ALL ITEMS | B1202 | 0X | 2 | 2019-06-05 | CON-BMP-VTRA-012001 | 2019-06-05 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-0910-004 | MATERIAL REQUISITION FOR BB5 PUMPS | WORTHINGTON S.r.l. | 018P0001A | SQ31E&32 | 000-G-PRO-40015-001 | DYE PENETRANT EXAMINATION PROCEDURE ALL ITEMS | B1202 | 0X | 2 | 2019-06-05 | CON-BMP-VTRA-012001 | 2019-06-05 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-0910-004 | MATERIAL REQUISITION FOR BB5 PUMPS | WORTHINGTON S.r.l. | 018P0001A | SQ56E & 57E | 000-G-PRO-40017-001 | MAGNETIC PARTICLE EXAMINATION PROCEDURE ALL ITEMS | B1202 | 0X | 2 | 2019-06-05 | CON-BMP-VTRA-012001 | 2019-06-05 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-0910-004 | MATERIAL REQUISITION FOR BB5 PUMPS | WORTHINGTON S.r.l. | 018P0001A | SSD-5237601 | 018-G-GAD-40068-001 | SEAL SYSTEM DRAWING 18P0001A/B | A2003 | AX | 1 | 2019-04-01 | CON-BMP-VTRA-010934 | 2019-04-01 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0910-004 | MATERIAL REQUISITION FOR BB5 PUMPS | WORTHINGTON S.r.l. | 018P0001B | DEK046369 | 018-G-GAD-40071-001 | 3X6X13 HDO LL-9 CENTRIFUGAL PUMP GENERAL ARRANGEMENT 018P0001B | A2001 | AX | 1 | 2019-05-15 | CON-BMP-VTRA-011607 | 2019-05-15 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0910-004 | MATERIAL REQUISITION FOR BB5 PUMPS | WORTHINGTON S.r.l. | 018P0001B | MSDS-5237611 | 018-G-DAT-40237-001 | MECHANICAL SEAL DATA SHEET 018P0001B | A1006 | AX | 2 | 2019-05-06 | CON-BMP-VTRA-011400 | 2019-05-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0910-004 | MATERIAL REQUISITION FOR BB5 PUMPS | WORTHINGTON S.r.l. | 018P0001B | PID-5237611 | 018-G-PID-40011-001 | CENTRIFUGAL PUMPS P&I DIAGRAM 018P0001B | A0106 | AX | 1 | 2019-04-15 | CON-BMP-VTRA-011167 | 2019-04-15 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0910-004 | MATERIAL REQUISITION FOR BB5 PUMPS | WORTHINGTON S.r.l. | 018P0019A | DEK046370 | 018-G-GAD-40054-001 | 8 WCC 15-9 CENTRIFUGAL PUMP GENERAL ARRANGEMENT 018P00019A/B | A2001 | AX | 1 | 2019-05-15 | CON-BMP-VTRA-011607 | 2019-05-15 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0910-004 | MATERIAL REQUISITION FOR BB5 PUMPS | WORTHINGTON S.r.l. | 018P0019A | MOD -5036631 | 018-G-GAD-40087-001 | HP LEAN AMINE PUMPS 018P0019ABELECTRIC MOTOR DRAWING | A4207 | 0AX | 2 | 2019-05-10 | CON-BMP-VTRA-011532 | 2019-05-10 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0910-004 | MATERIAL REQUISITION FOR BB5 PUMPS | WORTHINGTON S.r.l. | 018P0019A | MSA -5036631 | 018-G-GAD-40040-001 | MECHANICAL SEAL ASSEMBLY DRAWING WITH BILL OF MATERIALS 018P0019A/B | A1106 | AX | 2 | 2019-05-17 | CON-BMP-VTRA-011671 | 2019-05-17 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0910-004 | MATERIAL REQUISITION FOR BB5 PUMPS | WORTHINGTON S.r.l. | 018P0019A | MSA -5237601 | 018-G-GAD-40039-001 | RRDP DOUBLE CARTRIDGE 018P0001A/B | A1106 | AX | 2 | 2019-05-17 | CON-BMP-VTRA-011671 | 2019-05-17 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0910-004 | MATERIAL REQUISITION FOR BB5 PUMPS | WORTHINGTON S.r.l. | 018P0019A | MSDS-5036631 | 018-G-DAT-40238-001 | MECHANICAL SEAL DATA SHEET 018P0019A/B | A1006 | AX | 2 | 2019-05-06 | CON-BMP-VTRA-011400 | 2019-05-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0910-004 | MATERIAL REQUISITION FOR BB5 PUMPS | WORTHINGTON S.r.l. | 018P0019A | PDS-5036631 | 018-G-DAT-40102-001 | PUMP DATA SHEET 018P0019A/B | A1001 | AX | 2 | 2019-03-29 | CON-BMP-VTRA-010899 | 2019-03-29 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0910-004 | MATERIAL REQUISITION FOR BB5 PUMPS | WORTHINGTON S.r.l. | 018P0019A | PID-5036631 | 018-G-PID-40012-001 | CENTRIFUGAL PUMPS P&I DIAGRAM 018P0019A/B | A0106 | AX | 1 | 2019-04-15 | CON-BMP-VTRA-011167 | 2019-04-15 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0910-004 | MATERIAL REQUISITION FOR BB5 PUMPS | WORTHINGTON S.r.l. | 018P0019A | PIT-5036631 | 018-G-PQP-40015-001 | PUMP FABRICATION AND QUALITY CONTROL PLAN 018P00019A/B | B1002 | AX | 2 | 2019-03-29 | CON-BMP-VTRA-010902 | 2019-03-29 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0910-004 | MATERIAL REQUISITION FOR BB5 PUMPS | WORTHINGTON S.r.l. | 018P0019A | PPC-5036631 | 018-G-DAT-40133-001 | PUMP PERFORMANCE CURVES 018P0019A/B | A1002 | BX | 2 | 2019-06-07 | CON-BMP-VTRA-012090 | 2019-06-07 | FOR BAPCO REVIEW | 2019-06-21 | 2019-06-25 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001026 | CLASS 2
076551C-000R-MR-0910-004 | MATERIAL REQUISITION FOR BB5 PUMPS | WORTHINGTON S.r.l. | 018P0019A | SSD-5036631 | 018-G-GAD-40065-001 | SEAL SYSTEM DRAWING 018P0019A/B | A2003 | AX | 1 | 2019-04-01 | CON-BMP-VTRA-010934 | 2019-04-01 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0910-004 | MATERIAL REQUISITION FOR BB5 PUMPS | WORTHINGTON S.r.l. | 018P1001A | DEK 046364 | 018-G-GAD-40051-001 | CENTRIFUGAL PUMP GENERAL ARRANGEMENT 018P1001A | A2001 | AX | 1 | 2019-05-15 | CON-BMP-VTRA-011607 | 2019-05-15 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0910-004 | MATERIAL REQUISITION FOR BB5 PUMPS | WORTHINGTON S.r.l. | 018P1001A | MSA -0240601 | 018-G-GAD-40037-001 | MECHANICAL SEAL ASSEMBLY DRAWING WITH BILL OF MATERIALS 018P1001A/B | A1106 | AX | 2 | 2019-05-23 | CON-BMP-VTRA-011736 | 2019-05-23 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0910-004 | MATERIAL REQUISITION FOR BB5 PUMPS | WORTHINGTON S.r.l. | 018P1001A | MSDS-0240601 | 018-G-DAT-40232-001 | MECHANICAL SEAL DATA SHEET 018P1001A | A1006 | AX | 2 | 2019-05-06 | CON-BMP-VTRA-011400 | 2019-05-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0910-004 | MATERIAL REQUISITION FOR BB5 PUMPS | WORTHINGTON S.r.l. | 018P1001A | PDS-0240601 | 018-G-DAT-40099-001 | PUMP DATA SHEET 018P1001A/B | A1001 | AX | 2 | 2019-03-29 | CON-BMP-VTRA-010899 | 2019-03-29 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0910-004 | MATERIAL REQUISITION FOR BB5 PUMPS | WORTHINGTON S.r.l. | 018P1001A | PID-0240601 | 018-G-PID-40013-001 | CENTRIFUGAL PUMPS P&I DIAGRAM 018P1001A | A0106 | AX | 1 | 2019-04-15 | CON-BMP-VTRA-011167 | 2019-04-15 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0910-004 | MATERIAL REQUISITION FOR BB5 PUMPS | WORTHINGTON S.r.l. | 018P1001A | PIT-0240601 | 018-G-PQP-40012-001 | PUMP FABRICATION AND QUALITY CONTROL PLAN 018P1001A/B | B1002 | AX | 2 | 2019-03-29 | CON-BMP-VTRA-010902 | 2019-03-29 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0910-004 | MATERIAL REQUISITION FOR BB5 PUMPS | WORTHINGTON S.r.l. | 018P1001A | PPC-0240601 | 018-G-DAT-40130-001 | PUMP PERFORMANCE CURVES 018P1001A/B | A1002 | BX | 2 | 2019-06-07 | CON-BMP-VTRA-012090 | 2019-06-07 | FOR BAPCO REVIEW | 2019-06-21 | 2019-06-25 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001026 | CLASS 2
076551C-000R-MR-0910-004 | MATERIAL REQUISITION FOR BB5 PUMPS | WORTHINGTON S.r.l. | 018P1001A | SSD-0240601 | 018-G-GAD-40066-001 | SEAL SYSTEM DRAWING 018P1001A/B | A2003 | AX | 2 | 2019-05-14 | CON-BMP-VTRA-011567 | 2019-05-14 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0910-004 | MATERIAL REQUISITION FOR BB5 PUMPS | WORTHINGTON S.r.l. | 018P1001B | DEK 046365 | 018-G-GAD-40060-001 | 6 WCC 14-3 10 STG CENTRIFUGAL PUMP GENERAL ARRANGEMENT 018P1001B | A2001 | AX | 1 | 2019-05-17 | CON-BMP-VTRA-011667 | 2019-05-17 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0910-004 | MATERIAL REQUISITION FOR BB5 PUMPS | WORTHINGTON S.r.l. | 018P1001B | MOD-4834611 | 018-G-GAD-40084-001 | TRAIN 1 FEED PUMP 018P1001B ELECTRIC MOTOR DRAWING | A4207 | 0AX | 2 | 2019-05-10 | CON-BMP-VTRA-011532 | 2019-05-10 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0910-004 | MATERIAL REQUISITION FOR BB5 PUMPS | WORTHINGTON S.r.l. | 018P1001B | MSDS-4834611 | 018-G-DAT-40233-001 | MECHANICAL SEAL DATA SHEET 018P1001B | A1006 | AX | 2 | 2019-05-06 | CON-BMP-VTRA-011400 | 2019-05-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0910-004 | MATERIAL REQUISITION FOR BB5 PUMPS | WORTHINGTON S.r.l. | 018P1001B | PID-0240611 | 018-G-PID-40014-001 | CENTRIFUGAL PUMPS P&I DIAGRAM 018P1001B | A0106 | AX | 1 | 2019-04-15 | CON-BMP-VTRA-011167 | 2019-04-15 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0910-004 | MATERIAL REQUISITION FOR BB5 PUMPS | WORTHINGTON S.r.l. | 018P2001A | DEK 046366 | 018-G-GAD-40052-001 | 6WCC 14-3 10 STG CENTRIFUGAL PUMP GENERAL ARRANGEMENT 018P2001A | A2001 | AX | 1 | 2019-05-15 | CON-BMP-VTRA-011607 | 2019-05-15 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0910-004 | MATERIAL REQUISITION FOR BB5 PUMPS | WORTHINGTON S.r.l. | 018P2001A | MSA -0240611 | 018-G-GAD-40038-001 | MECHANICAL SEAL ASSEMBLY DRAWING WITH BILL OF MATERIALS 018P2001A/B | A1106 | AX | 2 | 2019-05-23 | CON-BMP-VTRA-011736 | 2019-05-23 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0910-004 | MATERIAL REQUISITION FOR BB5 PUMPS | WORTHINGTON S.r.l. | 018P2001A | MSDS-0240611 | 018-G-DAT-40234-001 | MECHANICAL SEAL DATA SHEET 018P2001A | A1006 | AX | 2 | 2019-05-06 | CON-BMP-VTRA-011400 | 2019-05-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0910-004 | MATERIAL REQUISITION FOR BB5 PUMPS | WORTHINGTON S.r.l. | 018P2001A | PDS-0240611 | 018-G-DAT-40107-001 | PUMP DATA SHEET 018P2001A/B | A1001 | AX | 2 | 2019-03-29 | CON-BMP-VTRA-010899 | 2019-03-29 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0910-004 | MATERIAL REQUISITION FOR BB5 PUMPS | WORTHINGTON S.r.l. | 018P2001A | PID-4834601 | 018-G-PID-40015-001 | CENTRIFUGAL PUMPS P&I DIAGRAM 018P2001A | A0106 | AX | 1 | 2019-04-15 | CON-BMP-VTRA-011167 | 2019-04-15 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0910-004 | MATERIAL REQUISITION FOR BB5 PUMPS | WORTHINGTON S.r.l. | 018P2001A | PIT-4834611 | 018-G-PQP-40013-001 | PUMP FABRICATION AND QUALITY CONTROL PLAN 018P2001A/B | B1002 | AX | 2 | 2019-03-29 | CON-BMP-VTRA-010902 | 2019-03-29 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0910-004 | MATERIAL REQUISITION FOR BB5 PUMPS | WORTHINGTON S.r.l. | 018P2001A | PPC-0240611 | 018-G-DAT-40131-001 | PUMP PERFORMANCE CURVES 018P2001A/B | A1002 | BX | 2 | 2019-06-07 | CON-BMP-VTRA-012090 | 2019-06-07 | FOR BAPCO REVIEW | 2019-06-21 | 2019-06-25 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001026 | CLASS 2
076551C-000R-MR-0910-004 | MATERIAL REQUISITION FOR BB5 PUMPS | WORTHINGTON S.r.l. | 018P2001A | SSD-0240611 | 018-G-GAD-40067-001 | SEAL SYSTEM DRAWING 018P2001AB | A2003 | AX | 2 | 2019-05-14 | CON-BMP-VTRA-011567 | 2019-05-14 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0910-004 | MATERIAL REQUISITION FOR BB5 PUMPS | WORTHINGTON S.r.l. | 018P2001B | DEK 046367 | 018-G-GAD-40070-001 | 6 WCC 14-3 10 STG CENTRIFUGAL PUMP GENERAL ARRANGEMENT 018P2001B | A2001 | AX | 1 | 2019-05-17 | CON-BMP-VTRA-011667 | 2019-05-17 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0910-004 | MATERIAL REQUISITION FOR BB5 PUMPS | WORTHINGTON S.r.l. | 018P2001B | MOD-4834601 | 018-G-GAD-40085-001 | TRAIN 2 FEED PUMP 018P2001B ELECTRIC MOTOR DRAWING | A4207 | 0AX | 2 | 2019-05-10 | CON-BMP-VTRA-011532 | 2019-05-10 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0910-004 | MATERIAL REQUISITION FOR BB5 PUMPS | WORTHINGTON S.r.l. | 018P2001B | MSDS-4834601 | 018-G-DAT-40235-001 | MECHANICAL SEAL DATA SHEET 018P2001B | A1006 | AX | 2 | 2019-05-06 | CON-BMP-VTRA-011400 | 2019-05-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0910-004 | MATERIAL REQUISITION FOR BB5 PUMPS | WORTHINGTON S.r.l. | 018P2001B | PID-4834611 | 018-G-PID-40016-001 | CENTRIFUGAL PUMPS P&I DIAGRAM 018P2001B | A0106 | AX | 1 | 2019-04-15 | CON-BMP-VTRA-011167 | 2019-04-15 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0910-004 | MATERIAL REQUISITION FOR BB5 PUMPS | WORTHINGTON S.r.l. | 018T0001A | STG-5237601 | 000-G-PRO-40008-001 | NOISE MEASURING SPECIFICATION FOR STEAM TURBINE 018T0001A 018T1001A 018T2001A | B1103 | AX | 1 | 2019-07-08 | CON-BMP-VTRA-012718 | 2019-07-08 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0910-004 | MATERIAL REQUISITION FOR BB5 PUMPS | WORTHINGTON S.r.l. | 018T0001A | TDS-5237601 | 018-G-DAT-40105-001 | TURBINE DATA SHEET QUENCH OIL PUMPS 018T0001A | A1001 | AX | 1 | 2019-06-19 | CON-BMP-VTRA-012291 | 2019-06-19 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0910-004 | MATERIAL REQUISITION FOR BB5 PUMPS | WORTHINGTON S.r.l. | 018T0001A | TDWG-5237601 | 018-G-GAD-40150-001 | ENCOMBREMENT SST 703HEK OUTLINE CORPS ADMISSION 4 TTV STEAM CHEST 018T0001A | A1109 | AX | 1 | 2019-05-23 | CON-BMP-VTRA-011742 | 2019-05-23 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0910-004 | MATERIAL REQUISITION FOR BB5 PUMPS | WORTHINGTON S.r.l. | 018T0001A | TIT-5237601 | 018-G-PQP-40017-001 | TURBINE FABRICATION AND QUALITY CONTROL PLAN 018T0001A | B1002 | AX | 2 | 2019-04-30 | CON-BMP-VTRA-011329 | 2019-04-30 | FOR BAPCO INFORMATION |  | 2019-05-27 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000796 | CLASS 2
076551C-000R-MR-0910-004 | MATERIAL REQUISITION FOR BB5 PUMPS | WORTHINGTON S.r.l. | 018T0001A | TPC-5237601 | 018-G-DAT-40136-001 | TURBINE PERFORMANCE CURVES 018T0001A | A1002 | AX | 2 | 2019-04-15 | CON-BMP-VTRA-011166 | 2019-04-15 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0910-004 | MATERIAL REQUISITION FOR BB5 PUMPS | WORTHINGTON S.r.l. | 018T1001A | TDS-0240601 | 018-G-DAT-40103-001 | TURBINE DATA SHEET FEED PUMPS 018T1001A | A1001 | AX | 1 | 2019-06-19 | CON-BMP-VTRA-012291 | 2019-06-19 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0910-004 | MATERIAL REQUISITION FOR BB5 PUMPS | WORTHINGTON S.r.l. | 018T1001A | TDWG-0240601 | 018-G-GAD-40149-001 | GENERAL ARRANGEMENT AND FOUNDATION PLAN FLOWSERVE 018T1001A | A1109 | AX | 2 | 2019-05-23 | CON-BMP-VTRA-011740 | 2019-05-23 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0910-004 | MATERIAL REQUISITION FOR BB5 PUMPS | WORTHINGTON S.r.l. | 018T1001A | TIT-0240601 | 018-G-PQP-40016-001 | TURBINE FABRICATION AND QUALITY CONTROL PLAN 018T1001A | B1002 | AX | 1 | 2019-05-23 | CON-BMP-VTRA-011735 | 2019-05-23 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0910-004 | MATERIAL REQUISITION FOR BB5 PUMPS | WORTHINGTON S.r.l. | 018T1001A | TND-0240601 | 018-G-DLB-40027-001 | TURBINE NAMEPLATE DRAWING FEEDPUMPS 018T1001A | A1112 | AX | 2 | 2019-06-17 | CON-BMP-VTRA-012247 | 2019-06-17 | FOR BAPCO REVIEW | 2019-07-01 | 2019-07-08 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001200 | CLASS 2
076551C-000R-MR-0910-004 | MATERIAL REQUISITION FOR BB5 PUMPS | WORTHINGTON S.r.l. | 018T1001A | TPC-0240601 | 018-G-DAT-40134-001 | TURBINE PERFORMANCE CURVES FEED PUMPS 018T1001A | A1002 | AX | 1 | 2019-06-17 | CON-BMP-VTRA-012244 | 2019-06-17 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0910-004 | MATERIAL REQUISITION FOR BB5 PUMPS | WORTHINGTON S.r.l. | 018T2001A | TDS-0240611 | 018-G-DAT-40104-001 | TURBINE DATA SHEET FEED PUMPS 018T2001A | A1001 | AX | 1 | 2019-06-19 | CON-BMP-VTRA-012291 | 2019-06-19 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0910-004 | MATERIAL REQUISITION FOR BB5 PUMPS | WORTHINGTON S.r.l. | 018T2001A | TDWG-0240611 | 018-G-GAD-40151-001 | GENERAL ARRANGEMENT AND FOUNDATION PLAN FLOWSERVE 018T2001A | A1109 | AX | 2 | 2019-05-23 | CON-BMP-VTRA-011740 | 2019-05-23 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0910-004 | MATERIAL REQUISITION FOR BB5 PUMPS | WORTHINGTON S.r.l. | 018T2001A | TIT-0240611 | 018-G-PQP-40023-001 | TURBINE FABRICATION AND QUALITY CONTROL PLAN 018T2001A | B1002 | AX | 1 | 2019-05-23 | CON-BMP-VTRA-011735 | 2019-05-23 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0910-004 | MATERIAL REQUISITION FOR BB5 PUMPS | WORTHINGTON S.r.l. | 018T2001A | TND -0240611 | 018-G-DLB-40028-001 | TURBINE NAMEPLATE DRAWING FEEDPUMPS 018T2001A | A1112 | AX | 2 | 2019-06-17 | CON-BMP-VTRA-012247 | 2019-06-17 | FOR BAPCO REVIEW | 2019-07-01 | 2019-07-08 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001200 | CLASS 2
076551C-000R-MR-0910-004 | MATERIAL REQUISITION FOR BB5 PUMPS | WORTHINGTON S.r.l. | 018T2001A | TPC-0240611 | 018-G-DAT-40135-001 | TURBINE PERFORMANCE CURVES FEED PUMPS 018T2001A | A1002 | AX | 1 | 2019-06-17 | CON-BMP-VTRA-012244 | 2019-06-17 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0910-004 | MATERIAL REQUISITION FOR BB5 PUMPS | WORTHINGTON S.r.l. | 018U0011 | LIT-5237601 | 018-G-PQP-40006-001 | QUENCH OIL PUMP 018P0001A L.O.S. FABRICATION AND QUALITYCONTROL PLAN 018U0011 | B1002 | AX | 2 | 2019-06-25 | CON-BMP-VTRA-012441 | 2019-06-25 | FOR BAPCO REVIEW | 2019-07-09 | 2019-07-09 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001232 | CLASS 2
076551C-000R-MR-0910-004 | MATERIAL REQUISITION FOR BB5 PUMPS | WORTHINGTON S.r.l. | 018U0012 | LIT-5036631 | 018-G-PQP-40008-001 | HP LEAN AMINE PUMPS 018P0019ABL.O.S. FABRICATION AND QUALITYCONTROL PLAN 018U0012 018U0013 | B1002 | AX | 2 | 2019-06-25 | CON-BMP-VTRA-012441 | 2019-06-25 | FOR BAPCO REVIEW | 2019-07-09 | 2019-07-09 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001232 | CLASS 2
076551C-000R-MR-0910-004 | MATERIAL REQUISITION FOR BB5 PUMPS | WORTHINGTON S.r.l. | 018U1006 | LIT -4834611 | 018-G-PQP-40005-001 | TRAIN 1 FEED PUMP 018P1001B L.O.S. FABRICATION AND QUALITYCONTROL PLAN 018U1006 | B1002 | AX | 2 | 2019-06-25 | CON-BMP-VTRA-012441 | 2019-06-25 | FOR BAPCO REVIEW | 2019-07-09 | 2019-07-09 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001232 | CLASS 2
076551C-000R-MR-0910-004 | MATERIAL REQUISITION FOR BB5 PUMPS | WORTHINGTON S.r.l. | 018U1007 | LIT -0240601 | 018-G-PQP-40004-001 | TRAIN 1 FEED PUMP 018P1001A L.O.S. FABRICATION AND QUALITYCONTROL PLAN 018U1007 | B1002 | AX | 2 | 2019-06-25 | CON-BMP-VTRA-012441 | 2019-06-25 | FOR BAPCO REVIEW | 2019-07-09 | 2019-07-09 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001232 | CLASS 2
076551C-000R-MR-0910-004 | MATERIAL REQUISITION FOR BB5 PUMPS | WORTHINGTON S.r.l. | 018U2006 | LFQ-4834601 | 018-G-PQP-40020-001 | TRAIN 2 FEED PUMP 018P2001B L.O.S. FABRICATION AND QUALITYCONTROL PLAN 018U2006 | B1002 | AX | 2 | 2019-06-25 | CON-BMP-VTRA-012441 | 2019-06-25 | FOR BAPCO REVIEW | 2019-07-09 | 2019-07-09 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001232 | CLASS 2
076551C-000R-MR-0910-004 | MATERIAL REQUISITION FOR BB5 PUMPS | WORTHINGTON S.r.l. | 018U2007 | LFQ -0240611 | 018-G-PQP-40019-001 | TRAIN 2 FEED PUMP L.O.S. FABRICATION AND QUALITY CONTROL PLAN 018U2007 | B1002 | AX | 2 | 2019-06-25 | CON-BMP-VTRA-012441 | 2019-06-25 | FOR BAPCO REVIEW | 2019-07-09 | 2019-07-09 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001232 | CLASS 2
076551C-000R-MR-0910-004 | MATERIAL REQUISITION FOR BB5 PUMPS | WORTHINGTON S.r.l. | 021M0001A | MDS-4835621 | 021-G-DAT-40019-001 | MOTOR DATA SHEET 021M0001A/B | A4102 | AX | 1 | 2019-04-26 | CON-BMP-VTRA-011288 | 2019-04-26 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0910-004 | MATERIAL REQUISITION FOR BB5 PUMPS | WORTHINGTON S.r.l. | 021M0001A | MND-4835621 | 021-G-DLB-40004-001 | FEED PUMPS 021P0001AB MOTOR NAMEPLATE DRAWING 021M0001A/B | A4205 | AX | 1 | 2019-07-10 | CON-BMP-VTRA-012800 | 2019-07-10 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0910-004 | MATERIAL REQUISITION FOR BB5 PUMPS | WORTHINGTON S.r.l. | 021M0001A | MOD-4835621 | 021-G-GAD-40012-001 | FEED PUMPS 0210001AB ELECTRIC MOTOR DRAWING | A4207 | AX | 1 | 2019-05-10 | CON-BMP-VTRA-011529 | 2019-05-10 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0910-004 | MATERIAL REQUISITION FOR BB5 PUMPS | WORTHINGTON S.r.l. | 021M0001A | MPC-4835621 | 021-G-DAT-40020-001 | MOTOR TORQUE VS SPEED, CURRENT, POWER FACTOR CURVES 021M0001A/B | A4104 | AX | 2 | 2019-03-28 | CON-BMP-VTRA-010898 | 2019-03-28 | FOR BAPCO REVIEW | 2019-04-12 | 2019-04-15 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000519 | CLASS 2
076551C-000R-MR-0910-004 | MATERIAL REQUISITION FOR BB5 PUMPS | WORTHINGTON S.r.l. | 021P0001A | DEK046371 | 021-G-GAD-40004-001 | 6 WCC 14-5 10 STG CENTRIFUGAL PUMP GENERAL ARRANGEMENT 021P0001A/B | A2001 | AX | 1 | 2019-05-15 | CON-BMP-VTRA-011607 | 2019-05-15 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0910-004 | MATERIAL REQUISITION FOR BB5 PUMPS | WORTHINGTON S.r.l. | 021P0001A | GA-225679 | 021-G-GAD-40069-001 | REFILLING UNIT 021P0001A/B | A2006 | AX | 2 | 2019-06-22 | CON-BMP-VTRA-012376 | 2019-06-22 | FOR BAPCO REVIEW | 2019-07-08 |  |  | CLASS 2
076551C-000R-MR-0910-004 | MATERIAL REQUISITION FOR BB5 PUMPS | WORTHINGTON S.r.l. | 021P0001A | MSA -4835621 | 021-G-GAD-40002-001 | MECHANICAL SEAL ASSEMBLY DRAWING WITH BILL OF MATERIALS 021P0001A/B | A1106 | AX | 2 | 2019-05-17 | CON-BMP-VTRA-011671 | 2019-05-17 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0910-004 | MATERIAL REQUISITION FOR BB5 PUMPS | WORTHINGTON S.r.l. | 021P0001A | MSDS-4835621 | 021-G-DAT-40027-001 | MECHANICAL SEAL DATA SHEET 021P0001A/B | A1006 | AX | 2 | 2019-05-06 | CON-BMP-VTRA-011400 | 2019-05-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0910-004 | MATERIAL REQUISITION FOR BB5 PUMPS | WORTHINGTON S.r.l. | 021P0001A | PDS-4835621 | 021-G-DAT-40002-001 | PUMP DATA SHEET 021P0001A/B | A1001 | AX | 2 | 2019-03-29 | CON-BMP-VTRA-010899 | 2019-03-29 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0910-004 | MATERIAL REQUISITION FOR BB5 PUMPS | WORTHINGTON S.r.l. | 021P0001A | PID-4835621 | 021-G-PID-40001-001 | PIPING & INSTRUMENT DIAGRAM FOR AROUND PUMP 021P0001A/B | A0106 | BX | 1 | 2019-06-10 | CON-BMP-VTRA-012113 | 2019-06-10 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0910-004 | MATERIAL REQUISITION FOR BB5 PUMPS | WORTHINGTON S.r.l. | 021P0001A | PIT-4835621 | 021-G-PQP-40003-001 | PUMP FABRICATION AND QUALITY CONTROL PLAN 021P0001A/B | B1002 | AX | 2 | 2019-03-29 | CON-BMP-VTRA-010902 | 2019-03-29 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0910-004 | MATERIAL REQUISITION FOR BB5 PUMPS | WORTHINGTON S.r.l. | 021P0001A | PPC-4835621 | 021-G-DAT-40005-001 | PUMP PERFORMANCE CURVES 021P0001A/B | A1002 | BX | 2 | 2019-06-07 | CON-BMP-VTRA-012090 | 2019-06-07 | FOR BAPCO REVIEW | 2019-06-21 | 2019-06-25 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001026 | CLASS 2
076551C-000R-MR-0910-004 | MATERIAL REQUISITION FOR BB5 PUMPS | WORTHINGTON S.r.l. | 021P0001A | SCD -4835621 | 021-G-GAD-40016-001 | FEED PUMPS 021P0001AB SEAL COOLER DWGS | A1103 | AX | 2 | 2019-05-10 | CON-BMP-VTRA-011531 | 2019-05-10 | FOR BAPCO INFORMATION |  | 2019-06-26 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001049 | CLASS 2
076551C-000R-MR-0910-004 | MATERIAL REQUISITION FOR BB5 PUMPS | WORTHINGTON S.r.l. | 021P0001A | SSD-4835621 | 021-G-GAD-40008-001 | SEAL SYSTEM DRAWING 021P0001AB | A2003 | AX | 2 | 2019-05-14 | CON-BMP-VTRA-011567 | 2019-05-14 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0910-004 | MATERIAL REQUISITION FOR BB5 PUMPS | WORTHINGTON S.r.l. | 021U0010 | LIT-4835621 | 021-G-PQP-40001-001 | FEED PUMPS 021P0001AB L.O.S. FABRICATION AND QUALITY CONTROL PLAN 021U0010 021U0011 | B1002 | AX | 2 | 2019-06-25 | CON-BMP-VTRA-012442 | 2019-06-25 | FOR BAPCO REVIEW | 2019-07-09 | 2019-07-08 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001224 | CLASS 2
076551C-000R-MR-0910-005 | MATERIAL REQUISITION FOR API 610 HIGH SPEED PUMPS | SUNDYNE INTERNATIONAL SA | 018E0130A | LUBCHARTS-D1740-D1741 | 000-G-TSP-40005-001 | COMPLETED LUBRICANT CHARTS ALL ITEMS | A1015 | AX | 2 | 2019-06-05 | CON-BMP-VTRA-011990 | 2019-06-05 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-0910-005 | MATERIAL REQUISITION FOR API 610 HIGH SPEED PUMPS | SUNDYNE INTERNATIONAL SA | 018E0130A | MONTHLY-D1740-D1741 | 000-G-MRS-40002-001 | MONTHLY PROGRESS REPORT ALL ITEMS | C1002 | BX | 4 | 2019-06-03 | CON-BMP-VTRA-011940 | 2019-06-03 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-0910-005 | MATERIAL REQUISITION FOR API 610 HIGH SPEED PUMPS | SUNDYNE INTERNATIONAL SA | 018E0130A | NDT-D1740-D1741 | 000-G-PRO-40023-001 | NTD PROCEDURE ALL ITEMS | B1202 | BX | 2 | 2019-06-07 | CON-BMP-VTRA-012091 | 2019-06-07 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-0910-005 | MATERIAL REQUISITION FOR API 610 HIGH SPEED PUMPS | SUNDYNE INTERNATIONAL SA | 018E0130A | PAINT-D1740-1 | 000-G-TSP-40004-001 | PAINTING PROCEDURE ALL ITEMS | A0106 | AX | 1 | 2019-05-10 | CON-BMP-VTRA-011527 | 2019-05-10 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0910-005 | MATERIAL REQUISITION FOR API 610 HIGH SPEED PUMPS | SUNDYNE INTERNATIONAL SA | 018E0130A | PMI-D1740-D1741 | 000-G-TSP-40006-001 | PMI PROCEDURE ALL ITEMS | B1204 | BX | 2 | 2019-06-07 | CON-BMP-VTRA-012092 | 2019-06-07 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0910-005 | MATERIAL REQUISITION FOR API 610 HIGH SPEED PUMPS | SUNDYNE INTERNATIONAL SA | 018E0130A | SCHEDULED-D1740 | 000-G-SCH-40002-001 | ENGINEERING PROCUREMENT MANUFACTURING & TEST SCHEDULE ALL ITEMS | C1001 | BX | 4 | 2019-06-18 | CON-BMP-VTRA-012273 | 2019-06-18 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-0910-005 | MATERIAL REQUISITION FOR API 610 HIGH SPEED PUMPS | SUNDYNE INTERNATIONAL SA | 018E0130A | UNPRICED-D1740-D1741 | 000-G-INV-40002-001 | UNPRICED COPY OF MAIN SUB ORDERS ALL ITEMS | C1005 | AX | 4 | 2019-06-07 | CON-BMP-VTRA-012096 | 2019-06-07 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-0910-005 | MATERIAL REQUISITION FOR API 610 HIGH SPEED PUMPS | SUNDYNE INTERNATIONAL SA | 018E0130A | VDL MR0910005 | 000-G-INX-40009-001 | LIST OF VENDOR¿S DOCUMENTS AND DRAWINGS ALL ITEMS | A0001 | BX | 2 | 2019-06-07 | CON-BMP-VTRA-012093 | 2019-06-07 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0910-005 | MATERIAL REQUISITION FOR API 610 HIGH SPEED PUMPS | SUNDYNE INTERNATIONAL SA | 018M0021A | MOTDS-D1741 | 018-G-DAT-40213-001 | ELECTRIC MOTOR DATA SHEET FOR HP WASH WATER PUMPS 018M0021 A/B | A4102 | AX | 1 | 2019-06-11 | CON-BMP-VTRA-012153 | 2019-06-11 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0910-005 | MATERIAL REQUISITION FOR API 610 HIGH SPEED PUMPS | SUNDYNE INTERNATIONAL SA | 018M0023A | MOTDS-D1740-7 | 018-G-DAT-40225-001 | ELECTRIC MOTOR DATA SHEET FOR CONDENSATE PUMPS 018M0023A/B | A4102 | AX | 1 | 2019-06-11 | CON-BMP-VTRA-012153 | 2019-06-11 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0910-005 | MATERIAL REQUISITION FOR API 610 HIGH SPEED PUMPS | SUNDYNE INTERNATIONAL SA | 018P0015A | EDS-D1740-1 | 018-G-DAT-40204-001 | CENTRIFUGAL PUMP DATA SHEET 018P0015A/B | A1001 | BX | 2 | 2019-05-21 | CON-BMP-VTRA-011694 | 2019-05-21 | FOR BAPCO REVIEW | 2019-06-05 | 2019-06-12 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000914 | CLASS 2
076551C-000R-MR-0910-005 | MATERIAL REQUISITION FOR API 610 HIGH SPEED PUMPS | SUNDYNE INTERNATIONAL SA | 018P0015A | EDS-D1740-10 | 021-G-DAT-40023-001 | CENTRIFUGAL PUMP DATA SHEET 021P0002A/B | A1001 | BX | 1 | 2019-05-17 | CON-BMP-VTRA-011670 | 2019-05-17 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0910-005 | MATERIAL REQUISITION FOR API 610 HIGH SPEED PUMPS | SUNDYNE INTERNATIONAL SA | 018P0015A | GA-D1740-1 | 018-G-GAD-40111-001 | OUTLINE DRAWING FOR LMV-316-Z S/N. D871740-1-A/B 018P0015A/B | A2001 | AX | 1 | 2019-04-29 | CON-BMP-VTRA-011299 | 2019-04-29 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0910-005 | MATERIAL REQUISITION FOR API 610 HIGH SPEED PUMPS | SUNDYNE INTERNATIONAL SA | 018P0015A | IL-D1740-1 | 018-G-INX-40031-001 | LIST OF INSTRUMENTS 018P0015A/B | A3001 | AX | 1 | 2019-06-28 | CON-BMP-VTRA-012538 | 2019-06-28 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0910-005 | MATERIAL REQUISITION FOR API 610 HIGH SPEED PUMPS | SUNDYNE INTERNATIONAL SA | 018P0015A | MSDWG-D1740-1 | 018-G-GAD-40109-001 | MECHANICAL SEAL DRAWING WITH MATERIAL LIST 018P0015A/B | A1106 | BX | 2 | 2019-06-18 | CON-BMP-VTRA-012272 | 2019-06-18 | FOR BAPCO REVIEW | 2019-07-02 | 2019-07-02 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001153 | CLASS 2
076551C-000R-MR-0910-005 | MATERIAL REQUISITION FOR API 610 HIGH SPEED PUMPS | SUNDYNE INTERNATIONAL SA | 018P0015A | NPDWG-D1740-1 | 018-G-DLB-40034-001 | NAME PLATE DRAWING 018P0015A/B | A1112 | AX | 2 | 2019-05-07 | CON-BMP-VTRA-011449 | 2019-05-07 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0910-005 | MATERIAL REQUISITION FOR API 610 HIGH SPEED PUMPS | SUNDYNE INTERNATIONAL SA | 018P0015A | PERFCURV-D1740-1 | 018-G-DAT-40205-001 | PERFORMANCE CURVES 018P0015A/B | A1002 | CX | 2 | 2019-06-07 | CON-BMP-VTRA-012094 | 2019-06-07 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0910-005 | MATERIAL REQUISITION FOR API 610 HIGH SPEED PUMPS | SUNDYNE INTERNATIONAL SA | 018P0015A | PID-D1740-1 | 018-G-PID-40017-001 | P & I DRAWING FOR LMV-316 Z 018P0015A/B | A0103 | AX | 2 | 2019-04-26 | CON-BMP-VTRA-011258 | 2019-04-26 | FOR BAPCO INFORMATION |  | 2019-06-01 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000870 | CLASS 2
076551C-000R-MR-0910-005 | MATERIAL REQUISITION FOR API 610 HIGH SPEED PUMPS | SUNDYNE INTERNATIONAL SA | 018P0015A | QCP-D1740-1 | 018-G-PQP-40025-001 | FABRICATION AND QUALITY CONTROL PLAN 018P0015A/B | B1002 | BX | 2 | 2019-05-06 | CON-BMP-VTRA-011401 | 2019-05-06 | FOR BAPCO REVIEW | 2019-05-20 | 2019-05-15 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000694 | CLASS 2
076551C-000R-MR-0910-005 | MATERIAL REQUISITION FOR API 610 HIGH SPEED PUMPS | SUNDYNE INTERNATIONAL SA | 018P0021A | EDS-D1741 | 018-G-DAT-40210-001 | EQUIPEMENT FILLED IN DATA SHEET API 610 018P0021/AB | A1001 | AX | 1 | 2019-03-25 | CON-BMP-VTRA-010851 | 2019-03-25 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0910-005 | MATERIAL REQUISITION FOR API 610 HIGH SPEED PUMPS | SUNDYNE INTERNATIONAL SA | 018P0021A | ELEMOTDSAPI-D1741 | 018-G-DAT-40230-001 | ELECTRIC MOTOR DATASHEET FOR API PLAN 54 MAIN PUMP FOR 018P0021 A/B | A4102 | AX | 1 | 2019-06-21 | CON-BMP-VTRA-012367 | 2019-06-21 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0910-005 | MATERIAL REQUISITION FOR API 610 HIGH SPEED PUMPS | SUNDYNE INTERNATIONAL SA | 018P0021A | INSTRANG-D1741 | 018-G-INX-40038-001 | LIST OF INSTR RANGES, SET POINTS AND SET OF ALARMS / TRIPS 018P0021A/B | A3005 | AX | 1 | 2019-04-12 | CON-BMP-VTRA-011147 | 2019-04-12 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0910-005 | MATERIAL REQUISITION FOR API 610 HIGH SPEED PUMPS | SUNDYNE INTERNATIONAL SA | 018P0021A | KT99DF33_OUT | 018-G-GAD-40117-001 | OUTLINE DRAWING 018P0021A/B | A2001 | AX | 1 | 2019-04-29 | CON-BMP-VTRA-011299 | 2019-04-29 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0910-005 | MATERIAL REQUISITION FOR API 610 HIGH SPEED PUMPS | SUNDYNE INTERNATIONAL SA | 018P0021A | MSDWG-D1741 | 018-G-GAD-40116-001 | MECHANICAL SEAL DRAWING WITH MATERIAL LIST 018P0021A/B | A1106 | BX | 2 | 2019-06-18 | CON-BMP-VTRA-012272 | 2019-06-18 | FOR BAPCO REVIEW | 2019-07-02 | 2019-07-02 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001153 | CLASS 2
076551C-000R-MR-0910-005 | MATERIAL REQUISITION FOR API 610 HIGH SPEED PUMPS | SUNDYNE INTERNATIONAL SA | 018P0021A | NPDWG-D1741 | 018-G-DLB-40036-001 | NAME PLATE DRAWING 018P0021A/B | A1112 | AX | 2 | 2019-05-07 | CON-BMP-VTRA-011449 | 2019-05-07 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0910-005 | MATERIAL REQUISITION FOR API 610 HIGH SPEED PUMPS | SUNDYNE INTERNATIONAL SA | 018P0021A | PERFCURV-D1741 | 018-G-DAT-40211-001 | PERFORMANCE CURVES 018P0021A/B | A1002 | BX | 2 | 2019-06-07 | CON-BMP-VTRA-012095 | 2019-06-07 | FOR BAPCO REVIEW | 2019-06-21 | 2019-06-25 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001027 | CLASS 2
076551C-000R-MR-0910-005 | MATERIAL REQUISITION FOR API 610 HIGH SPEED PUMPS | SUNDYNE INTERNATIONAL SA | 018P0021A | PID-D1741-1 | 018-G-PID-40018-001 | P & I DRAWING FOR HMP-3512 018P0021A/B | A0103 | AX | 2 | 2019-04-26 | CON-BMP-VTRA-011258 | 2019-04-26 | FOR BAPCO INFORMATION |  | 2019-06-01 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000870 | CLASS 2
076551C-000R-MR-0910-005 | MATERIAL REQUISITION FOR API 610 HIGH SPEED PUMPS | SUNDYNE INTERNATIONAL SA | 018P0021A | QCP 018P0021A/B | 018-G-PQP-40027-001 | FABRICATION AND QUALITY CONTROL PLAN 18P0021A/B | B1002 | BX | 2 | 2019-05-06 | CON-BMP-VTRA-011401 | 2019-05-06 | FOR BAPCO REVIEW | 2019-05-20 | 2019-05-15 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000694 | CLASS 2
076551C-000R-MR-0910-005 | MATERIAL REQUISITION FOR API 610 HIGH SPEED PUMPS | SUNDYNE INTERNATIONAL SA | 018P0022A | EDS-D1740-4 | 018-G-DAT-40216-001 | EQUIPEMENT FILLED IN DATA SHEET API 610 018P0022A/B | A1001 | CX | 1 | 2019-05-17 | CON-BMP-VTRA-011670 | 2019-05-17 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0910-005 | MATERIAL REQUISITION FOR API 610 HIGH SPEED PUMPS | SUNDYNE INTERNATIONAL SA | 018P0022A | GA-D1740-4 | 018-G-GAD-40123-001 | OUTLINE DRAWING FOR LMV-322-Z S/N. D871740-4-A/B 018P0022A/B | A2001 | AX | 1 | 2019-04-29 | CON-BMP-VTRA-011299 | 2019-04-29 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0910-005 | MATERIAL REQUISITION FOR API 610 HIGH SPEED PUMPS | SUNDYNE INTERNATIONAL SA | 018P0022A | IL-D1740-4 | 018-G-INX-40039-001 | LIST OF INSTRUMENTS 018P0022A/B | A3001 | AX | 1 | 2019-06-28 | CON-BMP-VTRA-012538 | 2019-06-28 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0910-005 | MATERIAL REQUISITION FOR API 610 HIGH SPEED PUMPS | SUNDYNE INTERNATIONAL SA | 018P0022A | MSDWG-D1740-4 | 018-G-GAD-40122-001 | MECHANICAL SEAL DRAWING WITH MATERIAL LIST 018P0022A/B | A1106 | BX | 2 | 2019-06-18 | CON-BMP-VTRA-012272 | 2019-06-18 | FOR BAPCO REVIEW | 2019-07-02 | 2019-07-02 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001153 | CLASS 2
076551C-000R-MR-0910-005 | MATERIAL REQUISITION FOR API 610 HIGH SPEED PUMPS | SUNDYNE INTERNATIONAL SA | 018P0022A | NPDWG-D1740-4 | 018-G-DLB-40038-001 | NAME PLATE DRAWING 018P0022A/B | A1112 | AX | 2 | 2019-05-07 | CON-BMP-VTRA-011449 | 2019-05-07 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0910-005 | MATERIAL REQUISITION FOR API 610 HIGH SPEED PUMPS | SUNDYNE INTERNATIONAL SA | 018P0022A | PERFCURV-D1740-4 | 018-G-DAT-40217-001 | PERFORMANCE CURVES 018P0022A/B | A1002 | CX | 2 | 2019-06-07 | CON-BMP-VTRA-012094 | 2019-06-07 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0910-005 | MATERIAL REQUISITION FOR API 610 HIGH SPEED PUMPS | SUNDYNE INTERNATIONAL SA | 018P0022A | PID-D1740-4 | 018-G-PID-40019-001 | P & I DRAWING FOR LMV-322 Z 018P0022A/B | A0103 | AX | 2 | 2019-04-26 | CON-BMP-VTRA-011258 | 2019-04-26 | FOR BAPCO INFORMATION |  | 2019-06-01 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000870 | CLASS 2
076551C-000R-MR-0910-005 | MATERIAL REQUISITION FOR API 610 HIGH SPEED PUMPS | SUNDYNE INTERNATIONAL SA | 018P0022A | QCP-D1740-4 | 018-G-PQP-40029-001 | FABRICATION AND QUALITY CONTROL PLAN 018P0022A/B | B1002 | BX | 2 | 2019-05-06 | CON-BMP-VTRA-011401 | 2019-05-06 | FOR BAPCO REVIEW | 2019-05-20 | 2019-05-15 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000694 | CLASS 2
076551C-000R-MR-0910-005 | MATERIAL REQUISITION FOR API 610 HIGH SPEED PUMPS | SUNDYNE INTERNATIONAL SA | 018P0023A | EDS-D1740-7 | 018-G-DAT-40223-001 | CENTRIFUGAL PUMP DATA SHEET 018P0023A/B | A1001 | BX | 1 | 2019-05-17 | CON-BMP-VTRA-011670 | 2019-05-17 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0910-005 | MATERIAL REQUISITION FOR API 610 HIGH SPEED PUMPS | SUNDYNE INTERNATIONAL SA | 018P0023A | GA-D1740-7 | 018-G-GAD-40129-001 | OUTLINE DRAWING FOR LMV-346 S/N. D871740-7-A/B 018P0023A/B | A2001 | AX | 1 | 2019-04-29 | CON-BMP-VTRA-011299 | 2019-04-29 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0910-005 | MATERIAL REQUISITION FOR API 610 HIGH SPEED PUMPS | SUNDYNE INTERNATIONAL SA | 018P0023A | IL-D1740-7 | 018-G-INX-40041-001 | LIST OF INSTRUMENTS 018P0023A/B | A3001 | AX | 1 | 2019-06-28 | CON-BMP-VTRA-012538 | 2019-06-28 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0910-005 | MATERIAL REQUISITION FOR API 610 HIGH SPEED PUMPS | SUNDYNE INTERNATIONAL SA | 018P0023A | MSDWG-D1740-7 | 018-G-GAD-40128-001 | MECHANICAL SEAL DRAWING WITH MATERIAL LIST 018P0023A/B | A1106 | BX | 2 | 2019-06-18 | CON-BMP-VTRA-012272 | 2019-06-18 | FOR BAPCO REVIEW | 2019-07-02 | 2019-07-02 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001153 | CLASS 2
076551C-000R-MR-0910-005 | MATERIAL REQUISITION FOR API 610 HIGH SPEED PUMPS | SUNDYNE INTERNATIONAL SA | 018P0023A | NPDWG-D1740-7 | 018-G-DLB-40040-001 | NAME PLATE DRAWING 018P0023A/B | A1112 | AX | 2 | 2019-05-07 | CON-BMP-VTRA-011449 | 2019-05-07 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0910-005 | MATERIAL REQUISITION FOR API 610 HIGH SPEED PUMPS | SUNDYNE INTERNATIONAL SA | 018P0023A | PERFCURV-D1740-7 | 018-G-DAT-40218-001 | PERFORMANCE CURVES 018P0023A/B | A1002 | CX | 2 | 2019-06-07 | CON-BMP-VTRA-012095 | 2019-06-07 | FOR BAPCO REVIEW | 2019-06-21 | 2019-06-25 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001027 | CLASS 2
076551C-000R-MR-0910-005 | MATERIAL REQUISITION FOR API 610 HIGH SPEED PUMPS | SUNDYNE INTERNATIONAL SA | 018P0023A | PID-D1740-7 | 018-G-PID-40020-001 | P & I DRAWING FOR LMV-346 Z 018P0023A/B | A0103 | AX | 2 | 2019-04-26 | CON-BMP-VTRA-011258 | 2019-04-26 | FOR BAPCO INFORMATION |  | 2019-06-01 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000870 | CLASS 2
076551C-000R-MR-0910-005 | MATERIAL REQUISITION FOR API 610 HIGH SPEED PUMPS | SUNDYNE INTERNATIONAL SA | 018P0023A | QCP-D1740-7 | 018-G-PQP-40031-001 | FABRICATION AND QUALITY CONTROL PLAN 018P0023A/B | B1002 | BX | 2 | 2019-05-06 | CON-BMP-VTRA-011401 | 2019-05-06 | FOR BAPCO REVIEW | 2019-05-20 | 2019-05-15 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000694 | CLASS 2
076551C-000R-MR-0910-005 | MATERIAL REQUISITION FOR API 610 HIGH SPEED PUMPS | SUNDYNE INTERNATIONAL SA | 021P0002A | GA-D1740-10 | 021-G-GAD-40019-001 | OUTLINE DRAWING FOR LMV-316 S/N. D871740-10-A/B 021P0002A/B | A2001 | AX | 1 | 2019-04-29 | CON-BMP-VTRA-011299 | 2019-04-29 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0910-005 | MATERIAL REQUISITION FOR API 610 HIGH SPEED PUMPS | SUNDYNE INTERNATIONAL SA | 021P0002A | IL-D1740-10 | 021-G-INX-40007-001 | LIST OF INSTRUMENTS 021P0002A/B | A3001 | AX | 1 | 2019-06-28 | CON-BMP-VTRA-012539 | 2019-06-28 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0910-005 | MATERIAL REQUISITION FOR API 610 HIGH SPEED PUMPS | SUNDYNE INTERNATIONAL SA | 021P0002A | NPDWG-D1740-10 | 021-G-DLB-40005-001 | NAME PLATE DRAWING 021P0002A/B | A1112 | AX | 2 | 2019-05-07 | CON-BMP-VTRA-011449 | 2019-05-07 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0910-005 | MATERIAL REQUISITION FOR API 610 HIGH SPEED PUMPS | SUNDYNE INTERNATIONAL SA | 021P0002A | PERFCURV-D1740-10 | 021-G-DAT-40021-001 | PERFORMANCE CURVES 021P0002A/B | A1002 | CX | 2 | 2019-06-07 | CON-BMP-VTRA-012094 | 2019-06-07 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0910-005 | MATERIAL REQUISITION FOR API 610 HIGH SPEED PUMPS | SUNDYNE INTERNATIONAL SA | 021P0002A | PID-D1740-10 | 021-G-PID-40002-001 | P & I DRAWING FOR LMV-316 Z 021P0002A/B | A0103 | AX | 2 | 2019-04-26 | CON-BMP-VTRA-011258 | 2019-04-26 | FOR BAPCO INFORMATION |  | 2019-06-01 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000870 | CLASS 2
076551C-000R-MR-0910-005 | MATERIAL REQUISITION FOR API 610 HIGH SPEED PUMPS | SUNDYNE INTERNATIONAL SA | 021P0002A | QCP-D1740-10 | 021-G-PQP-40006-001 | FABRICATION AND QUALITY CONTROL PLAN 021P0002A/B | B1002 | BX | 2 | 2019-05-06 | CON-BMP-VTRA-011401 | 2019-05-06 | FOR BAPCO REVIEW | 2019-05-20 | 2019-05-16 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000694 | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 018M0002A | 086048_MCU | 018-G-DAT-40380-001 | MOTOR PERFORMANCE CURVE - 018M0002 A | A4104 | AX | 2 | 2019-07-11 | CON-BMP-VTRA-012812 | 2019-07-11 | FOR BAPCO REVIEW | 2019-07-25 |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 018M0002A | 086048_MDS | 018-G-DAT-40362-001 | MOTOR DATA SHEET - 018M0002 A | A4102 | AX | 2 | 2019-06-25 | CON-BMP-VTRA-012447 | 2019-06-25 | FOR BAPCO REVIEW | 2019-07-10 | 2019-07-10 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000913 | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 018M0002A | 086048_MOT | 018-G-GAD-40268-001 | MOTOR OUTLINE DRAWING (INCLUDING NAMEPLATE, WIRING DETAILS AND TERMINAL BOX DWG) - 018M0002 A | A4206 | AX | 2 | 2019-07-10 | CON-BMP-VTRA-012805 | 2019-07-10 | FOR BAPCO REVIEW | 2019-07-25 |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 018M0003A | 086050_MCU | 018-G-DAT-40381-001 | MOTOR PERFORMANCE CURVE - 018M0003 A | A4104 | AX | 2 | 2019-07-11 | CON-BMP-VTRA-012812 | 2019-07-11 | FOR BAPCO REVIEW | 2019-07-25 |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 018M0003A | 086050_MDS | 018-G-DAT-40363-001 | MOTOR DATA SHEET - 018M0003 A | A4102 | AX | 2 | 2019-06-26 | CON-BMP-VTRA-012502 | 2019-06-26 | FOR BAPCO REVIEW | 2019-07-11 | 2019-07-10 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001275 | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 018M0003A | 086050_MOT | 018-G-GAD-40269-001 | MOTOR OUTLINE DRAWING (INCLUDING NAMEPLATE, WIRING DETAILS AND TERMINAL BOX DWG) - 018M0003 A | A4206 | AX | 2 | 2019-07-10 | CON-BMP-VTRA-012805 | 2019-07-10 | FOR BAPCO REVIEW | 2019-07-25 |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 018M0004A | 086052_MCU | 018-G-DAT-40382-001 | MOTOR PERFORMANCE CURVE - 018M0004 A/B | A4104 | AX | 2 | 2019-07-11 | CON-BMP-VTRA-012812 | 2019-07-11 | FOR BAPCO REVIEW | 2019-07-25 |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 018M0004A | 086052_MDS | 018-G-DAT-40364-001 | LV INDUCTION MOTOR DATA SHEET 018M0004A/B | A4102 | AX | 1 | 2019-06-25 | CON-BMP-VTRA-012453 | 2019-06-25 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 018M0004A | 086052_MOT | 018-G-GAD-40270-001 | MOTOR OUTLINE DRAWING (INCLUDING NAMEPLATE, WIRING DETAILS AND TERMINAL BOX DWG) - 018M0004 A/B | A4206 | AX | 2 | 2019-07-10 | CON-BMP-VTRA-012805 | 2019-07-10 | FOR BAPCO REVIEW | 2019-07-25 |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 018M0005A | 086053_MCU | 018-G-DAT-40383-001 | MOTOR PERFORMANCE CURVE - 018M0005 A/B | A4104 | AX | 2 | 2019-07-11 | CON-BMP-VTRA-012812 | 2019-07-11 | FOR BAPCO REVIEW | 2019-07-25 |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 018M0005A | 086053_MDS | 018-G-DAT-40365-001 | MOTOR DATA SHEET - 018M0005 A/B | A4102 | AX | 2 | 2019-06-26 | CON-BMP-VTRA-012502 | 2019-06-26 | FOR BAPCO REVIEW | 2019-07-11 | 2019-07-10 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001275 | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 018M0005A | 086053_MOT | 018-G-GAD-40271-001 | MOTOR OUTLINE DRAWING (INCLUDING NAMEPLATE, WIRING DETAILS AND TERMINAL BOX DWG) - 018M0005 A/B | A4206 | AX | 2 | 2019-07-10 | CON-BMP-VTRA-012805 | 2019-07-10 | FOR BAPCO REVIEW | 2019-07-25 |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 018M0006A | 086054_MDS | 018-G-DAT-40366-001 | LV INDUCTION MOTOR DATA SHEET 018M0006A/B | A4102 | AX | 1 | 2019-06-25 | CON-BMP-VTRA-012453 | 2019-06-25 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 018M0006A | 086054_MOT | 018-G-GAD-40272-001 | MOTOR OUTLINE DRAWING (INCLUDING NAMEPLATE WIRING DETAILS AND TERMINAL BOX DWG) 018M0006A/B | A4206 | AX | 2 | 2019-07-10 | CON-BMP-VTRA-012805 | 2019-07-10 | FOR BAPCO REVIEW | 2019-07-25 |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 018M0007A | 086038_GAD | 018-G-GAD-40155-001 | GENERAL ARRANGEMENT DRAWING PUMP TYPE DSA 400/200 018M0007A 018P0007A/B 018T0007B | A2001 | AX | 2 | 2019-05-24 | CON-BMP-VTRA-011789 | 2019-05-24 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 018M0007A | 086038_MDS | 018-G-DAT-40359-001 | MOTOR DATA SHEET - 018M0007 A | A4102 | AX | 2 | 2019-06-18 | CON-BMP-VTRA-012281 | 2019-06-18 | FOR BAPCO REVIEW | 2019-07-03 |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 018M0007A | 086038_MNP | 018-G-DLB-40065-001 | NAME PLATE (EL. MOTORS) 018M0007 A | A4205 | AX | 2 | 2019-07-10 | CON-BMP-VTRA-012802 | 2019-07-10 | FOR BAPCO REVIEW | 2019-07-25 |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 018M0007A | 086038_MOT | 018-G-GAD-40265-001 | MOTOR OUTLINE DRAWING (INCLUDING NAMEPLATE WIRING DETAILS AND TERMINAL BOX DWG) 018M0007A | A4206 | AX | 2 | 2019-07-10 | CON-BMP-VTRA-012805 | 2019-07-10 | FOR BAPCO REVIEW | 2019-07-25 |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 018M0010A | 086055_MCU | 018-G-DAT-40385-001 | MOTOR PERFORMANCE CURVE - 018M0010 A/B | A4104 | AX | 2 | 2019-07-11 | CON-BMP-VTRA-012812 | 2019-07-11 | FOR BAPCO REVIEW | 2019-07-25 |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 018M0010A | 086055_MDS | 018-G-DAT-40367-001 | MOTOR DATA SHEET - 018M0010 A/B | A4102 | AX | 2 | 2019-06-25 | CON-BMP-VTRA-012447 | 2019-06-25 | FOR BAPCO REVIEW | 2019-07-10 | 2019-07-10 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000913 | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 018M0010A | 086055_MOT | 018-G-GAD-40273-001 | MOTOR OUTLINE DRAWING (INCLUDING NAMEPLATE, WIRING DETAILS AND TERMINAL BOX DWG) - 018M0010 A/B | A4206 | AX | 2 | 2019-07-10 | CON-BMP-VTRA-012805 | 2019-07-10 | FOR BAPCO REVIEW | 2019-07-25 |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 018M0011A | 086056_MCU | 018-G-DAT-40386-001 | MOTOR PERFORMANCE CURVE - 018M0011 A/B | A4104 | AX | 2 | 2019-07-11 | CON-BMP-VTRA-012812 | 2019-07-11 | FOR BAPCO REVIEW | 2019-07-25 |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 018M0011A | 086056_MDS | 018-G-DAT-40368-001 | MOTOR DATA SHEET - 018M0011 A/B | A4102 | AX | 2 | 2019-06-25 | CON-BMP-VTRA-012447 | 2019-06-25 | FOR BAPCO REVIEW | 2019-07-10 | 2019-07-10 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000913 | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 018M0011A | 086056_MOT | 018-G-GAD-40274-001 | MOTOR OUTLINE DRAWING (INCLUDING NAMEPLATE, WIRING DETAILS AND TERMINAL BOX DWG) - 018M0011 A/B | A4206 | AX | 2 | 2019-07-10 | CON-BMP-VTRA-012805 | 2019-07-10 | FOR BAPCO REVIEW | 2019-07-25 |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 018M0012A | 086057_MCU | 018-G-DAT-40387-001 | MOTOR PERFORMANCE CURVE - 018M0012 A | A4104 | AX | 2 | 2019-07-11 | CON-BMP-VTRA-012812 | 2019-07-11 | FOR BAPCO REVIEW | 2019-07-25 |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 018M0012A | 086057_MDS | 018-G-DAT-40369-001 | MOTOR DATA SHEET - 018M0012 A | A4102 | AX | 2 | 2019-06-25 | CON-BMP-VTRA-012447 | 2019-06-25 | FOR BAPCO REVIEW | 2019-07-10 | 2019-07-10 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000913 | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 018M0012A | 086057_MOT | 018-G-GAD-40275-001 | MOTOR OUTLINE DRAWING (INCLUDING NAMEPLATE, WIRING DETAILS AND TERMINAL BOX DWG) - 018M0012 A | A4206 | AX | 2 | 2019-07-10 | CON-BMP-VTRA-012805 | 2019-07-10 | FOR BAPCO REVIEW | 2019-07-25 |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 018M0013A | 086040_GAD | 018-G-GAD-40156-001 | GENERAL ARRANGEMENT DRAWING PUMP TYPE DSA 450/250 018M0013A 018P0013A/B 018T0013B | A2001 | AX | 2 | 2019-05-24 | CON-BMP-VTRA-011789 | 2019-05-24 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 018M0013A | 086040_MDS | 018-G-DAT-40360-001 | MOTOR DATA SHEET - 018M0013 A | A4102 | AX | 2 | 2019-06-18 | CON-BMP-VTRA-012281 | 2019-06-18 | FOR BAPCO REVIEW | 2019-07-03 |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 018M0013A | 086040_MNP | 018-G-DLB-40066-001 | NAME PLATE (EL. MOTORS) 018M0013A | A4205 | AX | 2 | 2019-07-10 | CON-BMP-VTRA-012802 | 2019-07-10 | FOR BAPCO REVIEW | 2019-07-25 |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 018M0013A | 086040_MOT | 018-G-GAD-40266-001 | MOTOR OUTLINE DRAWING (INCLUDING NAMEPLATE, WIRING DETAILS AND TERMINAL BOX DWG) 018M0013A | A4206 | AX | 2 | 2019-07-10 | CON-BMP-VTRA-012805 | 2019-07-10 | FOR BAPCO REVIEW | 2019-07-25 |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 018M0014A | 086059_MDS | 018-G-DAT-40370-001 | MOTOR DATA SHEET - 018M0014 A/B | A4102 | AX | 2 | 2019-06-18 | CON-BMP-VTRA-012281 | 2019-06-18 | FOR BAPCO REVIEW | 2019-07-03 |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 018M0014A | 086059_MOT | 018-G-GAD-40276-001 | MOTOR OUTLINE DRAWING (INCLUDING NAMEPLATE, WIRING DETAILS AND TERMINAL BOX DWG) - 018M0014 A/B | A4206 | AX | 2 | 2019-07-10 | CON-BMP-VTRA-012805 | 2019-07-10 | FOR BAPCO REVIEW | 2019-07-25 |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 018M0016A | 086060_MCU | 018-G-DAT-40389-001 | MOTOR PERFORMANCE CURVE - 018M0016 A/B | A4104 | AX | 2 | 2019-07-11 | CON-BMP-VTRA-012812 | 2019-07-11 | FOR BAPCO REVIEW | 2019-07-25 |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 018M0016A | 086060_MDS | 018-G-DAT-40371-001 | MOTOR DATA SHEET - 018M0016 A/B | A4102 | AX | 2 | 2019-06-25 | CON-BMP-VTRA-012447 | 2019-06-25 | FOR BAPCO REVIEW | 2019-07-10 | 2019-07-10 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000913 | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 018M0016A | 086060_MOT | 018-G-GAD-40277-001 | MOTOR OUTLINE DRAWING (INCLUDING NAMEPLATE, WIRING DETAILS AND TERMINAL BOX DWG) - 018M0016 A/B | A4206 | AX | 2 | 2019-07-10 | CON-BMP-VTRA-012805 | 2019-07-10 | FOR BAPCO REVIEW | 2019-07-25 |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 018M0018A | 086042_MCU | 018-G-DAT-40379-001 | MOTOR PERFORMANCE CURVE - 018M0018 A/B | A4104 | AX | 2 | 2019-07-11 | CON-BMP-VTRA-012812 | 2019-07-11 | FOR BAPCO REVIEW | 2019-07-25 |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 018M0018A | 086042_MDS | 018-G-DAT-40361-001 | MOTOR DATA SHEET - 018M0018 A/B | A4102 | AX | 2 | 2019-06-26 | CON-BMP-VTRA-012502 | 2019-06-26 | FOR BAPCO REVIEW | 2019-07-11 | 2019-07-10 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001275 | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 018M0018A | 086042_MOT | 018-G-GAD-40267-001 | MOTOR OUTLINE DRAWING (INCLUDING NAMEPLATE, WIRING DETAILS AND TERMINAL BOX DWG) - 018M0018 A/B | A4206 | AX | 2 | 2019-07-10 | CON-BMP-VTRA-012805 | 2019-07-10 | FOR BAPCO REVIEW | 2019-07-25 |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 018M0020A | 086061_MCU | 018-G-DAT-40390-001 | MOTOR PERFORMANCE CURVE - 018M0020 A/B | A4104 | AX | 2 | 2019-07-11 | CON-BMP-VTRA-012812 | 2019-07-11 | FOR BAPCO REVIEW | 2019-07-25 |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 018M0020A | 086061_MDS | 018-G-DAT-40372-001 | MOTOR DATA SHEET - 018M0020 A/B | A4102 | AX | 2 | 2019-06-26 | CON-BMP-VTRA-012502 | 2019-06-26 | FOR BAPCO REVIEW | 2019-07-11 | 2019-07-10 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001275 | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 018M0020A | 086061_MOT | 018-G-GAD-40278-001 | MOTOR OUTLINE DRAWING (INCLUDING NAMEPLATE, WIRING DETAILS AND TERMINAL BOX DWG) - 018M0020 A/B | A4206 | AX | 2 | 2019-07-10 | CON-BMP-VTRA-012805 | 2019-07-10 | FOR BAPCO REVIEW | 2019-07-25 |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 018M0026A | 086062_MCU | 018-G-DAT-40391-001 | MOTOR PERFORMANCE CURVE - 018M0026 A/B | A4104 | AX | 2 | 2019-07-11 | CON-BMP-VTRA-012812 | 2019-07-11 | FOR BAPCO REVIEW | 2019-07-25 |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 018M0026A | 086062_MDS | 018-G-DAT-40373-001 | MOTOR DATA SHEET - 018M0026 A/B | A4102 | AX | 2 | 2019-06-26 | CON-BMP-VTRA-012502 | 2019-06-26 | FOR BAPCO REVIEW | 2019-07-11 | 2019-07-10 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001275 | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 018M0026A | 086062_MOT | 018-G-GAD-40279-001 | MOTOR OUTLINE DRAWING (INCLUDING NAMEPLATE, WIRING DETAILS AND TERMINAL BOX DWG) - 018M0026 A/B | A4206 | AX | 2 | 2019-07-10 | CON-BMP-VTRA-012805 | 2019-07-10 | FOR BAPCO REVIEW | 2019-07-25 |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 018M1007A | 086064_MCU | 018-G-DAT-40393-001 | MOTOR PERFORMANCE CURVE - 018M1007 A/B | A4104 | AX | 2 | 2019-07-11 | CON-BMP-VTRA-012812 | 2019-07-11 | FOR BAPCO REVIEW | 2019-07-25 |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 018M1007A | 086064_MDS | 018-G-DAT-40375-001 | MOTOR DATA SHEET - 018M1007 A/B | A4102 | AX | 2 | 2019-06-26 | CON-BMP-VTRA-012502 | 2019-06-26 | FOR BAPCO REVIEW | 2019-07-11 | 2019-07-10 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001275 | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 018M1007A | 086064_MOT | 018-G-GAD-40281-001 | MOTOR OUTLINE DRAWING (INCLUDING NAMEPLATE, WIRING DETAILS AND TERMINAL BOX DWG) - 018M1007 A/B | A4206 | AX | 2 | 2019-07-10 | CON-BMP-VTRA-012805 | 2019-07-10 | FOR BAPCO REVIEW | 2019-07-25 |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 018P0002A | 086048_GAD | 018-G-GAD-40158-001 | GENERAL ARRANGEMENT DRAWING PUMP TYPE R 360/80 018P0002A | A2001 | AX | 2 | 2019-05-24 | CON-BMP-VTRA-011789 | 2019-05-24 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 018P0002A | 086048_PDS | 018-G-DAT-40289-001 | PUMP DATA SHEET 018P0002 A | A1001 | AX | 2 | 2019-06-13 | CON-BMP-VTRA-012178 | 2019-06-13 | FOR BAPCO REVIEW | 2019-06-27 | 2019-06-26 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001038 | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 018P0002A | 086048_PPC | 018-G-DAT-40338-001 | PUMP PERFORMANCE CURVE - 018P0002 A/B | A1002 | AX | 2 | 2019-06-07 | CON-BMP-VTRA-012097 | 2019-06-07 | FOR BAPCO REVIEW | 2019-06-21 | 2019-06-24 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001023 | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 018P0002A | 086048_SYS | 018-G-GAD-40185-001 | SEAL SYSTEM DRAWING 018P0002A/B | A1103 | AX | 2 | 2019-07-02 | CON-BMP-VTRA-012623 | 2019-07-02 | FOR BAPCO REVIEW | 2019-07-17 |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 018P0002A | 086048_TEN | 018-G-GAD-40202-001 | MECHANICAL SEAL CROSS-SECTIONAL DRAWING - 018P0002 A/B | A1106 | AX | 2 | 2019-07-11 | CON-BMP-VTRA-012818 | 2019-07-11 | FOR BAPCO REVIEW | 2019-07-25 |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 018P0002B | 086049_GAD | 018-G-GAD-40242-001 | GENERAL ARRANGEMENT DRAWING R 360/80 018P0002B | A2001 | AX | 2 | 2019-06-01 | CON-BMP-VTRA-011908 | 2019-06-01 | FOR BAPCO INFORMATION | 2019-06-17 | 2019-07-11 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001293 | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 018P0002B | 086049_PDS | 018-G-DAT-40290-001 | PUMP DATA SHEET 018P0002B | A1001 | AX | 2 | 2019-06-24 | CON-BMP-VTRA-012394 | 2019-06-24 | FOR BAPCO REVIEW | 2019-07-08 |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 018P0003A | 086050_GAD | 018-G-GAD-40159-001 | GENERAL ARRANGEMENT DRAWING PUMP TYPE R 300/150 018P0003A | A2001 | AX | 2 | 2019-05-24 | CON-BMP-VTRA-011789 | 2019-05-24 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 018P0003A | 086050_PDS | 018-G-DAT-40291-001 | PUMP DATA SHEET 018P0003 A | A1001 | AX | 2 | 2019-06-24 | CON-BMP-VTRA-012394 | 2019-06-24 | FOR BAPCO REVIEW | 2019-07-08 |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 018P0003A | 086050_PPC | 018-G-DAT-40339-001 | PUMP PERFORMANCE CURVE - 018P0003 A/B | A1002 | AX | 2 | 2019-06-25 | CON-BMP-VTRA-012454 | 2019-06-25 | FOR BAPCO REVIEW | 2019-07-10 | 2019-07-10 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001277 | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 018P0003A | 086050_SYS | 018-G-GAD-40186-001 | SEAL SYSTEM DRAWING 018P0003A/B | A1103 | AX | 2 | 2019-07-02 | CON-BMP-VTRA-012623 | 2019-07-02 | FOR BAPCO REVIEW | 2019-07-17 |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 018P0003A | 086050_TEN | 018-G-GAD-40203-001 | MECHANICAL SEAL CROSS-SECTIONAL DRAWING - 018P0003 A/B | A1106 | AX | 2 | 2019-07-11 | CON-BMP-VTRA-012818 | 2019-07-11 | FOR BAPCO REVIEW | 2019-07-25 |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 018P0003B | 086051_GAD | 018-G-GAD-40243-001 | GENERAL ARRANGEMENT DRAWING R 300/150 018P0003B | A2001 | AX | 2 | 2019-06-01 | CON-BMP-VTRA-011908 | 2019-06-01 | FOR BAPCO INFORMATION | 2019-06-17 | 2019-07-11 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001293 | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 018P0003B | 086051_PDS | 018-G-DAT-40292-001 | PUMP DATA SHEET 018P0003B | A1001 | AX | 2 | 2019-06-24 | CON-BMP-VTRA-012394 | 2019-06-24 | FOR BAPCO REVIEW | 2019-07-08 |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 018P0004A | 086052_GAD | 018-G-GAD-40244-001 | GENERAL ARRANGEMENT DRAWING PUMP TYPE R 325/50 018P0004A/B | A2001 | AX | 2 | 2019-05-24 | CON-BMP-VTRA-011789 | 2019-05-24 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 018P0004A | 086052_PDS | 018-G-DAT-40293-001 | PUMP DATA SHEET 018P0004 A/B | A1001 | AX | 2 | 2019-06-24 | CON-BMP-VTRA-012394 | 2019-06-24 | FOR BAPCO REVIEW | 2019-07-08 |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 018P0004A | 086052_PPC | 018-G-DAT-40340-001 | PUMP PERFORMANCE CURVE - 018P0004 A/B | A1002 | AX | 2 | 2019-06-25 | CON-BMP-VTRA-012454 | 2019-06-25 | FOR BAPCO REVIEW | 2019-07-10 | 2019-07-10 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001277 | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 018P0004A | 086052_SYS | 018-G-GAD-40187-001 | SEAL SYSTEM DRAWING 018P0004A/B | A1103 | AX | 2 | 2019-07-02 | CON-BMP-VTRA-012623 | 2019-07-02 | FOR BAPCO REVIEW | 2019-07-17 |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 018P0004A | 086052_TEN | 018-G-GAD-40204-001 | MECHANICAL SEAL CROSS-SECTIONAL DRAWING - 018P0004 A/B | A1106 | AX | 2 | 2019-07-11 | CON-BMP-VTRA-012818 | 2019-07-11 | FOR BAPCO REVIEW | 2019-07-25 |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 018P0005A | 086053_GAD | 018-G-GAD-40245-001 | GENERAL ARRANGEMENT DRAWING PUMP TYPE R 350/50 018P0005A/B | A2001 | AX | 2 | 2019-05-24 | CON-BMP-VTRA-011789 | 2019-05-24 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 018P0005A | 086053_PDS | 018-G-DAT-40294-001 | PUMP DATA SHEET 018P0005 A/B | A1001 | AX | 2 | 2019-06-24 | CON-BMP-VTRA-012394 | 2019-06-24 | FOR BAPCO REVIEW | 2019-07-08 |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 018P0005A | 086053_PPC | 018-G-DAT-40341-001 | PUMP PERFORMANCE CURVE - 018P0005 A/B | A1002 | AX | 2 | 2019-06-25 | CON-BMP-VTRA-012454 | 2019-06-25 | FOR BAPCO REVIEW | 2019-07-10 | 2019-07-10 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001277 | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 018P0005A | 086053_SYS | 018-G-GAD-40188-001 | SEAL SYSTEM DRAWING 018P0005A/B | A1103 | AX | 2 | 2019-07-02 | CON-BMP-VTRA-012623 | 2019-07-02 | FOR BAPCO REVIEW | 2019-07-17 |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 018P0005A | 086053_TEN | 018-G-GAD-40205-001 | MECHANICAL SEAL CROSS-SECTIONAL DRAWING - 018P0005 A/B | A1106 | AX | 2 | 2019-07-11 | CON-BMP-VTRA-012818 | 2019-07-11 | FOR BAPCO REVIEW | 2019-07-25 |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 018P0006A | 086054_GAD | 018-G-GAD-40246-001 | GENERAL ARRANGEMENT DRAWING PUMP TYPE R 400/50 018P0006A/B | A2001 | AX | 2 | 2019-05-24 | CON-BMP-VTRA-011789 | 2019-05-24 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 018P0006A | 086054_PDS | 018-G-DAT-40295-001 | PUMP DATA SHEET 018P0006 A/B | A1001 | AX | 2 | 2019-06-24 | CON-BMP-VTRA-012394 | 2019-06-24 | FOR BAPCO REVIEW | 2019-07-08 |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 018P0006A | 086054_PPC | 018-G-DAT-40342-001 | PUMP PERFORMANCE CURVE - 018P0006 A/B | A1002 | AX | 2 | 2019-06-25 | CON-BMP-VTRA-012454 | 2019-06-25 | FOR BAPCO REVIEW | 2019-07-10 | 2019-07-10 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001277 | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 018P0006A | 086054_SYS | 018-G-GAD-40189-001 | SEAL SYSTEM DRAWING 018P0006A/B | A1103 | AX | 2 | 2019-07-02 | CON-BMP-VTRA-012623 | 2019-07-02 | FOR BAPCO REVIEW | 2019-07-17 |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 018P0006A | 086054_TEN | 018-G-GAD-40206-001 | MECHANICAL SEAL CROSS-SECTIONAL DRAWING - 018P0006 A/B | A1106 | AX | 2 | 2019-07-11 | CON-BMP-VTRA-012818 | 2019-07-11 | FOR BAPCO REVIEW | 2019-07-25 |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 018P0007A | 086038_PDS | 018-G-DAT-40284-001 | PUMP DATA SHEET 018P0007A | A1001 | AX | 2 | 2019-06-18 | CON-BMP-VTRA-012280 | 2019-06-18 | FOR BAPCO REVIEW | 2019-07-03 | 2019-07-03 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001157 | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 018P0007A | 086038_PPC | 018-G-DAT-40335-001 | PUMP PERFORMANCE CURVE - 018P0007 A/B | A1002 | AX | 2 | 2019-06-18 | CON-BMP-VTRA-012279 | 2019-06-18 | FOR BAPCO REVIEW | 2019-07-03 | 2019-07-02 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001154 | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 018P0007A | 086038_SYS | 018-G-GAD-40183-001 | SEAL SYSTEM DRAWING 018P0007A/B | A1103 | AX | 2 | 2019-07-02 | CON-BMP-VTRA-012623 | 2019-07-02 | FOR BAPCO REVIEW | 2019-07-17 |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 018P0007A | 086038_TEN | 018-G-GAD-40199-001 | MECHANICAL SEAL CROSS-SECTIONAL DRAWING - 018P0007 A/B | A1106 | AX | 2 | 2019-07-11 | CON-BMP-VTRA-012818 | 2019-07-11 | FOR BAPCO REVIEW | 2019-07-25 |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 018P0007B | 086039_GAD | 018-G-GAD-40240-001 | GENERAL ARRANGEMENT DRAWING DSA400/200 TT 018P0007B | A2001 | AX | 2 | 2019-06-01 | CON-BMP-VTRA-011908 | 2019-06-01 | FOR BAPCO INFORMATION | 2019-06-17 | 2019-07-11 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001293 | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 018P0007B | 086039_PDS | 018-G-DAT-40285-001 | PUMP DATA SHEET 018P0007B | A1001 | AX | 2 | 2019-06-18 | CON-BMP-VTRA-012280 | 2019-06-18 | FOR BAPCO REVIEW | 2019-07-03 | 2019-07-03 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001157 | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 018P0010A | 086055_GAD | 018-G-GAD-40247-001 | GENERAL ARRANGEMENT DRAWING PUMP TYPE R 325/25 018P0010A/B | A2001 | AX | 2 | 2019-05-24 | CON-BMP-VTRA-011789 | 2019-05-24 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 018P0010A | 086055_PDS | 018-G-DAT-40296-001 | PUMP DATA SHEET 018P0010 A/B | A1001 | AX | 2 | 2019-06-24 | CON-BMP-VTRA-012394 | 2019-06-24 | FOR BAPCO REVIEW | 2019-07-08 |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 018P0010A | 086055_PPC | 018-G-DAT-40343-001 | PUMP PERFORMANCE CURVE - 018P0010 A/B | A1002 | AX | 2 | 2019-06-25 | CON-BMP-VTRA-012454 | 2019-06-25 | FOR BAPCO REVIEW | 2019-07-10 | 2019-07-10 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001277 | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 018P0010A | 086055_SYS | 018-G-GAD-40190-001 | SEAL SYSTEM DRAWING 018P0010A/B | A1103 | AX | 2 | 2019-07-02 | CON-BMP-VTRA-012623 | 2019-07-02 | FOR BAPCO REVIEW | 2019-07-17 |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 018P0010A | 086055_TEN | 018-G-GAD-40207-001 | MECHANICAL SEAL CROSS-SECTIONAL DRAWING - 018P0010 A/B | A1106 | AX | 2 | 2019-07-11 | CON-BMP-VTRA-012818 | 2019-07-11 | FOR BAPCO REVIEW | 2019-07-25 |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 018P0011A | 086056_GAD | 018-G-GAD-40248-001 | GENERAL ARRANGEMENT DRAWING PUMP TYPE R 325/25 018P0011A/B | A2001 | AX | 2 | 2019-05-24 | CON-BMP-VTRA-011789 | 2019-05-24 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 018P0011A | 086056_PDS | 018-G-DAT-40297-001 | PUMP DATA SHEET 018P0011A/B | A1001 | AX | 2 | 2019-06-24 | CON-BMP-VTRA-012394 | 2019-06-24 | FOR BAPCO REVIEW | 2019-07-08 |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 018P0011A | 086056_PPC | 018-G-DAT-40344-001 | PUMP PERFORMANCE CURVE - 018P0011 A/B | A1002 | AX | 2 | 2019-06-25 | CON-BMP-VTRA-012454 | 2019-06-25 | FOR BAPCO REVIEW | 2019-07-10 | 2019-07-10 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001277 | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 018P0011A | 086056_SYS | 018-G-GAD-40191-001 | SEAL SYSTEM DRAWING 018P0011A/B | A1103 | AX | 2 | 2019-07-02 | CON-BMP-VTRA-012623 | 2019-07-02 | FOR BAPCO REVIEW | 2019-07-17 |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 018P0011A | 086056_TEN | 018-G-GAD-40208-001 | MECHANICAL SEAL CROSS-SECTIONAL DRAWING - 018P0011 A/B | A1106 | AX | 2 | 2019-07-11 | CON-BMP-VTRA-012818 | 2019-07-11 | FOR BAPCO REVIEW | 2019-07-25 |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 018P0012A | 086057_GAD | 018-G-GAD-40249-001 | GENERAL ARRANGEMENT DRAWING PUMP TYPE R400/100 018P0012A | A2001 | AX | 2 | 2019-05-24 | CON-BMP-VTRA-011789 | 2019-05-24 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 018P0012A | 086057_PDS | 018-G-DAT-40298-001 | PUMP DATA SHEET 018P0012A | A1001 | AX | 2 | 2019-06-24 | CON-BMP-VTRA-012394 | 2019-06-24 | FOR BAPCO REVIEW | 2019-07-08 |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 018P0012A | 086057_PPC | 018-G-DAT-40345-001 | PUMP PERFORMANCE CURVE - 018P0012 A/B | A1002 | AX | 2 | 2019-06-25 | CON-BMP-VTRA-012454 | 2019-06-25 | FOR BAPCO REVIEW | 2019-07-10 | 2019-07-10 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001277 | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 018P0012A | 086057_TEN | 018-G-GAD-40209-001 | MECHANICAL SEAL CROSS-SECTIONAL DRAWING - 018P0012 A/B | A1106 | AX | 2 | 2019-07-11 | CON-BMP-VTRA-012818 | 2019-07-11 | FOR BAPCO REVIEW | 2019-07-25 |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 018P0012B | 086058_GAD | 018-G-GAD-40250-001 | GENERAL ARRANGEMENT DRAWING R 400/100 A 018P0012B | A2001 | AX | 2 | 2019-06-01 | CON-BMP-VTRA-011908 | 2019-06-01 | FOR BAPCO INFORMATION | 2019-06-17 | 2019-07-11 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001293 | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 018P0012B | 086058_PDS | 018-G-DAT-40299-001 | PUMP DATA SHEET 018P0012 B | A1001 | AX | 2 | 2019-06-24 | CON-BMP-VTRA-012394 | 2019-06-24 | FOR BAPCO REVIEW | 2019-07-08 |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 018P0013A | 086040_PDS | 018-G-DAT-40286-001 | PUMP DATA SHEET 018P0013 A | A1001 | AX | 2 | 2019-06-24 | CON-BMP-VTRA-012394 | 2019-06-24 | FOR BAPCO REVIEW | 2019-07-08 |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 018P0013A | 086040_PPC | 018-G-DAT-40336-001 | PUMP PERFORMANCE CURVE - 018P0013 A/B | A1002 | AX | 2 | 2019-06-25 | CON-BMP-VTRA-012454 | 2019-06-25 | FOR BAPCO REVIEW | 2019-07-10 | 2019-07-10 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001277 | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 018P0013A | 086040_SYS | 018-G-GAD-40184-001 | SEAL SYSTEM DRAWING 018P0013A/B | A1103 | AX | 2 | 2019-07-02 | CON-BMP-VTRA-012623 | 2019-07-02 | FOR BAPCO REVIEW | 2019-07-17 |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 018P0013A | 086040_TEN | 018-G-GAD-40200-001 | MECHANICAL SEAL CROSS-SECTIONAL DRAWING - 018P0013 A/B | A1106 | AX | 2 | 2019-07-11 | CON-BMP-VTRA-012818 | 2019-07-11 | FOR BAPCO REVIEW | 2019-07-25 |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 018P0013B | 086041_GAD | 018-G-GAD-40241-001 | GENERAL ARRANGEMENT DRAWING DSA 450/250 TT 018P0013B | A2001 | AX | 2 | 2019-06-01 | CON-BMP-VTRA-011908 | 2019-06-01 | FOR BAPCO INFORMATION | 2019-06-17 | 2019-07-11 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001293 | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 018P0013B | 086041_PDS | 018-G-DAT-40287-001 | PUMP DATA SHEET 018P0013 B | A1001 | AX | 2 | 2019-06-24 | CON-BMP-VTRA-012394 | 2019-06-24 | FOR BAPCO REVIEW | 2019-07-08 |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 018P0014A | 086059_GAD | 018-G-GAD-40251-001 | GENERAL ARRANGEMENT DRAWING R 400/150 A 018P0014A/B | A2001 | AX | 2 | 2019-06-01 | CON-BMP-VTRA-011908 | 2019-06-01 | FOR BAPCO INFORMATION | 2019-06-17 | 2019-07-11 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001293 | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 018P0014A | 086059_PDS | 018-G-DAT-40300-001 | PUMP DATA SHEET 018P0014 A/B | A1001 | AX | 2 | 2019-06-24 | CON-BMP-VTRA-012394 | 2019-06-24 | FOR BAPCO REVIEW | 2019-07-08 |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 018P0014A | 086059_PPC | 018-G-DAT-40346-001 | PUMP PERFORMANCE CURVE - 018P0014 A/B | A1002 | AX | 2 | 2019-06-25 | CON-BMP-VTRA-012454 | 2019-06-25 | FOR BAPCO REVIEW | 2019-07-10 | 2019-07-10 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001277 | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 018P0014A | 086059_SYS | 018-G-GAD-40192-001 | SEAL SYSTEM DRAWING 018P0014A/B | A1103 | AX | 2 | 2019-07-02 | CON-BMP-VTRA-012623 | 2019-07-02 | FOR BAPCO REVIEW | 2019-07-17 |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 018P0014A | 086059_TEN | 018-G-GAD-40210-001 | MECHANICAL SEAL CROSS-SECTIONAL DRAWING - 018P0014 A/B | A1106 | AX | 2 | 2019-07-11 | CON-BMP-VTRA-012818 | 2019-07-11 | FOR BAPCO REVIEW | 2019-07-25 |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 018P0016A | 086060_GAD | 018-G-GAD-40252-001 | GENERAL ARRANGEMENT DRAWING R 320/100 A 018P0016A/B | A2001 | AX | 2 | 2019-06-01 | CON-BMP-VTRA-011908 | 2019-06-01 | FOR BAPCO INFORMATION | 2019-06-17 | 2019-07-11 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001293 | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 018P0016A | 086060_PDS | 018-G-DAT-40301-001 | PUMP DATA SHEET 018P0016 A/B | A1001 | AX | 2 | 2019-06-24 | CON-BMP-VTRA-012394 | 2019-06-24 | FOR BAPCO REVIEW | 2019-07-08 |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 018P0016A | 086060_PPC | 018-G-DAT-40347-001 | PUMP PERFORMANCE CURVE - 018P0016 A/B | A1002 | AX | 2 | 2019-06-25 | CON-BMP-VTRA-012454 | 2019-06-25 | FOR BAPCO REVIEW | 2019-07-10 | 2019-07-10 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001277 | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 018P0016A | 086060_SYS | 018-G-GAD-40193-001 | SEAL SYSTEM DRAWING 018P0016A/B | A1103 | AX | 2 | 2019-07-02 | CON-BMP-VTRA-012623 | 2019-07-02 | FOR BAPCO REVIEW | 2019-07-17 |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 018P0016A | 086060_TEN | 018-G-GAD-40211-001 | MECHANICAL SEAL CROSS-SECTIONAL DRAWING - 018P0016 A/B | A1106 | AX | 2 | 2019-07-11 | CON-BMP-VTRA-012818 | 2019-07-11 | FOR BAPCO REVIEW | 2019-07-25 |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 018P0018A | 086042_GAD | 018-G-GAD-40157-001 | GENERAL ARRANGEMENT DRAWING FOR CUTTER STOCK PUMP TYPE DH 360/80 018P0018A/B | A2001 | AX | 2 | 2019-05-21 | CON-BMP-VTRA-011695 | 2019-05-21 | FOR BAPCO REVIEW | 2019-06-05 | 2019-06-10 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000906 | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 018P0018A | 086042_PDS | 018-G-DAT-40288-001 | PUMP DATA SHEET 018P0018 A/B | A1001 | AX | 2 | 2019-06-24 | CON-BMP-VTRA-012394 | 2019-06-24 | FOR BAPCO REVIEW | 2019-07-08 |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 018P0018A | 086042_PPC | 018-G-DAT-40337-001 | PUMP PERFORMANCE CURVE - 018P0018 A/B | A1002 | AX | 2 | 2019-06-25 | CON-BMP-VTRA-012454 | 2019-06-25 | FOR BAPCO REVIEW | 2019-07-10 | 2019-07-10 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001277 | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 018P0018A | 086042_TEN | 018-G-GAD-40201-001 | MECHANICAL SEAL CROSS-SECTIONAL DRAWING - 018P0018 A/B | A1106 | AX | 2 | 2019-07-11 | CON-BMP-VTRA-012818 | 2019-07-11 | FOR BAPCO REVIEW | 2019-07-25 |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 018P0020A | 086061_GAD | 018-G-GAD-40253-001 | GENERAL ARRANGEMENT DRAWING PUMP TYPE R 320/25 018P0020A/B | A2001 | AX | 2 | 2019-05-24 | CON-BMP-VTRA-011789 | 2019-05-24 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 018P0020A | 086061_PDS | 018-G-DAT-40302-001 | PUMP DATA SHEET 018P0020 A/B | A1001 | AX | 2 | 2019-06-24 | CON-BMP-VTRA-012394 | 2019-06-24 | FOR BAPCO REVIEW | 2019-07-08 |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 018P0020A | 086061_PPC | 018-G-DAT-40348-001 | PUMP PERFORMANCE CURVE - 018P0020 A/B | A1002 | AX | 2 | 2019-06-25 | CON-BMP-VTRA-012443 | 2019-06-25 | FOR BAPCO REVIEW | 2019-07-09 |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 018P0020A | 086061_SYS | 018-G-GAD-40194-001 | SEAL SYSTEM DRAWING 018P0020A/B | A1103 | AX | 2 | 2019-07-02 | CON-BMP-VTRA-012623 | 2019-07-02 | FOR BAPCO REVIEW | 2019-07-17 |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 018P0020A | 086061_TEN | 018-G-GAD-40212-001 | MECHANICAL SEAL CROSS-SECTIONAL DRAWING - 018P0020 A/B | A1106 | AX | 2 | 2019-07-11 | CON-BMP-VTRA-012818 | 2019-07-11 | FOR BAPCO REVIEW | 2019-07-25 |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 018P0026A | 086062_GAD | 018-G-GAD-40254-001 | GENERAL ARRANGEMENT DRAWING PUMP TYPE R 400/50 018P0026A/B | A2001 | AX | 2 | 2019-05-24 | CON-BMP-VTRA-011789 | 2019-05-24 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 018P0026A | 086062_PDS | 018-G-DAT-40303-001 | PUMP DATA SHEET 018P0026 A/B | A1001 | AX | 2 | 2019-06-24 | CON-BMP-VTRA-012394 | 2019-06-24 | FOR BAPCO REVIEW | 2019-07-08 |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 018P0026A | 086062_PPC | 018-G-DAT-40349-001 | PUMP PERFORMANCE CURVE - 018P0026 A/B | A1002 | AX | 2 | 2019-06-25 | CON-BMP-VTRA-012443 | 2019-06-25 | FOR BAPCO REVIEW | 2019-07-09 |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 018P0026A | 086062_SYS | 018-G-GAD-40195-001 | SEAL SYSTEM DRAWING 018P0026A/B | A1103 | AX | 2 | 2019-07-02 | CON-BMP-VTRA-012623 | 2019-07-02 | FOR BAPCO REVIEW | 2019-07-17 |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 018P0026A | 086062_TEN | 018-G-GAD-40213-001 | MECHANICAL SEAL CROSS-SECTIONAL DRAWING - 018P0026 A/B | A1106 | AX | 2 | 2019-07-11 | CON-BMP-VTRA-012818 | 2019-07-11 | FOR BAPCO REVIEW | 2019-07-25 |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 018P0033A | 086063_GAD | 018-G-GAD-40255-001 | GENERAL ARRANGEMENT DRAWING PUMP TYPE R 400/50 018P0033A/B | A2001 | AX | 2 | 2019-05-24 | CON-BMP-VTRA-011789 | 2019-05-24 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 018P1007A | 086064_GAD | 018-G-GAD-40256-001 | GENERAL ARRANGEMENT DRAWING PUMP TYPE R 260/80 018P1007A/B | A2001 | AX | 2 | 2019-05-24 | CON-BMP-VTRA-011789 | 2019-05-24 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 018P1007A | 086064_PDS | 018-G-DAT-40305-001 | PUMP DATA SHEET 018P1007 A/B | A1001 | AX | 2 | 2019-06-24 | CON-BMP-VTRA-012394 | 2019-06-24 | FOR BAPCO REVIEW | 2019-07-08 |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 018P1007A | 086064_PPC | 018-G-DAT-40351-001 | PUMP PERFORMANCE CURVE - 018P1007 A/B | A1002 | AX | 2 | 2019-06-25 | CON-BMP-VTRA-012443 | 2019-06-25 | FOR BAPCO REVIEW | 2019-07-09 |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 018P1007A | 086064_SYS | 018-G-GAD-40197-001 | SEAL SYSTEM DRAWING 018P1007A/B | A1103 | AX | 2 | 2019-07-02 | CON-BMP-VTRA-012623 | 2019-07-02 | FOR BAPCO REVIEW | 2019-07-17 |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 018P1007A | 086064_TEN | 018-G-GAD-40215-001 | MECHANICAL SEAL CROSS-SECTIONAL DRAWING - 018P1007 A/B | A1106 | AX | 2 | 2019-07-11 | CON-BMP-VTRA-012818 | 2019-07-11 | FOR BAPCO REVIEW | 2019-07-25 |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 018P2007A | 086065_GAD | 018-G-GAD-40257-001 | GENERAL ARRANGEMENT DRAWING PUMP TYPE R 260/80 018P2007A/B | A2001 | AX | 2 | 2019-05-24 | CON-BMP-VTRA-011789 | 2019-05-24 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 018P2007A | 086065_PDS | 018-G-DAT-40306-001 | PUMP DATA SHEET 018P2007 A/B | A1001 | AX | 2 | 2019-06-24 | CON-BMP-VTRA-012394 | 2019-06-24 | FOR BAPCO REVIEW | 2019-07-08 |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 018P2007A | 086065_PPC | 018-G-DAT-40352-001 | PUMP PERFORMANCE CURVE - 018P2007 A/B | A1002 | AX | 2 | 2019-06-25 | CON-BMP-VTRA-012443 | 2019-06-25 | FOR BAPCO REVIEW | 2019-07-09 |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 018P2007A | 086065_SYS | 018-G-GAD-40198-001 | SEAL SYSTEM DRAWING 018P2007A/B | A1103 | AX | 2 | 2019-07-02 | CON-BMP-VTRA-012623 | 2019-07-02 | FOR BAPCO REVIEW | 2019-07-17 |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 018P2007A | 086065_TEN | 018-G-GAD-40216-001 | MECHANICAL SEAL CROSS-SECTIONAL DRAWING - 018P2007 A/B | A1106 | AX | 2 | 2019-07-11 | CON-BMP-VTRA-012818 | 2019-07-11 | FOR BAPCO REVIEW | 2019-07-25 |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 021M0003A | 086066_MCU | 021-G-DAT-40074-001 | MOTOR PERFORMANCE CURVE - 021M0003 A/B | A4104 | AX | 2 | 2019-07-11 | CON-BMP-VTRA-012813 | 2019-07-11 | FOR BAPCO REVIEW | 2019-07-25 |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 021M0003A | 086066_MDS | 021-G-DAT-40067-001 | MOTOR DATA SHEET - 021M0003 A/B | A4102 | AX | 2 | 2019-06-26 | CON-BMP-VTRA-012503 | 2019-06-26 | FOR BAPCO REVIEW | 2019-07-11 | 2019-07-10 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001278 | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 021M0003A | 086066_MOT | 021-G-GAD-40064-001 | MOTOR OUTLINE DRAWING (INCLUDING NAMEPLATE, WIRING DETAILS AND TERMINAL BOX DWG) - 021M0003 A/B | A4206 | AX | 2 | 2019-07-11 | CON-BMP-VTRA-012806 | 2019-07-11 | FOR BAPCO REVIEW | 2019-07-25 |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 021M0004A | 086043_GAD | 021-G-GAD-40052-001 | GENERAL ARRANGEMENT DRAWING PUMP TYPE DDH 360/200 021M0004A 021P0004A/B 021T0004B | A2001 | AX | 2 | 2019-05-24 | CON-BMP-VTRA-011789 | 2019-05-24 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 021M0004A | 086043_MDS | 021-G-DAT-40065-001 | MOTOR DATA SHEET - 021M0004 A | A4102 | AX | 2 | 2019-06-19 | CON-BMP-VTRA-012292 | 2019-06-19 | FOR BAPCO REVIEW | 2019-07-03 | 2019-07-08 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001201 | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 021M0004A | 086043_MNP | 021-G-DLB-40015-001 | NAME PLATE (EL. MOTORS) 021M0004A | A4205 | AX | 2 | 2019-07-10 | CON-BMP-VTRA-012803 | 2019-07-10 | FOR BAPCO REVIEW | 2019-07-25 |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 021M0004A | 086043_MOT | 021-G-GAD-40062-001 | MOTOR OUTLINE DRAWING (INCLUDING NAMEPLATE, WIRING DETAILS AND TERMINAL BOX DWG) 021M0004A | A4206 | AX | 2 | 2019-07-11 | CON-BMP-VTRA-012806 | 2019-07-11 | FOR BAPCO REVIEW | 2019-07-25 |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 021M0005A | 086067_MCU | 021-G-DAT-40075-001 | MOTOR PERFORMANCE CURVE - 021M0005 A/B | A4104 | AX | 2 | 2019-07-11 | CON-BMP-VTRA-012813 | 2019-07-11 | FOR BAPCO REVIEW | 2019-07-25 |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 021M0005A | 086067_MDS | 021-G-DAT-40068-001 | MOTOR DATA SHEET - 021M0005 A/B | A4102 | AX | 2 | 2019-06-26 | CON-BMP-VTRA-012503 | 2019-06-26 | FOR BAPCO REVIEW | 2019-07-11 | 2019-07-10 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001278 | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 021M0005A | 086067_MOT | 021-G-GAD-40065-001 | MOTOR OUTLINE DRAWING (INCLUDING NAMEPLATE, WIRING DETAILS AND TERMINAL BOX DWG) - 021M0005 A/B | A4206 | AX | 2 | 2019-07-11 | CON-BMP-VTRA-012806 | 2019-07-11 | FOR BAPCO REVIEW | 2019-07-25 |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 021M0006A | 086068_MCU | 021-G-DAT-40076-001 | MOTOR PERFORMANCE CURVE - 021M0006 A/B | A4104 | AX | 2 | 2019-07-11 | CON-BMP-VTRA-012813 | 2019-07-11 | FOR BAPCO REVIEW | 2019-07-25 |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 021M0006A | 086068_MDS | 021-G-DAT-40069-001 | MOTOR DATA SHEET - 021M0006 A/B | A4102 | AX | 2 | 2019-06-26 | CON-BMP-VTRA-012503 | 2019-06-26 | FOR BAPCO REVIEW | 2019-07-11 | 2019-07-10 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001278 | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 021M0006A | 086068_MOT | 021-G-GAD-40066-001 | MOTOR OUTLINE DRAWING (INCLUDING NAMEPLATE, WIRING DETAILS AND TERMINAL BOX DWG) - 021M0006 A/B | A4206 | AX | 2 | 2019-07-11 | CON-BMP-VTRA-012806 | 2019-07-11 | FOR BAPCO REVIEW | 2019-07-25 |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 021M0007A | 086045_GAD | 021-G-GAD-40054-001 | GENERAL ARRANGEMENT DRAWING PUMP TYPE AHPDS250/80-9 021M0007A/B 021P0007A/B | A2001 | AX | 2 | 2019-05-24 | CON-BMP-VTRA-011789 | 2019-05-24 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 021M0007A | 086045_MDS | 021-G-DAT-40066-001 | MOTOR DATA SHEET - 021M0007 A/B | A4102 | AX | 2 | 2019-06-25 | CON-BMP-VTRA-012448 | 2019-06-25 | FOR BAPCO REVIEW | 2019-07-10 |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 021M0007A | 086045_MNP | 021-G-DLB-40016-001 | NAME PLATE (EL. MOTORS) 021M0007A/B | A4205 | AX | 2 | 2019-07-10 | CON-BMP-VTRA-012803 | 2019-07-10 | FOR BAPCO REVIEW | 2019-07-25 |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 021M0007A | 086045_MOT | 021-G-GAD-40063-001 | MOTOR OUTLINE DRAWING (INCLUDING NAMEPLATE, WIRING DETAILS AND TERMINAL BOX DWG) 021M0007A/B | A4206 | AX | 2 | 2019-07-11 | CON-BMP-VTRA-012806 | 2019-07-11 | FOR BAPCO REVIEW | 2019-07-25 |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 021M0008A | 086069_MCU | 021-G-DAT-40077-001 | MOTOR PERFORMANCE CURVE - 021M0008 A/B | A4104 | AX | 2 | 2019-07-11 | CON-BMP-VTRA-012813 | 2019-07-11 | FOR BAPCO REVIEW | 2019-07-25 |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 021M0008A | 086069_MDS | 021-G-DAT-40070-001 | MOTOR DATA SHEET - 021M0008 A/B | A4102 | AX | 2 | 2019-06-26 | CON-BMP-VTRA-012503 | 2019-06-26 | FOR BAPCO REVIEW | 2019-07-11 | 2019-07-10 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001278 | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 021M0008A | 086069_MOT | 021-G-GAD-40067-001 | MOTOR OUTLINE DRAWING (INCLUDING NAMEPLATE, WIRING DETAILS AND TERMINAL BOX DWG) - 021M0008 A/B | A4206 | AX | 2 | 2019-07-11 | CON-BMP-VTRA-012806 | 2019-07-11 | FOR BAPCO REVIEW | 2019-07-25 |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 021M0012A | 086070_MCU | 021-G-DAT-40078-001 | MOTOR PERFORMANCE CURVE - 021M0012 A/B | A4104 | AX | 2 | 2019-07-11 | CON-BMP-VTRA-012813 | 2019-07-11 | FOR BAPCO REVIEW | 2019-07-25 |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 021M0012A | 086070_MDS | 021-G-DAT-40071-001 | MOTOR DATA SHEET - 021M0012 A/B | A4102 | AX | 2 | 2019-06-26 | CON-BMP-VTRA-012503 | 2019-06-26 | FOR BAPCO REVIEW | 2019-07-11 | 2019-07-10 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001278 | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 021M0012A | 086070_MOT | 021-G-GAD-40068-001 | MOTOR OUTLINE DRAWING (INCLUDING NAMEPLATE, WIRING DETAILS AND TERMINAL BOX DWG) - 021M0012 A/B | A4206 | AX | 2 | 2019-07-11 | CON-BMP-VTRA-012806 | 2019-07-11 | FOR BAPCO REVIEW | 2019-07-25 |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 021P0003A | 086066_GAD | 021-G-GAD-40055-001 | GENERAL ARRANGEMENT DRAWING - 021P0003 A/B | A2001 | AX | 2 | 2019-05-24 | CON-BMP-VTRA-011789 | 2019-05-24 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 021P0003A | 086066_PDS | 021-G-DAT-40042-001 | PUMP DATA SHEET 021P0003 A/B | A1001 | AX | 2 | 2019-06-22 | CON-BMP-VTRA-012393 | 2019-06-22 | FOR BAPCO REVIEW | 2019-07-08 |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 021P0003A | 086066_PPC | 021-G-DAT-40058-001 | PUMP PERFORMANCE CURVE - 021P0003 A/B | A1002 | AX | 2 | 2019-06-25 | CON-BMP-VTRA-012444 | 2019-06-25 | FOR BAPCO REVIEW | 2019-07-09 |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 021P0003A | 086066_SYS | 021-G-GAD-40035-001 | SEAL SYSTEM DRAWING 021P0003A/B | A1103 | AX | 2 | 2019-07-02 | CON-BMP-VTRA-012624 | 2019-07-02 | FOR BAPCO REVIEW | 2019-07-17 |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 021P0003A | 086066_TEN | 021-G-GAD-40039-001 | MECHANICAL SEAL CROSS-SECTIONAL DRAWING - 021P0003 A/B | A1106 | AX | 2 | 2019-07-11 | CON-BMP-VTRA-012819 | 2019-07-11 | FOR BAPCO REVIEW | 2019-07-25 |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 021P0004A | 086043_PDS | 021-G-DAT-40039-001 | PUMP DATA SHEET 021P0004A | A1001 | AX | 2 | 2019-06-22 | CON-BMP-VTRA-012393 | 2019-06-22 | FOR BAPCO REVIEW | 2019-07-08 |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 021P0004A | 086043_PPC | 021-G-DAT-40056-001 | PUMP PERFORMANCE CURVE - 021P0004 A/B | A1002 | AX | 2 | 2019-06-25 | CON-BMP-VTRA-012444 | 2019-06-25 | FOR BAPCO REVIEW | 2019-07-09 |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 021P0004A | 086043_TEN | 021-G-GAD-40037-001 | MECHANICAL SEAL CROSS SECTIONAL DRAWING 021P0004A/B | A1106 | AX | 2 | 2019-06-26 | CON-BMP-VTRA-012505 | 2019-06-26 | FOR BAPCO REVIEW | 2019-07-11 |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 021P0004B | 086044_GAD | 021-G-GAD-40053-001 | GENERAL ARRANGEMENT DRAWING DDH 360/200 IL 021P0004B | A2001 | AX | 2 | 2019-06-01 | CON-BMP-VTRA-011908 | 2019-06-01 | FOR BAPCO INFORMATION | 2019-06-17 | 2019-07-11 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001293 | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 021P0004B | 086044_PDS | 021-G-DAT-40040-001 | PUMP DATA SHEET 021P0004B | A1001 | AX | 2 | 2019-06-22 | CON-BMP-VTRA-012393 | 2019-06-22 | FOR BAPCO REVIEW | 2019-07-08 |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 021P0005A | 086067_GAD | 021-G-GAD-40056-001 | GENERAL ARRANGEMENT DRAWING FOR EJECTOR RECEIVER OIL PUMPS 021P0005 A/B | A2001 | AX | 2 | 2019-06-26 | CON-BMP-VTRA-012507 | 2019-06-26 | FOR BAPCO REVIEW | 2019-07-11 |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 021P0005A | 086067_PDS | 021-G-DAT-40043-001 | PUMP DATA SHEET 021P0005A/B | A1001 | AX | 2 | 2019-06-22 | CON-BMP-VTRA-012393 | 2019-06-22 | FOR BAPCO REVIEW | 2019-07-08 |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 021P0005A | 086067_PPC | 021-G-DAT-40059-001 | PUMP PERFORMANCE CURVE - 021P0005 A/B | A1002 | AX | 2 | 2019-06-25 | CON-BMP-VTRA-012444 | 2019-06-25 | FOR BAPCO REVIEW | 2019-07-09 |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 021P0005A | 086067_TEN | 021-G-GAD-40040-001 | MECHANICAL SEAL CROSS-SECTIONAL DRAWING - 021P0005 A/B | A1106 | AX | 2 | 2019-07-11 | CON-BMP-VTRA-012819 | 2019-07-11 | FOR BAPCO REVIEW | 2019-07-25 |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 021P0006A | 086068_GAD | 021-G-GAD-40057-001 | GENERAL ARRANGEMENT DRAWING FOR EJECTOR RECEIVER WATER PUMPS 021P0006 A/B | A2001 | AX | 2 | 2019-06-26 | CON-BMP-VTRA-012507 | 2019-06-26 | FOR BAPCO REVIEW | 2019-07-11 |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 021P0006A | 086068_PDS | 021-G-DAT-40044-001 | PUMP DATA SHEET 021P0006A/B | A1001 | AX | 2 | 2019-06-22 | CON-BMP-VTRA-012393 | 2019-06-22 | FOR BAPCO REVIEW | 2019-07-08 |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 021P0006A | 086068_PPC | 021-G-DAT-40060-001 | PUMP PERFORMANCE CURVE - 021P0006 A/B | A1002 | AX | 2 | 2019-06-25 | CON-BMP-VTRA-012444 | 2019-06-25 | FOR BAPCO REVIEW | 2019-07-09 |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 021P0006A | 086068_TEN | 021-G-GAD-40041-001 | MECHANICAL SEAL CROSS-SECTIONAL DRAWING - 021P0006 A/B | A1106 | AX | 2 | 2019-07-11 | CON-BMP-VTRA-012819 | 2019-07-11 | FOR BAPCO REVIEW | 2019-07-25 |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 021P0007A | 086045_PDS | 021-G-DAT-40041-001 | PUMP DATA SHEET 021P0007A/B | A1001 | AX | 2 | 2019-06-22 | CON-BMP-VTRA-012393 | 2019-06-22 | FOR BAPCO REVIEW | 2019-07-08 |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 021P0007A | 086045_PPC | 021-G-DAT-40057-001 | PUMP PERFORMANCE CURVE - 021P0007 A/B | A1002 | AX | 2 | 2019-06-25 | CON-BMP-VTRA-012455 | 2019-06-25 | FOR BAPCO REVIEW | 2019-07-10 |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 021P0007A | 086045_SYS | 021-G-GAD-40034-001 | SEAL SYSTEM DRAWING 021P0007A/B | A1103 | AX | 2 | 2019-07-02 | CON-BMP-VTRA-012624 | 2019-07-02 | FOR BAPCO REVIEW | 2019-07-17 |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 021P0007A | 086045_TEN | 021-G-GAD-40038-001 | MECHANICAL SEAL CROSS-SECTIONAL DRAWING 021P0007A/B | A1106 | AX | 2 | 2019-06-01 | CON-BMP-VTRA-011909 | 2019-06-01 | FOR BAPCO INFORMATION | 2019-06-17 | 2019-07-08 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001199 | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 021P0008A | 086069_GAD | 021-G-GAD-40058-001 | GENERAL ARRANGEMENT DRAWING FOR BACKWASH PUMPS 021P0008 A/B | A2001 | AX | 2 | 2019-06-26 | CON-BMP-VTRA-012507 | 2019-06-26 | FOR BAPCO REVIEW | 2019-07-11 |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 021P0008A | 086069_PDS | 021-G-DAT-40045-001 | PUMP DATA SHEET 021P0008 A/B | A1001 | AX | 2 | 2019-06-26 | CON-BMP-VTRA-012496 | 2019-06-26 | FOR BAPCO REVIEW | 2019-07-11 |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 021P0008A | 086069_PPC | 021-G-DAT-40061-001 | PUMP PERFORMANCE CURVE - 021P0008 A/B | A1002 | AX | 2 | 2019-06-25 | CON-BMP-VTRA-012444 | 2019-06-25 | FOR BAPCO REVIEW | 2019-07-09 |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 021P0008A | 086069_TEN | 021-G-GAD-40042-001 | MECHANICAL SEAL CROSS-SECTIONAL DRAWING - 021P0008 A/B | A1106 | AX | 2 | 2019-07-11 | CON-BMP-VTRA-012819 | 2019-07-11 | FOR BAPCO REVIEW | 2019-07-25 |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 021P0012A | 086070_GAD | 021-G-GAD-40059-001 | GENERAL ARRANGEMENT DRAWING FOR FLARE KO DRUM PUMP 021P0012 A/B | A2001 | AX | 2 | 2019-06-26 | CON-BMP-VTRA-012507 | 2019-06-26 | FOR BAPCO REVIEW | 2019-07-11 |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 021P0012A | 086070_PDS | 021-G-DAT-40046-001 | PUMP DATA SHEET 021P0012 A/B | A1001 | AX | 2 | 2019-06-26 | CON-BMP-VTRA-012496 | 2019-06-26 | FOR BAPCO REVIEW | 2019-07-11 |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 021P0012A | 086070_PPC | 021-G-DAT-40062-001 | PUMP PERFORMANCE CURVE - 021P0012 A/B | A1002 | AX | 2 | 2019-06-25 | CON-BMP-VTRA-012455 | 2019-06-25 | FOR BAPCO REVIEW | 2019-07-10 |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 021P0012A | 086070_SYS | 021-G-GAD-40036-001 | SEAL SYSTEM DRAWING 021P0012A/B | A1103 | AX | 2 | 2019-07-02 | CON-BMP-VTRA-012624 | 2019-07-02 | FOR BAPCO REVIEW | 2019-07-17 |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 021P0012A | 086070_TEN | 021-G-GAD-40043-001 | MECHANICAL SEAL CROSS-SECTIONAL DRAWING - 021P0012 A/B | A1106 | AX | 2 | 2019-07-11 | CON-BMP-VTRA-012819 | 2019-07-11 | FOR BAPCO REVIEW | 2019-07-25 |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 023M0001A | 086071_MCU | 023-G-DAT-40013-001 | MOTOR PERFORMANCE CURVE - 023M0001 A/B | A4104 | AX | 2 | 2019-07-11 | CON-BMP-VTRA-012814 | 2019-07-11 | FOR BAPCO REVIEW | 2019-07-25 |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 023M0001A | 086071_MDS | 023-G-DAT-40011-001 | MOTOR DATA SHEET - 023M0001 A/B | A4102 | AX | 2 | 2019-06-26 | CON-BMP-VTRA-012504 | 2019-06-26 | FOR BAPCO REVIEW | 2019-07-11 | 2019-07-09 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001245 | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 023M0001A | 086071_MOT | 023-G-GAD-40012-001 | MOTOR OUTLINE DRAWING (INCLUDING NAMEPLATE WIRING DETAILS AND TERMINAL BOX DWG) - 023M0001A/B | A4207 | AX | 2 | 2019-07-11 | CON-BMP-VTRA-012807 | 2019-07-11 | FOR BAPCO REVIEW | 2019-07-25 |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 023M0002A | 086046_MDS | 023-G-DAT-40010-001 | MOTOR DATA SHEET - 023M0002 A/B | A4102 | AX | 2 | 2019-06-18 | CON-BMP-VTRA-012282 | 2019-06-18 | FOR BAPCO REVIEW | 2019-07-03 | 2019-07-10 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000584 | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 023M0002A | 086046_MNP | 023-G-DLB-40003-001 | NAME PLATE (EL. MOTORS) 023M0002A/B | A4205 | AX | 2 | 2019-07-10 | CON-BMP-VTRA-012804 | 2019-07-10 | FOR BAPCO REVIEW | 2019-07-25 |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 023M0002A | 086046_MOT | 023-G-GAD-40011-001 | MOTOR OUTLINE DRAWING (INCLUDING NAMEPLATE, WIRING DETAILS AND TERMINAL BOX DWG) 023M0002A/B | A4206 | AX | 2 | 2019-07-11 | CON-BMP-VTRA-012807 | 2019-07-11 | FOR BAPCO REVIEW | 2019-07-25 |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 023P0001A | 086071_GAD | 023-G-GAD-40010-001 | GENERAL ARRANGEMENT DRAWING 023P0001 A/B | A2001 | AX | 2 | 2019-06-26 | CON-BMP-VTRA-012509 | 2019-06-26 | FOR BAPCO REVIEW | 2019-07-11 |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 023P0001A | 086071_PDS | 023-G-DAT-40004-001 | PUMP DATA SHEET 023P0001 A/B | A1001 | AX | 2 | 2019-06-26 | CON-BMP-VTRA-012497 | 2019-06-26 | FOR BAPCO REVIEW | 2019-07-11 |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 023P0001A | 086071_PPC | 023-G-DAT-40008-001 | PUMP PERFORMANCE CURVE - 023P0001 A/B | A1002 | AX | 2 | 2019-06-25 | CON-BMP-VTRA-012456 | 2019-06-25 | FOR BAPCO REVIEW | 2019-07-10 |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 023P0001A | 086071_SYS | 023-G-GAD-40004-001 | SEAL SYSTEM DRAWING 023P0001A/B | A1103 | AX | 2 | 2019-07-02 | CON-BMP-VTRA-012625 | 2019-07-02 | FOR BAPCO REVIEW | 2019-07-17 |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 023P0001A | 086071_TEN | 023-G-GAD-40006-001 | MECHANICAL SEAL CROSS-SECTIONAL DRAWING - 023P0001 A/B | A1106 | AX | 2 | 2019-07-11 | CON-BMP-VTRA-012820 | 2019-07-11 | FOR BAPCO REVIEW | 2019-07-26 |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 023P0002A | 086046_GAD | 023-G-GAD-40009-001 | GENERAL ARRANGEMENT DRAWING PUMP TYPE D H400/100 023P0002A/B | A2001 | AX | 2 | 2019-05-24 | CON-BMP-VTRA-011789 | 2019-05-24 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 023P0002A | 086046_PDS | 023-G-DAT-40003-001 | PUMP DATA SHEET 023P0002 A/B | A1001 | AX | 2 | 2019-06-26 | CON-BMP-VTRA-012497 | 2019-06-26 | FOR BAPCO REVIEW | 2019-07-11 |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 023P0002A | 086046_PPC | 023-G-DAT-40007-001 | PUMP PERFORMANCE CURVE - 023P0002 A/B | A1002 | AX | 2 | 2019-06-25 | CON-BMP-VTRA-012445 | 2019-06-25 | FOR BAPCO REVIEW | 2019-07-09 |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 023P0002A | 086046_SYS | 023-G-GAD-40003-001 | SEAL SYSTEM DRAWING 023P0002A/B | A1103 | AX | 2 | 2019-07-02 | CON-BMP-VTRA-012625 | 2019-07-02 | FOR BAPCO REVIEW | 2019-07-17 |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 023P0002A | 086046_TEN | 023-G-GAD-40005-001 | MECHANICAL SEAL CROSS-SECTIONAL DRAWING 023P0002A/B | A1106 | AX | 2 | 2019-07-11 | CON-BMP-VTRA-012820 | 2019-07-11 | FOR BAPCO REVIEW | 2019-07-26 |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 050M5077 | 086072_MCU | 050-G-DAT-40022-001 | MOTOR PERFORMANCE CURVE - 050M5077 | A4104 | AX | 2 | 2019-07-11 | CON-BMP-VTRA-012815 | 2019-07-11 | FOR BAPCO REVIEW | 2019-07-25 |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 050M5077 | 086072_MDS | 050-G-DAT-40019-001 | MOTOR DATA SHEET - 050M5077 | A4102 | AX | 2 | 2019-06-25 | CON-BMP-VTRA-012449 | 2019-06-25 | FOR BAPCO REVIEW | 2019-07-10 | 2019-07-11 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001286 | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 050M5077 | 086072_MOT | 050-G-GAD-40013-001 | MOTOR OUTLINE DRAWING (INCLUDING NAMEPLATE, WIRING DETAILS AND TERMINAL BOX DWG) - 050M5077 | A4206 | AX | 2 | 2019-07-11 | CON-BMP-VTRA-012808 | 2019-07-11 | FOR BAPCO REVIEW | 2019-07-25 |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 050M5080A | 086073_MCU | 050-G-DAT-40023-001 | MOTOR PERFORMANCE CURVE - 050M5080 A/B/C | A4104 | AX | 2 | 2019-07-11 | CON-BMP-VTRA-012815 | 2019-07-11 | FOR BAPCO REVIEW | 2019-07-25 |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 050M5080A | 086073_MDS | 050-G-DAT-40020-001 | MOTOR DATA SHEET - 050M5080 A/B/C | A4102 | AX | 2 | 2019-06-25 | CON-BMP-VTRA-012449 | 2019-06-25 | FOR BAPCO REVIEW | 2019-07-10 | 2019-07-11 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001286 | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 050M5080A | 086073_MOT | 050-G-GAD-40014-001 | MOTOR OUTLINE DRAWING (INCLUDING NAMEPLATE, WIRING DETAILS AND TERMINAL BOX DWG) - 050M5080 A/B/C | A4206 | AX | 2 | 2019-07-11 | CON-BMP-VTRA-012808 | 2019-07-11 | FOR BAPCO REVIEW | 2019-07-25 |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 050P5030 | 086072_GAD | 050-G-GAD-40010-001 | GENERAL ARRANGEMENT DRAWING PUMP TYPE R 700/150 050P5030 | A2001 | AX | 2 | 2019-06-13 | CON-BMP-VTRA-012181 | 2019-06-13 | FOR BAPCO REVIEW | 2019-06-27 | 2019-06-25 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001031 | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 050P5030 | 086072_PDS | 050-G-DAT-40006-001 | PUMP DATA SHEET 050P5030 | A1001 | AX | 2 | 2019-06-26 | CON-BMP-VTRA-012498 | 2019-06-26 | FOR BAPCO REVIEW | 2019-07-11 | 2019-07-10 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001262 | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 050P5030 | 086072_PPC | 050-G-DAT-40015-001 | PUMP PERFORMANCE CURVE - 050P5030 | A1002 | AX | 2 | 2019-06-25 | CON-BMP-VTRA-012457 | 2019-06-25 | FOR BAPCO REVIEW | 2019-07-10 | 2019-07-10 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001261 | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 050P5030 | 086072_TEN | 050-G-GAD-40004-001 | MECHANICAL SEAL CROSS-SECTIONAL DRAWING - 050P5030 | A1106 | AX | 2 | 2019-07-11 | CON-BMP-VTRA-012824 | 2019-07-11 | FOR BAPCO REVIEW | 2019-07-26 |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 050P5033A | 086073_GAD | 050-G-GAD-40011-001 | GENERAL ARRANGEMENT DRAWING PUMP TYPE R 700/200 050P5033A/B/C | A2001 | AX | 2 | 2019-06-13 | CON-BMP-VTRA-012181 | 2019-06-13 | FOR BAPCO REVIEW | 2019-06-27 | 2019-06-25 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001031 | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 050P5033A | 086073_PDS | 050-G-DAT-40010-001 | PUMP DATA SHEET 050P5033 A/B/C | A1001 | AX | 2 | 2019-06-26 | CON-BMP-VTRA-012498 | 2019-06-26 | FOR BAPCO REVIEW | 2019-07-11 | 2019-07-10 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001262 | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 050P5033A | 086073_PPC | 050-G-DAT-40016-001 | PUMP PERFORMANCE CURVE - 050P5033 A/B/C | A1002 | AX | 2 | 2019-06-25 | CON-BMP-VTRA-012457 | 2019-06-25 | FOR BAPCO REVIEW | 2019-07-10 | 2019-07-10 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001261 | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 050P5033A | 086073_TEN | 050-G-GAD-40005-001 | MECHANICAL SEAL CROSS-SECTIONAL DRAWING - 050P5033 A/B/C | A1106 | AX | 2 | 2019-07-11 | CON-BMP-VTRA-012824 | 2019-07-11 | FOR BAPCO REVIEW | 2019-07-26 |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 050P5038A | 086074_GAD | 050-G-GAD-40012-001 | GENERAL ARRANGEMENT DRAWING PUMP TYPE R 400/150 050P5038A/B | A2001 | AX | 2 | 2019-06-13 | CON-BMP-VTRA-012181 | 2019-06-13 | FOR BAPCO REVIEW | 2019-06-27 | 2019-06-25 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001031 | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 056M5606 | 086047_MDS | 056-G-DAT-40016-001 | MOTOR DATA SHEET - 056M5606 | A4102 | AX | 2 | 2019-06-25 | CON-BMP-VTRA-012450 | 2019-06-25 | FOR BAPCO REVIEW | 2019-07-10 | 2019-07-10 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001284 | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 056M5606 | 086047_MOT | 056-G-GAD-40010-001 | MOTOR OUTLINE DRAWING (INCLUDING NAMEPLATE WIRING DETAILS AND TERMINAL BOX DWG) 056M5606 | A4206 | AX | 2 | 2019-07-11 | CON-BMP-VTRA-012809 | 2019-07-11 | FOR BAPCO REVIEW | 2019-07-25 |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 056M5627A | 086079_GAD | 056-G-GAD-40001-001 | GENERAL ARRANGEMENT DRAWING PUMP TYPE R 505/150 056P5627A/B | A2001 | AX | 2 | 2019-06-13 | CON-BMP-VTRA-012182 | 2019-06-13 | FOR BAPCO REVIEW | 2019-06-27 | 2019-06-25 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001032 | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 056M5627A | 086079_PPC | 056-G-DAT-40014-001 | PUMP PERFORMANCE CURVE - 056P5627 A/B | A1002 | AX | 2 | 2019-06-25 | CON-BMP-VTRA-012458 | 2019-06-25 | FOR BAPCO REVIEW | 2019-07-10 | 2019-07-10 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001256 | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 056P5606 | 086047_PDS | 056-G-DAT-40007-001 | PUMP DATA SHEET 056P5606 | A1001 | AX | 2 | 2019-06-26 | CON-BMP-VTRA-012499 | 2019-06-26 | FOR BAPCO REVIEW | 2019-07-11 | 2019-07-10 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001263 | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 056P5606 | 086047_PPC | 056-G-DAT-40013-001 | PUMP PERFORMANCE CURVE - 056P5606 | A1002 | AX | 2 | 2019-06-25 | CON-BMP-VTRA-012446 | 2019-06-25 | FOR BAPCO REVIEW | 2019-07-09 | 2019-07-10 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001258 | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 056P5606 | 086047_TEN | 056-G-GAD-40005-001 | MECHANICAL SEAL CROSS-SECTIONAL DRAWING - 056P5606 | A1106 | AX | 2 | 2019-07-11 | CON-BMP-VTRA-012821 | 2019-07-11 | FOR BAPCO REVIEW | 2019-07-26 |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 056P5627A | 086079_PDS | 056-G-DAT-40010-001 | PUMP DATA SHEET 056P5627 A/B | A1001 | AX | 2 | 2019-06-26 | CON-BMP-VTRA-012499 | 2019-06-26 | FOR BAPCO REVIEW | 2019-07-11 | 2019-07-10 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001263 | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 056P5627A | 086079_SYS | 056-G-GAD-40004-001 | SEAL SYSTEM DRAWING 056P5627A/B | A1103 | AX | 2 | 2019-07-02 | CON-BMP-VTRA-012622 | 2019-07-02 | FOR BAPCO REVIEW | 2019-07-17 |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 056P5627A | 086079_TEN | 056-G-GAD-40006-001 | MECHANICAL SEAL CROSS-SECTIONAL DRAWING - 056P5627 A/B | A1106 | AX | 2 | 2019-07-11 | CON-BMP-VTRA-012821 | 2019-07-11 | FOR BAPCO REVIEW | 2019-07-26 |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 079P0002A | 086075_GAD | 079-G-GAD-40001-001 | GENERAL ARRANGEMENT DRAWING PUMP TYPE R 175/38 079P0002A/B | A2001 | AX | 2 | 2019-06-18 | CON-BMP-VTRA-012275 | 2019-06-18 | FOR BAPCO REVIEW | 2019-07-03 | 2019-07-01 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001131 | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 081M8102A | 086076_MCU | 081-G-DAT-40007-001 | MOTOR PERFORMANCE CURVE - 081M8102 A/B | A4104 | AX | 2 | 2019-07-11 | CON-BMP-VTRA-012816 | 2019-07-11 | FOR BAPCO REVIEW | 2019-07-25 |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 081M8102A | 086076_MDS | 081-G-DAT-40006-001 | MOTOR DATA SHEET - 081M8102 A/B | A4102 | AX | 2 | 2019-06-25 | CON-BMP-VTRA-012451 | 2019-06-25 | FOR BAPCO REVIEW | 2019-07-10 | 2019-07-10 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001283 | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 081M8102A | 086076_MOT | 081-G-GAD-40006-001 | MOTOR OUTLINE DRAWING (INCLUDING NAMEPLATE, WIRING DETAILS AND TERMINAL BOX DWG) - 081M8102 A/B | A4206 | AX | 2 | 2019-07-11 | CON-BMP-VTRA-012810 | 2019-07-11 | FOR BAPCO REVIEW | 2019-07-25 |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 081P8102A | 086076_GAD | 081-G-GAD-40001-001 | GENERAL ARRANGEMENT DRAWING PUMP TYPE R 400/50 081P8102A/B | A2001 | AX | 2 | 2019-06-13 | CON-BMP-VTRA-012183 | 2019-06-13 | FOR BAPCO REVIEW | 2019-06-27 | 2019-06-25 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001030 | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 081P8102A | 086076_PDS | 081-G-DAT-40002-001 | PUMP DATA SHEET 081P8102 A/B | A1001 | AX | 2 | 2019-06-26 | CON-BMP-VTRA-012500 | 2019-06-26 | FOR BAPCO REVIEW | 2019-07-11 | 2019-07-10 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001246 | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 081P8102A | 086076_PPC | 081-G-DAT-40004-001 | PUMP PERFORMANCE CURVE - 081P8102 A/B | A1002 | AX | 2 | 2019-06-25 | CON-BMP-VTRA-012459 | 2019-06-25 | FOR BAPCO REVIEW | 2019-07-10 | 2019-07-10 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001254 | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 081P8102A | 086076_SYS | 081-G-GAD-40003-001 | SEAL SYSTEM DRAWING 081P8102A/B | A1103 | AX | 2 | 2019-07-02 | CON-BMP-VTRA-012626 | 2019-07-02 | FOR BAPCO REVIEW | 2019-07-17 |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 081P8102A | 086076_TEN | 081-G-GAD-40004-001 | MECHANICAL SEAL CROSS-SECTIONAL DRAWING - 081P8102 A/B | A1106 | AX | 2 | 2019-07-11 | CON-BMP-VTRA-012822 | 2019-07-11 | FOR BAPCO REVIEW | 2019-07-26 |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 082M0001A | 086077_MDS | 082-G-DAT-40010-001 | MOTOR DATA SHEET - 082M0001 A/B | A4102 | AX | 2 | 2019-06-25 | CON-BMP-VTRA-012452 | 2019-06-25 | FOR BAPCO REVIEW | 2019-07-10 | 2019-07-10 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001282 | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 082M0001A | 086077_MOT | 082-G-GAD-40011-001 | MOTOR OUTLINE DRAWING (INCLUDING NAMEPLATE, WIRING DETAILS AND TERMINAL BOX DWG) - 082M0001 A/B | A4206 | AX | 2 | 2019-07-11 | CON-BMP-VTRA-012811 | 2019-07-11 | FOR BAPCO REVIEW | 2019-07-25 |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 082M0002A | 086078_MCU | 082-G-DAT-40013-001 | MOTOR PERFORMANCE CURVE - 082M0002 A/B | A4104 | AX | 2 | 2019-07-11 | CON-BMP-VTRA-012817 | 2019-07-11 | FOR BAPCO REVIEW | 2019-07-25 |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 082M0002A | 086078_MDS | 082-G-DAT-40011-001 | MOTOR DATA SHEET - 082M0002 A/B | A4102 | AX | 2 | 2019-06-25 | CON-BMP-VTRA-012452 | 2019-06-25 | FOR BAPCO REVIEW | 2019-07-10 | 2019-07-10 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001282 | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 082M0002A | 086078_MOT | 082-G-GAD-40012-001 | MOTOR OUTLINE DRAWING (INCLUDING NAMEPLATE, WIRING DETAILS AND TERMINAL BOX DWG) - 082M0002 A/B | A4206 | AX | 2 | 2019-07-11 | CON-BMP-VTRA-012811 | 2019-07-11 | FOR BAPCO REVIEW | 2019-07-25 |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 082P0001A | 086077_GAD | 082-G-GAD-40001-001 | GENERAL ARRANGEMENT DRAWING PUMP TYPE R 400/50 082P0001A/B | A2001 | AX | 2 | 2019-06-13 | CON-BMP-VTRA-012184 | 2019-06-13 | FOR BAPCO REVIEW | 2019-06-27 | 2019-06-25 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001029 | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 082P0001A | 086077_PDS | 082-G-DAT-40003-001 | PUMP DATA SHEET 082P0001 A/B | A1001 | AX | 2 | 2019-06-26 | CON-BMP-VTRA-012501 | 2019-06-26 | FOR BAPCO REVIEW | 2019-07-11 | 2019-07-10 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001264 | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 082P0001A | 086077_PPC | 082-G-DAT-40007-001 | PUMP PERFORMANCE CURVE - 082P0001 A/B | A1002 | AX | 2 | 2019-06-25 | CON-BMP-VTRA-012460 | 2019-06-25 | FOR BAPCO REVIEW | 2019-07-10 | 2019-07-10 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001251 | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 082P0001A | 086077_SYS | 082-G-GAD-40005-001 | SEAL SYSTEM DRAWING 082P0001A/B | A1103 | AX | 2 | 2019-07-03 | CON-BMP-VTRA-012633 | 2019-07-03 | FOR BAPCO REVIEW | 2019-07-17 |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 082P0001A | 086077_TEN | 082-G-GAD-40007-001 | MECHANICAL SEAL CROSS-SECTIONAL DRAWING - 082P0001 A/B | A1106 | AX | 2 | 2019-07-11 | CON-BMP-VTRA-012823 | 2019-07-11 | FOR BAPCO REVIEW | 2019-07-26 |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 082P0002A | 086078_GAD | 082-G-GAD-40002-001 | GENERAL ARRANGEMENT DRAWING PUMP TYPE R 320/25 082P0002A/B | A2001 | AX | 2 | 2019-06-13 | CON-BMP-VTRA-012184 | 2019-06-13 | FOR BAPCO REVIEW | 2019-06-27 | 2019-06-25 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001029 | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 082P0002A | 086078_PDS | 082-G-DAT-40004-001 | PUMP DATA SHEET 082P0002 A/B | A1001 | AX | 2 | 2019-06-26 | CON-BMP-VTRA-012501 | 2019-06-26 | FOR BAPCO REVIEW | 2019-07-11 | 2019-07-10 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001264 | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 082P0002A | 086078_PPC | 082-G-DAT-40008-001 | PUMP PERFORMANCE CURVE - 082P0002 A/B | A1002 | AX | 2 | 2019-06-25 | CON-BMP-VTRA-012460 | 2019-06-25 | FOR BAPCO REVIEW | 2019-07-10 | 2019-07-10 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001251 | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 082P0002A | 086078_SYS | 082-G-GAD-40006-001 | SEAL SYSTEM DRAWING 082P0002A/B | A1103 | AX | 2 | 2019-07-03 | CON-BMP-VTRA-012633 | 2019-07-03 | FOR BAPCO REVIEW | 2019-07-17 |  |  | CLASS 2
076551C-000R-MR-0910-101 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WEIR GABBIONETA SRL | 082P0002A | 086078_TEN | 082-G-GAD-40008-001 | MECHANICAL SEAL CROSS-SECTIONAL DRAWING - 082P0002 A/B | A1106 | AX | 2 | 2019-07-11 | CON-BMP-VTRA-012823 | 2019-07-11 | FOR BAPCO REVIEW | 2019-07-26 |  |  | CLASS 2
076551C-000R-MR-0910-103 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WORTHINGTON S.r.l. | 018M0009B | PPL-0445611 | 000-G-TSP-40013-001 | PAINTING SPECIFICATION ALL ITEMS | A0106 | AX | 1 | 2019-06-28 | CON-BMP-VTRA-012639 | 2019-07-03 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0910-103 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WORTHINGTON S.r.l. | 018M0009B | VDL-0445611 | 000-G-INX-40018-001 | LIST OF VENDOR'S DOCUMENT AND DRAWING ALL ITEMS | A0001 | AX | 1 | 2019-06-28 | CON-BMP-VTRA-012640 | 2019-07-03 | FOR BAPCO REVIEW | 2019-07-17 |  |  | CLASS 2
076551C-000R-MR-0910-103 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WORTHINGTON S.r.l. | 018P0009B | PDS-0445411 | 018-G-DAT-40441-001 | PUMP DATA SHEET 018P0009B | A1001 | AX | 1 | 2019-06-28 | CON-BMP-VTRA-012545 | 2019-06-28 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0910-103 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WORTHINGTON S.r.l. | 018P0025A | PDS-0445611 | 018-G-DAT-40444-001 | PUMP DATA SHEET 018P0025A/B | A1001 | AX | 1 | 2019-06-28 | CON-BMP-VTRA-012545 | 2019-06-28 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0910-103 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | WORTHINGTON S.r.l. | 018T0009A | PDS-0445401 | 018-G-DAT-40443-001 | PUMP DATA SHEET 018P0009A | A1001 | AX | 1 | 2019-06-28 | CON-BMP-VTRA-012545 | 2019-06-28 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0910-106 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | TERMOMECCANICA POMPE | 018M0008A | 2027495001 | 018-G-DAT-40413-001 | DATA SHEET DIESEL PRODUCT PUMPS 018P0008A/B | A1001 | AX | 1 | 2019-06-27 | CON-BMP-VTRA-012528 | 2019-06-27 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0910-106 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | TERMOMECCANICA POMPE | 018P0008A | 2027495000 | 018-G-GAD-40327-001 | GENERAL ARRANGEMENT 018P0008A/B | A2001 | AX | 2 | 2019-06-27 | CON-BMP-VTRA-012534 | 2019-06-27 | FOR BAPCO REVIEW | 2019-07-12 |  |  | CLASS 2
076551C-000R-MR-0910-106 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | TERMOMECCANICA POMPE | 018P0008A | 2027495050 | 018-G-PID-40047-001 | P&ID - DIESEL PRODUCT PUMPS FOR 018P0008A/B | A0103 | AX | 2 | 2019-06-27 | CON-BMP-VTRA-012533 | 2019-06-27 | FOR BAPCO REVIEW | 2019-07-11 |  |  | CLASS 2
076551C-000R-MR-0910-106 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | TERMOMECCANICA POMPE | 018P0008A | PCQ_1974 | 018-G-ITP-40030-001 | PUMP QUALITY CONTROL PLAN DIESEL PRODUCT PUMPS 018P0008A/B | B1002 | AX | 2 | 2019-07-08 | CON-BMP-VTRA-012700 | 2019-07-08 | FOR BAPCO REVIEW | 2019-07-22 |  |  | CLASS 2
076551C-000R-MR-0910-106 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | TERMOMECCANICA POMPE | 018P0017A | 2027595000 | 018-G-GAD-40328-001 | GENERAL ARRANGEMENT FOR 018P0017B | A2001 | AX | 2 | 2019-06-27 | CON-BMP-VTRA-012534 | 2019-06-27 | FOR BAPCO REVIEW | 2019-07-12 |  |  | CLASS 2
076551C-000R-MR-0910-106 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | TERMOMECCANICA POMPE | 018P0017A | 2027695000 | 018-G-GAD-40329-001 | GENERAL ARRANGEMENT FOR 018P0017A | A2001 | AX | 2 | 2019-06-27 | CON-BMP-VTRA-012534 | 2019-06-27 | FOR BAPCO REVIEW | 2019-07-12 |  |  | CLASS 2
076551C-000R-MR-0910-106 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | TERMOMECCANICA POMPE | 018P0017A | 2027695001 | 018-G-DAT-40415-001 | PUMP DATA SHEET VACUUM COLUMNBTMS PUMPS 018P0017A | A1001 | AX | 1 | 2019-06-27 | CON-BMP-VTRA-012528 | 2019-06-27 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0910-106 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | TERMOMECCANICA POMPE | 018P0017A | 2027695050 | 018-G-PID-40049-001 | P&ID - VACUUM COLUMN BOTTOMS PUMPS FOR 018P0017A | A0103 | AX | 2 | 2019-06-27 | CON-BMP-VTRA-012533 | 2019-06-27 | FOR BAPCO REVIEW | 2019-07-11 |  |  | CLASS 2
076551C-000R-MR-0910-106 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | TERMOMECCANICA POMPE | 018P0017A | PCQ_1975 | 018-G-ITP-40032-001 | PUMP QUALITY CONTROL PLAN VACUUM COLUMN BTMS PUMPS 018P0017A/B | B1002 | AX | 2 | 2019-07-08 | CON-BMP-VTRA-012700 | 2019-07-08 | FOR BAPCO REVIEW | 2019-07-22 |  |  | CLASS 2
076551C-000R-MR-0910-106 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | TERMOMECCANICA POMPE | 018P0017B | 2027595001 | 018-G-DAT-40414-001 | PUMP DATA SHEET VACUUM COLUMN BTMS PUMPS VACUUM COLUMN BTMS PUMPS 018P0017B | A1001 | AX | 1 | 2019-06-27 | CON-BMP-VTRA-012528 | 2019-06-27 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0910-106 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | TERMOMECCANICA POMPE | 018P0027A | 2027395000 | 018-G-GAD-40326-001 | GENERAL ARRANGEMENT FOR 018P0027A/B | A2001 | AX | 2 | 2019-06-27 | CON-BMP-VTRA-012534 | 2019-06-27 | FOR BAPCO REVIEW | 2019-07-12 |  |  | CLASS 2
076551C-000R-MR-0910-106 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | TERMOMECCANICA POMPE | 018P0027A | 2027395001 | 018-G-DAT-40412-001 | PUMP DATA SHEET SHORT CIRCULATION PUMPS 018P0027A/B | A1001 | AX | 1 | 2019-06-27 | CON-BMP-VTRA-012528 | 2019-06-27 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0910-106 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | TERMOMECCANICA POMPE | 018P0027A | 2027395050 | 018-G-PID-40046-001 | P&ID - SHORT CIRCULATION PUMPSFOR 018P0027A/B | A0103 | AX | 2 | 2019-06-27 | CON-BMP-VTRA-012533 | 2019-06-27 | FOR BAPCO REVIEW | 2019-07-11 |  |  | CLASS 2
076551C-000R-MR-0910-106 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | TERMOMECCANICA POMPE | 018P0027A | PCQ_1973 | 018-G-ITP-40029-001 | PUMP QUALITY CONTROL PLAN SHORT CIRCULATION PUMPS 018P0027A/B | B1002 | AX | 2 | 2019-07-08 | CON-BMP-VTRA-012700 | 2019-07-08 | FOR BAPCO REVIEW | 2019-07-22 |  |  | CLASS 2
076551C-000R-MR-0910-106 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | TERMOMECCANICA POMPE | 018P0028A | 2027895000 | 018-G-GAD-40325-001 | GENERAL ARRANGEMENT FOR 018P0028A | A2001 | AX | 2 | 2019-06-27 | CON-BMP-VTRA-012534 | 2019-06-27 | FOR BAPCO REVIEW | 2019-07-12 |  |  | CLASS 2
076551C-000R-MR-0910-106 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | TERMOMECCANICA POMPE | 018P0028A | 2027895001 | 018-G-DAT-40417-001 | PUMP DATA SHEET TEMPERED WATER PUMPS 018P0028A | A1001 | AX | 1 | 2019-06-27 | CON-BMP-VTRA-012528 | 2019-06-27 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0910-106 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | TERMOMECCANICA POMPE | 018P0028A | 2027895050 | 018-G-PID-40051-001 | P&ID - TEMPERED WATER PUMPS FOR 018P0028A | A0103 | AX | 2 | 2019-06-27 | CON-BMP-VTRA-012533 | 2019-06-27 | FOR BAPCO REVIEW | 2019-07-11 |  |  | CLASS 2
076551C-000R-MR-0910-106 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | TERMOMECCANICA POMPE | 018P0028A | PCQ_1976 | 018-G-ITP-40033-001 | PUMP QUALITY CONTROL PLAN TEMPERED WATER PUMPS 018P0028A/B | B1002 | AX | 2 | 2019-07-08 | CON-BMP-VTRA-012700 | 2019-07-08 | FOR BAPCO REVIEW | 2019-07-22 |  |  | CLASS 2
076551C-000R-MR-0910-106 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | TERMOMECCANICA POMPE | 018P0028B | 2027795000 | 018-G-GAD-40324-001 | GENERAL ARRANGEMENT FOR 018P0028B | A2001 | AX | 2 | 2019-06-27 | CON-BMP-VTRA-012534 | 2019-06-27 | FOR BAPCO REVIEW | 2019-07-12 |  |  | CLASS 2
076551C-000R-MR-0910-106 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | TERMOMECCANICA POMPE | 018P0028B | 2027795001 | 018-G-DAT-40416-001 | PUMP DATA SHEET TEMPERED WATER PUMPS 018P0028B | A1001 | AX | 1 | 2019-06-27 | CON-BMP-VTRA-012528 | 2019-06-27 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0910-106 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | TERMOMECCANICA POMPE | 050P5031 | 2028095001 | 050-G-DAT-40028-001 | PUMP DATA SHEET KEROSENE PUMP 050P5031 | A1001 | AX | 1 | 2019-06-27 | CON-BMP-VTRA-012527 | 2019-06-27 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0910-106 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | TERMOMECCANICA POMPE | 050P5031 | 2028095050 | 050-G-PID-40005-001 | P&ID - KEROSENE PUMP FOR 050P5031 | A0103 | AX | 2 | 2019-06-27 | CON-BMP-VTRA-012532 | 2019-06-27 | FOR BAPCO REVIEW | 2019-07-11 | 2019-07-10 | 1-APPROVED BMP-ROC-VTRE- 001248 | CLASS 2
076551C-000R-MR-0910-106 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | TERMOMECCANICA POMPE | 050P5031 | PCQ_1978 | 050-G-ITP-40005-001 | PUMP QUALITY CONTROL PLAN KEROSENE PUMP 050P5031 | B1002 | AX | 2 | 2019-07-08 | CON-BMP-VTRA-012701 | 2019-07-08 | FOR BAPCO REVIEW | 2019-07-22 |  |  | CLASS 2
076551C-000R-MR-0910-106 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | TERMOMECCANICA POMPE | 050P5034A | 2027995001 | 050-G-DAT-40027-001 | PUMP DATA SHEET 10PPM DIESEL BOOSTER PUMP 050P5034A/B | A1001 | AX | 1 | 2019-06-27 | CON-BMP-VTRA-012527 | 2019-06-27 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0910-106 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | TERMOMECCANICA POMPE | 050P5034A | 2027995050 | 050-G-PID-40004-001 | P&ID - DIESEL BOOSTER PUMPS FOR 050P5034A/B | A0103 | AX | 2 | 2019-06-27 | CON-BMP-VTRA-012532 | 2019-06-27 | FOR BAPCO REVIEW | 2019-07-11 | 2019-07-10 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001248 | CLASS 2
076551C-000R-MR-0910-106 | MATERIAL REQUISITION FOR API 610 CENTRIFUGAL PUMPS | TERMOMECCANICA POMPE | 050P5034A | PCQ_1977 | 050-G-ITP-40004-001 | PUMP QUALITY CONTROL PLAN 10PPM DIESEL BOOSTER PUMP 050P5034A/B | B1002 | AX | 2 | 2019-07-08 | CON-BMP-VTRA-012701 | 2019-07-08 | FOR BAPCO REVIEW | 2019-07-22 |  |  | CLASS 2
076551C-000R-MR-0920-001 | MATERIAL REQUISITION FOR RECIPROCATING PUMPS | PERONI POMPE S.p.A. | 018M0024A | 2J012-59100-J01 | 018-G-INX-40043-001 | LIST OF VENDOR DOCUMENTS AND DWGS - ALL ITEMS | A0001 | AX | 2 | 2019-05-10 | CON-BMP-VTRA-011526 | 2019-05-10 | FOR BAPCO INFORMATION |  | 2019-06-22 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001016 | CLASS 2
076551C-000R-MR-0920-001 | MATERIAL REQUISITION FOR RECIPROCATING PUMPS | PERONI POMPE S.p.A. | 018M0024A | 2J012-6G001-J01 | 018-G-ITP-40004-001 | FABRICATION AND QUALITY CONTROL PLAN (ITP) - ALL ITEMS | B1002 | AX | 2 | 2019-05-22 | CON-BMP-VTRA-011723 | 2019-05-22 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0920-001 | MATERIAL REQUISITION FOR RECIPROCATING PUMPS | PERONI POMPE S.p.A. | 018P0024A | 00529-574 | 018-G-PED-40007-001 | FOUNDATION LAYOUT AND LOADING PLAN - 018P0024 AB | A2006 | AX | 2 | 2019-06-07 | CON-BMP-VTRA-012101 | 2019-06-07 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-0920-001 | MATERIAL REQUISITION FOR RECIPROCATING PUMPS | PERONI POMPE S.p.A. | 018P0024A | 2J012-54001-A01 | 018-G-DAT-40397-001 | EQUIPMENTT FILLED-IN DATA SHEETS (PUMP) - ITEM 018P0024 AB | A1001 | AX | 2 | 2019-06-07 | CON-BMP-VTRA-012098 | 2019-06-07 | FOR BAPCO REVIEW | 2019-06-21 | 2019-06-24 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001025 | CLASS 2
076551C-000R-MR-0920-001 | MATERIAL REQUISITION FOR RECIPROCATING PUMPS | PERONI POMPE S.p.A. | 018P0024A | 3924K3000000PDI | 018-G-PID-40044-001 | PIPING & INSTRUMENT DIAGRAMS ITEM 018P0024A/B | A0103 | AX | 2 | 2019-06-07 | CON-BMP-VTRA-012102 | 2019-06-07 | FOR BAPCO REVIEW | 2019-06-24 | 2019-06-24 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001022 | CLASS 2
076551C-000R-MR-0920-001 | MATERIAL REQUISITION FOR RECIPROCATING PUMPS | PERONI POMPE S.p.A. | 018P0029A | 00529-575 | 018-G-PED-40008-001 | FOUNDATION LAYOUT AND LOADING PLAN 018P0029 AB | A2006 | AX | 2 | 2019-06-07 | CON-BMP-VTRA-012101 | 2019-06-07 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-0920-001 | MATERIAL REQUISITION FOR RECIPROCATING PUMPS | PERONI POMPE S.p.A. | 018P0029A | 2J012-54001-B01 | 018-G-DAT-40398-001 | EQUIPMENTT FILLED-IN DATA SHEETS (PUMP) - ITEM 018P0029 AB | A1001 | AX | 2 | 2019-06-07 | CON-BMP-VTRA-012098 | 2019-06-07 | FOR BAPCO REVIEW | 2019-06-21 | 2019-06-24 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001025 | CLASS 2
076551C-000R-MR-0920-001 | MATERIAL REQUISITION FOR RECIPROCATING PUMPS | PERONI POMPE S.p.A. | 018P0029A | 316NS5000000PDI | 018-G-PID-40045-001 | PIPING & INSTRUMENT DIAGRAMS -ITEM 018P0029 AB | A0103 | AX | 2 | 2019-06-07 | CON-BMP-VTRA-012102 | 2019-06-07 | FOR BAPCO REVIEW | 2019-06-24 | 2019-06-24 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001022 | CLASS 2
076551C-000R-MR-0960-001 | MATERIAL REQUISITION FOR EBULLATING PUMPS | FLOWSERVE CORPORATION PUMP DIVISION | 018M1002 | 168RLCB03427 | 018-G-INX-40001-001 | LIST OF VENDOR'S DOCUMENTS AND DRAWINGS ALL ITEMS | A0001 | BX | 2 | 2019-05-06 | CON-BMP-VTRA-011402 | 2019-05-06 | FOR BAPCO REVIEW | 2019-05-20 | 2019-05-24 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000757 | CLASS 2
076551C-000R-MR-0960-001 | MATERIAL REQUISITION FOR EBULLATING PUMPS | FLOWSERVE CORPORATION PUMP DIVISION | 018M1002 | 191RLCB03427 | 018-G-DAT-40012-001 | PUMP & MOTOR PERFORMANCE DATA HEAT EXCHANGER & THRUST BEARING ANALYSIS 018P1002/3/6/2002/3/6 018M1002/3/6/2002/3/6 | A4104 | AX | 2 | 2019-03-15 | CON-BMP-VTRA-010699 | 2019-03-15 | FOR BAPCO REVIEW | 2019-04-01 | 2019-03-31 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000426 | CLASS 2
076551C-000R-MR-0960-001 | MATERIAL REQUISITION FOR EBULLATING PUMPS | FLOWSERVE CORPORATION PUMP DIVISION | 018M1002 | 2302RLCB03427 | 018-G-ILD-40003-001 | VFD- LOOP DIAGR (OR TYPICAL I/O DATABASE OR ELECTR FILE) 018M1002/1003/1006/2002/2003/2 006 | A3407 | AX | 2 | 2019-03-15 | CON-BMP-VTRA-010697 | 2019-03-15 | FOR BAPCO REVIEW | 2019-04-01 | 2019-04-05 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000461 | CLASS 2
076551C-000R-MR-0960-001 | MATERIAL REQUISITION FOR EBULLATING PUMPS | FLOWSERVE CORPORATION PUMP DIVISION | 018M1002 | 2310RLCB03427 | 018-G-CWD-40003-001 | VFD SYSTEM CAB.TS PERIPHERALS INTERCONNECT BLOCK DIAGRAMS 018M1002/1003/1006/2002/2003/2 006 | A3304 | AX | 2 | 2019-03-14 | CON-BMP-VTRA-010695 | 2019-03-14 | FOR BAPCO REVIEW | 2019-03-29 | 2019-03-31 | 3-REVIEWED WITH COMMENTS BMP-ROC-VTRE-000431 | CLASS 2
076551C-000R-MR-0960-001 | MATERIAL REQUISITION FOR EBULLATING PUMPS | FLOWSERVE CORPORATION PUMP DIVISION | 018M1002 | 2314RLCB03427 | 018-G-SLD-40001-001 | VFD SINGLE LINE DIAGRAM 018M1002/1003/1006/2002/2003/2 006 | A4108 | AX | 2 | 2019-03-15 | CON-BMP-VTRA-010698 | 2019-03-15 | FOR BAPCO REVIEW | 2019-04-01 | 2019-03-31 | 3-REVIEWED WITH COMMENTS BMP-ROC-VTRE-000428 | CLASS 2
076551C-000R-MR-0960-001 | MATERIAL REQUISITION FOR EBULLATING PUMPS | FLOWSERVE CORPORATION PUMP DIVISION | 018M1002 | 2318RLCB03427 | 018-G-CAL-40008-001 | LIFE CYCLE COST ANALYSIS ALL ITEMS | A1003 | AX | 2 | 2019-07-11 | CON-BMP-VTRA-012825 | 2019-07-11 | FOR BAPCO REVIEW | 2019-07-26 |  |  | CLASS 2
076551C-000R-MR-0960-001 | MATERIAL REQUISITION FOR EBULLATING PUMPS | FLOWSERVE CORPORATION PUMP DIVISION | 018M1002 | 2320RLCB03427 | 018-G-GAD-40009-001 | VFD - CIVIL WORK GUIDE DWGS 018M1002/2002 018M1003/2003 | A2011 | AX | 2 | 2019-03-14 | CON-BMP-VTRA-010691 | 2019-03-14 | FOR BAPCO REVIEW | 2019-03-29 | 2019-03-31 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000423 | CLASS 2
076551C-000R-MR-0960-001 | MATERIAL REQUISITION FOR EBULLATING PUMPS | FLOWSERVE CORPORATION PUMP DIVISION | 018M1002 | 388RLCB03427 | 018-G-GAD-40007-001 | VFD TERMINAL BOX DETAIL DWG WITH TERMINATION DETAILS (FOR VFD AND TRASNSFORMER TOO) 018M1002/1003/1006/2002/2003/2006 | A4206 | AX | 2 | 2019-03-14 | CON-BMP-VTRA-010692 | 2019-03-14 | FOR BAPCO REVIEW | 2019-03-29 | 2019-03-31 | 3-REVIEWED WITH COMMENTS BMP-ROC-VTRE-000424 | CLASS 2
076551C-000R-MR-0960-001 | MATERIAL REQUISITION FOR EBULLATING PUMPS | FLOWSERVE CORPORATION PUMP DIVISION | 018M1002 | 634RLCB03427 | 018-G-CWD-40004-001 | VFD WIRING DIARGRAM (INTERNAL AND/OR INTERPANEL) 018M1002/1003/1006/ 2002/2003/2006 | A4211 | AX | 2 | 2019-03-15 | CON-BMP-VTRA-010696 | 2019-03-15 | FOR BAPCO REVIEW | 2019-04-01 | 2019-04-05 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000460 | CLASS 2
076551C-000R-MR-0960-001 | MATERIAL REQUISITION FOR EBULLATING PUMPS | FLOWSERVE CORPORATION PUMP DIVISION | 018M1002 | 740RLCB03427 | 018-G-RPT-40001-001 | UTILITIES CONSUMPTION LIST ALL ITEMS | A1014 | BX | 2 | 2019-06-05 | CON-BMP-VTRA-012009 | 2019-06-05 | FOR BAPCO REVIEW | 2019-06-20 | 2019-06-22 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001017 | CLASS 3
076551C-000R-MR-0960-001 | MATERIAL REQUISITION FOR EBULLATING PUMPS | FLOWSERVE CORPORATION PUMP DIVISION | 018M1002 | 903RLCB03427 | 018-G-INV-00001-001 | UNPRICED COPIES OF MAIN SUBORDERS LIST ALL ITEMS | C1005 | AX | 4 | 2018-12-19 | CON-BMP-VTRA-010170 | 2018-12-19 | FOR BAPCO REVIEW | 2018-01-10 | 2019-01-09 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000105 | CLASS 2
076551C-000R-MR-0960-001 | MATERIAL REQUISITION FOR EBULLATING PUMPS | FLOWSERVE CORPORATION PUMP DIVISION | 018P1002 | 130RLCB03427 | 018-G-MCD-40067-001 | WELDING BOOK 018P1002/2002 018P1003/2003 018P1006/2006 (EX BAPCO N.018-G-PRO-40007-001) | B1304 | BX | 1 | 2019-07-08 | CON-BMP-VTRA-012716 | 2019-07-08 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0960-001 | MATERIAL REQUISITION FOR EBULLATING PUMPS | FLOWSERVE CORPORATION PUMP DIVISION | 018P1002 | 141RLCB03427 | 018-G-PRO-40003-001 | NDT PROCEDURE RLCB03427 NDE PROCEDURES - PUMPS 018P1002 - 018P1003 - 018P2002 - 018P2003 - 018P1006 - 018P2006 | B1202 | AX | 2 | 2019-06-05 | CON-BMP-VTRA-012007 | 2019-06-05 | FOR BAPCO REVIEW | 2019-06-20 | 2019-06-17 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000960 | CLASS 2
076551C-000R-MR-0960-001 | MATERIAL REQUISITION FOR EBULLATING PUMPS | FLOWSERVE CORPORATION PUMP DIVISION | 018P1002 | 151RLCB03427 | 018-G-TSP-40001-001 | PAINT SPECIFICATION EBULLATINGPUMPS 018P1002/1003/1006/2002/2003/2006 | A0106 | AX | 1 | 2019-06-17 | CON-BMP-VTRA-012246 | 2019-06-17 | FOR INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0960-001 | MATERIAL REQUISITION FOR EBULLATING PUMPS | FLOWSERVE CORPORATION PUMP DIVISION | 018P1002 | 156RLCB03427 | 018-G-PRO-40001-001 | TESTING PROCEDURE - PUMPS 018P1002 - 018P1003 - 018P2002- 018P2003 - 018P1006 - 018P2006 | B1103 | AX | 2 | 2019-05-20 | CON-BMP-VTRA-011673 | 2019-05-21 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0960-001 | MATERIAL REQUISITION FOR EBULLATING PUMPS | FLOWSERVE CORPORATION PUMP DIVISION | 018P1002 | 163RLCB03427 | 018-G-PRO-40002-001 | PWHT PROCEDURE 018P1002 - 018P1003 - 018P2002 - 018P2003 - 018P1006 - 018P2006 | B1201 | AX | 2 | 2019-06-05 | CON-BMP-VTRA-012004 | 2019-06-05 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-0960-001 | MATERIAL REQUISITION FOR EBULLATING PUMPS | FLOWSERVE CORPORATION PUMP DIVISION | 018P1002 | 175RLCB03427 | 018-G-STS-40001-001 | LATERAL CRITICAL SPEED ANALYSIS 018P1002 018P1003 018P1006 018P2002 018P2003 018P2006 | A1007 | AX | 2 | 2019-05-22 | CON-BMP-VTRA-011721 | 2019-05-22 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0960-001 | MATERIAL REQUISITION FOR EBULLATING PUMPS | FLOWSERVE CORPORATION PUMP DIVISION | 018P1002 | 179RLCB03427 | 018-G-STS-40002-001 | TORSIONAL CRITICAL SPEED ANALYSIS 018P1002 018P1003 018P1006 018P2002 018P2003 018P2006 | A1009 | AX | 2 | 2019-05-22 | CON-BMP-VTRA-011722 | 2019-05-22 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0960-001 | MATERIAL REQUISITION FOR EBULLATING PUMPS | FLOWSERVE CORPORATION PUMP DIVISION | 018P1002 | 187RLCB03431 | 018-G-PQP-40001-001 | INSPECTION & TEST PLAN 018P1002 18P2002 18P1003 18P2003 18P1006 18P2006 | B1002 | BX | 2 | 2019-05-15 | CON-BMP-VTRA-011613 | 2019-05-15 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0960-001 | MATERIAL REQUISITION FOR EBULLATING PUMPS | FLOWSERVE CORPORATION PUMP DIVISION | 018P1002 | 189RLCB03427 | 018-G-CAL-40001-001 | THERMAL ANALYSIS OF REACTOR CIRCULATING PUMP/MOTOR UNIT 018P1002/1003/1006/2002/2003/2006 | A1003 | AX | 2 | 2019-06-27 | CON-BMP-VTRA-012519 | 2019-06-27 | FOR BAPCO REVIEW | 2019-07-11 |  |  | CLASS 2
076551C-000R-MR-0960-001 | MATERIAL REQUISITION FOR EBULLATING PUMPS | FLOWSERVE CORPORATION PUMP DIVISION | 018P1002 | 190RLCB03427 | 018-G-GAD-40002-001 | PRESSURE BOUNDARY DESIGN CALCULATIONS 018P1002/1003/2002/2003/1006/2 006 | A1103 | 0X | 2 | 2019-06-26 | CON-BMP-VTRA-012463 | 2019-06-26 | FOR BAPCO REVIEW | 2019-07-10 |  |  | CLASS 2
076551C-000R-MR-0960-001 | MATERIAL REQUISITION FOR EBULLATING PUMPS | FLOWSERVE CORPORATION PUMP DIVISION | 018P1002 | 2303RLCB03427 | 018-G-GAD-40010-001 | VFD - OUTLINE DIMENSIONAL DRAWING 018P1002 018P1003/018P2002/018P2003 | A4201 | AX | 2 | 2019-03-14 | CON-BMP-VTRA-010694 | 2019-03-14 | FOR BAPCO REVIEW | 2019-03-29 | 2019-03-31 | 3-REVIEWED WITH COMMENTS BMP-ROC-VTRE-000429 | CLASS 2
076551C-000R-MR-0960-001 | MATERIAL REQUISITION FOR EBULLATING PUMPS | FLOWSERVE CORPORATION PUMP DIVISION | 018P1002 | 2360RLCB03427 | 018-G-DAT-40090-001 | VFD DATA SHEETS 018P1002 (EX BAPCO NUMBER N. 018-G-DAT- 40011-001) | A4102 | AX | 1 | 2019-03-19 | CON-BMP-VTRA-010750 | 2019-03-19 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0960-001 | MATERIAL REQUISITION FOR EBULLATING PUMPS | FLOWSERVE CORPORATION PUMP DIVISION | 018P1002 | 248RLCB03427-1 | 018-G-DLB-40001-001 | PUMP NAMEPLATE DATA REACTOR RECYCLE PUMP - 16000-450 PR 018P1002/3/6 018P2002/3/6 | A1112 | AX | 2 | 2019-06-27 | CON-BMP-VTRA-012520 | 2019-06-27 | FOR BAPCO REVIEW | 2019-07-11 |  |  | CLASS 2
076551C-000R-MR-0960-001 | MATERIAL REQUISITION FOR EBULLATING PUMPS | FLOWSERVE CORPORATION PUMP DIVISION | 018P1002 | 266RLCB03427 | 018-G-DAT-40007-001 | PUMP AND MOTOR DATA SHEET 018P1002 | A1001 | AX | 2 | 2019-03-28 | CON-BMP-VTRA-010890 | 2019-03-28 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0960-001 | MATERIAL REQUISITION FOR EBULLATING PUMPS | FLOWSERVE CORPORATION PUMP DIVISION | 018P1002 | 286RLCB03427 | 018-G-DAT-40008-001 | AS SOLD PERFORMANCE CURVE - PUMP 018P1002 (EX BAPCO N 018- G-DAT-00008-001) | A1002 | CX | 2 | 2019-02-25 | CON-BMP-VTRA-010482 | 2019-02-25 | FOR BAPCO REVIEW | 2019-03-12 | 2019-03-12 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000290 | CLASS 2
076551C-000R-MR-0960-001 | MATERIAL REQUISITION FOR EBULLATING PUMPS | FLOWSERVE CORPORATION PUMP DIVISION | 018P1002 | 300RLCB03427 | 018-G-GAD-40003-001 | OUTLINE PUMP FIRST AND SECOND STAGE EBULLATING PUMP 16000- 450 PR 018P1002/3/6 018P2002/3/6 | A2001 | BX | 2 | 2019-05-10 | CON-BMP-VTRA-011530 | 2019-05-10 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0960-001 | MATERIAL REQUISITION FOR EBULLATING PUMPS | FLOWSERVE CORPORATION PUMP DIVISION | 018P1002 | 3032RLCB03427 | 018-G-SCH-40001-001 | ENGINEERING PROCUREMENT MANUFACTURING AND TEST SCHEDULE 018P1002-018P1003-018P2002-018P2003-018P1006-018P2006 | C1001 | AX | 4 | 2019-05-06 | CON-BMP-VTRA-011404 | 2019-05-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-0960-001 | MATERIAL REQUISITION FOR EBULLATING PUMPS | FLOWSERVE CORPORATION PUMP DIVISION | 018P1002 | 3077RLCB03427 | 018-G-MRS-40001-001 | MONTHLY PROGRESS REPORT 018P1002-1003-1006-2002-2003- 2006 | C1002 | BX | 4 | 2019-05-06 | CON-BMP-VTRA-011409 | 2019-05-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-0960-001 | MATERIAL REQUISITION FOR EBULLATING PUMPS | FLOWSERVE CORPORATION PUMP DIVISION | 018P1002 | 308RLCB03427 | 018-G-GAD-40004-001 | REACTOR INTERFACE REACTOR RECYCLE EBULLATOR 16000-450 PR 018P1002/3/6 018P2002/3/6 | A2001 | BX | 2 | 2019-05-10 | CON-BMP-VTRA-011530 | 2019-05-10 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0960-001 | MATERIAL REQUISITION FOR EBULLATING PUMPS | FLOWSERVE CORPORATION PUMP DIVISION | 018P1002 | 500RLCB03427 | 018-G-GAD-40001-001 | PUMP ASSEMBLY-SECTIONAL DWG 018P1002 018P1003 018P2002 018P2003 018P1006 018P2006 (EX BAPCO N.018-G-GAD-00001-001) | A1101 | CX | 2 | 2019-03-29 | CON-BMP-VTRA-010925 | 2019-03-29 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0960-001 | MATERIAL REQUISITION FOR EBULLATING PUMPS | FLOWSERVE CORPORATION PUMP DIVISION | 018P1002 | 582RLCB03427 | 018-G-PID-40001-001 | P & ID PUMP/MOTOR 018P1002 | A0103 | BX | 2 | 2019-06-05 | CON-BMP-VTRA-012006 | 2019-06-05 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0960-001 | MATERIAL REQUISITION FOR EBULLATING PUMPS | FLOWSERVE CORPORATION PUMP DIVISION | 018P1003 | 139RLCB03427 | 018-G-PRO-40005-001 | DOCUMENT COVER PUMPS PAMI PROCEDURES FOR 018P1002 - 018P1003 - 018P2002 - 018P2003- 018P1006 - 018P2006 | B1204 | AX | 2 | 2019-06-17 | CON-BMP-VTRA-012245 | 2019-06-17 | FOR BAPCO REVIEW | 2019-07-01 | 2019-06-29 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001069 | CLASS 2
076551C-000R-MR-0960-001 | MATERIAL REQUISITION FOR EBULLATING PUMPS | FLOWSERVE CORPORATION PUMP DIVISION | 018U0002 | 1053RLCB03427-2 | 018-G-MCD-40068-001 | WELDING BOOK - OIL CONDITIONING AND INJECTION SYSTEMS 018U1002 - 018U1008 - 018U2002 - 018U2008 - 018U0002 | B1304 | AX | 2 | 2019-05-22 | CON-BMP-VTRA-011724 | 2019-05-22 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0960-001 | MATERIAL REQUISITION FOR EBULLATING PUMPS | FLOWSERVE CORPORATION PUMP DIVISION | 018U0002 | 146RLCB03427-1 | 018-G-PRO-40004-001 | NDT PROCEDURE - OIL CONDITIONING AND INJECTION SYSTEMS 018U1002-018U1008- 018U2002-018U2008-018U0002 | B1202 | AX | 2 | 2019-04-01 | CON-BMP-VTRA-010930 | 2019-04-01 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-0960-001 | MATERIAL REQUISITION FOR EBULLATING PUMPS | FLOWSERVE CORPORATION PUMP DIVISION | 018U0002 | 1635RLCB03427 | 018-G-ITP-40002-001 | FABRICATION AND QUALITY CONTROL PLAN (1) - OIL INJECTION & COALESCER SYSTEM 018U0002 018U1002 018U1008 018U2002 018U2008 | B1002 | AX | 2 | 2019-05-15 | CON-BMP-VTRA-011610 | 2019-05-15 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0960-001 | MATERIAL REQUISITION FOR EBULLATING PUMPS | FLOWSERVE CORPORATION PUMP DIVISION | 018U0002 | 1640RLCB03427 | 018-G-DAT-40014-001 | MAJOR EQUIPMENT DATA SHEETS 018U1002 018U1008 018U2002 018U2008 018U0002 | A1006 | AX | 1 | 2019-01-11 | CON-BMP-VTRA-010202 | 2019-01-11 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0960-001 | MATERIAL REQUISITION FOR EBULLATING PUMPS | FLOWSERVE CORPORATION PUMP DIVISION | 018U0002 | 1681RLCB03427-2 | 018-G-GAD-40015-001 | OIL COALESCER SYSTEM GENERAL ARRANGMENT 018U0002 | A2002 | AX | 2 | 2019-05-02 | CON-BMP-VTRA-010349 | 2019-02-05 | FOR BAPCO REVIEW | 2019-02-19 | 2019-02-18 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000196 | CLASS 2
076551C-000R-MR-0960-001 | MATERIAL REQUISITION FOR EBULLATING PUMPS | FLOWSERVE CORPORATION PUMP DIVISION | 018U0002 | 1722RLCB03427 | 018-G-PRO-40006-001 | PAMI PROCEDURE OIL CONDITIONING AND INJECTION SYSTEMS 018U1002 - 018U1008 - 018U2002 - 018U2008 - 018U0002 | B1204 | AX | 2 | 2019-04-10 | CON-BMP-VTRA-011087 | 2019-04-10 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0960-001 | MATERIAL REQUISITION FOR EBULLATING PUMPS | FLOWSERVE CORPORATION PUMP DIVISION | 018U0002 | 1764RLCB03427 | 018-G-PRO-40012-001 | TESTING PROCEDURE - OIL INJECTION & COALESCER SYSTEM 018-U0002 - 018U1002 - 018U1008 - 018U2002 - 018U2008 | B1103 | AX | 2 | 2019-05-20 | CON-BMP-VTRA-011673 | 2019-05-21 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0960-001 | MATERIAL REQUISITION FOR EBULLATING PUMPS | FLOWSERVE CORPORATION PUMP DIVISION | 018U0002 | 1900RLCB03427-1 | 018-G-PID-40002-001 | P&D OIL CONDITIONING SYSTEM 018U0002 | A0103 | BX | 2 | 2019-06-05 | CON-BMP-VTRA-012006 | 2019-06-05 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0960-001 | MATERIAL REQUISITION FOR EBULLATING PUMPS | FLOWSERVE CORPORATION PUMP DIVISION | 018U0002 | 1911RLCB03427 | 018-G-MCD-40066-001 | WELDING BOOK - OIL CONDITIONING AND INJECTION SYSTEMS 018U1002 - 018U1008 - 018U2002 - 018U2008 - 018U0002 | B1304 | AX | 2 | 2019-05-22 | CON-BMP-VTRA-011724 | 2019-05-22 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0960-001 | MATERIAL REQUISITION FOR EBULLATING PUMPS | FLOWSERVE CORPORATION PUMP DIVISION | 018U0002 | 1917RLCB03427 | 018-G-TSP-40002-001 | OIL INJECTION & OIL COALESCER SYSTEM PAINTING PROCEDURE 018U1002 018U1008 018U2002 018U2008 018U0002 | A0106 | BX | 1 | 2019-05-20 | CON-BMP-VTRA-011674 | 2019-05-21 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-0960-001 | MATERIAL REQUISITION FOR EBULLATING PUMPS | FLOWSERVE CORPORATION PUMP DIVISION | 018U1002 | 1681RLCB03427-1 | 018-G-GAD-40005-001 | OIL INJECTION SYSTEM GENERAL ARRANGMENT 018U1002 | A2002 | AX | 2 | 2019-02-01 | CON-BMP-VTRA-010340 | 2019-02-01 | FOR BAPCO REVIEW | 2019-02-18 | 2019-02-19 | 3-REVIEWED WITH COMMENTS BMP-ROC-VTRE-000201 | CLASS 2
076551C-000R-MR-0960-001 | MATERIAL REQUISITION FOR EBULLATING PUMPS | FLOWSERVE CORPORATION PUMP DIVISION | 018U1002 | 1777RLCB03341 | 018-G-GAD-40006-001 | OIL INJECTION SYSTEM - LUBE OIL CONSOLE BILL OF MATERIALS 018U1002 018U2002 018U1008 018U2008 | A2003 | AX | 2 | 2019-06-27 | CON-BMP-VTRA-012518 | 2019-06-27 | FOR BAPCO REVIEW | 2019-07-11 |  |  | CLASS 2
076551C-000R-MR-0960-001 | MATERIAL REQUISITION FOR EBULLATING PUMPS | FLOWSERVE CORPORATION PUMP DIVISION | 018U1002 | 1900RLCB03427-2 | 018-G-PID-40003-001 | P&D OIL INJECTION SYSTEM 018U1002 | A0103 | BX | 2 | 2019-06-05 | CON-BMP-VTRA-012006 | 2019-06-05 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-1011-001 | MATERIAL REQUISITION FOR CENTRIFUGAL COMPRESSOR | NUOVO PIGNONE srl | 021E0023A | SOS4596914 | 021-K-INX-40001-001 | VENDOR DOCUMENT REGISTER LIST ALL ITEMS | A0001 | AX | 2 | 2019-05-07 | CON-BMP-VTRA-011455 | 2019-05-07 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-1011-001 | MATERIAL REQUISITION FOR CENTRIFUGAL COMPRESSOR | NUOVO PIGNONE srl | 021E0024A | SOV7355392 | 021-K-DAT-40010-001 | SHELL & TUBE LUBE OIL COOLER DATA SHEET 021E0024A/B | A1006 | AX | 2 | 2019-05-06 | CON-BMP-VTRA-011429 | 2019-05-06 | FOR BAPCO REVIEW | 2019-05-21 | 2019-05-26 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000775 | CLASS 2
076551C-000R-MR-1011-001 | MATERIAL REQUISITION FOR CENTRIFUGAL COMPRESSOR | NUOVO PIGNONE srl | 021E0024A | SVO17449 | 021-K-GAD-40008-001 | SHELL & TUBE LUBE OIL COOLER CONSTRUCTION DRAWING BAPCO 21KTRAIN - SITRA BAHREIN | A1103 | AX | 2 | 2019-03-21 | CON-BMP-VTRA-011962 | 2019-06-04 | FOR BAPCO REVIEW | 2019-06-19 | 2019-06-26 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001047 | CLASS 2
076551C-000R-MR-1011-001 | MATERIAL REQUISITION FOR CENTRIFUGAL COMPRESSOR | NUOVO PIGNONE srl | 021E0032 | SOV7354571 | 021-K-DAT-40011-001 | SHELL &TUBE GLAND STEAM CONDENSER DATA SHEET 021E0032 | A1006 | AX | 2 | 2019-05-10 | CON-BMP-VTRA-011524 | 2019-05-10 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-1011-001 | MATERIAL REQUISITION FOR CENTRIFUGAL COMPRESSOR | NUOVO PIGNONE srl | 021K0001 | MONTHLY REPORT MR1011001 | 021-K-MRS-40001-001 | MONTHY PROGRESS REPORT 021K0001 H2 RECYCLE COMPRESSOR | C1001 | AX | 4 | 2019-05-07 | CON-BMP-VTRA-011448 | 2019-05-07 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-1011-001 | MATERIAL REQUISITION FOR CENTRIFUGAL COMPRESSOR | NUOVO PIGNONE srl | 021K0001 | SOK0880224 | 021-K-PID-40001-001 | STEAM TURBINE MODEL SNC1-2 RELIP BCL308 COMPRESSOR PIPING AND INSTRUMENTS DIAGRAM 021K0001 | A0103 | BX | 2 | 2019-05-07 | CON-BMP-VTRA-011451 | 2019-05-07 | FOR BAPCO REVIEW | 2019-05-21 | 2019-06-01 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000868 | CLASS 2
076551C-000R-MR-1011-001 | MATERIAL REQUISITION FOR CENTRIFUGAL COMPRESSOR | NUOVO PIGNONE srl | 021K0001 | SOK0936379 | 021-K-RPT-40001-001 | UTILITY CONSUMPTION LIST 021K0001 021T0001 | A1014 | AX | 2 | 2019-03-21 | CON-BMP-VTRA-010821 | 2019-03-21 | FOR BAPCO REVIEW | 2019-04-05 | 2019-04-05 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000464 | CLASS 2
076551C-000R-MR-1011-001 | MATERIAL REQUISITION FOR CENTRIFUGAL COMPRESSOR | NUOVO PIGNONE srl | 021K0001 | SOK094175 | 021-K-DAT-40003-001 | NOISE DATA SHEET 021K0001 | A0105 | AX | 2 | 2019-06-04 | CON-BMP-VTRA-011960 | 2019-06-04 | FOR BAPCO REVIEW | 2019-06-19 | 2019-06-26 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001051 | CLASS 2
076551C-000R-MR-1011-001 | MATERIAL REQUISITION FOR CENTRIFUGAL COMPRESSOR | NUOVO PIGNONE srl | 021K0001 | SOK0970013 | 021-K-GAD-40012-001 | GENERAL ARRANGEMENT AND MECHANICAL PURCHASER CONNECTION DRAWING 021K0001/021T0001 | A2001 | AX | 1 | 2019-04-03 | CON-BMP-VTRA-010982 | 2019-04-03 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-1011-001 | MATERIAL REQUISITION FOR CENTRIFUGAL COMPRESSOR | NUOVO PIGNONE srl | 021K0001 | SOK6739071 | 021-K-PED-40001-001 | MACHINERY FOUNDATION LOADS & NOTES 021K0001 | A2006 | CX | 2 | 2019-05-07 | CON-BMP-VTRA-011450 | 2019-05-07 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-1011-001 | MATERIAL REQUISITION FOR CENTRIFUGAL COMPRESSOR | NUOVO PIGNONE srl | 021K0001 | SOK6756737 | 021-K-TSP-40002-001 | PIPING LINES SPECIFICATIONS 021K0001 | A2102 | AX | 2 | 2019-05-07 | CON-BMP-VTRA-011454 | 2019-05-07 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-1011-001 | MATERIAL REQUISITION FOR CENTRIFUGAL COMPRESSOR | NUOVO PIGNONE srl | 021K0001 | SOK7305193 | 021-K-INX-40003-001 | ELECTRICAL LOAD LIST 021K0001 | A4001 | AX | 2 | 2019-07-08 | CON-BMP-VTRA-012717 | 2019-07-08 | FOR BAPCO REVIEW | 2019-07-22 |  |  | CLASS 2
076551C-000R-MR-1011-001 | MATERIAL REQUISITION FOR CENTRIFUGAL COMPRESSOR | NUOVO PIGNONE srl | 021K0001 | SOK7305200 | 021-K-DAT-40004-001 | COMPRESSOR DATA SHEET 021K0001 | A1001 | AX | 2 | 2019-03-21 | CON-BMP-VTRA-010897 | 2019-03-28 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-1011-001 | MATERIAL REQUISITION FOR CENTRIFUGAL COMPRESSOR | NUOVO PIGNONE srl | 021K0001 | SOL33495 | 021-K-PQP-40001-001 | QUALITY CONTROL PLAN 021K0001 | B1002 | BX | 2 | 2019-05-13 | CON-BMP-VTRA-011535 | 2019-05-13 | FOR BAPCO REVIEW | 2019-05-28 | 2019-05-24 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000751 | CLASS 2
076551C-000R-MR-1011-001 | MATERIAL REQUISITION FOR CENTRIFUGAL COMPRESSOR | NUOVO PIGNONE srl | 021K0001 | SOS45714113 | 021-K-GAD-40002-001 | CENTRIFUGAL COMPRESSOR BCL308/N 021K0001 | A1101 | AX | 2 | 2019-05-13 | CON-BMP-VTRA-011536 | 2019-05-13 | FOR BAPCO REVIEW | 2019-06-28 | 2019-06-27 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001063 | CLASS 2
076551C-000R-MR-1011-001 | MATERIAL REQUISITION FOR CENTRIFUGAL COMPRESSOR | NUOVO PIGNONE srl | 021K0001 | SOS5001676 | 021-K-DAT-40006-001 | CENTRIFUGAL COMPRESSOR EXPECTED PERFORMANCE CURVES 021K0001 | A1002 | AX | 2 | 2019-05-07 | CON-BMP-VTRA-011453 | 2019-05-07 | FOR BAPCO INFORMATION |  | 2019-06-18 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000991 | CLASS 2
076551C-000R-MR-1011-001 | MATERIAL REQUISITION FOR CENTRIFUGAL COMPRESSOR | NUOVO PIGNONE srl | 021K0001 | SOS5001861 | 021-K-PRO-40007-001 | HYDROTEST PROCEDURE 021K0001 | B1103 | AX | 2 | 2019-05-06 | CON-BMP-VTRA-011427 | 2019-05-06 | FOR BAPCO INFORMATION |  | 2019-06-11 | 2-REVIEWED WTIH MINOR COMMENS BMP-ROC-VTRE-000903 | CLASS 3
076551C-000R-MR-1011-001 | MATERIAL REQUISITION FOR CENTRIFUGAL COMPRESSOR | NUOVO PIGNONE srl | 021K0001 | SOS5001864 | 021-K-PRO-40008-001 | BALANCING PROCEDURE 021K0001 | B1103 | AX | 2 | 2019-05-08 | CON-BMP-VTRA-011485 | 2019-05-08 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-1011-001 | MATERIAL REQUISITION FOR CENTRIFUGAL COMPRESSOR | NUOVO PIGNONE srl | 021K0001 | SOS5001931 | 021-K-TSP-40001-001 | PAINTING SPECIFICATION FOR BAPCO (21K) TURBOCOMPRESSOR PLANT 021K0001 021T0001 | A0106 | AX | 1 | 2019-04-11 | CON-BMP-VTRA-011128 | 2019-04-11 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-1011-001 | MATERIAL REQUISITION FOR CENTRIFUGAL COMPRESSOR | NUOVO PIGNONE srl | 021K0001 | SOV5019753 | 021-K-MCD-40001-001 | COMPRESSOR CASING WELDING BOOKCO/CE BCL 308 | B1304 | AX | 2 | 2019-06-10 | CON-BMP-VTRA-012115 | 2019-06-10 | FOR BAPCO REVIEW | 2019-06-24 |  |  | CLASS 2
076551C-000R-MR-1011-001 | MATERIAL REQUISITION FOR CENTRIFUGAL COMPRESSOR | NUOVO PIGNONE srl | 021T0001 | SOK0936384 | 021-K-DAT-40005-001 | MAIN STEAM TURBINE DATA SHEET 021T0001 | A1001 | AX | 2 | 2019-03-21 | CON-BMP-VTRA-010897 | 2019-03-28 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-1011-001 | MATERIAL REQUISITION FOR CENTRIFUGAL COMPRESSOR | NUOVO PIGNONE srl | 021T0001 | SOL00993 | 021-K-GAD-40003-00 | STEAM TURBINE CROSS SECTIONAL DWG 021T0001 | A1101 | AX | 2 | 2019-05-07 | CON-BMP-VTRA-011452 | 2019-05-07 | FOR BAPCO INFORMATION |  | 2019-06-17 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000999 | CLASS 2
076551C-000R-MR-1011-001 | MATERIAL REQUISITION FOR CENTRIFUGAL COMPRESSOR | NUOVO PIGNONE srl | 021T0001 | SOL5050898 | 021-K-STS-40002-001 | STEAM TURBINE ROTOR DYNAMIC REPORT 021T0001 | A1007 | AX | 1 | 2019-05-10 | CON-BMP-VTRA-011525 | 2019-05-10 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-1011-001 | MATERIAL REQUISITION FOR CENTRIFUGAL COMPRESSOR | NUOVO PIGNONE srl | 021T0001 | SOM6824030 | 021-K-S3D-40001-001 | 3D MODEL REVIEW 021K0001 021T0001 | A2013 | AX | 2 | 2019-05-15 | CON-BMP-VTRA-011606 | 2019-05-15 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-1011-001 | MATERIAL REQUISITION FOR CENTRIFUGAL COMPRESSOR | NUOVO PIGNONE srl | 021U0007 | SOK7358077 | 021-K-GAD-40013-001 | MINERAL LUBE OIL CONSOLE OUTLINE 021U0007 | A2002 | BX | 2 | 2019-05-30 | CON-BMP-VTRA-011860 | 2019-05-30 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-1011-001 | MATERIAL REQUISITION FOR CENTRIFUGAL COMPRESSOR | NUOVO PIGNONE srl | 021U0009 | SOS0451924 | 021-K-PRO-40003-001 | LUBE OIL CONSOLE FUNCTIONAL TEST PROCEDURE 021U0009 | B1103 | AX | 2 | 2019-05-13 | CON-BMP-VTRA-011538 | 2019-05-13 | FOR BAPCO REVIEW | 2019-06-28 | 2019-07-04 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001168 | CLASS 2
076551C-000R-MR-1011-101 | MATERIAL REQUISITION FOR CENTRIFUGAL COMPRESSOR | ELLIOT EBARA | 018GB0002 | 18E134A0010916A0 | 018-K-GAD-40022-001 | GEAR DRAWING 018GB0001 018GB0002 | A1109 | AX | 2 | 2019-05-08 | CON-BMP-VTRA-011490 | 2019-05-08 | FOR BAPCO REVIEW | 2019-05-23 | 2019-05-27 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000803 | CLASS 2
076551C-000R-MR-1011-101 | MATERIAL REQUISITION FOR CENTRIFUGAL COMPRESSOR | ELLIOT EBARA | 018K0002A | 18E134A0010901A0 | 018-K-PID-40002-001 | P&ID FLOW SHEET 018K0002A 018K0002B | A0103 | AX | 2 | 2019-03-05 | CON-BMP-VTRA-010586 | 2019-03-05 | FOR BAPCO REVIEW | 2019-03-20 | 2019-03-22 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000365 | CLASS 2
076551C-000R-MR-1011-101 | MATERIAL REQUISITION FOR CENTRIFUGAL COMPRESSOR | ELLIOT EBARA | 018K0002A | 18E134A0010906A0 | 018-K-SLD-40001-001 | SINGLE LINE DIAGRAM 018K0002A/B | A4108 | AX | 2 | 2019-04-26 | CON-BMP-VTRA-011259 | 2019-04-26 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-1011-101 | MATERIAL REQUISITION FOR CENTRIFUGAL COMPRESSOR | ELLIOT EBARA | 018K0002A | 18E134A0010910A0 | 018-K-GAD-40012-001 | MAIN SKID OUTLINE 018K0002A 018K0002B | A2001 | BX | 2 | 2019-06-06 | CON-BMP-VTRA-012027 | 2019-06-06 | FOR BAPCO REVIEW | 2019-06-20 |  |  | CLASS 2
076551C-000R-MR-1011-101 | MATERIAL REQUISITION FOR CENTRIFUGAL COMPRESSOR | ELLIOT EBARA | 018K0002A | 18E134A0010936A0 | 018-K-PED-40002-001 | CHOCK BLOCK ARRANGEMENT 018K0002A/B | A2006 | AX | 2 | 2019-04-10 | CON-BMP-VTRA-011090 | 2019-04-10 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-1011-101 | MATERIAL REQUISITION FOR CENTRIFUGAL COMPRESSOR | ELLIOT EBARA | 018K0002A | 18E134A0010998A0 | 018-K-GAD-40021-001 | VFD DRAWING 018K0002A/B | A4201 | AX | 2 | 2019-04-17 | CON-BMP-VTRA-011211 | 2019-04-17 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-1011-101 | MATERIAL REQUISITION FOR CENTRIFUGAL COMPRESSOR | ELLIOT EBARA | 018K0002A | 18E134A0011001A0 | 000-K-INX-40002-001 | LIST OF VENDOR'S DOCUMENTS ANDDWGS 018K0002A/B 023K0002A/B 051K0001A/B | A0001 | AX | 2 | 2019-05-10 | CON-BMP-VTRA-011521 | 2019-05-10 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-1011-101 | MATERIAL REQUISITION FOR CENTRIFUGAL COMPRESSOR | ELLIOT EBARA | 018K0002A | 18E134A0011003A0 | 000-K-RPT-40001-001 | UTILITY BALANCE (ALL UNITS) 018K0002A/B 023K0002A/B 051K0001A/B | A1014 | AX | 2 | 2019-07-02 | CON-BMP-VTRA-012617 | 2019-07-02 | FOR BAPCO REVIEW | 2019-07-16 |  |  | CLASS 2
076551C-000R-MR-1011-101 | MATERIAL REQUISITION FOR CENTRIFUGAL COMPRESSOR | ELLIOT EBARA | 018K0002A | 18E134A0011011A0 | 000-K-INX-40006-001 | ELECTRICAL LOAD LIST 018K0002A/B - 023K0002A/B - 051K0001A/B | A4001 | AX | 2 | 2019-06-03 | CON-BMP-VTRA-011941 | 2019-06-03 | FOR BAPCO REVIEW | 2019-06-18 | 2019-06-18 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000992 | CLASS 2
076551C-000R-MR-1011-101 | MATERIAL REQUISITION FOR CENTRIFUGAL COMPRESSOR | ELLIOT EBARA | 018K0002A | 18E134A0011012A0 | 000-K-TSP-40003-001 | SHOP PAINTING PROCEDURE (ALL UNITS) 018K0002AB 023K0002AB 051K0001A/B | A0106 | AX | 1 | 2019-07-12 | CON-BMP-VTRA-012835 | 2019-07-12 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-1011-101 | MATERIAL REQUISITION FOR CENTRIFUGAL COMPRESSOR | ELLIOT EBARA | 018K0002A | 18E134A0011114A0 | 018-K-INX-40009-001 | INSTRUMENT LIST I/O LIST AND ALARM SET POINTS 018K0002A/B | A3001 | AX | 1 | 2019-07-01 | CON-BMP-VTRA-012606 | 2019-07-01 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-1011-101 | MATERIAL REQUISITION FOR CENTRIFUGAL COMPRESSOR | ELLIOT EBARA | 018K0002A | 18E134A0011125A0 | 018-K-CWD-40009-001 | SYSTEM CONFIGURATION DIAGRAM 018K0002A/B | A3304 | AX | 2 | 2019-05-03 | CON-BMP-VTRA-011373 | 2019-05-03 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-1011-101 | MATERIAL REQUISITION FOR CENTRIFUGAL COMPRESSOR | ELLIOT EBARA | 018K0002A | 18E134A0011151A0 | 000-K-SCH-40004-001 | ENGINEERING PROCUREMENT MANUFACTURING & TEST SCHEDULE 018K0002A/B 023K0002A/B 051K0001A/B | C1001 | CX | 2 | 2019-07-02 | CON-BMP-VTRA-012618 | 2019-07-02 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-1011-101 | MATERIAL REQUISITION FOR CENTRIFUGAL COMPRESSOR | ELLIOT EBARA | 018K0002A | 18E134A0011152A0 | 000-K-MRS-40002-001 | MONTHLY PROGRESS REPORT 018K0002A/B 023K0002A/B 051K0001A/B | C1002 | CX | 2 | 2019-07-02 | CON-BMP-VTRA-012619 | 2019-07-02 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-1011-101 | MATERIAL REQUISITION FOR CENTRIFUGAL COMPRESSOR | ELLIOT EBARA | 018K0002A | 18E134A0011153A0 | 000-K-INV-40002-001 | UNPRICED COPY OF MAIN SUBORDERS 018K0002A/B 023K0002A/B 051K0001A/B | C1005 | BX | 2 | 2019-05-13 | CON-BMP-VTRA-011537 | 2019-05-13 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-1011-101 | MATERIAL REQUISITION FOR CENTRIFUGAL COMPRESSOR | ELLIOT EBARA | 018K0002A | 18E134A0012001A0 | 018-K-PQP-40002-001 | INSPECTION AND TEST QUALITY PLAN 018K0002A/B | B1002 | BX | 2 | 2019-07-08 | CON-BMP-VTRA-012729 | 2019-07-08 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-1011-101 | MATERIAL REQUISITION FOR CENTRIFUGAL COMPRESSOR | ELLIOT EBARA | 018K0002A | 18E134A0012031A0 | 018-K-CAL-40008-001 | ANTISURGE CALCULATION SHEET 018K0002AB | A1004 | AX | 2 | 2019-07-01 | CON-BMP-VTRA-012605 | 2019-07-01 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-1011-101 | MATERIAL REQUISITION FOR CENTRIFUGAL COMPRESSOR | ELLIOT EBARA | 018K0002A | 18E134A0012033A0 | 018-K-MCD-40004-001 | COMPRESSOR WELDING PROCEDURE 018K0002A/B | B1304 | BX | 2 | 2019-06-03 | CON-BMP-VTRA-011944 | 2019-06-03 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-1011-101 | MATERIAL REQUISITION FOR CENTRIFUGAL COMPRESSOR | ELLIOT EBARA | 018K0002A | 18E134AC019031A0 | 018-K-GAD-40017-001 | COMPRESSOR MAJOR PARTS MATERIAL LIST 018K0002A/B | A1101 | AX | 2 | 2019-07-01 | CON-BMP-VTRA-012604 | 2019-07-01 | FOR BAPCO REVIEW | 2019-07-16 |  |  | CLASS 2
076551C-000R-MR-1011-101 | MATERIAL REQUISITION FOR CENTRIFUGAL COMPRESSOR | ELLIOT EBARA | 018K0002A | 18E134AC019032A0 | 018-K-DAT-40018-001 | COMPRESSOR ESTIMATED PERFORMANCE CURVE 018K0002A/B | A1002 | AX | 2 | 2019-05-08 | CON-BMP-VTRA-011493 | 2019-05-08 | FOR BAPCO REVIEW | 2019-05-30 | 2019-06-06 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000885 | CLASS 2
076551C-000R-MR-1011-101 | MATERIAL REQUISITION FOR CENTRIFUGAL COMPRESSOR | ELLIOT EBARA | 018K0002A | 18E134AC019033A0 | 018-K-CAL-40003-001 | ALLOWABLE NOZZLE FORCES AND MOMENTS CALCULATION FOR COMPRESSOR 018K0002A/B | A1003 | AX | 2 | 2019-07-01 | CON-BMP-VTRA-012596 | 2019-07-01 | FOR BAPCO REVIEW | 2019-07-15
076551C-000R-MR-1011-101 | MATERIAL REQUISITION FOR CENTRIFUGAL COMPRESSOR | ELLIOT EBARA | 018M0070A | 18E134A0010912A0 | 018-K-GAD-40019-00 | MAIN MOTOR DRAWING AND NAME PLATE DRAWING 018M0070A/B | A4205 | AX | 2 | 2019-07-01 | CON-BMP-VTRA-012597 | 2019-07-01 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-1011-101 | MATERIAL REQUISITION FOR CENTRIFUGAL COMPRESSOR | ELLIOT EBARA | 018M0070A | 18E134A0011060A0 | 018-K-DAT-40019-001 | MAIN MOTOR DATA SHEET AND MAIN MOTOR PERFORMANCE CURVES 018M0070A/B | A4102 | CX | 2 | 2019-07-09 | CON-BMP-VTRA-012766 | 2019-07-09 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-1011-101 | MATERIAL REQUISITION FOR CENTRIFUGAL COMPRESSOR | ELLIOT EBARA | 018U0006 | 18E134A0010917A0 | 018-K-GAD-40013-001 | G.A. DRAWING FOR LUBE OIL CONSOLE 018U0006 018U0008 | A2002 | AX | 1 | 2019-04-10 | CON-BMP-VTRA-011091 | 2019-04-10 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-1011-101 | MATERIAL REQUISITION FOR CENTRIFUGAL COMPRESSOR | ELLIOT EBARA | 023GB0002 | 18E135A0010916A0 | 023-K-GAD-40022-001 | GEAR DRAWING 023GB0001 023GB0002 | A1109 | AX | 2 | 2019-05-08 | CON-BMP-VTRA-011490 | 2019-05-08 | FOR BAPCO REVIEW | 2019-05-23 | 2019-05-27 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000803 | CLASS 2
076551C-000R-MR-1011-101 | MATERIAL REQUISITION FOR CENTRIFUGAL COMPRESSOR | ELLIOT EBARA | 023K0002A | 18E134AC019030A0 | 018-K-DAT-40016-001 | COMPRESSOR DATA SHEET 018K0002A/B | A1001 | AX | 2 | 2019-04-12 | CON-BMP-VTRA-011158 | 2019-04-12 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-1011-101 | MATERIAL REQUISITION FOR CENTRIFUGAL COMPRESSOR | ELLIOT EBARA | 023K0002A | 18E135A0010901A0 | 023-K-PID-40002-001 | P&ID FLOW SHEET 023K0002A 023K0002B | A0103 | BX | 2 | 2019-06-22 | CON-BMP-VTRA-012379 | 2019-06-22 | FOR BAPCO REVIEW | 2019-07-08 | 2019-07-11 | 3-REVIEWED WITH COMMENTS BMP-ROC-VTRE-001295 | CLASS 2
076551C-000R-MR-1011-101 | MATERIAL REQUISITION FOR CENTRIFUGAL COMPRESSOR | ELLIOT EBARA | 023K0002A | 18E135A0010906A0 | 023-K-SLD-40001-001 | SINGLE LINE DIAGRAM 023K0002A/B | A4108 | AX | 2 | 2019-04-26 | CON-BMP-VTRA-011259 | 2019-04-26 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-1011-101 | MATERIAL REQUISITION FOR CENTRIFUGAL COMPRESSOR | ELLIOT EBARA | 023K0002A | 18E135A0010910A0 | 023-K-GAD-40012-001 | MAIN SKID OUTLINE 023K0002A 023K0002B | A2001 | BX | 2 | 2019-06-22 | CON-BMP-VTRA-012377 | 2019-06-22 | FOR BAPCO REVIEW | 2019-07-08 | 2019-07-11 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001305 | CLASS 2
076551C-000R-MR-1011-101 | MATERIAL REQUISITION FOR CENTRIFUGAL COMPRESSOR | ELLIOT EBARA | 023K0002A | 18E135A0010936A0 | 023-K-PED-40002-001 | CHOCK BLOCK ARRANGEMENT 023K0002A/B | A2006 | AX | 2 | 2019-04-10 | CON-BMP-VTRA-011090 | 2019-04-10 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-1011-101 | MATERIAL REQUISITION FOR CENTRIFUGAL COMPRESSOR | ELLIOT EBARA | 023K0002A | 18E135A0010998A0 | 023-K-GAD-40021-001 | VFD DRAWING 023K0002A/B | A4201 | AX | 2 | 2019-04-17 | CON-BMP-VTRA-011211 | 2019-04-17 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-1011-101 | MATERIAL REQUISITION FOR CENTRIFUGAL COMPRESSOR | ELLIOT EBARA | 023K0002A | 18E135A0011114A0 | 023-K-INX-40009-001 | INSTRUMENT LIST I/O LIST AND ALARM SET POINTS 023K0002A/B | A3001 | AX | 1 | 2019-07-02 | CON-BMP-VTRA-012615 | 2019-07-02 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-1011-101 | MATERIAL REQUISITION FOR CENTRIFUGAL COMPRESSOR | ELLIOT EBARA | 023K0002A | 18E135A0011125A0 | 023-K-CWD-40013-001 | SYSTEM CONFIGURATION DIAGRAM 023K0002A/B | A3304 | AX | 2 | 2019-05-03 | CON-BMP-VTRA-011373 | 2019-05-03 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-1011-101 | MATERIAL REQUISITION FOR CENTRIFUGAL COMPRESSOR | ELLIOT EBARA | 023K0002A | 18E135A0012001A0 | 023-K-PQP-40002-001 | INSPECTION AND TEST QUALITY PLAN 023K0002A/B | B1002 | BX | 2 | 2019-07-08 | CON-BMP-VTRA-012731 | 2019-07-08 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-1011-101 | MATERIAL REQUISITION FOR CENTRIFUGAL COMPRESSOR | ELLIOT EBARA | 023K0002A | 18E135A0012033A0 | 023-K-MCD-40004-001 | COMPRESSOR WELDING PROCEDURE 023K0002A/B | B1304 | BX | 2 | 2019-06-03 | CON-BMP-VTRA-011944 | 2019-06-03 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-1011-101 | MATERIAL REQUISITION FOR CENTRIFUGAL COMPRESSOR | ELLIOT EBARA | 023K0002A | 18E135AC019030A0 | 023-K-DAT-40007-001 | COMPRESSOR DATA SHEET 023K0002A/B | A1001 | AX | 2 | 2019-05-06 | CON-BMP-VTRA-011425 | 2019-05-06 | FOR BAPCO REVIEW | 2019-05-21 | 2019-05-26 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000769 | CLASS 2
076551C-000R-MR-1011-101 | MATERIAL REQUISITION FOR CENTRIFUGAL COMPRESSOR | ELLIOT EBARA | 023K0002A | 18E135AC019031A0 | 023-K-GAD-40017-001 | COMPRESSOR MAJOR PARTS MATERIAL LIST 023K0002A/B | A1101 | AX | 2 | 2019-07-01 | CON-BMP-VTRA-012594 | 2019-07-01 | FOR BAPCO REVIEW | 2019-07-15 |  |  | CLASS 2
076551C-000R-MR-1011-101 | MATERIAL REQUISITION FOR CENTRIFUGAL COMPRESSOR | ELLIOT EBARA | 023K0002A | 18E135AC019032A0 | 023-K-DAT-40009-001 | COMPRESSOR ESTIMATED PERFORMANCE CURVE 023K0002A/B | A1002 | AX | 2 | 2019-05-08 | CON-BMP-VTRA-011493 | 2019-05-08 | FOR BAPCO REVIEW | 2019-05-30 | 2019-06-06 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000885 | CLASS 2
076551C-000R-MR-1011-101 | MATERIAL REQUISITION FOR CENTRIFUGAL COMPRESSOR | ELLIOT EBARA | 023K0002A | 18E135AC019033A0 | 023-K-CAL-40003-001 | ALLOWABLE NOZZLE FORCES AND MOMENTS CALCULATION FOR COMPRESSOR 023K0002A/B | A1003 | AX | 2 | 2019-07-01 | CON-BMP-VTRA-012595 | 2019-07-01 | FOR BAPCO REVIEW | 2019-07-15 |  |  | CLASS 2
076551C-000R-MR-1011-101 | MATERIAL REQUISITION FOR CENTRIFUGAL COMPRESSOR | ELLIOT EBARA | 023M0021A | 18E135A0010912A0 | 023-K-GAD-40019-001 | MAIN MOTOR DRAWING AND NAME PLATE DRAWING 023M0021 A/B | A4205 | AX | 2 | 2019-07-01 | CON-BMP-VTRA-012593 | 2019-07-01 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-1011-101 | MATERIAL REQUISITION FOR CENTRIFUGAL COMPRESSOR | ELLIOT EBARA | 023M0021A | 18E135A0011060A0 | 023-K-DAT-40010-001 | MAIN MOTOR DATA SHEET AND MAIN MOTOR PERFORMANCE CURVES 023M0021A 023M0021B | A4102 | CX | 2 | 2019-07-09 | CON-BMP-VTRA-012767 | 2019-07-09 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-1011-101 | MATERIAL REQUISITION FOR CENTRIFUGAL COMPRESSOR | ELLIOT EBARA | 023U0005 | 18E135A0010917A0 | 023-K-GAD-40013-001 | G.A. DRAWING FOR LUBE OIL CONSOLE 023U0005 023U0007 | A2002 | AX | 2 | 2019-05-03 | CON-BMP-VTRA-011375 | 2019-05-03 | FOR BAPCO INFORMATION |  | 2019-06-16 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000941 | CLASS 2
076551C-000R-MR-1011-101 | MATERIAL REQUISITION FOR CENTRIFUGAL COMPRESSOR | ELLIOT EBARA | 051E0004A | 18E136A0010970A0 | 051-K-GAD-40003-001 | OIL COLLER DRAWING 051E0004A 051E0006A | A1109 | AX | 2 | 2019-04-18 | CON-BMP-VTRA-011215 | 2019-04-18 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-1011-101 | MATERIAL REQUISITION FOR CENTRIFUGAL COMPRESSOR | ELLIOT EBARA | 051GB0002 | 18E136A0010916A0 | 051-K-GAD-40011-001 | GEAR DRAWING 051GB0001 051GB0002 | A1109 | AX | 2 | 2019-05-08 | CON-BMP-VTRA-011490 | 2019-05-08 | FOR BAPCO REVIEW | 2019-05-23 | 2019-05-27 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000803 | CLASS 2
076551C-000R-MR-1011-101 | MATERIAL REQUISITION FOR CENTRIFUGAL COMPRESSOR | ELLIOT EBARA | 051K0001A | 18E136A0010901A0 | 051-K-PID-40001-001 | P&ID FLOW SHEET 051K0001A/B | A0103 | AX | 2 | 2019-04-03 | CON-BMP-VTRA-010983 | 2019-04-03 | FOR BAPCO REVIEW | 2019-04-18 | 2019-04-24 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000565 | CLASS 2
076551C-000R-MR-1011-101 | MATERIAL REQUISITION FOR CENTRIFUGAL COMPRESSOR | ELLIOT EBARA | 051K0001A | 18E136A0010910A0 | 051-K-GAD-40001-001 | MAIN SKID OUTLINE 051K0001A/B | A2001 | AX | 1 | 2019-03-18 | CON-BMP-VTRA-010727 | 2019-03-18 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-1011-101 | MATERIAL REQUISITION FOR CENTRIFUGAL COMPRESSOR | ELLIOT EBARA | 051K0001A | 18E136A0010936A0 | 051-K-PED-40001-001 | CHOCK BLOCK ARRANGEMENT 051K0001A/B | A2006 | AX | 2 | 2019-06-17 | CON-BMP-VTRA-012248 | 2019-06-17 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-1011-101 | MATERIAL REQUISITION FOR CENTRIFUGAL COMPRESSOR | ELLIOT EBARA | 051K0001A | 18E136A0011114A0 | 051-K-INX-40002-001 | INSTRUMENT LIST I/O LIST AND ALARM SET POINTS 051K0001A/B | A3001 | AX | 1 | 2019-07-01 | CON-BMP-VTRA-012607 | 2019-07-01 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-1011-101 | MATERIAL REQUISITION FOR CENTRIFUGAL COMPRESSOR | ELLIOT EBARA | 051K0001A | 18E136A0011125A0 | 051-K-CWD-40003-001 | SYSTEM CONFIGURATION DIAGRAM 051K0001A/B | A3304 | AX | 2 | 2019-05-03 | CON-BMP-VTRA-011373 | 2019-05-03 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-1011-101 | MATERIAL REQUISITION FOR CENTRIFUGAL COMPRESSOR | ELLIOT EBARA | 051K0001A | 18E136A0012001A0 | 051-K-PQP-40001-001 | INSPECTION AND TEST QUALITY PLAN 051K0001A/B | B1002 | BX | 2 | 2019-07-08 | CON-BMP-VTRA-012732 | 2019-07-08 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-1011-101 | MATERIAL REQUISITION FOR CENTRIFUGAL COMPRESSOR | ELLIOT EBARA | 051K0001A | 18E136A0012031A0 | 051-K-CAL-40008-001 | ANTISURGE CALCULATION SHEET 051K0001A/B | A1004 | AX | 2 | 2019-07-02 | CON-BMP-VTRA-012614 | 2019-07-02 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-1011-101 | MATERIAL REQUISITION FOR CENTRIFUGAL COMPRESSOR | ELLIOT EBARA | 051K0001A | 18E136A0012033A0 | 051-K-MCD-40002-001 | COMPRESSOR WELDING PROCEDURE 051K0001A/B | B1304 | BX | 2 | 2019-06-03 | CON-BMP-VTRA-011944 | 2019-06-03 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-1011-101 | MATERIAL REQUISITION FOR CENTRIFUGAL COMPRESSOR | ELLIOT EBARA | 051K0001A | 18E136AC019030A0 | 051-K-DAT-40001-001 | COMPRESSOR DATA SHEET 051K0001A/B | A1001 | AX | 2 | 2019-05-06 | CON-BMP-VTRA-011425 | 2019-05-06 | FOR BAPCO REVIEW | 2019-05-21 | 2019-05-26 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000769 | CLASS 2
076551C-000R-MR-1011-101 | MATERIAL REQUISITION FOR CENTRIFUGAL COMPRESSOR | ELLIOT EBARA | 051K0001A | 18E136AC019031A0 | 051-K-GAD-40007-001 | COMPRESSOR MAJOR PARTS MATERIAL LIST 051K0001A/B | A1101 | AX | 2 | 2019-07-01 | CON-BMP-VTRA-012608 | 2019-07-01 | FOR BAPCO REVIEW | 2019-07-16 |  |  | CLASS 2
076551C-000R-MR-1011-101 | MATERIAL REQUISITION FOR CENTRIFUGAL COMPRESSOR | ELLIOT EBARA | 051K0001A | 18E136AC019032A0 | 051-K-DAT-40003-001 | COMPRESSOR ESTIMATED PERFORMANCE CURVE 051K0001A/B | A1002 | AX | 2 | 2019-05-08 | CON-BMP-VTRA-011493 | 2019-05-08 | FOR BAPCO REVIEW | 2019-05-30 | 2019-06-06 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000885 | CLASS 2
076551C-000R-MR-1011-101 | MATERIAL REQUISITION FOR CENTRIFUGAL COMPRESSOR | ELLIOT EBARA | 051K0001A | 18E136AC019033A0 | 051-K-CAL-40003-001 | ALLOWABLE NOZZLE FORCES AND MOMENTS CALCULATION FOR COMPRESSOR 051K0001A/B | A1003 | AX | 2 | 2019-07-02 | CON-BMP-VTRA-012616 | 2019-07-02 | FOR BAPCO REVIEW | 2019-07-16 |  |  | CLASS 2
076551C-000R-MR-1011-101 | MATERIAL REQUISITION FOR CENTRIFUGAL COMPRESSOR | ELLIOT EBARA | 051M0050A | 18E136A0010906A0 | 051-K-SLD-40001-001 | SINGLE LINE DIAGRAM 051M0050A/B | A4108 | AX | 2 | 2019-04-17 | CON-BMP-VTRA-011214 | 2019-04-17 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-1011-101 | MATERIAL REQUISITION FOR CENTRIFUGAL COMPRESSOR | ELLIOT EBARA | 051M0050A | 18E136A0011060A0 | 051-K-DAT-40004-001 | MAIN MOTOR DATA SHEET AND MAIN MOTOR PERFORMANCE CURVES 051M0050A/B | A4102 | AX | 2 | 2019-04-29 | CON-BMP-VTRA-011300 | 2019-04-29 | FOR BAPCO INFORMATION |  | 2019-05-28 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000825 | CLASS 3
076551C-000R-MR-1011-101 | MATERIAL REQUISITION FOR CENTRIFUGAL COMPRESSOR | ELLIOT EBARA | 051U0010 | 18E136A0010917A0 | 051-K-GAD-40002-001 | G.A. DRAWING FOR LUBE OIL CONSOLE 051U0010 051U0012 | A2002 | AX | 1 | 2019-04-10 | CON-BMP-VTRA-011091 | 2019-04-10 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-1020-001 | MATERIAL REQUISITION FOR RECIPROCATING COMPRESSOR | KOBE STEE LTD | 018E0044 | 03S-K75927 | 018-K-GAD-40083-001 | ELECTRIC HEATER GA DRAWING & WIRING DIAGRAM 018E0044/45/1013/1014/1016/1017/1025/2013/2014/2016/2017/2025 | A4201 | AX | 2 | 2019-07-08 | CON-BMP-VTRA-012737 | 2019-07-08 | FOR BAPCO REVIEW | 2019-07-23 |  |  | CLASS 2
076551C-000R-MR-1020-001 | MATERIAL REQUISITION FOR RECIPROCATING COMPRESSOR | KOBE STEE LTD | 018E0044 | 22S-19675 | 018-K-MCD-40002-001 | WPS & PQR FOR PULSATION DAMPENER RECIPROCATING COMPRESSOR | B1304 | AX | 2 | 2019-06-28 | CON-BMP-VTRA-012551 | 2019-06-28 | FOR BAPCO REVIEW | 2019-07-12 | 2019-07-11 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001279 | CLASS 2
076551C-000R-MR-1020-001 | MATERIAL REQUISITION FOR RECIPROCATING COMPRESSOR | KOBE STEE LTD | 018E0046 | 22S-19658 | 018-K-GAD-40004-001 | LUBE OIL COOLER DRAWING 018E0046 018E1021 018E1026 018E2021 018E2026 | A1103 | AX | 2 | 2019-05-23 | CON-BMP-VTRA-011749 | 2019-05-23 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-1020-001 | MATERIAL REQUISITION FOR RECIPROCATING COMPRESSOR | KOBE STEE LTD | 018E0046 | 22S-20071 | 018-K-DLB-40007-001 | NAMEPLATE (LUBE OIL COOLER) 018E0046 018E1021 018E1026 018E2021 018E2026 | A1112 | AX | 2 | 2019-06-17 | CON-BMP-VTRA-012253 | 2019-06-17 | FOR BAPCO REVIEW | 2019-07-02 | 2019-07-07 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001176 | CLASS 2
076551C-000R-MR-1020-001 | MATERIAL REQUISITION FOR RECIPROCATING COMPRESSOR | KOBE STEE LTD | 018E1024A | 22S-19659 | 018-K-GAD-40005-001 | TEMPERED COOLING WATER COOLER DRAWING 018E1024A/018E1024B/018E2024A/ 018E2024B | A1103 | AX | 2 | 2019-05-23 | CON-BMP-VTRA-011749 | 2019-05-23 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-1020-001 | MATERIAL REQUISITION FOR RECIPROCATING COMPRESSOR | KOBE STEE LTD | 018E1024A | 22S-20073 | 018-K-DLB-40008-001 | NAMEPLATE (TEMPERED COOLING WATER COOLER) 018E1024A/B 018E2024A/B | A1112 | AX | 2 | 2019-06-17 | CON-BMP-VTRA-012253 | 2019-06-17 | FOR BAPCO REVIEW | 2019-07-02 | 2019-07-07 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001176 | CLASS 2
076551C-000R-MR-1020-001 | MATERIAL REQUISITION FOR RECIPROCATING COMPRESSOR | KOBE STEE LTD | 018E1024B | 03S-K74291 | 018-K-DLB-40002-001 | HV MOTOR NAME PLATE 018M0071 018M1031 018M1032 018M2031 018M2032 | A4205 | AX | 2 | 2019-04-16 | CON-BMP-VTRA-011187 | 2019-04-16 | FOR BAPCO INFORMATION |  | 2019-05-15 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000672 | CLASS 3
076551C-000R-MR-1020-001 | MATERIAL REQUISITION FOR RECIPROCATING COMPRESSOR | KOBE STEE LTD | 018K0001 | 03S-K74269 | 018-K-INX-40003-001 | LIST OF INSTRUMENTS 18K0001/1001/1002/2001/2002 | A3001 | AX | 1 | 2019-03-18 | CON-BMP-VTRA-010721 | 2019-03-18 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-1020-001 | MATERIAL REQUISITION FOR RECIPROCATING COMPRESSOR | KOBE STEE LTD | 018K0001 | 03S-K74270 | 018-K-INX-40005-001 | LIST OF JUNCTION BOXES & LOCALSWITCH BOXES 018K0001/1001/1002/2001/2002 | A3003 | AX | 2 | 2019-05-13 | CON-BMP-VTRA-011542 | 2019-05-13 | FOR BAPCO REVIEW | 2019-06-28 |  |  | CLASS 2
076551C-000R-MR-1020-001 | MATERIAL REQUISITION FOR RECIPROCATING COMPRESSOR | KOBE STEE LTD | 018K0001 | 03S-K74273 | 018-K-CWD-40002-001 | INSTRUMENT (FIELD) WIRING DIAGRAM 018K1001/018K1002/018K2001/018K2002/018K0001 | A3403 | AX | 2 | 2019-05-13 | CON-BMP-VTRA-011541 | 2019-05-13 | FOR BAPCO REVIEW | 2019-06-28 | 2019-07-11 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001291 | CLASS 2
076551C-000R-MR-1020-001 | MATERIAL REQUISITION FOR RECIPROCATING COMPRESSOR | KOBE STEE LTD | 018K0001 | 03S-K74274 | 018-K-DAT-40009-001 | INSTRUMENT DATASHEETS 018K1001/K1002/K0001/K2001/K20 02 | A3101 | AX | 2 | 2019-05-24 | CON-BMP-VTRA-011801 | 2019-05-24 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-1020-001 | MATERIAL REQUISITION FOR RECIPROCATING COMPRESSOR | KOBE STEE LTD | 018K0001 | 03S-K74278 | 018-K-MTX-40002-001 | CAUSE & EFFECT CHART 018K1001/K1002/K0001/K2001/K2002 | A3505 | AX | 1 | 2019-06-22 | CON-BMP-VTRA-012375 | 2019-06-22 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-1020-001 | MATERIAL REQUISITION FOR RECIPROCATING COMPRESSOR | KOBE STEE LTD | 018K0001 | 22S-19584 | 018-K-DAT-40007-001 | COMPRESSOR DATASHEET 018K1001 018K1002 018K0001 018K2001 018K2002 | A1001 | AX | 2 | 2019-04-11 | CON-BMP-VTRA-011120 | 2019-04-11 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-1020-001 | MATERIAL REQUISITION FOR RECIPROCATING COMPRESSOR | KOBE STEE LTD | 018K0001 | 22S-19585 | 018-K-PQP-40001-001 | FABRICATION AND QUALITY CONTROL PLAN 018K1001/K1002/K0001/K2001/K2002 | B1002 | BX | 2 | 2019-06-10 | CON-BMP-VTRA-012116 | 2019-06-10 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-1020-001 | MATERIAL REQUISITION FOR RECIPROCATING COMPRESSOR | KOBE STEE LTD | 018K0001 | 22S-19586 | 000-K-TSP-40001-001 | PAINTING SPECIFICATION 018K1001/1002/K0001/K2001/2002 023K0001A/B | A0106 | BX | 2 | 2019-05-23 | CON-BMP-VTRA-011747 | 2019-05-23 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-1020-001 | MATERIAL REQUISITION FOR RECIPROCATING COMPRESSOR | KOBE STEE LTD | 018K0001 | 22S-19587 | 018-K-TSP-40002-001 | PIPING SPECIFICATION 018K0001 018K1001/1002 018K2001/2002 | A1109 | AX | 2 | 2019-06-04 | CON-BMP-VTRA-011958 | 2019-06-04 | FOR BAPCO REVIEW | 2019-06-19 | 2019-06-27 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001062 | CLASS 2
076551C-000R-MR-1020-001 | MATERIAL REQUISITION FOR RECIPROCATING COMPRESSOR | KOBE STEE LTD | 018K0001 | 22S-19588 | 000-K-SIN-40001-001 | RUST PREVENTING PROCEDURE AT SHOP 018K1001 018K1002 018K0001 018K2001 018K2002 023K0001A/B | A5002 | AX | 2 | 2019-04-12 | CON-BMP-VTRA-011143 | 2019-04-12 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-1020-001 | MATERIAL REQUISITION FOR RECIPROCATING COMPRESSOR | KOBE STEE LTD | 018K0001 | 22S-19605 | 000-K-INX-40001-001 | LIST OF VENDOR'S DOCUMENTS AND DRAWINGS 018K1001/K1002/K0001/K2001/K2002 023K0001A/B | A0001 | AX | 2 | 2019-04-26 | CON-BMP-VTRA-011268 | 2019-04-26 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-1020-001 | MATERIAL REQUISITION FOR RECIPROCATING COMPRESSOR | KOBE STEE LTD | 018K0001 | 22S-19632 | 000-K-MRS-40001-001 | PROGRESS REPORT 018K1001/K1002/K0001/K2001/K20 02 023K0001A/B | C1002 | BX | 2 | 2019-06-04 | CON-BMP-VTRA-011952 | 2019-06-04 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-1020-001 | MATERIAL REQUISITION FOR RECIPROCATING COMPRESSOR | KOBE STEE LTD | 018K0001 | 22S-19643 | 018-K-DAT-40006-001 | NOISE DATA SHEET 018K1001/1002/0001/2001/2002018K2001 018K2002 | A0105 | AX | 1 | 2019-04-01 | CON-BMP-VTRA-010931 | 2019-04-01 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-1020-001 | MATERIAL REQUISITION FOR RECIPROCATING COMPRESSOR | KOBE STEE LTD | 018K0001 | 22S-19645 | 018-K-CAL-40001-001 | CYLINDER VALVE DYNAMIC CALCULATION 018K1001/K1002/K0001/K2001/K2002 | A1003 | AX | 2 | 2019-06-10 | CON-BMP-VTRA-012118 | 2019-06-10 | FOR BAPCO REVIEW | 2019-06-24 | 2019-06-26 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001044 | CLASS 2
076551C-000R-MR-1020-001 | MATERIAL REQUISITION FOR RECIPROCATING COMPRESSOR | KOBE STEE LTD | 018K0001 | 22S-19650 | 018-K-BLD-40001-001 | ROD LOAD DIAGRAM 018K1001/1002/0001/2001/2002 | A1011 | AX | 2 | 2019-03-19 | CON-BMP-VTRA-010752 | 2019-03-19 | FOR BAPCO REVIEW | 2019-04-03 | 2019-04-03 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000446 | CLASS 2
076551C-000R-MR-1020-001 | MATERIAL REQUISITION FOR RECIPROCATING COMPRESSOR | KOBE STEE LTD | 018K0001 | 22S-19653 | 018-K-RPT-40001-001 | UTILITY LIST 018K0001/1001/1002/2001/2002 | A1014 | AX | 2 | 2019-03-19 | CON-BMP-VTRA-010755 | 2019-03-19 | FOR BAPCO REVIEW | 2019-04-03 | 2019-04-03 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000443 | CLASS 2
076551C-000R-MR-1020-001 | MATERIAL REQUISITION FOR RECIPROCATING COMPRESSOR | KOBE STEE LTD | 018K0001 | 22S-19656 | 018-K-GAD-40002-001 | CROSS SECTIONAL DRAWING FOR COMPRESSOR 018K0001 018K1001 018K1002 018K2001 018K2002 | A1101 | AX | 1 | 2019-04-01 | CON-BMP-VTRA-010928 | 2019-04-01 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-1020-001 | MATERIAL REQUISITION FOR RECIPROCATING COMPRESSOR | KOBE STEE LTD | 018K0001 | 22S-19660 | 018-K-GAD-40006-001 | GENERAL ARRANGEMENT DRAWING 018K1001/K1002/K0001/K2001/K20 02 | A2001 | BX | 2 | 2019-05-23 | CON-BMP-VTRA-011746 | 2019-05-23 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-1020-001 | MATERIAL REQUISITION FOR RECIPROCATING COMPRESSOR | KOBE STEE LTD | 018K0001 | 22S-19664 | 018-K-PED-40001-001 | FOUNDATION LAYOUT AND LOADING PLAN 018K0001/1001/1002/2001/2002 | A2006 | BX | 2 | 2019-05-23 | CON-BMP-VTRA-011748 | 2019-05-23 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-1020-001 | MATERIAL REQUISITION FOR RECIPROCATING COMPRESSOR | KOBE STEE LTD | 018K0001 | 22S-19665 | 018-K-S3D-40001-001 | 3D EQUIPMENT MODEL 018K0001 018K1001 018K1002 018K2001 018K2002 | A2013 | BX | 2 | 2019-06-11 | CON-BMP-VTRA-012140 | 2019-06-11 | FOR BAPCO REVIEW | 2019-06-25 |  |  | CLASS 3
076551C-000R-MR-1020-001 | MATERIAL REQUISITION FOR RECIPROCATING COMPRESSOR | KOBE STEE LTD | 018K0001 | 22S-19669 | 018-K-INX-40007-001 | ELECTRIC LOAD LIST 018K0001 018K1001 018K1002 018K2001 018K2002 | A4001 | AX | 2 | 2019-04-11 | CON-BMP-VTRA-011124 | 2019-04-11 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-1020-001 | MATERIAL REQUISITION FOR RECIPROCATING COMPRESSOR | KOBE STEE LTD | 018K0001 | 22S-19671 | 018-K-PRO-40001-001 | TESTING PROCEDURE (FOR COMPRESSOR, PULSATION DAMPENERS & CONSOLES) 018K0001018K1001 018K1002 018K2001 018K2002 | B1103 | AX | 2 | 2019-03-25 | CON-BMP-VTRA-010858 | 2019-03-25 | FOR BAPCO REVIEW | 2019-04-09 | 2019-04-07 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000485 | CLASS 2
076551C-000R-MR-1020-001 | MATERIAL REQUISITION FOR RECIPROCATING COMPRESSOR | KOBE STEE LTD | 018K0001 | 22S-19674 | 000-K-PRO-40002-001 | PAMI PROCEDURE 018K1001/K1002/K0001/K2001/K2002 023K0001A/B | B1204 | AX | 2 | 2019-06-17 | CON-BMP-VTRA-012250 | 2019-06-17 | FOR BAPCO REVIEW | 2019-07-01 | 2019-06-30 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001108 | CLASS 2
076551C-000R-MR-1020-001 | MATERIAL REQUISITION FOR RECIPROCATING COMPRESSOR | KOBE STEE LTD | 018K0001 | 22S-19676 | 000-K-SCH-40001-001 | ENGINEERING PROCUREMENT MANUFACTURING & TEST SCHEDULE 018K1001/K1002/K0001/K2001/K20 02 023K0001A/B | C1001 | AX | 2 | 2019-03-19 | CON-BMP-VTRA-010754 | 2019-03-19 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-1020-001 | MATERIAL REQUISITION FOR RECIPROCATING COMPRESSOR | KOBE STEE LTD | 018K0001 | 22S-19677 | 000-K-INV-40001-001 | UNPRICED COPY OF MAIN SUBORDERS 018K0001 018K1001 018K1002 018K2001 018K2002 023K0001A/B | C1005 | BX | 4 | 2019-06-03 | CON-BMP-VTRA-011945 | 2019-06-03 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-1020-001 | MATERIAL REQUISITION FOR RECIPROCATING COMPRESSOR | KOBE STEE LTD | 018K0001 | 22S-19708 | 018-K-CAL-40002-001 | PSV CALCULATION 018K1001 018K1002 018K0001 018K2001 018K2002 | A3102 | AX | 1 | 2019-07-08 | CON-BMP-VTRA-012719 | 2019-07-08 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-1020-001 | MATERIAL REQUISITION FOR RECIPROCATING COMPRESSOR | KOBE STEE LTD | 018K0001 | 22S-19842 | 018-K-PED-40003-001 | INSERT PLATE LIST 018K1001/K1002/K0001/K2001/K20 02 | A2006 | AX | 2 | 2019-04-11 | CON-BMP-VTRA-011125 | 2019-04-11 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-1020-001 | MATERIAL REQUISITION FOR RECIPROCATING COMPRESSOR | KOBE STEE LTD | 018K0001 | 22S-19946 | 018-K-PID-40006-001 | MAKE-UP H2 COMPRESSOR (KR70-4) P&I DIAGRAM FOR GAS (1/2) 018K0001 | A0103 | AX | 2 | 2019-04-26 | CON-BMP-VTRA-011260 | 2019-04-26 | FOR BAPCO INFORMATION |  | 2019-05-31 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000854 | CLASS 2
076551C-000R-MR-1020-001 | MATERIAL REQUISITION FOR RECIPROCATING COMPRESSOR | KOBE STEE LTD | 018K1001 | 22S-19673 | 000-K-PRO-40001-001 | NDT PROCEDURE 018K0001 018K1001 018K1002 018K2001 018K2002 023K0001A 023K0001B | B1202 | AX | 2 | 2019-06-04 | CON-BMP-VTRA-011950 | 2019-06-04 | FOR BAPCO REVIEW | 2019-06-19 | 2019-06-16 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000940 | CLASS 2
076551C-000R-MR-1020-001 | MATERIAL REQUISITION FOR RECIPROCATING COMPRESSOR | KOBE STEE LTD | 018M0043 | 03S-K74313 | 018-K-DAT-40013-001 | LV MOTOR DATASHEET AND CURVES 018M0043 018M1009 018M1012 018M2009 018M2012 | A4102 | AX | 2 | 2019-04-16 | CON-BMP-VTRA-011186 | 2019-04-16 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-1020-001 | MATERIAL REQUISITION FOR RECIPROCATING COMPRESSOR | KOBE STEE LTD | 018M0043 | 03S-K74314 | 018-K-GAD-40011-001 | LV MOTOR GA DRAWING FOR CYLINDER LUBRICATOR ELECTRIC MOTOR 018M0043 018M1009 018M1012 018M2009 018M2012 | A4201 | AX | 2 | 2019-05-23 | CON-BMP-VTRA-011756 | 2019-05-23 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-1020-001 | MATERIAL REQUISITION FOR RECIPROCATING COMPRESSOR | KOBE STEE LTD | 018M0044B | 03S-K75465 | 018-K-GAD-40077-001 | LV MOTOR GA DRAWING FOR LUBE OIL PUMP ELECTRIC MOTOR 018M0044B 018M1008B 018M1011B 018M2008B 018M2011B | A4201 | AX | 2 | 2019-05-23 | CON-BMP-VTRA-011756 | 2019-05-23 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-1020-001 | MATERIAL REQUISITION FOR RECIPROCATING COMPRESSOR | KOBE STEE LTD | 018M0071 | 03S-K74286 | 018-K-DAT-40010-001 | HV MOTOR DATASHEET AND CURVES 018M0071 | A4102 | AX | 2 | 2019-04-11 | CON-BMP-VTRA-011121 | 2019-04-11 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-1020-001 | MATERIAL REQUISITION FOR RECIPROCATING COMPRESSOR | KOBE STEE LTD | 018M0071 | 03S-K74288 | 018-K-GAD-40010-001 | HV MOTOR GA DRAWING MAKE UP HYDROGEN COMPRESSORS 018M0071 | A4201 | AX | 2 | 2019-04-12 | CON-BMP-VTRA-011134 | 2019-04-12 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-1020-001 | MATERIAL REQUISITION FOR RECIPROCATING COMPRESSOR | KOBE STEE LTD | 018M0071 | 03S-K74290 | 018-K-CWD-40003-001 | HV MOTOR WIRING DRAWING 018M0071/1031/1032/2031/2032 | A4211 | AX | 2 | 2019-04-11 | CON-BMP-VTRA-011123 | 2019-04-11 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-1020-001 | MATERIAL REQUISITION FOR RECIPROCATING COMPRESSOR | KOBE STEE LTD | 018M0071 | 03S-K74322 | 018-K-PRO-40002-001 | TESTING PROCEDURE (FOR MAIN MOTOR) 018M0071 018M1031 018M1032 018M2031 018M2032 | B1103 | BX | 2 | 2019-06-04 | CON-BMP-VTRA-011951 | 2019-06-04 | FOR BAPCO REVIEW | 2019-06-19 | 2019-06-15 | 1-APPROVED BMP-ROC-VTRE-000925 | CLASS 2
076551C-000R-MR-1020-001 | MATERIAL REQUISITION FOR RECIPROCATING COMPRESSOR | KOBE STEE LTD | 018M1010A | 03S-K75466 | 018-K-GAD-40079-001 | LV MOTOR GA DRAWING FOR TRAIN 1 TEMPERED WATER PUMP ELECTRIC MOTOR 018M2010A/B 018M1010A/B | A4201 | AX | 2 | 2019-05-23 | CON-BMP-VTRA-011756 | 2019-05-23 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-1020-001 | MATERIAL REQUISITION FOR RECIPROCATING COMPRESSOR | KOBE STEE LTD | 018P0044A | 03S-K74308 | 023-K-DLB-40002-001 | HV MOTOR NAME PLATE 023M0020A/B | A4205 | AX | 2 | 2019-04-16 | CON-BMP-VTRA-011187 | 2019-04-16 | FOR BAPCO INFORMATION |  | 2019-05-15 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000672 | CLASS 3
076551C-000R-MR-1020-001 | MATERIAL REQUISITION FOR RECIPROCATING COMPRESSOR | KOBE STEE LTD | 018P0044A | 22S-19847 | 018-K-DAT-40032-001 | AUXILIARY DATASHEET (OIL PUMP) 018P0044B 018P1008B 018P1011B 018P2008B 018P2011B | A1006 | AX | 2 | 2019-04-12 | CON-BMP-VTRA-011139 | 2019-04-12 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-1020-001 | MATERIAL REQUISITION FOR RECIPROCATING COMPRESSOR | KOBE STEE LTD | 018P0044B | 22S-19849 | 018-K-GAD-40037-001 | AUXILIARY DRAWING (OIL PUMP) 018P0044B 018P1008B 018P1011B 018P2008B 018P2011B | A1109 | BX | 2 | 2019-06-04 | CON-BMP-VTRA-011956 | 2019-06-04 | FOR BAPCO REVIEW | 2019-06-19 | 2019-06-27 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001061 | CLASS 2
076551C-000R-MR-1020-001 | MATERIAL REQUISITION FOR RECIPROCATING COMPRESSOR | KOBE STEE LTD | 018P0044B | 22S-19917 | 018-K-DLB-40012-001 | AUXILIARY NAMEPLATE (OIL PUMP) 018P0044B 018P1008B 018P1011B 018P2008B 018P2011B | A1112 | AX | 2 | 2019-05-23 | CON-BMP-VTRA-011758 | 2019-05-23 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-1020-001 | MATERIAL REQUISITION FOR RECIPROCATING COMPRESSOR | KOBE STEE LTD | 018P1010A | 22S-19648 | 018-K-DLB-40001-001 | AUXILIARY NAMEPLATE (TEMPERED COOLING WATER PUMP) 018P1010A/B 018P2010A/B | A1112 | AX | 2 | 2019-05-23 | CON-BMP-VTRA-011758 | 2019-05-23 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-1020-001 | MATERIAL REQUISITION FOR RECIPROCATING COMPRESSOR | KOBE STEE LTD | 018P1010A | 22S-19863 | 018-K-DAT-40033-001 | AUXILIARY DATASHEET (TEMPERED COOLING WATER PUMP) 018P1010A/B 018P2010A/B | A1006 | AX | 2 | 2019-04-12 | CON-BMP-VTRA-011139 | 2019-04-12 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-1020-001 | MATERIAL REQUISITION FOR RECIPROCATING COMPRESSOR | KOBE STEE LTD | 018P1010A | 22S-19865 | 018-K-GAD-40038-001 | AUXILIARY DRAWING (TEMPERED COOLING WATER PUMP) 018P1010A/B 018P2010A/B | A1109 | AX | 2 | 2019-05-23 | CON-BMP-VTRA-011743 | 2019-05-23 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-1020-001 | MATERIAL REQUISITION FOR RECIPROCATING COMPRESSOR | KOBE STEE LTD | 018U0005 | 22S-19662 | 018-K-GAD-40008-001 | LUBE OIL CONSOLE ARRANGEMENT DRAWING 018U0005 018U1003 018U1004 018U2003 018U2004 | A2002 | AX | 1 | 2019-03-19 | CON-BMP-VTRA-010756 | 2019-03-19 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-1020-001 | MATERIAL REQUISITION FOR RECIPROCATING COMPRESSOR | KOBE STEE LTD | 018U1005 | 22S-19663 | 018-K-GAD-40009-001 | TEMPERED COOLING WATER CONSOLE ARRANGEMENT DRAWING 018U1005 018U2005 | A2002 | AX | 1 | 2019-03-19 | CON-BMP-VTRA-010756 | 2019-03-19 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-1020-001 | MATERIAL REQUISITION FOR RECIPROCATING COMPRESSOR | KOBE STEE LTD | 018V0074 | 22S-19969 | 018-K-GAD-40082-001 | DISTANCE PIECE DRAIN POT 018V2026/2027/2035/2036 018V0074/0075 018V1026/1027 018V1035/1036 | A1109 | AX | 2 | 2019-06-17 | CON-BMP-VTRA-012251 | 2019-06-17 | FOR BAPCO REVIEW | 2019-07-01 | 2019-07-02 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001150 | CLASS 2
076551C-000R-MR-1020-001 | MATERIAL REQUISITION FOR RECIPROCATING COMPRESSOR | KOBE STEE LTD | 018V0076A | 22S-19646 | 018-K-DAT-40008-001 | AUXILIARY DATASHEET (OIL FILTER) 018V0076A/B 018V1028A/B 018V1037A/B 018V2028A/B 018V2037A/B | A1006 | BX | 2 | 2019-06-04 | CON-BMP-VTRA-011953 | 2019-06-04 | FOR BAPCO REVIEW | 2019-06-19 | 2019-06-26 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001037 | CLASS 2
076551C-000R-MR-1020-001 | MATERIAL REQUISITION FOR RECIPROCATING COMPRESSOR | KOBE STEE LTD | 018V0076A | 22S-19647 | 018-K-GAD-40001-001 | AUXILIARY DRAWING (OIL FILTER) 018V0076A/B 018V1028A/B 018V1037A/B 018V2028A/B 018V2037A/B | A1109 | BX | 2 | 2019-06-04 | CON-BMP-VTRA-011955 | 2019-06-04 | FOR BAPCO REVIEW | 2019-06-19 | 2019-06-26 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001050 | CLASS 2
076551C-000R-MR-1020-001 | MATERIAL REQUISITION FOR RECIPROCATING COMPRESSOR | KOBE STEE LTD | 018V0076A | 22S-19888 | 018-K-DLB-40009-001 | MAKE-UP H2 COMPRESSOR (KR70-4) P&I DIAGRAM FOR GAS (1/2) 018K0001 | A1112 | AX | 1 | 2019-05-23 | CON-BMP-VTRA-011745 | 2019-05-23 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-1020-001 | MATERIAL REQUISITION FOR RECIPROCATING COMPRESSOR | KOBE STEE LTD | 018V0155 | 22S-19657 | 018-K-GAD-40003-001 | DRAWING FOR SUCTION PULSATION DAMPNER FIRST STAGE 018V0068 | A1103 | AX | 2 | 2019-03-29 | CON-BMP-VTRA-010926 | 2019-03-29 | FOR BAPCO INFORMATION |  | 2019-05-15 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000679 | CLASS 2
076551C-000R-MR-1020-001 | MATERIAL REQUISITION FOR RECIPROCATING COMPRESSOR | KOBE STEE LTD | 018V1038A | 22S-19819 | 018-K-DAT-40031-001 | AUXILIARY DATASHEET (COOLING WATER FILTER) 018V1038A/B 018V2038A/B | A1006 | BX | 2 | 2019-06-10 | CON-BMP-VTRA-012119 | 2019-06-10 | FOR BAPCO REVIEW | 2019-06-24 | 2019-06-26 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001045 | CLASS 2
076551C-000R-MR-1020-001 | MATERIAL REQUISITION FOR RECIPROCATING COMPRESSOR | KOBE STEE LTD | 018V1038A | 22S-19972 | 018-K-DLB-40010-001 | AUXILIARY NAMEPLATE (TEMPERED WATER FILTER) 018V1038A/B 018V2038A/B | A1112 | AX | 2 | 2019-05-23 | CON-BMP-VTRA-011758 | 2019-05-23 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-1020-001 | MATERIAL REQUISITION FOR RECIPROCATING COMPRESSOR | KOBE STEE LTD | 018V2038A | 22S-19821 | 018-K-GAD-40036-001 | AUXILIARY DRAWING (COOLING WATER FILTER) 018V1038A/B 018V2038A/B | A1109 | AX | 2 | 2019-05-23 | CON-BMP-VTRA-011753 | 2019-05-23 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-1020-001 | MATERIAL REQUISITION FOR RECIPROCATING COMPRESSOR | KOBE STEE LTD | 023E0007 | 22S-19691 | 023-K-GAD-40004-001 | LUBE OIL COOLER DRAWING 023E0007/023E0012 | A1103 | AX | 2 | 2019-07-03 | CON-BMP-VTRA-012636 | 2019-07-03 | FOR BAPCO REVIEW | 2019-07-17 |  |  | CLASS 2
076551C-000R-MR-1020-001 | MATERIAL REQUISITION FOR RECIPROCATING COMPRESSOR | KOBE STEE LTD | 023E0007 | 22S-20072 | 023-K-DLB-40010-001 | NAMEPLATE (LUBE OIL COOLER) 023E0007 023E0012 | A1112 | AX | 2 | 2019-06-17 | CON-BMP-VTRA-012254 | 2019-06-17 | FOR BAPCO REVIEW | 2019-07-02 | 2019-07-07 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001187 | CLASS 2
076551C-000R-MR-1020-001 | MATERIAL REQUISITION FOR RECIPROCATING COMPRESSOR | KOBE STEE LTD | 023E0008 | 03S-K75929 | 023-K-GAD-40061-001 | ELECTRIC HEATER GA DRAWING & WIRING DIAGRAM 023E0008 / 023E0009 / 023E0010 / 023E0013/ 023E0014 | A4201 | AX | 2 | 2019-07-08 | CON-BMP-VTRA-012736 | 2019-07-08 | FOR BAPCO REVIEW | 2019-07-23 |  |  | CLASS 2
076551C-000R-MR-1020-001 | MATERIAL REQUISITION FOR RECIPROCATING COMPRESSOR | KOBE STEE LTD | 023E0011A | 22S-2007 | 023-K-DLB-40011-001 | NAMEPLATE (TEMPERED COOLING WATER COOLER) 023E0011A/B | A1112 | AX | 2 | 2019-06-17 | CON-BMP-VTRA-012254 | 2019-06-17 | FOR BAPCO REVIEW | 2019-07-02 | 2019-07-07 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001187 | CLASS 2
076551C-000R-MR-1020-001 | MATERIAL REQUISITION FOR RECIPROCATING COMPRESSOR | KOBE STEE LTD | 023K0001A | 03S-K74292 | 023-K-INX-40003-001 | LIST OF INSTRUMENTS 023K0001/023K0001B | A3001 | AX | 1 | 2019-03-18 | CON-BMP-VTRA-010721 | 2019-03-18 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-1020-001 | MATERIAL REQUISITION FOR RECIPROCATING COMPRESSOR | KOBE STEE LTD | 023K0001A | 03S-K74293 | 023-K-INX-40005-001 | LIST OF JUNCTION BOXES & LOCALSWITCH BOXES 023K0001A/B | A3003 | AX | 2 | 2019-05-13 | CON-BMP-VTRA-011542 | 2019-05-13 | FOR BAPCO REVIEW | 2019-06-28 |  |  | CLASS 2
076551C-000R-MR-1020-001 | MATERIAL REQUISITION FOR RECIPROCATING COMPRESSOR | KOBE STEE LTD | 023K0001A | 03S-K74295 | 023-K-CWD-40002-001 | INSTRUMENT (FIELD) WIRING DIAGRAM 023K0001A/B | A3403 | AX | 2 | 2019-05-13 | CON-BMP-VTRA-011541 | 2019-05-13 | FOR BAPCO REVIEW | 2019-06-28 | 2019-07-11 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001291 | CLASS 2
076551C-000R-MR-1020-001 | MATERIAL REQUISITION FOR RECIPROCATING COMPRESSOR | KOBE STEE LTD | 023K0001A | 03S-K74297 | 023-K-DAT-40008-001 | INSTRUMENT DATASHEETS 023K0001A/B | A3101 | AX | 2 | 2019-05-24 | CON-BMP-VTRA-011801 | 2019-05-24 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-1020-001 | MATERIAL REQUISITION FOR RECIPROCATING COMPRESSOR | KOBE STEE LTD | 023K0001A | 03S-K74307 | 023-K-CWD-40003-001 | HV MOTOR WIRING DRAWING 023K0001A/B | A4211 | AX | 2 | 2019-04-12 | CON-BMP-VTRA-011144 | 2019-04-12 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-1020-001 | MATERIAL REQUISITION FOR RECIPROCATING COMPRESSOR | KOBE STEE LTD | 023K0001A | 22S-19591 | 023-K-DAT-40006-001 | COMPRESSOR DATASHEET 023K0001A/B | A1001 | AX | 2 | 2019-04-11 | CON-BMP-VTRA-011120 | 2019-04-11 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-1020-001 | MATERIAL REQUISITION FOR RECIPROCATING COMPRESSOR | KOBE STEE LTD | 023K0001A | 22S-19592 | 023-K-PQP-40001-001 | FABRICATION AND QUALITY CONTROL PLAN 023K0001A 023K0001B | B1002 | BX | 2 | 2019-06-10 | CON-BMP-VTRA-012117 | 2019-06-10 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-1020-001 | MATERIAL REQUISITION FOR RECIPROCATING COMPRESSOR | KOBE STEE LTD | 023K0001A | 22S-19594 | 023-K-TSP-40002-001 | PIPING SPECIFICATION 023K0001A/ | A1109 | AX | 2 | 2019-06-04 | CON-BMP-VTRA-011958 | 2019-06-04 | FOR BAPCO REVIEW | 2019-06-19 | 2019-06-27 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001062 | CLASS 2
076551C-000R-MR-1020-001 | MATERIAL REQUISITION FOR RECIPROCATING COMPRESSOR | KOBE STEE LTD | 023K0001A | 22S-19631 | 023-K-PID-40001-001 | FEED GAS COMPRESSOR (KR 30-2) P&I DIAGRAM FOR GAS 023K0001A/B | A0103 | CX | 2 | 2019-06-05 | CON-BMP-VTRA-012010 | 2019-06-05 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-1020-001 | MATERIAL REQUISITION FOR RECIPROCATING COMPRESSOR | KOBE STEE LTD | 023K0001A | 22S-19678 | 023-K-DAT-40005-001 | NOISE DATA SHEET 023K0001A/B | A0105 | AX | 1 | 2019-04-01 | CON-BMP-VTRA-010931 | 2019-04-01 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-1020-001 | MATERIAL REQUISITION FOR RECIPROCATING COMPRESSOR | KOBE STEE LTD | 023K0001A | 22S-19684 | 023-K-BLD-40001-001 | ROD LOAD DIAGRAM 023K0001A/B | A1011 | AX | 2 | 2019-04-01 | CON-BMP-VTRA-010929 | 2019-04-01 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-1020-001 | MATERIAL REQUISITION FOR RECIPROCATING COMPRESSOR | KOBE STEE LTD | 023K0001A | 22S-19686 | 023-K-RPT-40001-001 | UTILITY LIST FEED GAS COMPRESSORS 023K0001A/023K0001B | A1014 | AX | 2 | 2019-04-12 | CON-BMP-VTRA-011135 | 2019-04-12 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-1020-001 | MATERIAL REQUISITION FOR RECIPROCATING COMPRESSOR | KOBE STEE LTD | 023K0001A | 22S-19689 | 023-K-GAD-40002-001 | CROSS SECTIONAL DRAWING FOR COMPRESSOR 023K0001A/B | A1101 | AX | 1 | 2019-04-01 | CON-BMP-VTRA-010928 | 2019-04-01 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-1020-001 | MATERIAL REQUISITION FOR RECIPROCATING COMPRESSOR | KOBE STEE LTD | 023K0001A | 22S-19690 | 023-K-GAD-40003-001 | PULSATION DAMPENER DRAWING 023K0001A/B | A1103 | AX | 2 | 2019-03-16 | CON-BMP-VTRA-010719 | 2019-03-16 | FOR BAPCO REVIEW | 2019-04-01 | 2019-04-05 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000459 | CLASS 2
076551C-000R-MR-1020-001 | MATERIAL REQUISITION FOR RECIPROCATING COMPRESSOR | KOBE STEE LTD | 023K0001A | 22S-19693 | 023-K-GAD-40006-001 | GENERAL ARRANGEMENT DRAWING 023K0001A/B | A2001 | AX | 2 | 2019-03-12 | CON-BMP-VTRA-010660 | 2019-03-12 | FOR BAPCO REVIEW | 2019-03-27 | 2019-03-27 | 2-REVIEWD WITH MINOR COMMENTS BMP-ROC-VTRE-000395 | CLASS 2
076551C-000R-MR-1020-001 | MATERIAL REQUISITION FOR RECIPROCATING COMPRESSOR | KOBE STEE LTD | 023K0001A | 22S-19695 | 023-K-GAD-40008-001 | LUBE OIL CONSOLE ARRANGEMENT DRAWING 023K0001A/B | A2002 | BX | 2 | 2019-06-04 | CON-BMP-VTRA-011954 | 2019-06-04 | FOR BAPCO REVIEW | 2019-06-19 | 2019-06-20 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001008 | CLASS 2
076551C-000R-MR-1020-001 | MATERIAL REQUISITION FOR RECIPROCATING COMPRESSOR | KOBE STEE LTD | 023K0001A | 22S-19696 | 023-K-GAD-40009-001 | TEMPERED COOLING WATER CONSOLE ARRANGEMENT DRAWING 023K0001A/B | A2002 | BX | 2 | 2019-06-17 | CON-BMP-VTRA-012249 | 2019-06-17 | FOR BAPCO REVIEW | 2019-07-01 | 2019-07-02 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001148 | CLASS 2
076551C-000R-MR-1020-001 | MATERIAL REQUISITION FOR RECIPROCATING COMPRESSOR | KOBE STEE LTD | 023K0001A | 22S-19697 | 023-K-PED-40001-001 | FOUNDATION LAYOUT AND LOADING PLAN 023K0001A/B | A2006 | BX | 2 | 2019-05-13 | CON-BMP-VTRA-011539 | 2019-05-13 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-1020-001 | MATERIAL REQUISITION FOR RECIPROCATING COMPRESSOR | KOBE STEE LTD | 023K0001A | 22S-19698 | 023-K-S3D-40001-001 | 3D EQUIPMENT MODEL 023K0001AB | A2013 | BX | 2 | 2019-06-11 | CON-BMP-VTRA-012141 | 2019-06-11 | FOR BAPCO REVIEW | 2019-06-25 | 2019-06-29 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001088 | CLASS 3
076551C-000R-MR-1020-001 | MATERIAL REQUISITION FOR RECIPROCATING COMPRESSOR | KOBE STEE LTD | 023K0001A | 22S-19701 | 023-K-INX-40007-001 | ELECTRIC LOAD LIST 023K0001A/B | A4001 | AX | 2 | 2019-04-11 | CON-BMP-VTRA-011124 | 2019-04-11 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-1020-001 | MATERIAL REQUISITION FOR RECIPROCATING COMPRESSOR | KOBE STEE LTD | 023K0001A | 22S-19703 | 023-K-PRO-40001-001 | TESTING PROCEDURE (FOR COMPRESSOR, PULSATION DAMPENERS & CONSOLES) 023K0001A/B | B1103 | AX | 2 | 2019-03-25 | CON-BMP-VTRA-010858 | 2019-03-25 | FOR BAPCO REVIEW | 2019-04-09 | 2019-04-07 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000485 | CLASS 2
076551C-000R-MR-1020-001 | MATERIAL REQUISITION FOR RECIPROCATING COMPRESSOR | KOBE STEE LTD | 023K0001A | 22S-19709 | 023-K-CAL-40002-001 | PSV CALCULATION 023K0001AB | A3102 | AX | 1 | 2019-07-08 | CON-BMP-VTRA-012721 | 2019-07-08 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-1020-001 | MATERIAL REQUISITION FOR RECIPROCATING COMPRESSOR | KOBE STEE LTD | 023K0001A | 22S-19843 | 023-K-PED-40003-001 | INSERT PLATE LIST 023K0001A/B | A2006 | AX | 2 | 2019-04-11 | CON-BMP-VTRA-011125 | 2019-04-11 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-1020-001 | MATERIAL REQUISITION FOR RECIPROCATING COMPRESSOR | KOBE STEE LTD | 023M0003B | 03S-K75469 | 023-K-GAD-40049-001 | LV MOTOR GA DRAWING FOR LUBE OIL PUMP ELECTRIC MOTOR 023M0006B 023M0003B | A4201 | AX | 2 | 2019-05-23 | CON-BMP-VTRA-011756 | 2019-05-23 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-1020-001 | MATERIAL REQUISITION FOR RECIPROCATING COMPRESSOR | KOBE STEE LTD | 023M0004 | 03S-K74317 | 023-K-DAT-40004-001 | LV MOTOR DATASHEET AND CURVES 023M0004 023M0007 | A4102 | AX | 2 | 2019-04-16 | CON-BMP-VTRA-011186 | 2019-04-16 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-1020-001 | MATERIAL REQUISITION FOR RECIPROCATING COMPRESSOR | KOBE STEE LTD | 023M0004 | 03S-K74318 | 023-K-GAD-40011-001 | LV MOTOR GA DRAWING FOR CYLINDER LUBRICATOR ELECTRIC MOTOR 023M0004 023M0007 | A4201 | AX | 2 | 2019-05-23 | CON-BMP-VTRA-011756 | 2019-05-23 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-1020-001 | MATERIAL REQUISITION FOR RECIPROCATING COMPRESSOR | KOBE STEE LTD | 023M0005A | 03S-K75470 | 023-K-GAD-40050-001 | LV MOTOR GA DRAWING FOR TEMPERED WATER PUMP ELECTRIC MOTOR 023M0005A/B | A4201 | AX | 2 | 2019-05-23 | CON-BMP-VTRA-011756 | 2019-05-23 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-1020-001 | MATERIAL REQUISITION FOR RECIPROCATING COMPRESSOR | KOBE STEE LTD | 023M0020A | 03S-K74305 | 023-K-DAT-40030-001 | HV MOTOR DATASHEET AND CURVES 023M0020A/B | A4102 | AX | 2 | 2019-04-11 | CON-BMP-VTRA-011121 | 2019-04-11 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-1020-001 | MATERIAL REQUISITION FOR RECIPROCATING COMPRESSOR | KOBE STEE LTD | 023M0020A | 03S-K74306 | 023-K-GAD-40010-001 | HV MOTOR GA DRAWING FEED GAS COMPRESSORS 023M0020A/B | A4201 | AX | 2 | 2019-04-12 | CON-BMP-VTRA-011134 | 2019-04-12 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-1020-001 | MATERIAL REQUISITION FOR RECIPROCATING COMPRESSOR | KOBE STEE LTD | 023M0020A | 03S-K74323 | 023-K-PRO-40002-001 | TESTING PROCEDURE (FOR MAIN MOTOR) 023M0020A/B | B1103 | BX | 2 | 2019-06-04 | CON-BMP-VTRA-011951 | 2019-06-04 | FOR BAPCO REVIEW | 2019-06-19 | 2019-06-15 | 1-APPROVED BMP-ROC-VTRE-000925 | CLASS 2
076551C-000R-MR-1020-001 | MATERIAL REQUISITION FOR RECIPROCATING COMPRESSOR | KOBE STEE LTD | 023P0003B | 22S-19848 | 023-K-DAT-40023-001 | AUXILIARY DATASHEET (OIL PUMP) 023P0003B 023P0006B | A1006 | AX | 2 | 2019-04-12 | CON-BMP-VTRA-011139 | 2019-04-12 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-1020-001 | MATERIAL REQUISITION FOR RECIPROCATING COMPRESSOR | KOBE STEE LTD | 023P0003B | 22S-19850 | 023-K-GAD-40037-001 | AUXILIARY DRAWING (OIL PUMP) 023P0003B 023P0006B | A1109 | BX | 2 | 2019-06-04 | CON-BMP-VTRA-011956 | 2019-06-04 | FOR BAPCO REVIEW | 2019-06-19 | 2019-06-27 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001061 | CLASS 2
076551C-000R-MR-1020-001 | MATERIAL REQUISITION FOR RECIPROCATING COMPRESSOR | KOBE STEE LTD | 023P0003B | 22S-19918 | 023-K-DLB-40014-001 | AUXILIARY NAMEPLATE (OIL PUMP) 023P0003B 023P0006B | A1112 | AX | 2 | 2019-05-23 | CON-BMP-VTRA-011758 | 2019-05-23 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-1020-001 | MATERIAL REQUISITION FOR RECIPROCATING COMPRESSOR | KOBE STEE LTD | 023P0005A | 22S-19682 | 023-K-DLB-40001-001 | AUXILIARY NAMEPLATE (TEMPERED COOLING WATER PUMP) 023P0005A/B | A1112 | AX | 2 | 2019-05-23 | CON-BMP-VTRA-011758 | 2019-05-23 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-1020-001 | MATERIAL REQUISITION FOR RECIPROCATING COMPRESSOR | KOBE STEE LTD | 023P0005A | 22S-19864 | 023-K-DAT-40024-001 | AUXILIARY DATASHEET (TEMPERED COOLING WATER PUMP) 023P0005A/B | A1006 | AX | 2 | 2019-04-12 | CON-BMP-VTRA-011141 | 2019-04-12 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-1020-001 | MATERIAL REQUISITION FOR RECIPROCATING COMPRESSOR | KOBE STEE LTD | 023P0005A | 22S-19866 | 023-K-GAD-40038-001 | AUXILIARY DRAWING (TEMPERED COOLING WATER PUMP) 023P0005A/B | A1109 | AX | 2 | 2019-05-23 | CON-BMP-VTRA-011753 | 2019-05-23 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-1020-001 | MATERIAL REQUISITION FOR RECIPROCATING COMPRESSOR | KOBE STEE LTD | 023V0007 | 22C-05740 | 023-K-CAL-40007-001 | STRENGTH CLCULATION FOR PULSATION DAMPENER 023V0007/0008/0011/0015/0016/0019/0040/0041/0042 | A1003 | AX | 2 | 2019-07-03 | CON-BMP-VTRA-012638 | 2019-07-03 | FOR BAPCO REVIEW | 2019-07-17 |  |  | CLASS 2
076551C-000R-MR-1020-001 | MATERIAL REQUISITION FOR RECIPROCATING COMPRESSOR | KOBE STEE LTD | 023V0007 | 22S-19705 | 023-K-MCD-40002-001 | WPS & PQR FOR PULSATION DAMPENER RECIPROCATING COMPRESSOR 023V0007/0008/0011/0015/0016/0019/0040/0041/0042 | B1304 | AX | 2 | 2019-07-03 | CON-BMP-VTRA-012637 | 2019-07-03 | FOR BAPCO REVIEW | 2019-07-17 |  |  | CLASS 2
076551C-000R-MR-1020-001 | MATERIAL REQUISITION FOR RECIPROCATING COMPRESSOR | KOBE STEE LTD | 023V0009 | 22S-19970 | 023-K-GAD-40056-001 | AUXILIARY DRAWING (DRAIN POT FOR ROD PACKING AND DISTANCE PIECE) | A1109 | AX | 2 | 2019-06-17 | CON-BMP-VTRA-012252 | 2019-06-17 | FOR BAPCO REVIEW | 2019-07-01 | 2019-07-01 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001124 | CLASS 2
076551C-000R-MR-1020-001 | MATERIAL REQUISITION FOR RECIPROCATING COMPRESSOR | KOBE STEE LTD | 023V0012A | 22S-19680 | 023-K-DAT-40029-001 | AUXILIARY DATASHEET (OIL FILTER)023V0012A/B 023V0020A/B | A1006 | BX | 2 | 2019-06-04 | CON-BMP-VTRA-011953 | 2019-06-04 | FOR BAPCO REVIEW | 2019-06-19 | 2019-06-26 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001037 | CLASS 2
076551C-000R-MR-1020-001 | MATERIAL REQUISITION FOR RECIPROCATING COMPRESSOR | KOBE STEE LTD | 023V0012A | 22S-19681 | 023-K-GAD-40001-001 | AUXILIARY DRAWING (OIL FILTER) 023V0012A/B 023V0020A/B | A1109 | BX | 2 | 2019-06-04 | CON-BMP-VTRA-011956 | 2019-06-04 | FOR BAPCO REVIEW | 2019-06-19 | 2019-06-27 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001061 | CLASS 2
076551C-000R-MR-1020-001 | MATERIAL REQUISITION FOR RECIPROCATING COMPRESSOR | KOBE STEE LTD | 023V0012A | 22S-19889 | 023-K-DLB-40008-001 | AUXILIARY NAMEPLATE (OIL FILTER) 023V0012A/B 023V0020/AB | A1112 | AX | 2 | 2019-05-23 | CON-BMP-VTRA-011758 | 2019-05-23 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-1020-001 | MATERIAL REQUISITION FOR RECIPROCATING COMPRESSOR | KOBE STEE LTD | 023V0014A | 22S-19820 | 023-K-DAT-40022-001 | AUXILIARY DATASHEET (COOLING WATER FILTER) 023V0014A/B | A1006 | BX | 2 | 2019-06-10 | CON-BMP-VTRA-012120 | 2019-06-10 | FOR BAPCO REVIEW | 2019-06-24 | 2019-06-20 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001009 | CLASS 2
076551C-000R-MR-1020-001 | MATERIAL REQUISITION FOR RECIPROCATING COMPRESSOR | KOBE STEE LTD | 023V0014A | 22S-19822 | 023-K-GAD-40036-001 | AUXILIARY DRAWING (COOLING WATER FILTER) 023V0014A/B | A1109 | AX | 2 | 2019-05-23 | CON-BMP-VTRA-011743 | 2019-05-23 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-1020-001 | MATERIAL REQUISITION FOR RECIPROCATING COMPRESSOR | KOBE STEE LTD | 023V0014A | 22S-19973 | 023-K-DLB-40012-001 | AUXILIARY NAMEPLATE (TEMPERED WATER FILTER) 023V0014A/B | A1112 | AX | 2 | 2019-05-23 | CON-BMP-VTRA-011758 | 2019-05-23 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-1628-001 | MATERIAL REQUISITION FOR LV INDOOR DISTRIBUTION PANEL BOARDS | CORTEM SPA | BUS4028N | A3-C 24770 | 392-P-GAD-40414-001 | LV INDOOR DISTRIBUTION PANEL BOARD GENERAL EXTERNAL LAYOUT BUS4028N | A4201 | AX | 2 | 2019-07-10 | CON-BMP-VTRA-012784 | 2019-07-10 | FOR BAPCO REVIEW | 2019-07-24 |  |  | CLASS 2
076551C-000R-MR-1628-001 | MATERIAL REQUISITION FOR LV INDOOR DISTRIBUTION PANEL BOARDS | CORTEM SPA | BUS4028N | DS_87010_72 | 392-P-DAT-40006-001 | FILLED-IN DATA SHEET (BUS4028N) | A4101 | AX | 1 | 2019-07-12 | CON-BMP-VTRA-012841 | 2019-07-12 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-1628-001 | MATERIAL REQUISITION FOR LV INDOOR DISTRIBUTION PANEL BOARDS | CORTEM SPA | BUS4028N | ITP_87010 | 000-P-PQP-40003-001 | FABRICATION AND QUALITY CONTROL PLAN FOR LV INDOOR DISTRIBUTION PANEL BOARDS ALL ITEMS | B1002 | AX | 2 | 2019-07-12 | CON-BMP-VTRA-012844 | 2019-07-12 | FOR BAPCO REVIEW | 2019-07-26 |  |  | CLASS 2
076551C-000R-MR-1628-001 | MATERIAL REQUISITION FOR LV INDOOR DISTRIBUTION PANEL BOARDS | CORTEM SPA | BUS4028N | WD_87010_72 | 392-P-WRD-40001-001 | LV INDOOR DISTRIBUTION PANEL BOARD WIRING DIAGRAM BUS4028N | A4110 | AX | 2 | 2019-07-12 | CON-BMP-VTRA-012851 | 2019-07-12 | FOR BAPCO REVIEW | 2019-07-26 |  |  | CLASS 2
076551C-000R-MR-1628-001 | MATERIAL REQUISITION FOR LV INDOOR DISTRIBUTION PANEL BOARDS | CORTEM SPA | BUS4130N | A3-C 24763 | 018-P-GAD-40035-001 | LV INDOOR DISTRIBUTION PANEL BOARD GENERAL EXTERNAL LAYOUT BUS4130N | A4201 | AX | 2 | 2019-07-09 | CON-BMP-VTRA-012778 | 2019-07-09 | FOR BAPCO REVIEW | 2019-07-24 |  |  | CLASS 2
076551C-000R-MR-1628-001 | MATERIAL REQUISITION FOR LV INDOOR DISTRIBUTION PANEL BOARDS | CORTEM SPA | BUS4130N | DS_87010_2 | 018-P-DAT-40046-001 | FILLED IN DATA SHEET (BUS4130N) | A4101 | AX | 1 | 2019-07-12 | CON-BMP-VTRA-012834 | 2019-07-12 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-1628-001 | MATERIAL REQUISITION FOR LV INDOOR DISTRIBUTION PANEL BOARDS | CORTEM SPA | BUS4130N | WD_87010_2 | 018-P-WRD-40003-001 | LV INDOOR DISTRIBUTION PANEL BOARD WIRING DIAGRAM BUS4130N | A4110 | AX | 2 | 2019-07-12 | CON-BMP-VTRA-012845 | 2019-07-12 | FOR BAPCO REVIEW | 2019-07-26 |  |  | CLASS 2
076551C-000R-MR-1628-001 | MATERIAL REQUISITION FOR LV INDOOR DISTRIBUTION PANEL BOARDS | CORTEM SPA | BUS4138N | A3-C 24764 | 018-P-GAD-40036-001 | LV INDOOR DISTRIBUTION PANEL BOARD GENERAL EXTERNAL LAYOUT BUS4138N | A4201 | AX | 2 | 2019-07-09 | CON-BMP-VTRA-012778 | 2019-07-09 | FOR BAPCO REVIEW | 2019-07-24 |  |  | CLASS 2
076551C-000R-MR-1628-001 | MATERIAL REQUISITION FOR LV INDOOR DISTRIBUTION PANEL BOARDS | CORTEM SPA | BUS4138N | DS_87010_12 | 018-P-DAT-40047-001 | FILLED IN DATA SHEET (BUS4138N) | A4101 | AX | 1 | 2019-07-12 | CON-BMP-VTRA-012834 | 2019-07-12 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-1628-001 | MATERIAL REQUISITION FOR LV INDOOR DISTRIBUTION PANEL BOARDS | CORTEM SPA | BUS4138N | WD_87010_12 | 018-P-WRD-40004-001 | LV INDOOR DISTRIBUTION PANEL BOARD WIRING DIAGRAM BUS4138N | A4110 | AX | 2 | 2019-07-12 | CON-BMP-VTRA-012845 | 2019-07-12 | FOR BAPCO REVIEW | 2019-07-26 |  |  | CLASS 2
076551C-000R-MR-1628-001 | MATERIAL REQUISITION FOR LV INDOOR DISTRIBUTION PANEL BOARDS | CORTEM SPA | BUS4230N | A3-C 24766 | 021-P-GAD-40029-001 | LV INDOOR DISTRIBUTION PANEL BOARD GENERAL EXTERNAL LAYOUT BUS4230N | A4201 | AX | 2 | 2019-07-10 | CON-BMP-VTRA-012780 | 2019-07-10 | FOR BAPCO REVIEW | 2019-07-24 |  |  | CLASS 2
076551C-000R-MR-1628-001 | MATERIAL REQUISITION FOR LV INDOOR DISTRIBUTION PANEL BOARDS | CORTEM SPA | BUS4230N | DS_87010_22 | 021-P-DAT-40032-001 | FILLED-IN DATA SHEET (BUS4230N) | A4101 | AX | 1 | 2019-07-12 | CON-BMP-VTRA-012837 | 2019-07-12 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-1628-001 | MATERIAL REQUISITION FOR LV INDOOR DISTRIBUTION PANEL BOARDS | CORTEM SPA | BUS4230N | WD_87010_22 | 021-P-WRD-40003-001 | LV INDOOR DISTRIBUTION PANEL BOARD WIRING DIAGRAM BUS4230N | A4110 | AX | 2 | 2019-07-12 | CON-BMP-VTRA-012846 | 2019-07-12 | FOR BAPCO REVIEW | 2019-07-26 |  |  | CLASS 2
076551C-000R-MR-1628-001 | MATERIAL REQUISITION FOR LV INDOOR DISTRIBUTION PANEL BOARDS | CORTEM SPA | BUS4328N | A3-C 24769 | 176-P-GAD-40313-001 | LV INDOOR DISTRIBUTION PANEL BOARD GENERAL EXTERNAL LAYOUT BUS4328N | A4201 | AX | 2 | 2019-07-10 | CON-BMP-VTRA-012783 | 2019-07-10 | FOR BAPCO REVIEW | 2019-07-24 |  |  | CLASS 2
076551C-000R-MR-1628-001 | MATERIAL REQUISITION FOR LV INDOOR DISTRIBUTION PANEL BOARDS | CORTEM SPA | BUS4328N | DS_87010_62 | 176-P-DAT-40016-001 | FILLED-IN DATA SHEET (BUS4328N) | A4101 | AX | 1 | 2019-07-12 | CON-BMP-VTRA-012842 | 2019-07-12 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-1628-001 | MATERIAL REQUISITION FOR LV INDOOR DISTRIBUTION PANEL BOARDS | CORTEM SPA | BUS4328N | WD_87010_62 | 176-P-WRD-40002-001 | LV INDOOR DISTRIBUTION PANEL BOARD WIRING DIAGRAM BUS4328N | A4110 | AX | 2 | 2019-07-12 | CON-BMP-VTRA-012850 | 2019-07-12 | FOR BAPCO REVIEW | 2019-07-26 |  |  | CLASS 2
076551C-000R-MR-1628-001 | MATERIAL REQUISITION FOR LV INDOOR DISTRIBUTION PANEL BOARDS | CORTEM SPA | BUS4357N | A3-C 24765 | 105-P-GAD-40305-001 | LV INDOOR DISTRIBUTION PANEL BOARD GENERAL EXTERNAL LAYOUT BUS4357N | A4201 | AX | 2 | 2019-07-09 | CON-BMP-VTRA-012779 | 2019-07-09 | FOR BAPCO REVIEW | 2019-07-24 |  |  | CLASS 2
076551C-000R-MR-1628-001 | MATERIAL REQUISITION FOR LV INDOOR DISTRIBUTION PANEL BOARDS | CORTEM SPA | BUS4357N | DS_87010_94 | 105-P-DAT-40008-001 | FILLED-IN DATA SHEET (BUS4357N) | A4101 | AX | 1 | 2019-07-12 | CON-BMP-VTRA-012838 | 2019-07-12 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-1628-001 | MATERIAL REQUISITION FOR LV INDOOR DISTRIBUTION PANEL BOARDS | CORTEM SPA | BUS4430N | A3-C 24768 | 056-P-GAD-40414-001 | LV INDOOR DISTRIBUTION PANEL BOARD GENERAL EXTERNAL LAYOUT BUS4430N | A4201 | AX | 2 | 2019-07-10 | CON-BMP-VTRA-012782 | 2019-07-10 | FOR BAPCO REVIEW | 2019-07-24 |  |  | CLASS 2
076551C-000R-MR-1628-001 | MATERIAL REQUISITION FOR LV INDOOR DISTRIBUTION PANEL BOARDS | CORTEM SPA | BUS4430N | WD_87010_42 | 056-P-WRD-40001-001 | LV INDOOR DISTRIBUTION PANEL BOARD WIRING DIAGRAM BUS4430N | A4110 | AX | 2 | 2019-07-12 | CON-BMP-VTRA-012848 | 2019-07-12 | FOR BAPCO REVIEW | 2019-07-26 |  |  | CLASS 2
076551C-000R-MR-1628-001 | MATERIAL REQUISITION FOR LV INDOOR DISTRIBUTION PANEL BOARDS | CORTEM SPA | BUS4529N | A3-C 24767 | 051-P-GAD-40424-001 | LV INDOOR DISTRIBUTION PANEL BOARD GENERAL EXTERNAL LAYOUT BUS4529N | A4201 | AX | 2 | 2019-07-10 | CON-BMP-VTRA-012781 | 2019-07-10 | FOR BAPCO REVIEW | 2019-07-24 |  |  | CLASS 2
076551C-000R-MR-1628-001 | MATERIAL REQUISITION FOR LV INDOOR DISTRIBUTION PANEL BOARDS | CORTEM SPA | BUS4529N | DS_87010_32 | 051-P-DAT-40028-001 | FILLEDIN DATA SHEET BUS4529N | A4101 | AX | 1 | 2019-07-12 | CON-BMP-VTRA-012836 | 2019-07-12 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-1628-001 | MATERIAL REQUISITION FOR LV INDOOR DISTRIBUTION PANEL BOARDS | CORTEM SPA | BUS4529N | WD_87010_32 | 051-P-WRD-40003-001 | LV INDOOR DISTRIBUTION PANEL BOARD WIRING DIAGRAM BUS4529N | A4110 | AX | 2 | 2019-07-12 | CON-BMP-VTRA-012847 | 2019-07-12 | FOR BAPCO REVIEW | 2019-07-26 |  |  | CLASS 2
076551C-000R-MR-1628-001 | MATERIAL REQUISITION FOR LV INDOOR DISTRIBUTION PANEL BOARDS | CORTEM SPA | BUS4630N | A3-C 24771 | 934-P-GAD-40424-001 | LV INDOOR DISTRIBUTION PANEL BOARD GENERAL EXTERNAL LAYOUT BUS4630N | A4201 | AX | 2 | 2019-07-10 | CON-BMP-VTRA-012785 | 2019-07-10 | FOR BAPCO REVIEW | 2019-07-24 |  |  | CLASS 2
076551C-000R-MR-1628-001 | MATERIAL REQUISITION FOR LV INDOOR DISTRIBUTION PANEL BOARDS | CORTEM SPA | BUS4630N | DS_87010_52 | 934-P-DAT-40026-001 | FILLED-IN DATA SHEET (BUS4630N) | A4101 | AX | 1 | 2019-07-12 | CON-BMP-VTRA-012843 | 2019-07-12 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-1628-001 | MATERIAL REQUISITION FOR LV INDOOR DISTRIBUTION PANEL BOARDS | CORTEM SPA | BUS4630N | WD_87010_52 | 934-P-WRD-40003-001 | LV INDOOR DISTRIBUTION PANEL BOARD WIRING DIAGRAM BUS4630N | A4110 | AX | 2 | 2019-07-12 | CON-BMP-VTRA-012849 | 2019-07-12 | FOR BAPCO REVIEW | 2019-07-26 |  |  | CLASS 2
076551C-000R-MR-1628-001 | MATERIAL REQUISITION FOR LV INDOOR DISTRIBUTION PANEL BOARDS | CORTEM SPA | BUS4645N | A3-C 24772 | 180-P-GAD-40313-001 | LV INDOOR DISTRIBUTION PANEL BOARD GENERAL EXTERNAL LAYOUT BUS4645N | A4201 | AX | 2 | 2019-07-10 | CON-BMP-VTRA-012786 | 2019-07-10 | FOR BAPCO REVIEW | 2019-07-24 |  |  | CLASS 2
076551C-000R-MR-1628-001 | MATERIAL REQUISITION FOR LV INDOOR DISTRIBUTION PANEL BOARDS | CORTEM SPA | BUS4645N | DS_87010_82 | 180-P-DAT-40012-001 | FILLED-IN DATA SHEET (BUS4645N) | A4101 | AX | 1 | 2019-07-12 | CON-BMP-VTRA-012840 | 2019-07-12 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-1641-001 | MATERIAL REQUISITION FOR POWER TRANSFORMERS AND NEUTRAL EARTHING RESISTORS | SCHNEIDER ENERJI | NER4001V1 | D20196532 | 000-P-INX-40017-001 | LIST OF VENDOR'S DOCUMENTS ANDDRAWINGS ALL ITEMS | A0001 | AX | 1 | 2019-06-06 | CON-BMP-VTRA-012034 | 2019-06-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-1641-001 | MATERIAL REQUISITION FOR POWER TRANSFORMERS AND NEUTRAL EARTHING RESISTORS | SCHNEIDER ENERJI | NER4001V1 | D20196532-104 | 000-P-SCH-40007-001 | ENGINEERING PROCUREMENT MANUFACTURING & TEST SCHEDULE POWER TRANSFORMERS AND NEUTRAL EARTHING RESISTORS ALL ITEMS | C1001 | AX | 4 | 2019-07-03 | CON-BMP-VTRA-012643 | 2019-07-03 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-1641-001 | MATERIAL REQUISITION FOR POWER TRANSFORMERS AND NEUTRAL EARTHING RESISTORS | SCHNEIDER ENERJI | NER4001V1 | D20196532-105 | 000-P-MRS-40006-001 | MONTHLY PROGRESS REPORT POWER TRANSFORMERS AND NEUTRAL EARTHING RESISTORS ALL ITEMS | C1002 | AX | 4 | 2019-07-03 | CON-BMP-VTRA-012634 | 2019-07-03 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-1641-001 | MATERIAL REQUISITION FOR POWER TRANSFORMERS AND NEUTRAL EARTHING RESISTORS | SCHNEIDER ENERJI | NER4001V1 | D20196532-109 | 000-P-INV-40006-001 | UNPRICED COPY OF MAIN SUBORDERS POWER TRANSFORMERS AND NEUTRAL EARTHING RESISTORS ALL ITEMS | C1005 | AX | 4 | 2019-07-03 | CON-BMP-VTRA-012635 | 2019-07-03 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-1641-001 | MATERIAL REQUISITION FOR POWER TRANSFORMERS AND NEUTRAL EARTHING RESISTORS | SCHNEIDER ENERJI | NER4001V1 | D20196532-110 | 000-P-ITP-40019-001 | INSPECTION AND TEST PLAN FOR POWER TRANSFORMERS AND NEUTRAL EARTHING RESISTORS ALL ITEMS ITEMS | B1002 | AX | 2 | 2019-07-01 | CON-BMP-VTRA-012612 | 2019-07-01 | FOR BAPCO REVIEW | 2019-07-16 |  |  | CLASS 2
076551C-000R-MR-1641-001 | MATERIAL REQUISITION FOR POWER TRANSFORMERS AND NEUTRAL EARTHING RESISTORS | SCHNEIDER ENERJI | NER4001V1 | D20196532-22 | 021-P-DAT-40048-001 | DATA SHEET FOR NER - NER4001V1 | A4101 | AX | 2 | 2019-07-09 | CON-BMP-VTRA-012772 | 2019-07-09 | FOR BAPCO REVIEW | 2019-07-24 |  |  | CLASS 2
076551C-000R-MR-1641-001 | MATERIAL REQUISITION FOR POWER TRANSFORMERS AND NEUTRAL EARTHING RESISTORS | SCHNEIDER ENERJI | NER4001V1 | D20196532-83 | 000-P-ITP-40015-001 | FABRICATION AND QUALITY CONTROL PLAN FOR POWER TRANSFORMERS AND NEUTRAL EARTHING RESISTORS ALL ITEMS | B1002 | AX | 2 | 2019-07-01 | CON-BMP-VTRA-012612 | 2019-07-01 | FOR BAPCO REVIEW | 2019-07-16 |  |  | CLASS 2
076551C-000R-MR-1641-001 | MATERIAL REQUISITION FOR POWER TRANSFORMERS AND NEUTRAL EARTHING RESISTORS | SCHNEIDER ENERJI | NER4001V1 | NTD.O.B.4A.10T.01R.19.0594-2 | 021-P-GAD-40047-001 | TECHNICAL DRAWING NER4001V1 | A4201 | AX | 1 | 2019-07-09 | CON-BMP-VTRA-012768 | 2019-07-09 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-1641-001 | MATERIAL REQUISITION FOR POWER TRANSFORMERS AND NEUTRAL EARTHING RESISTORS | SCHNEIDER ENERJI | NER4001V2 | D20196532-23 | 021-P-DAT-40049-001 | DATA SHEET FOR NER - NER4001V2 | A4101 | AX | 2 | 2019-07-09 | CON-BMP-VTRA-012772 | 2019-07-09 | FOR BAPCO REVIEW | 2019-07-24 |  |  | CLASS 2
076551C-000R-MR-1641-001 | MATERIAL REQUISITION FOR POWER TRANSFORMERS AND NEUTRAL EARTHING RESISTORS | SCHNEIDER ENERJI | NER4001V2 | NTD.O.B.4A.10T.00R.18.1460-7 | 021-P-GAD-40048-001 | TECHNICAL DRAWING NER4001V2 | A4201 | AX | 1 | 2019-07-09 | CON-BMP-VTRA-012768 | 2019-07-09 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-1641-001 | MATERIAL REQUISITION FOR POWER TRANSFORMERS AND NEUTRAL EARTHING RESISTORS | SCHNEIDER ENERJI | NER4001V3 | D20196532-24 | 018-P-DAT-40067-001 | DATA SHEET FOR NER - NER4001V3 | A4101 | AX | 2 | 2019-07-01 | CON-BMP-VTRA-012611 | 2019-07-01 | FOR BAPCO REVIEW | 2019-07-16 |  |  | CLASS 2
076551C-000R-MR-1641-001 | MATERIAL REQUISITION FOR POWER TRANSFORMERS AND NEUTRAL EARTHING RESISTORS | SCHNEIDER ENERJI | NER4001V3 | NTD.O.B.4A.10T.01R.19.0594 | 018-P-GAD-40057-001 | TECHNICAL DRAWING NER4001V3 | A4201 | AX | 1 | 2019-07-01 | CON-BMP-VTRA-012613 | 2019-07-01 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-1641-001 | MATERIAL REQUISITION FOR POWER TRANSFORMERS AND NEUTRAL EARTHING RESISTORS | SCHNEIDER ENERJI | NER4001V4 | D20196532-25 | 018-P-DAT-40068-001 | DATA SHEET FOR NER - NER4001V4 | A4101 | AX | 2 | 2019-07-01 | CON-BMP-VTRA-012611 | 2019-07-01 | FOR BAPCO REVIEW | 2019-07-16 |  |  | CLASS 2
076551C-000R-MR-1641-001 | MATERIAL REQUISITION FOR POWER TRANSFORMERS AND NEUTRAL EARTHING RESISTORS | SCHNEIDER ENERJI | NER4001V4 | NTD.O.B.4A.10T.00R.18.1460 | 018-P-GAD-40058-001 | TECHNICAL DRAWING NER4001V4 | A4201 | AX | 1 | 2019-07-01 | CON-BMP-VTRA-012613 | 2019-07-01 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-1641-001 | MATERIAL REQUISITION FOR POWER TRANSFORMERS AND NEUTRAL EARTHING RESISTORS | SCHNEIDER ENERJI | NER4002V1 | D20196532-26 | 021-P-DAT-40050-001 | DATA SHEET FOR NER - NER4002V1 | A4101 | AX | 2 | 2019-07-09 | CON-BMP-VTRA-012772 | 2019-07-09 | FOR BAPCO REVIEW | 2019-07-24 |  |  | CLASS 2
076551C-000R-MR-1641-001 | MATERIAL REQUISITION FOR POWER TRANSFORMERS AND NEUTRAL EARTHING RESISTORS | SCHNEIDER ENERJI | NER4002V1 | NTD.O.B.4A.10T.01R.19.0594-3 | 021-P-GAD-40049-001 | TECHNICAL DRAWING NER4002V1 | A4201 | AX | 1 | 2019-07-09 | CON-BMP-VTRA-012768 | 2019-07-09 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-1641-001 | MATERIAL REQUISITION FOR POWER TRANSFORMERS AND NEUTRAL EARTHING RESISTORS | SCHNEIDER ENERJI | NER4002V2 | D20196532-27 | 021-P-DAT-40051-001 | DATA SHEET FOR NER - NER4002V2 | A4101 | AX | 2 | 2019-07-09 | CON-BMP-VTRA-012772 | 2019-07-09 | FOR BAPCO REVIEW | 2019-07-24 |  |  | CLASS 2
076551C-000R-MR-1641-001 | MATERIAL REQUISITION FOR POWER TRANSFORMERS AND NEUTRAL EARTHING RESISTORS | SCHNEIDER ENERJI | NER4002V2 | NTD.O.B.4A.10T.00R.18.1460-8 | 021-P-GAD-40050-001 | TECHNICAL DRAWING NER4002V2 | A4201 | AX | 1 | 2019-07-09 | CON-BMP-VTRA-012768 | 2019-07-09 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-1641-001 | MATERIAL REQUISITION FOR POWER TRANSFORMERS AND NEUTRAL EARTHING RESISTORS | SCHNEIDER ENERJI | NER4002V3 | D20196532-28 | 018-P-DAT-40069-001 | DATA SHEET FOR NER - NER4002V3 | A4101 | AX | 2 | 2019-07-01 | CON-BMP-VTRA-012611 | 2019-07-01 | FOR BAPCO REVIEW | 2019-07-16 |  |  | CLASS 2
076551C-000R-MR-1641-001 | MATERIAL REQUISITION FOR POWER TRANSFORMERS AND NEUTRAL EARTHING RESISTORS | SCHNEIDER ENERJI | NER4002V3 | NTD.O.B.4A.10T.01R.19.0594-1 | 018-P-GAD-40059-001 | TECHNICAL DRAWING NER4002V3 | A4201 | AX | 1 | 2019-07-01 | CON-BMP-VTRA-012613 | 2019-07-01 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-1641-001 | MATERIAL REQUISITION FOR POWER TRANSFORMERS AND NEUTRAL EARTHING RESISTORS | SCHNEIDER ENERJI | NER4002V4 | D20196532-29 | 018-P-DAT-40070-001 | DATA SHEET FOR NER - NER4002V4 | A4101 | AX | 2 | 2019-07-01 | CON-BMP-VTRA-012611 | 2019-07-01 | FOR BAPCO REVIEW | 2019-07-16 |  |  | CLASS 2
076551C-000R-MR-1641-001 | MATERIAL REQUISITION FOR POWER TRANSFORMERS AND NEUTRAL EARTHING RESISTORS | SCHNEIDER ENERJI | NER4002V4 | NTD.O.B.4A.10T.00R.18.1460-1 | 018-P-GAD-40060-001 | TECHNICAL DRAWING NER4002V4 | A4201 | AX | 1 | 2019-07-01 | CON-BMP-VTRA-012613 | 2019-07-01 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-1641-001 | MATERIAL REQUISITION FOR POWER TRANSFORMERS AND NEUTRAL EARTHING RESISTORS | SCHNEIDER ENERJI | NER4003V1 | D20196532-30 | 934-P-DAT-40037-001 | DATA SHEET FOR NER - NER4003V1 | A4101 | AX | 2 | 2019-07-09 | CON-BMP-VTRA-012775 | 2019-07-09 | FOR BAPCO REVIEW | 2019-07-24 |  |  | CLASS 2
076551C-000R-MR-1641-001 | MATERIAL REQUISITION FOR POWER TRANSFORMERS AND NEUTRAL EARTHING RESISTORS | SCHNEIDER ENERJI | NER4003V1 | NTD.O.B.4A.10T.00R.18.1460-9 | 934-P-GAD-40437-001 | TECHNICAL DRAWING NER4003V1 | A4201 | AX | 1 | 2019-07-09 | CON-BMP-VTRA-012771 | 2019-07-09 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-1641-001 | MATERIAL REQUISITION FOR POWER TRANSFORMERS AND NEUTRAL EARTHING RESISTORS | SCHNEIDER ENERJI | NER4004V1 | D20196532-17 | 934-P-DAT-40036-001 | DATA SHEET FOR NER - NER4004V1 | A4101 | AX | 2 | 2019-07-09 | CON-BMP-VTRA-012775 | 2019-07-09 | FOR BAPCO REVIEW | 2019-07-24 |  |  | CLASS 2
076551C-000R-MR-1641-001 | MATERIAL REQUISITION FOR POWER TRANSFORMERS AND NEUTRAL EARTHING RESISTORS | SCHNEIDER ENERJI | NER4401V1 | D20196532-18 | 056-P-DAT-40036-001 | DATA SHEET FOR NER - NER4401V1 | A4101 | AX | 2 | 2019-07-09 | CON-BMP-VTRA-012774 | 2019-07-09 | FOR BAPCO REVIEW | 2019-07-24 |  |  | CLASS 2
076551C-000R-MR-1641-001 | MATERIAL REQUISITION FOR POWER TRANSFORMERS AND NEUTRAL EARTHING RESISTORS | SCHNEIDER ENERJI | NER4401V1 | NTD.O.B.4A.10T.00R.18.1460-3 | 056-P-GAD-40435-001 | TECHNICAL DRAWING NER4401V1 | A4201 | AX | 1 | 2019-07-09 | CON-BMP-VTRA-012770 | 2019-07-09 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-1641-001 | MATERIAL REQUISITION FOR POWER TRANSFORMERS AND NEUTRAL EARTHING RESISTORS | SCHNEIDER ENERJI | NER4402V1 | D20196532-19 | 056-P-DAT-40037-001 | DATA SHEET FOR NER - NER4402V1 | A4101 | AX | 2 | 2019-07-09 | CON-BMP-VTRA-012774 | 2019-07-09 | FOR BAPCO REVIEW | 2019-07-24 |  |  | CLASS 2
076551C-000R-MR-1641-001 | MATERIAL REQUISITION FOR POWER TRANSFORMERS AND NEUTRAL EARTHING RESISTORS | SCHNEIDER ENERJI | NER4402V1 | NTD.O.B.4A.10T.00R.18.1460-4 | 056-P-GAD-40436-001 | TECHNICAL DRAWING NER4402V1 | A4201 | AX | 1 | 2019-07-09 | CON-BMP-VTRA-012770 | 2019-07-09 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-1641-001 | MATERIAL REQUISITION FOR POWER TRANSFORMERS AND NEUTRAL EARTHING RESISTORS | SCHNEIDER ENERJI | NER4501V1 | D20196532-20 | 051-P-DAT-40042-001 | DATA SHEET FOR NER - NER4501V1 | A4101 | AX | 2 | 2019-07-09 | CON-BMP-VTRA-012773 | 2019-07-09 | FOR BAPCO REVIEW | 2019-07-24 |  |  | CLASS 2
076551C-000R-MR-1641-001 | MATERIAL REQUISITION FOR POWER TRANSFORMERS AND NEUTRAL EARTHING RESISTORS | SCHNEIDER ENERJI | NER4501V1 | NTD.O.B.4A.10T.00R.18.1460-5 | 051-P-GAD-40442-001 | TECHNICAL DRAWING NER4501V1 | A4201 | AX | 1 | 2019-07-09 | CON-BMP-VTRA-012769 | 2019-07-09 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-1641-001 | MATERIAL REQUISITION FOR POWER TRANSFORMERS AND NEUTRAL EARTHING RESISTORS | SCHNEIDER ENERJI | NER4502V1 | D20196532-21 | 051-P-DAT-40043-001 | DATA SHEET FOR NER - NER4502V1 | A4101 | AX | 2 | 2019-07-09 | CON-BMP-VTRA-012773 | 2019-07-09 | FOR BAPCO REVIEW | 2019-07-24 |  |  | CLASS 2
076551C-000R-MR-1641-001 | MATERIAL REQUISITION FOR POWER TRANSFORMERS AND NEUTRAL EARTHING RESISTORS | SCHNEIDER ENERJI | NER4502V1 | NTD.O.B.4A.10T.00R.18.1460-6 | 051-P-GAD-40443-001 | TECHNICAL DRAWING NER4502V1 | A4201 | AX | 1 | 2019-07-09 | CON-BMP-VTRA-012769 | 2019-07-09 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-1641-001 | MATERIAL REQUISITION FOR POWER TRANSFORMERS AND NEUTRAL EARTHING RESISTORS | SCHNEIDER ENERJI | TR4001J2 | BUS100D282981 | 021-P-GAD-40065-001 | TRANSFORMER / BUCDUCT FLANGE DRAWING FOR 10/12.5 MVA - TR4001J2 | A4218 | AX | 2 | 2019-06-06 | CON-BMP-VTRA-012046 | 2019-06-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-1641-001 | MATERIAL REQUISITION FOR POWER TRANSFORMERS AND NEUTRAL EARTHING RESISTORS | SCHNEIDER ENERJI | TR4001J2 | D20196532-07 | 021-P-DAT-40042-001 | DATA SHEET FOR 10/12.5 MVA - TR4001J2 | A4101 | AX | 2 | 2019-07-01 | CON-BMP-VTRA-012610 | 2019-07-01 | FOR BAPCO REVIEW | 2019-07-16 |  |  | CLASS 2
076551C-000R-MR-1641-001 | MATERIAL REQUISITION FOR POWER TRANSFORMERS AND NEUTRAL EARTHING RESISTORS | SCHNEIDER ENERJI | TR4001J2 | DIM100D282981 | 021-P-GAD-40041-001 | OUTLINE DRAWING FOR 10/12.5 MVA - TR4001J2 | A4201 | AX | 2 | 2019-06-06 | CON-BMP-VTRA-012063 | 2019-06-06 | FOR BAPCO REVIEW | 2019-06-20 | 2019-06-18 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000997 | CLASS 2
076551C-000R-MR-1641-001 | MATERIAL REQUISITION FOR POWER TRANSFORMERS AND NEUTRAL EARTHING RESISTORS | SCHNEIDER ENERJI | TR4001J2 | FNP100D282981 | 021-P-GAD-40053-001 | FOUNDATION DRAWING FOR 10/12.5MVA - TR4001J2 | A2011 | AX | 2 | 2019-06-06 | CON-BMP-VTRA-012058 | 2019-06-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-1641-001 | MATERIAL REQUISITION FOR POWER TRANSFORMERS AND NEUTRAL EARTHING RESISTORS | SCHNEIDER ENERJI | TR4001J2 | HVC100D282980 | 051-P-GAD-40469-001 | HV AND NEUTRAL TERMINAL BOX DETAIL DWG WITH TERMINATION DETAILS FOR 10/12.5 MVA - TR4502K1 | A4206 | AX | 2 | 2019-06-06 | CON-BMP-VTRA-012055 | 2019-06-06 | FOR BAPCO REVIEW | 2019-06-20 | 2019-06-22 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001012 | CLASS 2
076551C-000R-MR-1641-001 | MATERIAL REQUISITION FOR POWER TRANSFORMERS AND NEUTRAL EARTHING RESISTORS | SCHNEIDER ENERJI | TR4001J3 | D20196532-01 | 018-P-DAT-40063-001 | DATA SHEET FOR 40/50 MVATR4001J3 | A4101 | AX | 2 | 2019-07-01 | CON-BMP-VTRA-012611 | 2019-07-01 | FOR BAPCO REVIEW | 2019-07-16 |  |  | CLASS 2
076551C-000R-MR-1641-001 | MATERIAL REQUISITION FOR POWER TRANSFORMERS AND NEUTRAL EARTHING RESISTORS | SCHNEIDER ENERJI | TR4001J3 | DIM100D282985 | 018-P-GAD-40053-001 | OUTLINE DRAWING FOR 40/50 MVA-TR4001J3 | A4201 | AX | 2 | 2019-06-06 | CON-BMP-VTRA-012063 | 2019-06-06 | FOR BAPCO REVIEW | 2019-06-20 | 2019-06-18 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000997 | CLASS 2
076551C-000R-MR-1641-001 | MATERIAL REQUISITION FOR POWER TRANSFORMERS AND NEUTRAL EARTHING RESISTORS | SCHNEIDER ENERJI | TR4001J3 | FNP100D282985 | 018-P-GAD-40067-001 | FOUNDATION DRAWING FOR 40/50 MVA- TR4001J3 | A2011 | AX | 2 | 2019-06-06 | CON-BMP-VTRA-012058 | 2019-06-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-1641-001 | MATERIAL REQUISITION FOR POWER TRANSFORMERS AND NEUTRAL EARTHING RESISTORS | SCHNEIDER ENERJI | TR4001J3 | HVC100D282985 | 018-P-GAD-40100-001 | HV AND NEUTRAL TERMINAL BOX DETAIL DWG WITH TERMINATION DETAILS FOR 40/50 MVA- TR4001J3 | A4206 | AX | 2 | 2019-06-06 | CON-BMP-VTRA-012052 | 2019-06-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-1641-001 | MATERIAL REQUISITION FOR POWER TRANSFORMERS AND NEUTRAL EARTHING RESISTORS | SCHNEIDER ENERJI | TR4001J4 | BUS100D282983 | 018-P-GAD-40092-001 | TRANSFORMER / BUCDUCT FLANGE DRAWING FOR 20/25 MVA - TR4001J4 | A4218 | AX | 2 | 2019-06-06 | CON-BMP-VTRA-012046 | 2019-06-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-1641-001 | MATERIAL REQUISITION FOR POWER TRANSFORMERS AND NEUTRAL EARTHING RESISTORS | SCHNEIDER ENERJI | TR4001J4 | D20196532-05 | 018-P-DAT-40065-001 | DATA SHEET FOR 20/25 MVA - TR4001J4 | A4101 | AX | 2 | 2019-07-01 | CON-BMP-VTRA-012611 | 2019-07-01 | FOR BAPCO REVIEW | 2019-07-16 |  |  | CLASS 2
076551C-000R-MR-1641-001 | MATERIAL REQUISITION FOR POWER TRANSFORMERS AND NEUTRAL EARTHING RESISTORS | SCHNEIDER ENERJI | TR4001J4 | DIM101D282983 | 018-P-GAD-40055-001 | OUTLINE DRAWING FOR 20/25 MVA - TR4001J4 | A4201 | AX | 2 | 2019-06-06 | CON-BMP-VTRA-012063 | 2019-06-06 | FOR BAPCO REVIEW | 2019-06-20 | 2019-06-18 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000997 | CLASS 2
076551C-000R-MR-1641-001 | MATERIAL REQUISITION FOR POWER TRANSFORMERS AND NEUTRAL EARTHING RESISTORS | SCHNEIDER ENERJI | TR4001J4 | FNP100D282983 | 018-P-GAD-40069-001 | FOUNDATION PLAN DRAWING FOR 20/25 MVA - TR4001J4 | A2011 | AX | 2 | 2019-06-06 | CON-BMP-VTRA-012058 | 2019-06-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-1641-001 | MATERIAL REQUISITION FOR POWER TRANSFORMERS AND NEUTRAL EARTHING RESISTORS | SCHNEIDER ENERJI | TR4001J4 | HVC100D282983 | 018-P-GAD-40102-001 | HV AND NEUTRAL TERMINAL BOX DETAIL DWG WITH TERMINATION DETAILSFOR 20/25 MVA - TR4001J4 | A4206 | AX | 2 | 2019-06-06 | CON-BMP-VTRA-012055 | 2019-06-06 | FOR BAPCO REVIEW | 2019-06-20 | 2019-06-22 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001012 | CLASS 2
076551C-000R-MR-1641-001 | MATERIAL REQUISITION FOR POWER TRANSFORMERS AND NEUTRAL EARTHING RESISTORS | SCHNEIDER ENERJI | TR4002J2 | BUS100D282982 | 021-P-GAD-40066-001 | TRANSFORMER / BUCDUCT FLANGE DRAWING FOR 10/12.5 MVA - TR4002J2 | A4218 | AX | 2 | 2019-06-06 | CON-BMP-VTRA-012046 | 2019-06-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-1641-001 | MATERIAL REQUISITION FOR POWER TRANSFORMERS AND NEUTRAL EARTHING RESISTORS | SCHNEIDER ENERJI | TR4002J2 | D20196532-08 | 021-P-DAT-40043-001 | DATA SHEET FOR 10/12.5 MVA - TR4002J2 | A4101 | AX | 2 | 2019-07-01 | CON-BMP-VTRA-012610 | 2019-07-01 | FOR BAPCO REVIEW | 2019-07-16 |  |  | CLASS 2
076551C-000R-MR-1641-001 | MATERIAL REQUISITION FOR POWER TRANSFORMERS AND NEUTRAL EARTHING RESISTORS | SCHNEIDER ENERJI | TR4002J2 | DIM100D282982 | 021-P-GAD-40042-001 | OUTLINE DRAWING FOR 10/12.5 MVA - TR4002J2 | A4201 | AX | 2 | 2019-06-06 | CON-BMP-VTRA-012063 | 2019-06-06 | FOR BAPCO REVIEW | 2019-06-20 | 2019-06-18 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000997 | CLASS 2
076551C-000R-MR-1641-001 | MATERIAL REQUISITION FOR POWER TRANSFORMERS AND NEUTRAL EARTHING RESISTORS | SCHNEIDER ENERJI | TR4002J2 | FNP100D282982 | 021-P-GAD-40054-001 | FOUNDATION DRAWING FOR 10/12.5MVA - TR4002J2 | A2011 | AX | 2 | 2019-06-06 | CON-BMP-VTRA-012058 | 2019-06-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-1641-001 | MATERIAL REQUISITION FOR POWER TRANSFORMERS AND NEUTRAL EARTHING RESISTORS | SCHNEIDER ENERJI | TR4002J2 | HVC100D282981 | 021-P-GAD-40073-001 | HV CABLE BOX GEN. ARRANGEMENT DRAWING TR4001J2 | A4206 | AX | 2 | 2019-06-06 | CON-BMP-VTRA-012055 | 2019-06-06 | FOR BAPCO REVIEW | 2019-06-20 | 2019-06-22 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001012 | CLASS 2
076551C-000R-MR-1641-001 | MATERIAL REQUISITION FOR POWER TRANSFORMERS AND NEUTRAL EARTHING RESISTORS | SCHNEIDER ENERJI | TR4002J2 | HVC100D282982 | 021-P-GAD-40074-001 | HV AND NEUTRAL TERMINAL BOX DETAIL DWG WITH TERMINATION DETAILS 10/12.5 MVA - TR4002J2 | A4206 | AX | 2 | 2019-06-06 | CON-BMP-VTRA-012055 | 2019-06-06 | FOR BAPCO REVIEW | 2019-06-20 | 2019-06-22 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001012 | CLASS 2
076551C-000R-MR-1641-001 | MATERIAL REQUISITION FOR POWER TRANSFORMERS AND NEUTRAL EARTHING RESISTORS | SCHNEIDER ENERJI | TR4002J3 | BUS100D282986 | 018-P-GAD-40091-001 | TRANSFORMER / BUCDUCT FLANGE DRAWING FOR 40/50 MVA - TR4002J3 | A4218 | AX | 2 | 2019-06-06 | CON-BMP-VTRA-012046 | 2019-06-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-1641-001 | MATERIAL REQUISITION FOR POWER TRANSFORMERS AND NEUTRAL EARTHING RESISTORS | SCHNEIDER ENERJI | TR4002J3 | D20196532-02 | 018-P-DAT-40064-001 | DATA SHEET FOR 40/50 MVATR4002J3 | A4101 | AX | 2 | 2019-07-01 | CON-BMP-VTRA-012611 | 2019-07-01 | FOR BAPCO REVIEW | 2019-07-16 |  |  | CLASS 2
076551C-000R-MR-1641-001 | MATERIAL REQUISITION FOR POWER TRANSFORMERS AND NEUTRAL EARTHING RESISTORS | SCHNEIDER ENERJI | TR4002J3 | DIM100D282986 | 018-P-GAD-40054-001 | OUTLINE DRAWING FOR 40/50 MVA - TR4002J3 | A4201 | AX | 2 | 2019-06-06 | CON-BMP-VTRA-012063 | 2019-06-06 | FOR BAPCO REVIEW | 2019-06-20 | 2019-06-18 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000997 | CLASS 2
076551C-000R-MR-1641-001 | MATERIAL REQUISITION FOR POWER TRANSFORMERS AND NEUTRAL EARTHING RESISTORS | SCHNEIDER ENERJI | TR4002J3 | FNP100D282986 | 018-P-GAD-40068-001 | FOUNDATION DRAWING FOR 40/50 MVA - TR4002J3 | A2011 | AX | 2 | 2019-06-06 | CON-BMP-VTRA-012058 | 2019-06-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-1641-001 | MATERIAL REQUISITION FOR POWER TRANSFORMERS AND NEUTRAL EARTHING RESISTORS | SCHNEIDER ENERJI | TR4002J3 | HVC100D282986 | 018-P-GAD-40101-001 | HV AND NEUTRAL TERMINAL BOX DETAIL DWG WITH TERMINATION DETAILS FOR 40/50 MVA- TR4002J3 | A4206 | AX | 2 | 2019-06-06 | CON-BMP-VTRA-012055 | 2019-06-06 | FOR BAPCO REVIEW | 2019-06-20 | 2019-06-22 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001012 | CLASS 2
076551C-000R-MR-1641-001 | MATERIAL REQUISITION FOR POWER TRANSFORMERS AND NEUTRAL EARTHING RESISTORS | SCHNEIDER ENERJI | TR4002J4 | BUS100D282984 | 018-P-GAD-40093-001 | TRANSFORMER / BUCDUCT FLANGE DRAWING FOR 20/25 MVA - TR4002J4 | A4218 | AX | 2 | 2019-06-06 | CON-BMP-VTRA-012046 | 2019-06-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-1641-001 | MATERIAL REQUISITION FOR POWER TRANSFORMERS AND NEUTRAL EARTHING RESISTORS | SCHNEIDER ENERJI | TR4002J4 | D20196532-06 | 018-P-DAT-40066-001 | DATA SHEET FOR 20/25 MVA - TR4002J4 | A4101 | AX | 2 | 2019-07-01 | CON-BMP-VTRA-012611 | 2019-07-01 | FOR BAPCO REVIEW | 2019-07-16 |  |  | CLASS 2
076551C-000R-MR-1641-001 | MATERIAL REQUISITION FOR POWER TRANSFORMERS AND NEUTRAL EARTHING RESISTORS | SCHNEIDER ENERJI | TR4002J4 | DIM101D282984 | 018-P-GAD-40056-001 | OUTLINE DRAWING FOR 20/25 MVA - TR4002J4 | A4201 | AX | 2 | 2019-06-06 | CON-BMP-VTRA-012063 | 2019-06-06 | FOR BAPCO REVIEW | 2019-06-20 | 2019-06-18 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000997 | CLASS 2
076551C-000R-MR-1641-001 | MATERIAL REQUISITION FOR POWER TRANSFORMERS AND NEUTRAL EARTHING RESISTORS | SCHNEIDER ENERJI | TR4002J4 | FNP100D282984 | 018-P-GAD-40070-001 | FOUNDATION PLAN DRAWING FOR 20/25 MVA - TR4002J4 | A2011 | AX | 2 | 2019-06-06 | CON-BMP-VTRA-012058 | 2019-06-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-1641-001 | MATERIAL REQUISITION FOR POWER TRANSFORMERS AND NEUTRAL EARTHING RESISTORS | SCHNEIDER ENERJI | TR4002J4 | HVC100D282984 | 018-P-GAD-40103-001 | HV AND NEUTRAL TERMINAL BOX DETAIL DWG WITH TERMINATION DETAILS FOR 20/25 MVA - TR4002J4 | A4206 | AX | 2 | 2019-06-06 | CON-BMP-VTRA-012055 | 2019-06-06 | FOR BAPCO REVIEW | 2019-06-20 | 2019-06-22 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001012 | CLASS 2
076551C-000R-MR-1641-001 | MATERIAL REQUISITION FOR POWER TRANSFORMERS AND NEUTRAL EARTHING RESISTORS | SCHNEIDER ENERJI | TR4003J1 | BUS100D282985 | 018-P-GAD-40090-001 | TRANSFORMER / BUCDUCT FLANGE DRAWING FOR 40/50 MVA- TR4001J3 | A4218 | AX | 2 | 2019-06-06 | CON-BMP-VTRA-012046 | 2019-06-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-1641-001 | MATERIAL REQUISITION FOR POWER TRANSFORMERS AND NEUTRAL EARTHING RESISTORS | SCHNEIDER ENERJI | TR4203L1 | D20196532-11 | 021-P-DAT-40044-001 | DATA SHEET FOR 2 MVA - TR4203L1 | A4101 | AX | 2 | 2019-07-01 | CON-BMP-VTRA-012610 | 2019-07-01 | FOR BAPCO REVIEW | 2019-07-16 |  |  | CLASS 2
076551C-000R-MR-1641-001 | MATERIAL REQUISITION FOR POWER TRANSFORMERS AND NEUTRAL EARTHING RESISTORS | SCHNEIDER ENERJI | TR4203L1 | DIM100D228554 | 021-P-GAD-40043-001 | OUTLINE DRAWING FOR 2 MVA - TR4203L1 | A4201 | AX | 2 | 2019-06-06 | CON-BMP-VTRA-012063 | 2019-06-06 | FOR BAPCO REVIEW | 2019-06-20 | 2019-06-18 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000997 | CLASS 2
076551C-000R-MR-1641-001 | MATERIAL REQUISITION FOR POWER TRANSFORMERS AND NEUTRAL EARTHING RESISTORS | SCHNEIDER ENERJI | TR4203L1 | FNP100D228554 | 021-P-GAD-40055-001 | FOUNDATION DRAWING FOR 2 MVA -TR4203L1 | A2011 | AX | 2 | 2019-06-06 | CON-BMP-VTRA-012058 | 2019-06-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-1641-001 | MATERIAL REQUISITION FOR POWER TRANSFORMERS AND NEUTRAL EARTHING RESISTORS | SCHNEIDER ENERJI | TR4203L2 | D20196532-12 | 021-P-DAT-40045-001 | DATA SHEET FOR 2 MVA - TR4203L2 | A4101 | AX | 2 | 2019-07-01 | CON-BMP-VTRA-012610 | 2019-07-01 | FOR BAPCO REVIEW | 2019-07-16 |  |  | CLASS 2
076551C-000R-MR-1641-001 | MATERIAL REQUISITION FOR POWER TRANSFORMERS AND NEUTRAL EARTHING RESISTORS | SCHNEIDER ENERJI | TR4203L2 | DIM100D228555 | 021-P-GAD-40044-001 | OUTLINE DRAWING FOR 2 MVA - TR4203L2 | A4201 | AX | 2 | 2019-06-06 | CON-BMP-VTRA-012063 | 2019-06-06 | FOR BAPCO REVIEW | 2019-06-20 | 2019-06-18 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000997 | CLASS 2
076551C-000R-MR-1641-001 | MATERIAL REQUISITION FOR POWER TRANSFORMERS AND NEUTRAL EARTHING RESISTORS | SCHNEIDER ENERJI | TR4203L2 | FNP100D228555 | 021-P-GAD-40056-001 | FOUNDATION DRAWING FOR 2 MVA -TR4203L2 | A2011 | AX | 2 | 2019-06-06 | CON-BMP-VTRA-012058 | 2019-06-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-1641-001 | MATERIAL REQUISITION FOR POWER TRANSFORMERS AND NEUTRAL EARTHING RESISTORS | SCHNEIDER ENERJI | TR4204L1 | D20196532-13 | 021-P-DAT-40046-001 | DATA SHEET FOR 2 MVA - TR4204L1 | A4101 | AX | 2 | 2019-07-01 | CON-BMP-VTRA-012610 | 2019-07-01 | FOR BAPCO REVIEW | 2019-07-16 |  |  | CLASS 2
076551C-000R-MR-1641-001 | MATERIAL REQUISITION FOR POWER TRANSFORMERS AND NEUTRAL EARTHING RESISTORS | SCHNEIDER ENERJI | TR4204L1 | DIM100D228556 | 021-P-GAD-40045-001 | OUTLINE DRAWING FOR 2 MVA - TR4204L1 | A4201 | AX | 2 | 2019-06-06 | CON-BMP-VTRA-012063 | 2019-06-06 | FOR BAPCO REVIEW | 2019-06-20 | 2019-06-18 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000997 | CLASS 2
076551C-000R-MR-1641-001 | MATERIAL REQUISITION FOR POWER TRANSFORMERS AND NEUTRAL EARTHING RESISTORS | SCHNEIDER ENERJI | TR4204L1 | FNP100D228556 | 021-P-GAD-40057-001 | FOUNDATION DRAWING FOR 2 MVA -TR4204L1 | A2011 | AX | 2 | 2019-06-06 | CON-BMP-VTRA-012058 | 2019-06-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-1641-001 | MATERIAL REQUISITION FOR POWER TRANSFORMERS AND NEUTRAL EARTHING RESISTORS | SCHNEIDER ENERJI | TR4204L2 | D20196532-14 | 021-P-DAT-40047-001 | DATA SHEET FOR 2 MVA - TR4204L2 | A4101 | AX | 2 | 2019-07-01 | CON-BMP-VTRA-012610 | 2019-07-01 | FOR BAPCO REVIEW | 2019-07-16 |  |  | CLASS 2
076551C-000R-MR-1641-001 | MATERIAL REQUISITION FOR POWER TRANSFORMERS AND NEUTRAL EARTHING RESISTORS | SCHNEIDER ENERJI | TR4204L2 | DIM100D228557 | 021-P-GAD-40046-001 | OUTLINE DRAWING FOR 2 MVA - TR4204L2 | A4201 | AX | 2 | 2019-06-06 | CON-BMP-VTRA-012063 | 2019-06-06 | FOR BAPCO REVIEW | 2019-06-20 | 2019-06-18 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000997 | CLASS 2
076551C-000R-MR-1641-001 | MATERIAL REQUISITION FOR POWER TRANSFORMERS AND NEUTRAL EARTHING RESISTORS | SCHNEIDER ENERJI | TR4204L2 | FNP100D228557 | 021-P-GAD-40058-001 | FOUNDATION DRAWING FOR 2 MVA -TR4204L2 | A2011 | AX | 2 | 2019-06-06 | CON-BMP-VTRA-012058 | 2019-06-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-1641-001 | MATERIAL REQUISITION FOR POWER TRANSFORMERS AND NEUTRAL EARTHING RESISTORS | SCHNEIDER ENERJI | TR4401K1 | BUS100D282977 | 056-P-GAD-40443-001 | TRANSFORMER / BUCDUCT FLANGE DRAWING FOR 25/30 MVA - TR4401K1 | A4218 | AX | 2 | 2019-06-06 | CON-BMP-VTRA-012046 | 2019-06-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-1641-001 | MATERIAL REQUISITION FOR POWER TRANSFORMERS AND NEUTRAL EARTHING RESISTORS | SCHNEIDER ENERJI | TR4401K1 | D20196532-03 | 056-P-DAT-40032-001 | DATA SHEET FOR 25/30 MVA - TR4401K1 | A4101 | AX | 2 | 2019-07-01 | CON-BMP-VTRA-012600 | 2019-07-01 | FOR BAPCO REVIEW | 2019-07-15 |  |  | CLASS 2
076551C-000R-MR-1641-001 | MATERIAL REQUISITION FOR POWER TRANSFORMERS AND NEUTRAL EARTHING RESISTORS | SCHNEIDER ENERJI | TR4401K1 | DIM100D282977 | 056-P-GAD-40431-001 | OUTLINE DRAWING FOR 25/30 MVA - TR4401K1 | A4201 | AX | 2 | 2019-06-06 | CON-BMP-VTRA-012063 | 2019-06-06 | FOR BAPCO REVIEW | 2019-06-20 | 2019-06-18 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000997 | CLASS 2
076551C-000R-MR-1641-001 | MATERIAL REQUISITION FOR POWER TRANSFORMERS AND NEUTRAL EARTHING RESISTORS | SCHNEIDER ENERJI | TR4401K1 | FNP100D282977 | 056-P-GAD-40437-001 | FOUNDATION DRAWING FOR 25/30 MVA - TR4401K1 | A2011 | AX | 2 | 2019-06-06 | CON-BMP-VTRA-012058 | 2019-06-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-1641-001 | MATERIAL REQUISITION FOR POWER TRANSFORMERS AND NEUTRAL EARTHING RESISTORS | SCHNEIDER ENERJI | TR4401K1 | HVC100D282977 | 056-P-GAD-40447-001 | HV AND NEUTRAL TERMINAL BOX DETAIL DWG WITH TERMINATION DETAILSFOR 25/30 MVA - TR4401K1 | A4206 | AX | 2 | 2019-06-06 | CON-BMP-VTRA-012055 | 2019-06-06 | FOR BAPCO REVIEW | 2019-06-20 | 2019-06-22 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001012 | CLASS 2
076551C-000R-MR-1641-001 | MATERIAL REQUISITION FOR POWER TRANSFORMERS AND NEUTRAL EARTHING RESISTORS | SCHNEIDER ENERJI | TR4402K1 | BUS100D282978 | 056-P-GAD-40444-001 | TRANSFORMER / BUCDUCT FLANGE DRAWING FOR 25/30 MVA - TR4402K1 | A4218 | AX | 2 | 2019-06-06 | CON-BMP-VTRA-012046 | 2019-06-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-1641-001 | MATERIAL REQUISITION FOR POWER TRANSFORMERS AND NEUTRAL EARTHING RESISTORS | SCHNEIDER ENERJI | TR4402K1 | D20196532-04 | 056-P-DAT-40033-001 | DATA SHEET FOR 25/30 MVA - TR4402K1 | A4101 | AX | 2 | 2019-07-01 | CON-BMP-VTRA-012600 | 2019-07-01 | FOR BAPCO REVIEW | 2019-07-15 |  |  | CLASS 2
076551C-000R-MR-1641-001 | MATERIAL REQUISITION FOR POWER TRANSFORMERS AND NEUTRAL EARTHING RESISTORS | SCHNEIDER ENERJI | TR4402K1 | DIM100D282978 | 056-P-GAD-40432-001 | OUTLINE DRAWING FOR 25/30 MVA - TR4402K1 | A4201 | AX | 2 | 2019-06-06 | CON-BMP-VTRA-012063 | 2019-06-06 | FOR BAPCO REVIEW | 2019-06-20 | 2019-06-18 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000997 | CLASS 2
076551C-000R-MR-1641-001 | MATERIAL REQUISITION FOR POWER TRANSFORMERS AND NEUTRAL EARTHING RESISTORS | SCHNEIDER ENERJI | TR4402K1 | FNP100D282978 | 056-P-GAD-40438-001 | FOUNDATION DRAWING FOR 25/30 MVA - TR4402K1 | A2011 | AX | 2 | 2019-06-06 | CON-BMP-VTRA-012058 | 2019-06-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-1641-001 | MATERIAL REQUISITION FOR POWER TRANSFORMERS AND NEUTRAL EARTHING RESISTORS | SCHNEIDER ENERJI | TR4402K1 | HVC100D282978 | 056-P-GAD-40448-001 | HV AND NEUTRAL TERMINAL BOX DETAIL DWG WITH TERMINATION DETAILS FOR 25/30 MVA - TR4402K1 | A4206 | AX | 2 | 2019-06-06 | CON-BMP-VTRA-012055 | 2019-06-06 | FOR BAPCO REVIEW | 2019-06-20 | 2019-06-22 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001012 | CLASS 2
076551C-000R-MR-1641-001 | MATERIAL REQUISITION FOR POWER TRANSFORMERS AND NEUTRAL EARTHING RESISTORS | SCHNEIDER ENERJI | TR4403L1 | D20196532-15 | 056-P-DAT-40034-001 | DATA SHEET FOR 2 MVA - TR4403L1 | A4101 | AX | 2 | 2019-07-01 | CON-BMP-VTRA-012600 | 2019-07-01 | FOR BAPCO REVIEW | 2019-07-15 |  |  | CLASS 2
076551C-000R-MR-1641-001 | MATERIAL REQUISITION FOR POWER TRANSFORMERS AND NEUTRAL EARTHING RESISTORS | SCHNEIDER ENERJI | TR4403L1 | DIM100D228558 | 056-P-GAD-40433-001 | OUTLINE DRAWING FOR 2 MVA - TR4403L1 | A4201 | AX | 2 | 2019-06-06 | CON-BMP-VTRA-012063 | 2019-06-06 | FOR BAPCO REVIEW | 2019-06-20 | 2019-06-18 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000997 | CLASS 2
076551C-000R-MR-1641-001 | MATERIAL REQUISITION FOR POWER TRANSFORMERS AND NEUTRAL EARTHING RESISTORS | SCHNEIDER ENERJI | TR4403L1 | FNP100D228558 | 056-P-GAD-40439-001 | FOUNDATION DRAWING FOR 2 MVA -TR4403L1 | A2011 | AX | 2 | 2019-06-06 | CON-BMP-VTRA-012058 | 2019-06-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-1641-001 | MATERIAL REQUISITION FOR POWER TRANSFORMERS AND NEUTRAL EARTHING RESISTORS | SCHNEIDER ENERJI | TR4404L1 | D20196532-16 | 056-P-DAT-40035-001 | DATA SHEET FOR 2 MVA - TR4404L1 | A4101 | AX | 2 | 2019-07-01 | CON-BMP-VTRA-012600 | 2019-07-01 | FOR BAPCO REVIEW | 2019-07-15 |  |  | CLASS 2
076551C-000R-MR-1641-001 | MATERIAL REQUISITION FOR POWER TRANSFORMERS AND NEUTRAL EARTHING RESISTORS | SCHNEIDER ENERJI | TR4404L1 | DIM100D228559 | 056-P-GAD-40434-001 | OUTLINE DRAWING FOR 2 MVA - TR4404L1 | A4201 | AX | 2 | 2019-06-06 | CON-BMP-VTRA-012063 | 2019-06-06 | FOR BAPCO REVIEW | 2019-06-20 | 2019-06-18 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000997 | CLASS 2
076551C-000R-MR-1641-001 | MATERIAL REQUISITION FOR POWER TRANSFORMERS AND NEUTRAL EARTHING RESISTORS | SCHNEIDER ENERJI | TR4404L1 | FNP100D228559 | 056-P-GAD-40440-001 | FOUNDATION DRAWING FOR 2 MVA -TR4404L1 | A2011 | AX | 2 | 2019-06-06 | CON-BMP-VTRA-012058 | 2019-06-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-1641-001 | MATERIAL REQUISITION FOR POWER TRANSFORMERS AND NEUTRAL EARTHING RESISTORS | SCHNEIDER ENERJI | TR4501K1 | BUS100D282979 | 051-P-GAD-40460-001 | TRANSFORMER / BUCDUCT FLANGE DRAWING FOR 10/12.5 MVA - TR4501K1 | A4218 | AX | 2 | 2019-06-06 | CON-BMP-VTRA-012046 | 2019-06-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-1641-001 | MATERIAL REQUISITION FOR POWER TRANSFORMERS AND NEUTRAL EARTHING RESISTORS | SCHNEIDER ENERJI | TR4501K1 | D20196532-09 | 051-P-DAT-40040-001 | DATA SHEET FOR 10/12.5 MVA - TR4501K1 | A4101 | AX | 2 | 2019-07-01 | CON-BMP-VTRA-012609 | 2019-07-01 | FOR BAPCO REVIEW | 2019-07-16 |  |  | CLASS 2
076551C-000R-MR-1641-001 | MATERIAL REQUISITION FOR POWER TRANSFORMERS AND NEUTRAL EARTHING RESISTORS | SCHNEIDER ENERJI | TR4501K1 | DIM100D282979 | 051-P-GAD-40440-001 | OUTLINE DRAWING FOR 10/12.5 MVA - TR4501K1 | A4201 | AX | 2 | 2019-06-06 | CON-BMP-VTRA-012063 | 2019-06-06 | FOR BAPCO REVIEW | 2019-06-20 | 2019-06-18 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000997 | CLASS 2
076551C-000R-MR-1641-001 | MATERIAL REQUISITION FOR POWER TRANSFORMERS AND NEUTRAL EARTHING RESISTORS | SCHNEIDER ENERJI | TR4501K1 | FNP100D282979 | 051-P-GAD-40450-001 | FOUNDATION DRAWING FOR 10/12.5MVA - TR4501K1 | A2011 | AX | 2 | 2019-06-06 | CON-BMP-VTRA-012058 | 2019-06-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-1641-001 | MATERIAL REQUISITION FOR POWER TRANSFORMERS AND NEUTRAL EARTHING RESISTORS | SCHNEIDER ENERJI | TR4502K1 | BUS100D282980 | 051-P-GAD-40461-001 | TRANSFORMER / BUCDUCT FLANGE DRAWING FOR 10/12.5 MVA - TR4502K1 | A4218 | AX | 2 | 2019-06-06 | CON-BMP-VTRA-012046 | 2019-06-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-1641-001 | MATERIAL REQUISITION FOR POWER TRANSFORMERS AND NEUTRAL EARTHING RESISTORS | SCHNEIDER ENERJI | TR4502K1 | D20196532-10 | 051-P-DAT-40041-001 | DATA SHEET FOR 10/12.5 MVA - TR4502K1 | A4101 | AX | 2 | 2019-07-01 | CON-BMP-VTRA-012609 | 2019-07-01 | FOR BAPCO REVIEW | 2019-07-16 |  |  | CLASS 2
076551C-000R-MR-1641-001 | MATERIAL REQUISITION FOR POWER TRANSFORMERS AND NEUTRAL EARTHING RESISTORS | SCHNEIDER ENERJI | TR4502K1 | DIM100D282980 | 051-P-GAD-40441-001 | OUTLINE DRAWING FOR 10/12.5 MVA - TR4502K1 | A4201 | AX | 2 | 2019-06-06 | CON-BMP-VTRA-012063 | 2019-06-06 | FOR BAPCO REVIEW | 2019-06-20 | 2019-06-18 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000997 | CLASS 2
076551C-000R-MR-1641-001 | MATERIAL REQUISITION FOR POWER TRANSFORMERS AND NEUTRAL EARTHING RESISTORS | SCHNEIDER ENERJI | TR4502K1 | FNP100D282980 | 051-P-GAD-40451-001 | FOUNDATION DRAWING FOR 10/12.5MVA - TR4502K1 | A2011 | AX | 2 | 2019-06-06 | CON-BMP-VTRA-012058 | 2019-06-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-1641-001 | MATERIAL REQUISITION FOR POWER TRANSFORMERS AND NEUTRAL EARTHING RESISTORS | SCHNEIDER ENERJI | TR4502K1 | HVC100D282979 | 051-P-GAD-40468-001 | HV AND NEUTRAL TERMINAL BOX DETAIL DWG WITH TERMINATION DETAILS 10/12.5 MVA - TR4501K1 | A4206 | AX | 2 | 2019-06-06 | CON-BMP-VTRA-012055 | 2019-06-06 | FOR BAPCO REVIEW | 2019-06-20 | 2019-06-22 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001012 | CLASS 2
076551C-000R-MR-1651-001 | MATERIAL REQUISITION FOR HV GAS INSULATED SWITCHGEARS | SCHNEIDER ELECTRIC S.P.A. | BUS4001J | G 047039 001 | 392-P-SLD-40104-001 | SINGLE LINE DIAGRAM 33KV MAIN SUBSTATION BUS4001J | A4108 | AX | 2 | 2019-05-06 | CON-BMP-VTRA-011432 | 2019-05-06 | FOR BAPCO REVIEW | 2019-05-21 | 2019-05-26 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000768 | CLASS 2
076551C-000R-MR-1651-001 | MATERIAL REQUISITION FOR HV GAS INSULATED SWITCHGEARS | SCHNEIDER ELECTRIC S.P.A. | BUS4001J | G 047039 003 | 392-P-GAD-40401-001 | GENERAL ARRANGEMENT PLANE 33KVMAIN SUBSTATION BUS4001J | A2011 | AX | 2 | 2019-05-06 | CON-BMP-VTRA-011966 | 2019-06-04 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-1651-001 | MATERIAL REQUISITION FOR HV GAS INSULATED SWITCHGEARS | SCHNEIDER ELECTRIC S.P.A. | BUS4001J | G 047039 004 | 392-P-GAD-40405-001 | FRONT VIEW 33KV MAIN SUBSTATION BUS4001J FRONT VIEW AND NAME PLATE DRAWING | A4204 | BX | 2 | 2019-07-08 | CON-BMP-VTRA-012742 | 2019-07-08 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-1651-001 | MATERIAL REQUISITION FOR HV GAS INSULATED SWITCHGEARS | SCHNEIDER ELECTRIC S.P.A. | BUS4001J | GHA-1843-06 | 392-P-PQP-40001-001 | FABRICATION AND QUALITY CONTROL PLAN HV GAS INSULATED SWITCHGEARS ALL ITEMS | B1002 | BX | 2 | 2019-07-05 | CON-BMP-VTRA-012686 | 2019-07-05 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-1651-001 | MATERIAL REQUISITION FOR HV GAS INSULATED SWITCHGEARS | SCHNEIDER ELECTRIC S.P.A. | BUS4001J | NHJC261903 | 392-P-INX-40007-001 | LIST OF VENDOR'S DOCUMENTS AND DRAWINGS MATERIAL REQUISITION FOR HV GIS SWITCHGEARS ALL ITEMS | A0001 | BX | 2 | 2019-06-10 | CON-BMP-VTRA-012121 | 2019-06-10 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-1651-001 | MATERIAL REQUISITION FOR HV GAS INSULATED SWITCHGEARS | SCHNEIDER ELECTRIC S.P.A. | BUS4001J | NHJC261904 | 392-P-TSP-40001-001 | 33KV MAIN SUBSTATION HV GAS INSULATED SWITCHGEAR BUS4001J BUS4002J BUS4003J BUS4004J 33KV PAINTING AND CORROSION SYS | A0106 | AX | 3 | 2019-05-06 | CON-BMP-VTRA-011413 | 2019-05-06 | FOR BAPCO REVIEW | 2019-05-20 | 2019-05-25 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000766 | CLASS 2
076551C-000R-MR-1651-001 | MATERIAL REQUISITION FOR HV GAS INSULATED SWITCHGEARS | SCHNEIDER ELECTRIC S.P.A. | BUS4001J | NHJC261907 | 392-P-S3D-40001-001 | 3D EQUIPMENT MODEL HV GAS INSULATED SWITCHGEARS ALL ITEMS | A2013 | AX | 2 | 2019-07-05 | CON-BMP-VTRA-012687 | 2019-07-05 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-1651-001 | MATERIAL REQUISITION FOR HV GAS INSULATED SWITCHGEARS | SCHNEIDER ELECTRIC S.P.A. | BUS4001J | NHJC261908 | 392-P-TSP-40002-001 | SW CONFIGURATION SPECIFICATION DOCUMENTATION MANUALS HV GAS INSULATED SWITCHGEARS ALL ITEMS | A3503 | AX | 2 | 2019-07-05 | CON-BMP-VTRA-012688 | 2019-07-05 | FOR BAPCO REVIEW | 2019-07-19 |  |  | CLASS 2
076551C-000R-MR-1651-001 | MATERIAL REQUISITION FOR HV GAS INSULATED SWITCHGEARS | SCHNEIDER ELECTRIC S.P.A. | BUS4001J | NHJC261909 | 392-P-DAT-40005-001 | DATA SHEET FOR 33KV HV GAS INSULATED SWITCHGEARS BUS4001J, BUS4002J, BUS4003J, BUS4004J | A4101 | AX | 2 | 2019-05-30 | CON-BMP-VTRA-011859 | 2019-05-30 | FOR BAPCO REVIEW | 2019-06-14 | 2019-06-18 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000995 | CLASS 2
076551C-000R-MR-1651-001 | MATERIAL REQUISITION FOR HV GAS INSULATED SWITCHGEARS | SCHNEIDER ELECTRIC S.P.A. | BUS4001J | NHJC261910 | 392-P-CAL-40005-001 | CTS AND VTS CALCULATION BUS4001J BUS4002J BUS4003J BUS4004J | A4111 | AX | 2 | 2019-05-24 | CON-BMP-VTRA-011779 | 2019-05-24 | FOR BAPCO REVIEW | 2019-06-07 | 2019-06-15 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000922 | CLASS 2
076551C-000R-MR-1651-001 | MATERIAL REQUISITION FOR HV GAS INSULATED SWITCHGEARS | SCHNEIDER ELECTRIC S.P.A. | BUS4001J | NHJC261911 | 392-P-TSP-40003-001 | BULLETINS AND CATALOGUES HV GAS INSULATED SWITCHGEARS ALL ITEMS | A4216 | AX | 4 | 2019-05-30 | CON-BMP-VTRA-011858 | 2019-05-30 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-1651-001 | MATERIAL REQUISITION FOR HV GAS INSULATED SWITCHGEARS | SCHNEIDER ELECTRIC S.P.A. | BUS4001J | NHJC261913 | 392-P-SIN-40001-001 | HV GAS INSULATED SWITCHGEARS RECOMMENDATION FOR STORAGE PRIOR AND AFTER ERECTION ALL ITEMS | A5002 | BX | 2 | 2019-07-05 | CON-BMP-VTRA-012689 | 2019-07-05 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-1651-001 | MATERIAL REQUISITION FOR HV GAS INSULATED SWITCHGEARS | SCHNEIDER ELECTRIC S.P.A. | BUS4001J | NHJC261915 | 392-P-IOM-40001-001 | INSTALLATION START-UP AND COMMISIONING MANUALS HV GAS INSULATED SWITCHGEARS ALL ITEMS | A5015 | AX | 2 | 2019-07-05 | CON-BMP-VTRA-012690 | 2019-07-05 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-1651-001 | MATERIAL REQUISITION FOR HV GAS INSULATED SWITCHGEARS | SCHNEIDER ELECTRIC S.P.A. | BUS4001J | NHJC261916 | 392-P-IOM-40002-001 | OPERATION AND MAINTENANCE MANUALS HV GAS INSULATED SWITCHGEARS ALL ITEMS | A5016 | AX | 2 | 2019-07-05 | CON-BMP-VTRA-012691 | 2019-07-05 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-1651-001 | MATERIAL REQUISITION FOR HV GAS INSULATED SWITCHGEARS | SCHNEIDER ELECTRIC S.P.A. | BUS4001J | NHJC261919 | 392-P-ITP-40001-001 | INSPECTION AND TEST PLAN 33 KV MAIN SUBSTATION HV GAS INSULATED SWITCHGEAR ALL ITEMS | B1002 | AX | 2 | 2019-06-05 | CON-BMP-VTRA-012012 | 2019-06-05 | FOR BAPCO REVIEW | 2019-06-20 | 2019-06-17 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000958 | CLASS 2
076551C-000R-MR-1651-001 | MATERIAL REQUISITION FOR HV GAS INSULATED SWITCHGEARS | SCHNEIDER ELECTRIC S.P.A. | BUS4001J | NHJC261921 | 392-P-PRO-40001-001 | FACTORY ACCEPTANCE TESTS PROCEDURE (FAT) 33 KV MAIN SUBSTATION HV GAS INSULATED SWITCHGEAR ALL ITEMS | B1104 | AX | 2 | 2019-07-05 | CON-BMP-VTRA-012692 | 2019-07-05 | FOR BAPCO REVIEW | 2019-07-22 |  |  | CLASS 2
076551C-000R-MR-1651-001 | MATERIAL REQUISITION FOR HV GAS INSULATED SWITCHGEARS | SCHNEIDER ELECTRIC S.P.A. | BUS4001J | NHJC261924 | 392-P-PQS-40001-001 | 33 KV MAIN SUBSTATION HV GAS INSULATED SWITCHGEAR SUB VENDOR QUALIFICATION 33KV GIS ALL ITEMS | B1401 | AX | 4 | 2019-06-10 | CON-BMP-VTRA-012122 | 2019-06-10 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-1651-001 | MATERIAL REQUISITION FOR HV GAS INSULATED SWITCHGEARS | SCHNEIDER ELECTRIC S.P.A. | BUS4001J | NHJC261925 | 392-P-SCH-40002-001 | HV GAS INSULATED SWITCHGEARS ENGINEERING PROCUREMENT MANUFACTURING AND TEST SCHEDULE ALL ITEMS | C1001 | AX | 4 | 2019-05-06 | CON-BMP-VTRA-011412 | 2019-05-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-1651-001 | MATERIAL REQUISITION FOR HV GAS INSULATED SWITCHGEARS | SCHNEIDER ELECTRIC S.P.A. | BUS4001J | NHJC261926 | 392-P-MRS-40001-001 | HV GAS INSULATED SWITCHGEARS MONTHLY PROGRESS REPORT ALL ITEMS | C1002 | BX | 4 | 2019-06-04 | CON-BMP-VTRA-011964 | 2019-06-04 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-1651-001 | MATERIAL REQUISITION FOR HV GAS INSULATED SWITCHGEARS | SCHNEIDER ELECTRIC S.P.A. | BUS4001J | NHJC261928 | 392-P-BOM-40001-001 | LIST OF MATERIALS HV GAS INSULATED SWITCHGEARS ALL ITEMS | A0002 | AX | 2 | 2019-06-06 | CON-BMP-VTRA-012042 | 2019-06-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-1651-001 | MATERIAL REQUISITION FOR HV GAS INSULATED SWITCHGEARS | SCHNEIDER ELECTRIC S.P.A. | BUS4001J | NHJC261929 | 392-P-DLB-40001-001 | NAME PLATE BUS4001J | A4205 | BX | 2 | 2019-07-05 | CON-BMP-VTRA-012697 | 2019-07-05 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-1651-001 | MATERIAL REQUISITION FOR HV GAS INSULATED SWITCHGEARS | SCHNEIDER ELECTRIC S.P.A. | BUS4001J | NHJC261933 | 392-P-GAD-40413-001 | ASSEMBLY DRAWING SCHEMATIC DIAGRAM EWA DIFFERENTIAL PROTECTIONS CABINETS ALL ITEMS | A4201 | AX | 2 | 2019-07-05 | CON-BMP-VTRA-012694 | 2019-07-05 | FOR BAPCO REVIEW | 2019-07-22 |  |  | CLASS 2
076551C-000R-MR-1651-001 | MATERIAL REQUISITION FOR HV GAS INSULATED SWITCHGEARS | SCHNEIDER ELECTRIC S.P.A. | BUS4001J | NHJC261934 | 392-P-CAL-40006-001 | HEAT DISSIPATION AND POWER SUPPLY CONSUMPTION HV GAS INSULATED SWITCHGEARS ALL ITEMS | A4305 | BX | 2 | 2019-07-05 | CON-BMP-VTRA-012693 | 2019-07-05 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-1651-001 | MATERIAL REQUISITION FOR HV GAS INSULATED SWITCHGEARS | SCHNEIDER ELECTRIC S.P.A. | BUS4001J | R.047039.01.600-3-GHA | 392-P-CWD-40001-001 | INTERCONNECTION DRAWING BUS4001J | A4211 | AX | 2 | 2019-07-05 | CON-BMP-VTRA-012695 | 2019-07-05 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-1651-001 | MATERIAL REQUISITION FOR HV GAS INSULATED SWITCHGEARS | SCHNEIDER ELECTRIC S.P.A. | BUS4001J | R.047039.01.700-3-GHA | 392-P-WRD-40001-001 | SCHEMATIC DIAGRAMS LIST OF MATERIALS AND TERMINAL BLOCKS DRAWING BUS4001J | A4110 | AX | 2 | 2019-07-05 | CON-BMP-VTRA-012696 | 2019-07-05 | FOR BAPCO REVIEW | 2019-07-22 |  |  | CLASS 2
076551C-000R-MR-1651-001 | MATERIAL REQUISITION FOR HV GAS INSULATED SWITCHGEARS | SCHNEIDER ELECTRIC S.P.A. | BUS4002J | G 047039 101 | 392-P-SLD-40105-001 | SINGLE LINE DIAGRAM 33KV MAIN SUBSTATION BUS4002J | A4108 | BX | 2 | 2019-07-08 | CON-BMP-VTRA-012727 | 2019-07-08 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-1651-001 | MATERIAL REQUISITION FOR HV GAS INSULATED SWITCHGEARS | SCHNEIDER ELECTRIC S.P.A. | BUS4002J | G 047039 103 | 392-P-GAD-40402-001 | GENERAL ARRANGEMENT PLANE 33 KV MAIN SUBSTATION BUS4002J | A2011 | AX | 2 | 2019-05-06 | CON-BMP-VTRA-011966 | 2019-06-04 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-1651-001 | MATERIAL REQUISITION FOR HV GAS INSULATED SWITCHGEARS | SCHNEIDER ELECTRIC S.P.A. | BUS4002J | G 047039 104 | 392-P-GAD-40406-001 | FRONT VIEW 33KV MAIN SUBSTATION BUS4002J FRONT VIEW AND NAME PLATE DRAWING | A4204 | BX | 2 | 2019-07-08 | CON-BMP-VTRA-012742 | 2019-07-08 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-1651-001 | MATERIAL REQUISITION FOR HV GAS INSULATED SWITCHGEARS | SCHNEIDER ELECTRIC S.P.A. | BUS4002J | NHJC261930 | 392-P-DLB-40002-001 | NAME PLATE BUS4002J | A4205 | BX | 2 | 2019-07-05 | CON-BMP-VTRA-012697 | 2019-07-05 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-1651-001 | MATERIAL REQUISITION FOR HV GAS INSULATED SWITCHGEARS | SCHNEIDER ELECTRIC S.P.A. | BUS4002J | R.047039.02.600-3-GHA | 392-P-CWD-40002-001 | INTERCONNECTION DRAWING BUS4002J | A4211 | AX | 2 | 2019-07-05 | CON-BMP-VTRA-012695 | 2019-07-05 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-1651-001 | MATERIAL REQUISITION FOR HV GAS INSULATED SWITCHGEARS | SCHNEIDER ELECTRIC S.P.A. | BUS4002J | R.047039.02.700-3.GHA | 392-P-WRD-40002-001 | SCHEMATIC DIAGRAMS LIST OF MATERIALS AND TERMINAL BLOCKS DRAWING BUS4002J | A4110 | AX | 2 | 2019-07-05 | CON-BMP-VTRA-012696 | 2019-07-05 | FOR BAPCO REVIEW | 2019-07-22 |  |  | CLASS 2
076551C-000R-MR-1651-001 | MATERIAL REQUISITION FOR HV GAS INSULATED SWITCHGEARS | SCHNEIDER ELECTRIC S.P.A. | BUS4003J | G 047039 201 | 392-P-SLD-40106-001 | SINGLE LINE DIAGRAM 33KV MAIN SUBSTATION BUS4003J | A4108 | BX | 2 | 2019-07-08 | CON-BMP-VTRA-012727 | 2019-07-08 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-1651-001 | MATERIAL REQUISITION FOR HV GAS INSULATED SWITCHGEARS | SCHNEIDER ELECTRIC S.P.A. | BUS4003J | G 047039 203 | 392-P-GAD-40403-001 | GENERAL ARRANGEMENT PLANE 33KVMAIN SUBSTATION BUS4003J - CIVIL WORK, OUTLINE AND SECTIONS DRAWING | A2011 | AX | 2 | 2019-05-06 | CON-BMP-VTRA-011966 | 2019-06-04 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-1651-001 | MATERIAL REQUISITION FOR HV GAS INSULATED SWITCHGEARS | SCHNEIDER ELECTRIC S.P.A. | BUS4003J | G 047039 204 | 392-P-GAD-40407-001 | FRONT VIEW 33KV MAIN SUBSTATION BUS4003J FRONT VIEW AND NAME PLATE DRAWING | A4204 | BX | 2 | 2019-07-08 | CON-BMP-VTRA-012742 | 2019-07-08 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-1651-001 | MATERIAL REQUISITION FOR HV GAS INSULATED SWITCHGEARS | SCHNEIDER ELECTRIC S.P.A. | BUS4003J | NHJC261931 | 392-P-DLB-40003-001 | NAME PLATE BUS4003J | A4205 | BX | 2 | 2019-07-05 | CON-BMP-VTRA-012697 | 2019-07-05 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-1651-001 | MATERIAL REQUISITION FOR HV GAS INSULATED SWITCHGEARS | SCHNEIDER ELECTRIC S.P.A. | BUS4003J | R.047039.03.600-3-GHA | 392-P-CWD-40003-001 | INTERCONNECTION DRAWING BUS4003J | A4211 | AX | 2 | 2019-07-05 | CON-BMP-VTRA-012695 | 2019-07-05 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-1651-001 | MATERIAL REQUISITION FOR HV GAS INSULATED SWITCHGEARS | SCHNEIDER ELECTRIC S.P.A. | BUS4003J | R.047039.03.700-3-GHA | 392-P-WRD-40003-001 | SCHEMATIC DIAGRAMS LIST OF MATERIALS AND TERMINAL BLOCKS DRAWING BUS4003J | A4110 | AX | 2 | 2019-07-05 | CON-BMP-VTRA-012696 | 2019-07-05 | FOR BAPCO REVIEW | 2019-07-22 |  |  | CLASS 2
076551C-000R-MR-1651-001 | MATERIAL REQUISITION FOR HV GAS INSULATED SWITCHGEARS | SCHNEIDER ELECTRIC S.P.A. | BUS4004J | G 047039 301 | 392-P-SLD-40107-001 | SINGLE LINE DIAGRAM 33KV MAIN SUBSTATION BUS4004J | A4108 | BX | 2 | 2019-07-08 | CON-BMP-VTRA-012727 | 2019-07-08 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-1651-001 | MATERIAL REQUISITION FOR HV GAS INSULATED SWITCHGEARS | SCHNEIDER ELECTRIC S.P.A. | BUS4004J | G 047039 303 | 392-P-GAD-40404-001 | GENERAL ARRANGEMENT PLANE 33KVMAIN SUBSTATION BUS4004J - CIVIL WORK, OUTLINE AND SECTIONS DRAWING | A2011 | AX | 2 | 2019-05-06 | CON-BMP-VTRA-011966 | 2019-06-04 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-1651-001 | MATERIAL REQUISITION FOR HV GAS INSULATED SWITCHGEARS | SCHNEIDER ELECTRIC S.P.A. | BUS4004J | G 047039 304 | 392-P-GAD-40408-001 | FRONT VIEW 33KV MAIN SUBSTATION BUS4004J FRONT VIEW AND NAME PLATE DRAWING | A4204 | BX | 2 | 2019-07-08 | CON-BMP-VTRA-012742 | 2019-07-08 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-1651-001 | MATERIAL REQUISITION FOR HV GAS INSULATED SWITCHGEARS | SCHNEIDER ELECTRIC S.P.A. | BUS4004J | NHJC261932 | 392-P-DLB-40004-001 | NAME PLATE BUS4004J | A4205 | BX | 2 | 2019-07-05 | CON-BMP-VTRA-012697 | 2019-07-05 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-1651-001 | MATERIAL REQUISITION FOR HV GAS INSULATED SWITCHGEARS | SCHNEIDER ELECTRIC S.P.A. | BUS4004J | R.047039.04.600-3-GHA | 392-P-CWD-40004-001 | INTERCONNECTION DRAWING BUS4004J | A4211 | AX | 2 | 2019-07-05 | CON-BMP-VTRA-012695 | 2019-07-05 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-1651-001 | MATERIAL REQUISITION FOR HV GAS INSULATED SWITCHGEARS | SCHNEIDER ELECTRIC S.P.A. | BUS4004J | R.047039.04.700-3-GHA | 392-P-WRD-40004-001 | SCHEMATIC DIAGRAMS LIST OF MATERIALS AND TERMINAL BLOCKS DRAWING BUS4004J | A4110 | AX | 2 | 2019-07-05 | CON-BMP-VTRA-012696 | 2019-07-05 | FOR BAPCO REVIEW | 2019-07-22 |  |  | CLASS 2
076551C-000R-MR-1652-001 | MATERIAL REQUISITION FOR HV SWITCHGEARS | L&T ELECTRICAL & AUTOMATION | BUS4101K_BUS4102K | HLP0113 | 018-P-SLD-40354-001 | SINGLE LINE DIAGRAM 11KV SWITCHGEAR (BUS4101K & BUS4102K) | A4108 | AX | 2 | 2019-06-19 | CON-BMP-VTRA-012296 | 2019-06-19 | FOR BAPCO REVIEW | 2019-07-03 | 2019-07-08 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001197 | CLASS 2
076551C-000R-MR-1652-001 | MATERIAL REQUISITION FOR HV SWITCHGEARS | L&T ELECTRICAL & AUTOMATION | BUS4101K_BUS4102K | HYP0113 | 018-P-GAD-40014-001 | GENERAL ARRANGEMENT DRAWING 11KV SWITCHGEAR (BUS4101K & BUS4102K) | A4201 | AX | 2 | 2019-06-19 | CON-BMP-VTRA-012299 | 2019-06-19 | FOR BAPCO REVIEW | 2019-07-03 | 2019-07-07 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001182 | CLASS 2
076551C-000R-MR-1652-001 | MATERIAL REQUISITION FOR HV SWITCHGEARS | L&T ELECTRICAL & AUTOMATION | BUS4101K_BUS4102K | LTEASA-ROC-MPR-001 | 000-P-MRS-40002-001 | MONTHLY PROGRESS REPORT 6.6KV AND 11KV SWITCHGEARS ALL ITEMS | C1002 | AX | 2 | 2019-06-28 | CON-BMP-VTRA-012547 | 2019-06-28 | FOR BAPCO REVIEW | 2019-07-12 |  |  | CLASS 2
076551C-000R-MR-1652-001 | MATERIAL REQUISITION FOR HV SWITCHGEARS | L&T ELECTRICAL & AUTOMATION | BUS4101K_BUS4102K | LTEASA-ROC-QAP-001 | 000-P-PQP-40002-001 | FABRICATION AND QUALITY CONTROL PLAN 6.6KV & 11KV SWITCHGEARS ALL ITEMS | B1002 | AX | 2 | 2019-06-19 | CON-BMP-VTRA-012297 | 2019-06-19 | FOR BAPCO REVIEW | 2019-07-03 | 2019-06-30 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001121 | CLASS 2
076551C-000R-MR-1652-001 | MATERIAL REQUISITION FOR HV SWITCHGEARS | L&T ELECTRICAL & AUTOMATION | BUS4101K_BUS4102K | LTEASA-ROC-VPIS-001 | 000-P-INX-40007-001 | LIST OF VENDORS DOCUMENTS AND DRAWINGS FOR HV SWITCHGEARS ALL ITEMS | A0001 | AX | 2 | 2019-06-06 | CON-BMP-VTRA-012069 | 2019-06-06 | FOR BAPCO REVIEW | 2019-06-21 | 2019-06-22 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001014 | CLASS 2
076551C-000R-MR-1652-001 | MATERIAL REQUISITION FOR HV SWITCHGEARS | L&T ELECTRICAL & AUTOMATION | BUS4103L_BUS4104L | HLP0116 | 018-P-SLD-40353-001 | SINGLE LINE DIAGRAM 6.6KV SWITCHGEAR (BUS4103L & BUS4104L) | A4108 | AX | 2 | 2019-06-19 | CON-BMP-VTRA-012296 | 2019-06-19 | FOR BAPCO REVIEW | 2019-07-03 | 2019-07-08 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001197 | CLASS 2
076551C-000R-MR-1652-001 | MATERIAL REQUISITION FOR HV SWITCHGEARS | L&T ELECTRICAL & AUTOMATION | BUS4103L_BUS4104L | HYP0116 | 018-P-GAD-40013-001 | GENERAL ARRANGEMENT DRAWING 6.6KV SWITCHGEAR (BUS4103L & BUS4104L) | A4201 | AX | 2 | 2019-06-19 | CON-BMP-VTRA-012299 | 2019-06-19 | FOR BAPCO REVIEW | 2019-07-03 | 2019-07-07 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001182 | CLASS 2
076551C-000R-MR-1652-001 | MATERIAL REQUISITION FOR HV SWITCHGEARS | L&T ELECTRICAL & AUTOMATION | BUS4203L_BUS4204L | HLP0119 | 021-P-SLD-40204-001 | SINGLE LINE DIAGRAM 6.6KV SWITCHGEAR (BUS4203L & BUS4204L) | A4108 | AX | 2 | 2019-06-19 | CON-BMP-VTRA-012294 | 2019-06-19 | FOR BAPCO REVIEW | 2019-07-03 | 2019-07-08 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001196 | CLASS 2
076551C-000R-MR-1652-001 | MATERIAL REQUISITION FOR HV SWITCHGEARS | L&T ELECTRICAL & AUTOMATION | BUS4203L_BUS4204L | HYP0119 | 021-P-GAD-40025-001 | GENERAL ARRANGEMENT DRAWING 6.6KV SWITCHGEAR (BUS4203L & BUS4204L) | A4201 | AX | 2 | 2019-06-19 | CON-BMP-VTRA-012300 | 2019-06-19 | FOR BAPCO REVIEW | 2019-07-03 | 2019-07-07 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001181 | CLASS 2
076551C-000R-MR-1652-001 | MATERIAL REQUISITION FOR HV SWITCHGEARS | L&T ELECTRICAL & AUTOMATION | BUS4401K_BUS4400K_BUS4402K | HLP0112 | 056-P-SLD-40515-001 | SINGLE LINE DIAGRAM 11KV SWITCHGEAR (BUS4400K , BUS4401K & BUS4402K) | A4108 | AX | 2 | 2019-06-19 | CON-BMP-VTRA-012293 | 2019-06-19 | FOR BAPCO REVIEW | 2019-07-03 | 2019-07-07 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001193 | CLASS 2
076551C-000R-MR-1652-001 | MATERIAL REQUISITION FOR HV SWITCHGEARS | L&T ELECTRICAL & AUTOMATION | BUS4401K_BUS4400K_BUS4402K | HYP0112 | 056-P-GAD-40421-001 | GENERAL ARRANGEMENT DRAWING 11KV SWITCHGEAR (BUS4400K , BUS4401K & BUS4402K) | A4201 | AX | 2 | 2019-06-19 | CON-BMP-VTRA-012301 | 2019-06-19 | FOR BAPCO REVIEW | 2019-07-03 |  |  | CLASS 2
076551C-000R-MR-1652-001 | MATERIAL REQUISITION FOR HV SWITCHGEARS | L&T ELECTRICAL & AUTOMATION | BUS4401K_BUS4400K_BUS4402K | HYP0123 | 056-P-GAD-40422-001 | GENERAL ARRANGEMENT DRAWING FOR DIFFERENTIAL PROTECTION EWA CABINET BUS4400K BUS4401K BUS4402K | A4201 | AX | 2 | 2019-06-19 | CON-BMP-VTRA-012301 | 2019-06-19 | FOR BAPCO REVIEW | 2019-07-03 |  |  | CLASS 2
076551C-000R-MR-1652-001 | MATERIAL REQUISITION FOR HV SWITCHGEARS | L&T ELECTRICAL & AUTOMATION | BUS4403L_BUS4404L | HLP0117 | 056-P-SLD-40514-001 | SINGLE LINE DIAGRAM 6.6KV SWITCHGEAR (BUS4403L & BUS4404L) | A4108 | AX | 2 | 2019-06-19 | CON-BMP-VTRA-012293 | 2019-06-19 | FOR BAPCO REVIEW | 2019-07-03 | 2019-07-07 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001193 | CLASS 2
076551C-000R-MR-1652-001 | MATERIAL REQUISITION FOR HV SWITCHGEARS | L&T ELECTRICAL & AUTOMATION | BUS4403L_BUS4404L | HYP0117 | 056-P-GAD-40449-001 | GENERAL ARRANGEMENT DRAWING 6.6KV SWITCHGEAR (BUS4403L & BUS4404L) | A4201 | AX | 2 | 2019-06-19 | CON-BMP-VTRA-012301 | 2019-06-19 | FOR BAPCO REVIEW | 2019-07-03 |  |  | CLASS 2
076551C-000R-MR-1652-001 | MATERIAL REQUISITION FOR HV SWITCHGEARS | L&T ELECTRICAL & AUTOMATION | BUS4501K_BUS4502K | HLP0115 | 051-P-SLD-40205-001 | SINGLE LINE DIAGRAM 11KV SWITCHGEAR (BUS4501K & BUS4502K) | A4108 | AX | 2 | 2019-06-19 | CON-BMP-VTRA-012295 | 2019-06-19 | FOR BAPCO REVIEW | 2019-07-03 |  |  | CLASS 2
076551C-000R-MR-1652-001 | MATERIAL REQUISITION FOR HV SWITCHGEARS | L&T ELECTRICAL & AUTOMATION | BUS4501K_BUS4502K | HYP0115 | 051-P-GAD-40421-001 | GENERAL ARRANGEMENT DRAWING 11KV SWITCHGEAR (BUS4501K & BUS4502K) | A4201 | AX | 2 | 2019-06-19 | CON-BMP-VTRA-012298 | 2019-06-19 | FOR BAPCO REVIEW | 2019-07-03 | 2019-07-08 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001223 | CLASS 2
076551C-000R-MR-1652-001 | MATERIAL REQUISITION FOR HV SWITCHGEARS | L&T ELECTRICAL & AUTOMATION | BUS4503L_BUS4504L | HLP0121 | 051-P-SLD-40204-001 | SINGLE LINE DIAGRAM 6.6 KV SWITCHGEAR (BUS4503L & BUS4504L) | A4108 | AX | 2 | 2019-06-19 | CON-BMP-VTRA-012295 | 2019-06-19 | FOR BAPCO REVIEW | 2019-07-03 |  |  | CLASS 2
076551C-000R-MR-1652-001 | MATERIAL REQUISITION FOR HV SWITCHGEARS | L&T ELECTRICAL & AUTOMATION | BUS4503L_BUS4504L | HYP0121 | 051-P-GAD-40420-001 | GENERAL ARRANGEMENT DRAWING 6.6 KV SWITCHGEAR (BUS4503L & BUS4504L) | A4201 | AX | 2 | 2019-06-19 | CON-BMP-VTRA-012298 | 2019-06-19 | FOR BAPCO REVIEW | 2019-07-03 | 2019-07-08 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001223 | CLASS 2
076551C-000R-MR-1653-001 | MATERIAL REQUISITION FOR HV & LV BUS DUCTS | EAE | BDE4101K | EAE-BOM | 000-P-BOM-40001-001 | LIST OF MATERIALS ALL ITEMS | A0002 | AX | 4 | 2019-06-04 | CON-BMP-VTRA-011968 | 2019-06-04 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-1653-001 | MATERIAL REQUISITION FOR HV & LV BUS DUCTS | EAE | BDE4101K | EAE-DLB | 000-P-DLB-40001-001 | NAMEPLATE DRAWING ALL ITEMS | A4205 | AX | 2 | 2019-05-30 | CON-BMP-VTRA-011854 | 2019-05-30 | FOR BAPCO REVIEW | 2019-06-14 | 2019-07-09 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001239 | CLASS 2
076551C-000R-MR-1653-001 | MATERIAL REQUISITION FOR HV & LV BUS DUCTS | EAE | BDE4101K | EAE-GAD-BDE4101K | 018-P-GAD-40001-001 | BUS DUCT ARRANGEMENT DRAWING WITH SUPPORTING DETAILS BDE4101K | A4221 | AX | 1 | 2019-06-05 | CON-BMP-VTRA-012014 | 2019-06-05 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-1653-001 | MATERIAL REQUISITION FOR HV & LV BUS DUCTS | EAE | BDE4101K | EAE-INX | 000-P-INX-40004-001 | LIST OF VENDOR'S DOCUMENTS ANDDRAWINGS ALL ITEMS | A0001 | AX | 2 | 2019-05-30 | CON-BMP-VTRA-011856 | 2019-05-30 | FOR BAPCO REVIEW | 2019-06-14 | 2019-06-17 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000953 | CLASS 2
076551C-000R-MR-1653-001 | MATERIAL REQUISITION FOR HV & LV BUS DUCTS | EAE | BDE4101K | EAE-ITP | 000-P-ITP-40012-001 | INSPECTION TEST PLAN ALL ITEMS | B1002 | AX | 2 | 2019-05-30 | CON-BMP-VTRA-011853 | 2019-05-30 | FOR BAPCO REVIEW | 2019-09-14 | 2019-06-11 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000909 | CLASS 2
076551C-000R-MR-1653-001 | MATERIAL REQUISITION FOR HV & LV BUS DUCTS | EAE | BDE4101K | EAE-OUTLINE-BDE4101K | 018-P-GAD-40009-001 | OUTLINE DIMENSIONAL DWGS (WITHSTATIC & DYNAMIC LOADS INDIC) BDE4101K | A2011 | AX | 1 | 2019-05-30 | CON-BMP-VTRA-011850 | 2019-05-30 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-1653-001 | MATERIAL REQUISITION FOR HV & LV BUS DUCTS | EAE | BDE4101K | EAE-S3D-BDE4101K | 018-P-S3D-40004-001 | 3D MODEL HV BUS DUCT 11 KV 3150 A 50 KA 3PH 50 HZ BDE4101K | A2013 | AX | 2 | 2019-06-05 | CON-BMP-VTRA-011980 | 2019-06-05 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-1653-001 | MATERIAL REQUISITION FOR HV & LV BUS DUCTS | EAE | BDE4101K | EAE-SCH | 000-P-SCH-40002-001 | ENGINEERING PROCUREMENT MANUFACTURING & TEST SCHEDULE (1) ALL ITEMS | C1001 | AX | 4 | 2019-06-04 | CON-BMP-VTRA-011972 | 2019-06-04 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-1653-001 | MATERIAL REQUISITION FOR HV & LV BUS DUCTS | EAE | BDE4101K | EAE-TRGAD-BDE4101K | 018-P-GAD-40005-001 | TRANSFORMER/BUS DUCT FLANGE DRAWING (1) BDE4101K | A4218 | AX | 2 | 2019-05-30 | CON-BMP-VTRA-011851 | 2019-05-30 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-1653-001 | MATERIAL REQUISITION FOR HV & LV BUS DUCTS | EAE | BDE4101K | EAE-TSP | 000-P-TSP-40002-001 | PAINTING SPECIFICATION ALL ITEMS | A0106 | AX | 2 | 2019-06-05 | CON-BMP-VTRA-011978 | 2019-06-05 | FOR BAPCO REVIEW | 2019-06-19 | 2019-06-17 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000968 | CLASS 2
076551C-000R-MR-1653-001 | MATERIAL REQUISITION FOR HV & LV BUS DUCTS | EAE | BDE4101K | EAE-TSPCAT | 000-P-TSP-40003-001 | BULLETINS AND CATALOGUES ALL ITEMS | A4216 | AX | 4 | 2019-06-04 | CON-BMP-VTRA-011970 | 2019-06-04 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-1653-001 | MATERIAL REQUISITION FOR HV & LV BUS DUCTS | EAE | BDE4102K | EAE-GAD-BDE4102K | 018-P-GAD-40002-001 | BUS DUCT ARRANGEMENT DRAWING WITH SUPPORTING DETAILS BDE4102K | A4221 | AX | 1 | 2019-06-05 | CON-BMP-VTRA-012014 | 2019-06-05 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-1653-001 | MATERIAL REQUISITION FOR HV & LV BUS DUCTS | EAE | BDE4102K | EAE-OUTLINE-BDE4102K | 018-P-GAD-40010-001 | OUTLINE DIMENSIONAL DWGS (WITHSTATIC & DYNAMIC LOADS INDIC).BDE4102K | A2011 | AX | 1 | 2019-05-30 | CON-BMP-VTRA-011850 | 2019-05-30 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-1653-001 | MATERIAL REQUISITION FOR HV & LV BUS DUCTS | EAE | BDE4102K | EAE-S3D-BDE4102K | 018-P-S3D-40003-001 | 3D MODEL HV BUS DUCT 11 KV 3150 A 50 KA 3PH 50 HZ BDE4102K | A2013 | AX | 2 | 2019-06-05 | CON-BMP-VTRA-011980 | 2019-06-05 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-1653-001 | MATERIAL REQUISITION FOR HV & LV BUS DUCTS | EAE | BDE4102K | EAE-TRGAD-BDE4102K | 018-P-GAD-40006-001 | TRANSFORMER/BUS DUCT FLANGE DRAWING (1) BDE4102K | A4218 | AX | 2 | 2019-05-30 | CON-BMP-VTRA-011851 | 2019-05-30 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-1653-001 | MATERIAL REQUISITION FOR HV & LV BUS DUCTS | EAE | BDE4103L | EAE-GAD-BDE4103L | 018-P-GAD-40004-001 | BUS DUCT ARRANGEMENT DRAWING WITH SUPPORTING DETAILS BDE4103L | A4221 | AX | 1 | 2019-06-05 | CON-BMP-VTRA-012014 | 2019-06-05 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-1653-001 | MATERIAL REQUISITION FOR HV & LV BUS DUCTS | EAE | BDE4103L | EAE-OUTLINE-BDE4103L | 018-P-GAD-40012-001 | OUTLINE DIMENSIONAL DWGS (WITHSTATIC & DYNAMIC LOADS INDIC).BDE4103L | A2011 | AX | 1 | 2019-05-30 | CON-BMP-VTRA-011850 | 2019-05-30 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-1653-001 | MATERIAL REQUISITION FOR HV & LV BUS DUCTS | EAE | BDE4103L | EAE-S3D-BDE4103L | 018-P-S3D-40001-001 | 3D MODEL HV BUS DUCT 6.6 KV 3150 A 50 KA 3PH 50 HZ BDE4103L | A2013 | AX | 2 | 2019-06-05 | CON-BMP-VTRA-011980 | 2019-06-05 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-1653-001 | MATERIAL REQUISITION FOR HV & LV BUS DUCTS | EAE | BDE4103L | EAE-TRGAD-BDE4103L | 018-P-GAD-40008-001 | TRANSFORMER/BUS DUCT FLANGE DRAWING (1) BDE4103L | A4218 | AX | 2 | 2019-05-30 | CON-BMP-VTRA-011851 | 2019-05-30 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-1653-001 | MATERIAL REQUISITION FOR HV & LV BUS DUCTS | EAE | BDE4104L | EAE-GAD-BDE4104L | 018-P-GAD-40003-001 | BUS DUCT ARRANGEMENT DRAWING WITH SUPPORTING DETAILS BDE4104L | A4221 | AX | 1 | 2019-06-05 | CON-BMP-VTRA-012014 | 2019-06-05 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-1653-001 | MATERIAL REQUISITION FOR HV & LV BUS DUCTS | EAE | BDE4104L | EAE-OUTLINE-BDE4104L | 018-P-GAD-40011-001 | OUTLINE DIMENSIONAL DWGS (WITHSTATIC & DYNAMIC LOADS INDIC).BDE4104L | A2011 | AX | 1 | 2019-05-30 | CON-BMP-VTRA-011850 | 2019-05-30 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-1653-001 | MATERIAL REQUISITION FOR HV & LV BUS DUCTS | EAE | BDE4104L | EAE-S3D-BDE4104L | 018-P-S3D-40002-001 | 3D MODEL HV BUS DUCT 6.6 KV 3150 A 50 KA 3PH 50 HZ BDE4104L | A2013 | AX | 2 | 2019-06-05 | CON-BMP-VTRA-011980 | 2019-06-05 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-1653-001 | MATERIAL REQUISITION FOR HV & LV BUS DUCTS | EAE | BDE4104L | EAE-TRGAD-BDE4104L | 018-P-GAD-40007-001 | TRANSFORMER/BUS DUCT FLANGE DRAWING (1) BDE4104L | A4218 | AX | 2 | 2019-05-30 | CON-BMP-VTRA-011851 | 2019-05-30 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-1653-001 | MATERIAL REQUISITION FOR HV & LV BUS DUCTS | EAE | BDE4203L | EAE-GAD-BDE4203L | 021-P-GAD-40017-001 | BUS DUCT ARRANGEMENT DRAWING WITH SUPPORTING DETAILS BDE4203L | A4221 | AX | 1 | 2019-06-05 | CON-BMP-VTRA-012014 | 2019-06-05 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-1653-001 | MATERIAL REQUISITION FOR HV & LV BUS DUCTS | EAE | BDE4203L | EAE-OUTLINE-BDE4203L | 021-P-GAD-40001-001 | OUTLINE DIMENSIONAL DWGS (WITHSTATIC & DYNAMIC LOADS INDIC).BDE4203L | A2011 | AX | 1 | 2019-05-30 | CON-BMP-VTRA-011850 | 2019-05-30 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-1653-001 | MATERIAL REQUISITION FOR HV & LV BUS DUCTS | EAE | BDE4203L | EAE-S3D-BDE4203L | 021-P-S3D-40001-001 | 3D MODEL HV BUS DUCT 6.6 KV 1250 A 40 KA 3PH 50 HZ BDE4203L | A2013 | AX | 2 | 2019-06-05 | CON-BMP-VTRA-011980 | 2019-06-05 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-1653-001 | MATERIAL REQUISITION FOR HV & LV BUS DUCTS | EAE | BDE4203L | EAE-TRGAD-BDE4203L | 021-P-GAD-40009-001 | TRANSFORMER/BUS DUCT FLANGE DRAWING (1) BDE4203L | A4218 | AX | 2 | 2019-05-30 | CON-BMP-VTRA-011851 | 2019-05-30 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-1653-001 | MATERIAL REQUISITION FOR HV & LV BUS DUCTS | EAE | BDE4204L | EAE-GAD-BDE4204L | 021-P-GAD-40018-001 | BUS DUCT ARRANGEMENT DRAWING WITH SUPPORTING DETAILS BDE4204L | A4221 | AX | 1 | 2019-06-05 | CON-BMP-VTRA-012014 | 2019-06-05 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-1653-001 | MATERIAL REQUISITION FOR HV & LV BUS DUCTS | EAE | BDE4204L | EAE-OUTLINE-BDE4204L | 021-P-GAD-40002-001 | OUTLINE DIMENSIONAL DWGS (WITHSTATIC & DYNAMIC LOADS INDIC).BDE4204L | A2011 | AX | 1 | 2019-05-30 | CON-BMP-VTRA-011850 | 2019-05-30 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-1653-001 | MATERIAL REQUISITION FOR HV & LV BUS DUCTS | EAE | BDE4204L | EAE-S3D-BDE4204L | 021-P-S3D-40002-001 | 3D MODEL HV BUS DUCT 6.6 KV 1250 A 40 KA 3PH 50 HZ BDE4204L | A2013 | AX | 2 | 2019-06-05 | CON-BMP-VTRA-011980 | 2019-06-05 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-1653-001 | MATERIAL REQUISITION FOR HV & LV BUS DUCTS | EAE | BDE4204L | EAE-TRGAD-BDE4204L | 021-P-GAD-40010-001 | TRANSFORMER/BUS DUCT FLANGE DRAWING (1) BDE4204L | A4218 | AX | 2 | 2019-05-30 | CON-BMP-VTRA-011851 | 2019-05-30 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-1653-001 | MATERIAL REQUISITION FOR HV & LV BUS DUCTS | EAE | BDE4403L | EAE-OUTLINE-BDE4403L | 056-P-GAD-40403-001 | OUTLINE DIMENSIONAL DWGS (WITHSTATIC & DYNAMIC LOADS INDIC).BDE4403L | A2011 | AX | 1 | 2019-05-30 | CON-BMP-VTRA-011850 | 2019-05-30 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-1653-001 | MATERIAL REQUISITION FOR HV & LV BUS DUCTS | EAE | BDE4403L | EAE-S3D-BDE4403L | 056-P-S3D-40002-001 | 3D MODEL HV BUS DUCT 6.6 KV 3150 A 40 KA 3PH 50 HZ BDE4403L | A2013 | AX | 2 | 2019-06-05 | CON-BMP-VTRA-011980 | 2019-06-05 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-1653-001 | MATERIAL REQUISITION FOR HV & LV BUS DUCTS | EAE | BDE4403L | EAE-TRGAD-BDE4403L | 056-P-GAD-40407-001 | TRANSFORMER/BUS DUCT FLANGE DRAWING (1) BDE4403L | A4218 | AX | 2 | 2019-05-30 | CON-BMP-VTRA-011851 | 2019-05-30 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-1653-001 | MATERIAL REQUISITION FOR HV & LV BUS DUCTS | EAE | BDE4404L | EAE-OUTLINE-BDE4404L | 056-P-GAD-40402-001 | OUTLINE DIMENSIONAL DWGS (WITHSTATIC & DYNAMIC LOADS INDIC).BDE4404L | A2011 | AX | 1 | 2019-05-30 | CON-BMP-VTRA-011850 | 2019-05-30 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-1653-001 | MATERIAL REQUISITION FOR HV & LV BUS DUCTS | EAE | BDE4404L | EAE-S3D-BDE4404L | 056-P-S3D-40001-001 | 3D MODEL HV BUS DUCT 6.6 KV 3150 A 40 KA 3PH 50 HZ BDE4404L | A2013 | AX | 2 | 2019-06-05 | CON-BMP-VTRA-011980 | 2019-06-05 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-1653-001 | MATERIAL REQUISITION FOR HV & LV BUS DUCTS | EAE | BDE4404L | EAE-TRGAD-BDE4404L | 056-P-GAD-40406-001 | TRANSFORMER/BUS DUCT FLANGE DRAWING (1) BDE4404L | A4218 | AX | 2 | 2019-05-30 | CON-BMP-VTRA-011851 | 2019-05-30 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-1653-001 | MATERIAL REQUISITION FOR HV & LV BUS DUCTS | EAE | BDE4503L | EAE-GAD-BDE4503L | 051-P-GAD-40415-001 | BUS DUCT ARRANGEMENT DRAWING WITH SUPPORTING DETAILS BDE4503L | A4221 | AX | 1 | 2019-06-22 | CON-BMP-VTRA-012374 | 2019-06-22 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-1653-001 | MATERIAL REQUISITION FOR HV & LV BUS DUCTS | EAE | BDE4503L | EAE-OUTLINE-BDE4503L | 051-P-GAD-40403-001 | OUTLINE DIMENSIONAL DWGS (WITHSTATIC & DYNAMIC LOADS INDIC).BDE4503L | A2011 | AX | 1 | 2019-05-30 | CON-BMP-VTRA-011850 | 2019-05-30 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-1653-001 | MATERIAL REQUISITION FOR HV & LV BUS DUCTS | EAE | BDE4503L | EAE-S3D-BDE4503L | 051-P-S3D-40002-001 | 3D MODEL HV BUS DUCT 6.6 KV 1250 A 40 KA 3PH 50 HZ BDE4503L | A2013 | AX | 2 | 2019-06-05 | CON-BMP-VTRA-011980 | 2019-06-05 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-1653-001 | MATERIAL REQUISITION FOR HV & LV BUS DUCTS | EAE | BDE4503L | EAE-TRGAD-BDE4503L | 051-P-GAD-40409-001 | TRANSFORMER/BUS DUCT FLANGE DRAWING (1) BDE4503L | A4218 | AX | 2 | 2019-05-30 | CON-BMP-VTRA-011851 | 2019-05-30 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-1653-001 | MATERIAL REQUISITION FOR HV & LV BUS DUCTS | EAE | BDE4504L | EAE-GAD-BDE4504L | 051-P-GAD-40414-001 | BUS DUCT ARRANGEMENT DRAWING WITH SUPPORTING DETAILS BDE4504L | A4221 | AX | 1 | 2019-06-22 | CON-BMP-VTRA-012380 | 2019-06-22 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-1653-001 | MATERIAL REQUISITION FOR HV & LV BUS DUCTS | EAE | BDE4504L | EAE-OUTLINE-BDE4504L | 051-P-GAD-40402-001 | OUTLINE DIMENSIONAL DWGS (WITHSTATIC & DYNAMIC LOADS INDIC).BDE4504L | A2011 | AX | 1 | 2019-05-30 | CON-BMP-VTRA-011850 | 2019-05-30 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-1653-001 | MATERIAL REQUISITION FOR HV & LV BUS DUCTS | EAE | BDE4504L | EAE-S3D-BDE4504L | 051-P-S3D-40001-001 | 3D MODEL HV BUS DUCT 6.6 KV 1250 A 40 KA 3PH 50 HZ BDE4504L | A2013 | AX | 2 | 2019-06-05 | CON-BMP-VTRA-011980 | 2019-06-05 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-1653-001 | MATERIAL REQUISITION FOR HV & LV BUS DUCTS | EAE | BDE4504L | EAE-TRGAD-BDE4504L | 051-P-GAD-40408-001 | TRANSFORMER/BUS DUCT FLANGE DRAWING (1) BDE4504L | A4218 | AX | 2 | 2019-05-30 | CON-BMP-VTRA-011851 | 2019-05-30 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-1671-001 | MATERIAL REQUISITION FOR AC AND DC UPS SYSTEM | BORRI SPA | CHG4005N1-A_CHG4005N1-B | DBX15057 | 392-P-SLD-40108-001 | SINGLE LINE DIAGRAM 110V DC UPS CHG4005N1-A_CHG4005N1-B 33KV MAIN SUBSTATION 392SSTR01 | A4108 | AX | 1 | 2019-06-10 | CON-BMP-VTRA-012136 | 2019-06-10 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-1671-001 | MATERIAL REQUISITION FOR AC AND DC UPS SYSTEM | BORRI SPA | CHG4005N1-A_CHG4005N1-B | DBX15058 | 392-P-GAD-40415-001 | GENERAL ARRANGEMENT 110V DC UPS CHG4005N1-A_CHG4005N1-B 3 SUPHUR PLANT WEST SUBSTATION 036SSTR01 | A4201 | AX | 1 | 2019-06-10 | CON-BMP-VTRA-012128 | 2019-06-10 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-1671-001 | MATERIAL REQUISITION FOR AC AND DC UPS SYSTEM | BORRI SPA | CHG4005N1-A_CHG4005N1-B | DBX15059 | 392-P-GAD-40416-001 | BATTERY GAD FOR DC UPS 110V DCUPS CHG4005N1-A_CHG4005N1-B 33KV MAIN SUBSTATION 392SSTR01 | A4224 | AX | 2 | 2019-06-06 | CON-BMP-VTRA-012066 | 2019-06-06 | FOR BAPCO REVIEW | 2019-06-21 | 2019-06-17 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000987 | CLASS 2
076551C-000R-MR-1671-001 | MATERIAL REQUISITION FOR AC AND DC UPS SYSTEM | BORRI SPA | CHG4005N1-A_CHG4005N1-B | MCX15062 | 392-P-CAL-40007-001 | BATTERY SIZING CALCULATION AC AND DC UPS SYSTEM CHG4005N1-A_CHG4005N1-B | A4223 | AX | 2 | 2019-06-06 | CON-BMP-VTRA-012070 | 2019-06-06 | FOR BAPCO REVIEW | 2019-06-21 | 2019-06-18 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000972 | CLASS 2
076551C-000R-MR-1671-001 | MATERIAL REQUISITION FOR AC AND DC UPS SYSTEM | BORRI SPA | CHG4005N1-A_CHG4005N1-B | MCX15081 | 000-P-INX-40013-001 | LIST OF VENDOR'S DOCUMENTS ANDDRAWINGS ALL ITEMS | A0001 | AX | 2 | 2019-06-10 | CON-BMP-VTRA-012138 | 2019-06-10 | FOR BAPCO REVIEW | 2019-06-25 | 2019-06-18 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000998 | CLASS 2
076551C-000R-MR-1671-001 | MATERIAL REQUISITION FOR AC AND DC UPS SYSTEM | BORRI SPA | CHG4005N1-A_CHG4005N1-B | MCX15084 | 000-P-TSP-40010-001 | CATALOGUES AC AND DC UPS SYSTEM ALL ITEMS | A4216 | BX | 4 | 2019-07-03 | CON-BMP-VTRA-012632 | 2019-07-03 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-1671-001 | MATERIAL REQUISITION FOR AC AND DC UPS SYSTEM | BORRI SPA | CHG4005N1-A_CHG4005N1-B | MCX15086 | 000-P-STS-40001-001 | DATA OF HARMONIC ANALYSIS AC AND DC UPS SYSTEM ALL ITEMS | A4304 | AX | 1 | 2019-07-12 | CON-BMP-VTRA-012832 | 2019-07-12 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-1671-001 | MATERIAL REQUISITION FOR AC AND DC UPS SYSTEM | BORRI SPA | CHG4005N1-A_CHG4005N1-B | MCX15087 | 000-P-CAL-40009-001 | HEAT DISSIPATION & AUX POWER SUPPLY CONSUMPTION AC & DC UPSSYSTEM ALL ITEMS | A4305 | AX | 2 | 2019-06-06 | CON-BMP-VTRA-012074 | 2019-06-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-1671-001 | MATERIAL REQUISITION FOR AC AND DC UPS SYSTEM | BORRI SPA | CHG4005N1-A_CHG4005N1-B | MCX15100 | 000-P-SCH-40005-001 | ENGINEERING PROCUREMENT MANUFACTURING & TEST SCHEDULE AC & DC UPS SYSTEM ALL ITEMS | C1001 | AX | 2 | 2019-06-06 | CON-BMP-VTRA-012079 | 2019-06-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-1671-001 | MATERIAL REQUISITION FOR AC AND DC UPS SYSTEM | BORRI SPA | CHG4005N1-A_CHG4005N1-B | MCX15101 | 000-P-MRS-40004-001 | MONTHLY PROGRESS REPORT AC & DC UPS SYSTEM ALL ITEMS | C1002 | AX | 4 | 2019-07-12 | CON-BMP-VTRA-012839 | 2019-07-12 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-1671-001 | MATERIAL REQUISITION FOR AC AND DC UPS SYSTEM | BORRI SPA | CHG4109N1_CHG4111N1 | DBX15001 | 018-P-SLD-40355-001 | SINGLE LINE DIAGRAM 110V DC UPS CHG4109N1_CHG4111N1 33KV MAIN SUBSTATION 392SSTR01 | A4108 | AX | 1 | 2019-06-10 | CON-BMP-VTRA-012130 | 2019-06-10 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-1671-001 | MATERIAL REQUISITION FOR AC AND DC UPS SYSTEM | BORRI SPA | CHG4109N1_CHG4111N1 | DBX15002 | 018-P-GAD-40037-001 | GENERAL ARRANGEMENT 110V DC UPS CHG4109N1_CHG4111N1 3 SUPHUR PLANT WEST SUBSTATION 036SSTR01 | A4201 | AX | 1 | 2019-06-10 | CON-BMP-VTRA-012123 | 2019-06-10 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-1671-001 | MATERIAL REQUISITION FOR AC AND DC UPS SYSTEM | BORRI SPA | CHG4109N1_CHG4111N1 | DBX15003 | 018-P-GAD-40038-001 | BATTERY GAD FOR DC UPS 110V DCUPS CHG4109N1_CHG4111N1 33KV MAIN SUBSTATION 392SSTR01 | A4224 | AX | 2 | 2019-06-06 | CON-BMP-VTRA-012066 | 2019-06-06 | FOR BAPCO REVIEW | 2019-06-21 | 2019-06-17 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000987 | CLASS 2
076551C-000R-MR-1671-001 | MATERIAL REQUISITION FOR AC AND DC UPS SYSTEM | BORRI SPA | CHG4109N1_CHG4111N1 | MCX15006 | 018-P-CAL-40001-001 | BATTERY SIZING CALCULATION AC AND DC UPS SYSTEM CHG4109N1_CHG4111N1 | A4223 | AX | 2 | 2019-06-06 | CON-BMP-VTRA-012070 | 2019-06-06 | FOR BAPCO REVIEW | 2019-06-21 | 2019-06-18 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000972 | CLASS 2
076551C-000R-MR-1671-001 | MATERIAL REQUISITION FOR AC AND DC UPS SYSTEM | BORRI SPA | CHG4109N1_CHG4111N1 | OMX15082 | 000-P-TSP-40009-001 | PAINTING SPECIFICATION AC & DCUPS SYSTEM ALL ITEMS | A0106 | AX | 2 | 2019-06-06 | CON-BMP-VTRA-012083 | 2019-06-06 | FOR BAPCO REVIEW | 2019-06-21 | 2019-06-19 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001004 | CLASS 2
076551C-000R-MR-1671-001 | MATERIAL REQUISITION FOR AC AND DC UPS SYSTEM | BORRI SPA | CHG4109N1_CHG4111N1 | QPX15094 | 000-P-ITP-40013-001 | FABRICATION AND QUALITY CONTROL PLAN (ITP) AC AND DC UPS SYSTEMS ALL ITEMS | B1002 | AX | 2 | 2019-06-27 | CON-BMP-VTRA-012525 | 2019-06-27 | FOR BAPCO REVIEW | 2019-07-11 |  |  | CLASS 2
076551C-000R-MR-1671-001 | MATERIAL REQUISITION FOR AC AND DC UPS SYSTEM | BORRI SPA | CHG4207N1_CHG4209N1 | DBX15009 | 021-P-SLD-40206-001 | SINGLE LINE DIAGRAM 110V DC UPS CHG4207N1_CHG4209N1 33KV MAIN SUBSTATION 392SSTR01 | A4108 | AX | 1 | 2019-06-10 | CON-BMP-VTRA-012131 | 2019-06-10 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-1671-001 | MATERIAL REQUISITION FOR AC AND DC UPS SYSTEM | BORRI SPA | CHG4207N1_CHG4209N1 | DBX15010 | 021-P-GAD-40030-001 | GENERAL ARRANGEMENT 110V DC UPS CHG4207N1_CHG4209N1 3 SUPHUR PLANT WEST SUBSTATION 036SSTR01 | A4201 | AX | 1 | 2019-06-10 | CON-BMP-VTRA-012124 | 2019-06-10 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-1671-001 | MATERIAL REQUISITION FOR AC AND DC UPS SYSTEM | BORRI SPA | CHG4207N1_CHG4209N1 | DBX15011 | 021-P-GAD-40031-001 | BATTERY GAD FOR DC UPS 110V DCUPS CHG4207N1_CHG4209N1 33KV MAIN SUBSTATION 392SSTR01 | A4224 | AX | 2 | 2019-06-06 | CON-BMP-VTRA-012066 | 2019-06-06 | FOR BAPCO REVIEW | 2019-06-21 | 2019-06-17 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000987 | CLASS 2
076551C-000R-MR-1671-001 | MATERIAL REQUISITION FOR AC AND DC UPS SYSTEM | BORRI SPA | CHG4207N1_CHG4209N1 | MCX15014 | 021-P-CAL-40001-001 | BATTERY SIZING CALCULATION AC AND DC UPS SYSTEM CHG4207N1_CHG4209N1 | A4223 | AX | 2 | 2019-06-06 | CON-BMP-VTRA-012070 | 2019-06-06 | FOR BAPCO REVIEW | 2019-06-21 | 2019-06-18 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000972 | CLASS 2
076551C-000R-MR-1671-001 | MATERIAL REQUISITION FOR AC AND DC UPS SYSTEM | BORRI SPA | CHG4303N1_CHG4309N1 | DBX15025 | 176-P-SLD-40206-001 | SINGLE LINE DIAGRAM 110V DC UPS CHG4303N1_CHG4309N1 33KV MAIN SUBSTATION 392SSTR01 | A4108 | AX | 1 | 2019-06-10 | CON-BMP-VTRA-012134 | 2019-06-10 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-1671-001 | MATERIAL REQUISITION FOR AC AND DC UPS SYSTEM | BORRI SPA | CHG4303N1_CHG4309N1 | DBX15026 | 176-P-GAD-40314-001 | GENERAL ARRANGEMENT 110V DC UPS CHG4303N1_CHG4309N1 3 SUPHUR PLANT WEST SUBSTATION 036SSTR01 | A4201 | AX | 1 | 2019-06-10 | CON-BMP-VTRA-012129 | 2019-06-26 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-1671-001 | MATERIAL REQUISITION FOR AC AND DC UPS SYSTEM | BORRI SPA | CHG4303N1_CHG4309N1 | DBX15027 | 176-P-GAD-40315-001 | BATTERY GAD FOR DC UPS 110V DCUPS CHG4303N1_CHG4309N1 33KV MAIN SUBSTATION 392SSTR01 | A4224 | AX | 2 | 2019-06-06 | CON-BMP-VTRA-012066 | 2019-06-06 | FOR BAPCO REVIEW | 2019-06-21 | 2019-06-17 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000987 | CLASS 2
076551C-000R-MR-1671-001 | MATERIAL REQUISITION FOR AC AND DC UPS SYSTEM | BORRI SPA | CHG4303N1_CHG4309N1 | MCX15030 | 176-P-CAL-40001-001 | BATTERY SIZING CALCULATION AC AND DC UPS SYSTEM CHG4303N1_CHG4309N1 | A4223 | AX | 2 | 2019-06-06 | CON-BMP-VTRA-012070 | 2019-06-06 | FOR BAPCO REVIEW | 2019-06-21 | 2019-06-18 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000972 | CLASS 2
076551C-000R-MR-1671-001 | MATERIAL REQUISITION FOR AC AND DC UPS SYSTEM | BORRI SPA | CHG4405N1_CHG4407N1 | DBX15041 | 056-P-SLD-40511-001 | SINGLE LINE DIAGRAM 110V DC UPS CHG4405N1_CHG4407N1 33KV MAIN SUBSTATION 392SSTR01 | A4108 | AX | 1 | 2019-06-10 | CON-BMP-VTRA-012133 | 2019-06-10 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-1671-001 | MATERIAL REQUISITION FOR AC AND DC UPS SYSTEM | BORRI SPA | CHG4405N1_CHG4407N1 | DBX15042 | 056-P-GAD-40415-001 | GENERAL ARRANGEMENT 110V DC UPS CHG4405N1_CHG4407N1 3 SUPHUR PLANT WEST SUBSTATION 036SSTR01 | A4201 | AX | 1 | 2019-06-10 | CON-BMP-VTRA-012126 | 2019-06-10 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-1671-001 | MATERIAL REQUISITION FOR AC AND DC UPS SYSTEM | BORRI SPA | CHG4405N1_CHG4407N1 | DBX15043 | 056-P-GAD-40416-001 | BATTERY GAD FOR DC UPS 110V DCUPS CHG4405N1_CHG4407N1 33KV MAIN SUBSTATION 392SSTR01 | A4224 | AX | 2 | 2019-06-06 | CON-BMP-VTRA-012066 | 2019-06-06 | FOR BAPCO REVIEW | 2019-06-21 | 2019-06-17 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000987 | CLASS 2
076551C-000R-MR-1671-001 | MATERIAL REQUISITION FOR AC AND DC UPS SYSTEM | BORRI SPA | CHG4405N1_CHG4407N1 | MCX15046 | 056-P-CAL-40001-001 | BATTERY SIZING CALCULATION AC AND DC UPS SYSTEM CHG4405N1_CHG4407N1 | A4223 | AX | 2 | 2019-06-06 | CON-BMP-VTRA-012070 | 2019-06-06 | FOR BAPCO REVIEW | 2019-06-21 | 2019-06-18 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000972 | CLASS 2
076551C-000R-MR-1671-001 | MATERIAL REQUISITION FOR AC AND DC UPS SYSTEM | BORRI SPA | CHG4505N1_CHG4507N1 | DBX15049 | 051-P-SLD-40206-001 | SINGLE LINE DIAGRAM 110V DC UPS CHG4505N1_CHG4507N1 33KV MAIN SUBSTATION 392SSTR01 | A4108 | AX | 1 | 2019-06-10 | CON-BMP-VTRA-012132 | 2019-06-10 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-1671-001 | MATERIAL REQUISITION FOR AC AND DC UPS SYSTEM | BORRI SPA | CHG4505N1_CHG4507N1 | DBX15050 | 051-P-GAD-40425-001 | GENERAL ARRANGEMENT 110V DC UPS CHG4505N1_CHG4507N1 3 SUPHUR PLANT WEST SUBSTATION 036SSTR01 | A4201 | AX | 1 | 2019-06-10 | CON-BMP-VTRA-012125 | 2019-06-10 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-1671-001 | MATERIAL REQUISITION FOR AC AND DC UPS SYSTEM | BORRI SPA | CHG4505N1_CHG4507N1 | DBX15051 | 051-P-GAD-40426-001 | BATTERY GAD FOR DC UPS 110V DCUPS CHG4505N1_CHG4507N1 33KV MAIN SUBSTATION 392SSTR01 | A4224 | AX | 2 | 2019-06-06 | CON-BMP-VTRA-012066 | 2019-06-06 | FOR BAPCO REVIEW | 2019-06-21 | 2019-06-17 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000987 | CLASS 2
076551C-000R-MR-1671-001 | MATERIAL REQUISITION FOR AC AND DC UPS SYSTEM | BORRI SPA | CHG4505N1_CHG4507N1 | MCX15054 | 051-P-CAL-40001-001 | BATTERY SIZING CALCULATION AC AND DC UPS SYSTEM CHG4505N1_CHG4507N1 | A4223 | AX | 2 | 2019-06-06 | CON-BMP-VTRA-012070 | 2019-06-06 | FOR BAPCO REVIEW | 2019-06-21 | 2019-06-18 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000972 | CLASS 2
076551C-000R-MR-1671-001 | MATERIAL REQUISITION FOR AC AND DC UPS SYSTEM | BORRI SPA | CHG4605N1_CHG4610N1 | DBX15017 | 934-P-SLD-40108-001 | SINGLE LINE DIAGRAM 110V DC UPS CHG4605N1_CHG4610N1 33KV MAIN SUBSTATION 392SSTR01 | A4108 | AX | 1 | 2019-06-10 | CON-BMP-VTRA-012137 | 2019-06-10 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-1671-001 | MATERIAL REQUISITION FOR AC AND DC UPS SYSTEM | BORRI SPA | CHG4605N1_CHG4610N1 | DBX15018 | 934-P-GAD-40425-001 | GENERAL ARRANGEMENT 110V DC UPS CHG4605N1_CHG4610N1 3 SUPHUR PLANT WEST SUBSTATION 036SSTR01 | A4201 | AX | 1 | 2019-06-10 | CON-BMP-VTRA-012127 | 2019-06-10 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-1671-001 | MATERIAL REQUISITION FOR AC AND DC UPS SYSTEM | BORRI SPA | CHG4605N1_CHG4610N1 | DBX15019 | 934-P-GAD-40426-001 | BATTERY GAD FOR DC UPS 110V DCUPS CHG4605N1_CHG4610N1 33KV MAIN SUBSTATION 392SSTR01 | A4224 | AX | 2 | 2019-06-06 | CON-BMP-VTRA-012066 | 2019-06-06 | FOR BAPCO REVIEW | 2019-06-21 | 2019-06-17 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000987 | CLASS 2
076551C-000R-MR-1671-001 | MATERIAL REQUISITION FOR AC AND DC UPS SYSTEM | BORRI SPA | CHG4605N1_CHG4610N1 | MCX15022 | 934-P-CAL-40001-001 | BATTERY SIZING CALCULATION AC AND DC UPS SYSTEM CHG4605N1_CHG4610N1 | A4223 | AX | 2 | 2019-06-06 | CON-BMP-VTRA-012070 | 2019-06-06 | FOR BAPCO REVIEW | 2019-06-21 | 2019-06-18 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000972 | CLASS 2
076551C-000R-MR-1671-001 | MATERIAL REQUISITION FOR AC AND DC UPS SYSTEM | BORRI SPA | CHG4613N1_CHG4615N1 | DBX15033 | 180-P-SLD-40205-001 | SINGLE LINE DIAGRAM 110V DC UPS CHG4613N1_CHG4615N1 33KV MAIN SUBSTATION 392SSTR01 | A4108 | AX | 1 | 2019-06-10 | CON-BMP-VTRA-012135 | 2019-06-10 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-1671-001 | MATERIAL REQUISITION FOR AC AND DC UPS SYSTEM | BORRI SPA | CHG4613N1_CHG4615N1 | DBX15034 | 180-P-GAD-40328-001 | GENERAL ARRANGEMENT 110-DC-UPS CHG4613N1_CHG4615N1 | A4201 | AX | 1 | 2019-06-27 | CON-BMP-VTRA-012524 | 2019-06-27 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-1671-001 | MATERIAL REQUISITION FOR AC AND DC UPS SYSTEM | BORRI SPA | CHG4613N1_CHG4615N1 | DBX15035 | 180-P-GAD-40314-001 | BATTERY GAD FOR DC UPS 110V DCUPS CHG4613N1_CHG4615N1 33KV MAIN SUBSTATION 392SSTR01 | A4224 | AX | 2 | 2019-06-06 | CON-BMP-VTRA-012066 | 2019-06-06 | FOR BAPCO REVIEW | 2019-06-21 | 2019-06-17 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000987 | CLASS 2
076551C-000R-MR-1671-001 | MATERIAL REQUISITION FOR AC AND DC UPS SYSTEM | BORRI SPA | CHG4613N1_CHG4615N1 | MCX15038 | 180-P-CAL-40001-001 | BATTERY SIZING CALCULATION AC AND DC UPS SYSTEM CHG4613N1_CHG4615N1 | A4223 | AX | 2 | 2019-06-06 | CON-BMP-VTRA-012070 | 2019-06-06 | FOR BAPCO REVIEW | 2019-06-21 | 2019-06-18 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000972 | CLASS 2
076551C-000R-MR-1800-001 | MATERIAL REQUISITION FOR STEEL STRUCTURES | A.I.C. | 018PR201 | 000-M-SCH-40004-001 | 000-M-SCH-40004-001 | MANUFACTURING SCHEDULE ALL ITEMS | C1001 | AX | 2 | 2019-05-06 | CON-BMP-VTRA-011420 | 2019-05-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-1800-001 | MATERIAL REQUISITION FOR STEEL STRUCTURES | A.I.C. | 018PR201 | A0001 MR1800001 | 000-M-INX-40001-001 | LIST OF VENDOR¿S DOCUMENTS AND DRAWINGS ALL ITEMS | A0001 | AX | 2 | 2019-06-01 | CON-BMP-VTRA-011928 | 2019-06-01 | FOR BAPCO REVIEW | 2019-06-17 | 2019-06-18 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000989 | CLASS 2
076551C-000R-MR-1800-001 | MATERIAL REQUISITION FOR STEEL STRUCTURES | A.I.C. | 018PR201 | AIC-ITP-1907 | 000-M-ITP-40001-001 | INSPECTION & TEST PLAN ALL ITEMS | B1002 | 0X | 3 | 2019-06-04 | CON-BMP-VTRA-011974 | 2019-06-04 | FOR BAPCO REVIEW | 2019-06-19 | 2019-07-04 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001166 | CLASS 2
076551C-000R-MR-1800-001 | MATERIAL REQUISITION FOR STEEL STRUCTURES | A.I.C. | 018PR201 | AIC-MPR-001 | 000-M-MRS-40001-001 | MONTHLY PROGRESS REPORT ALL ITEMS | C1002 | AX | 1 | 2019-06-01 | CON-BMP-VTRA-011924 | 2019-06-01 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-1800-001 | MATERIAL REQUISITION FOR STEEL STRUCTURES | A.I.C. | 018PR201 | AIC-NDE-1907 | 000-M-PRO-40001-001 | NDE PROCEDURES FOR STEEL STRUCTURES ALL ITEMS | B1202 | BX | 2 | 2019-06-01 | CON-BMP-VTRA-011932 | 2019-06-01 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-1800-001 | MATERIAL REQUISITION FOR STEEL STRUCTURES | A.I.C. | 018PR201 | AIC-QCP-1907-01 | 000-M-PQP-40001-001 | QUALITY CONTROL PLAN ALL ITEMS | B1002 | BX | 2 | 2019-06-03 | CON-BMP-VTRA-011937 | 2019-06-03 | FOR BAPCO REVIEW | 2019-06-18 | 2019-06-12 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000917 | CLASS 2
076551C-000R-MR-1800-001 | MATERIAL REQUISITION FOR STEEL STRUCTURES | A.I.C. | 018PR201 | AIC-QCP-1907-05 | 000-M-TSP-40001-001 | PAINTING SPECIFICATION FOR STEEL STRUCTURES ALL ITEMS | A0106 | BX | 2 | 2019-06-01 | CON-BMP-VTRA-011931 | 2019-06-01 | FOR BAPCO REVIEW | 2019-06-17 | 2019-06-11 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000905 | CLASS 2
076551C-000R-MR-1800-001 | MATERIAL REQUISITION FOR STEEL STRUCTURES | A.I.C. | 018PR201 | SUB-VENDORS LIST MR1800001 | 000-M-PQS-40001-001 | SUB-VENDORS LIST ALL ITEMS | B1401 | 0X | 3 | 2019-06-04 | CON-BMP-VTRA-011975 | 2019-06-04 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-1800-001 | MATERIAL REQUISITION FOR STEEL STRUCTURES | A.I.C. | 018PR201 | WPA-PQR-1907 | 000-M-MCD-40001-001 | WELDING BOOK STEEL STRUCTURES ALL ITEMS | B1304 | BX | 2 | 2019-06-01 | CON-BMP-VTRA-011933 | 2019-06-01 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-1800-001 | MATERIAL REQUISITION FOR STEEL STRUCTURES | A.I.C. | 930PR106 | 1907063-CALCULATION | 930-M-CAL-40013-001 | STRUCTURAL STEEL CALCULATION NOTE FOR 930PR106 | A2201 | AX | 2 | 2019-07-05 | CON-BMP-VTRA-012699 | 2019-07-05 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-1800-001 | MATERIAL REQUISITION FOR STEEL STRUCTURES | A.I.C. | 930PR108 | 1907067-CALCULATION | 930-M-CAL-40015-001 | STRUCTURAL STEEL CALCULATION NOTE FOR 930PR108 | A2201 | AX | 2 | 2019-07-05 | CON-BMP-VTRA-012699 | 2019-07-05 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-1800-001 | MATERIAL REQUISITION FOR STEEL STRUCTURES | A.I.C. | 930PR109 | 1907069-CALCULATION | 930-M-CAL-40016-001 | STRUCTURAL STEEL CALCULATION NOTE FOR 930PR109 | A2201 | AX | 1 | 2019-07-05 | CON-BMP-VTRA-012698 | 2019-07-05 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-1800-001 | MATERIAL REQUISITION FOR STEEL STRUCTURES | A.I.C. | 930PR111 | 1907073-CALCULATION | 930-M-CAL-40018-001 | STRUCTURAL STEEL CALCULATION NOTE FOR 930PR111 | A2201 | AX | 2 | 2019-07-05 | CON-BMP-VTRA-012699 | 2019-07-05 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-1800-001 | MATERIAL REQUISITION FOR STEEL STRUCTURES | A.I.C. | 930PR201 | 1907019-CALCULATION | 930-M-CAL-40020-001 | STRUCTURAL STEEL CALCULATION NOTE FOR 930PR201 | A2201 | AX | 1 | 2019-07-05 | CON-BMP-VTRA-012698 | 2019-07-05 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-1800-001 | MATERIAL REQUISITION FOR STEEL STRUCTURES | A.I.C. | 930PR202 | 1907021-CALCULATION | 930-M-CAL-40021-001 | STRUCTURAL STEEL CALCULATION NOTE FOR 930PR202 | A2201 | AX | 2 | 2019-07-05 | CON-BMP-VTRA-012699 | 2019-07-05 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-1800-001 | MATERIAL REQUISITION FOR STEEL STRUCTURES | A.I.C. | 930PR203 | 1907023-CALCULATION | 930-M-CAL-40022-001 | STRUCTURAL STEEL CALCULATION NOTE FOR 930PR203 | A2201 | AX | 2 | 2019-07-05 | CON-BMP-VTRA-012699 | 2019-07-05 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-1800-001 | MATERIAL REQUISITION FOR STEEL STRUCTURES | A.I.C. | 930PR204 | 1907025-CALCULATION | 930-M-CAL-40023-001 | STRUCTURAL STEEL CALCULATION NOTE FOR 930PR204 | A2201 | AX | 2 | 2019-07-05 | CON-BMP-VTRA-012699 | 2019-07-05 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-1800-001 | MATERIAL REQUISITION FOR STEEL STRUCTURES | A.I.C. | 930PR205 | 1907027-CALCULATION | 930-M-CAL-40024-001 | STRUCTURAL STEEL CALCULATION NOTE FOR 930PR205 | A2201 | AX | 2 | 2019-07-05 | CON-BMP-VTRA-012699 | 2019-07-05 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-1800-001 | MATERIAL REQUISITION FOR STEEL STRUCTURES | A.I.C. | 930PR206 | 1907029-CALCULATION | 930-M-CAL-40025-001 | STRUCTURAL STEEL CALCULATION NOTE FOR 930PR206 | A2201 | AX | 2 | 2019-07-05 | CON-BMP-VTRA-012699 | 2019-07-05 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-1800-001 | MATERIAL REQUISITION FOR STEEL STRUCTURES | A.I.C. | 930PR213 | 1907043-CALCULATION | 930-M-CAL-40032-001 | STRUCTURAL STEEL CALCULATION NOTE FOR 930PR213 | A2201 | AX | 2 | 2019-07-05 | CON-BMP-VTRA-012699 | 2019-07-05 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-1800-101 | MATERIAL REQUISITION FOR STEEL STRUCTURES | AL SHAFAR STEEL ENGINEERING LLC | 018IS000 | PR-2019-05-001 | 018-M-INX-40001-001 | LIST OF VENDOR DOCUMENTS AND DWGS ALL ITEMS | A0001 | AX | 2 | 2019-04-12 | CON-BMP-VTRA-011157 | 2019-04-12 | FOR BAPCO REVIEW | 2019-04-29 | 2019-05-09 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000646 | CLASS 2
076551C-000R-MR-1800-101 | MATERIAL REQUISITION FOR STEEL STRUCTURES | AL SHAFAR STEEL ENGINEERING LLC | 018IS000 | PR-2019-05-002 | 018-M-ITP-40001-001 | INSPECTION AND TEST PLAN ALL ITEMS | B1002 | BX | 2 | 2019-05-30 | CON-BMP-VTRA-011849 | 2019-05-30 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-1800-101 | MATERIAL REQUISITION FOR STEEL STRUCTURES | AL SHAFAR STEEL ENGINEERING LLC | 018IS000 | PR-2019-05-004 | 018-M-PRO-40001-001 | NDE PROCEDURES ALL ITEMS | B1202 | AX | 2 | 2019-04-04 | CON-BMP-VTRA-011009 | 2019-04-04 | FOR BAPCO REVIEW | 2019-04-19 | 2019-04-16 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000531 | CLASS 2
076551C-000R-MR-1800-101 | MATERIAL REQUISITION FOR STEEL STRUCTURES | AL SHAFAR STEEL ENGINEERING LLC | 018IS000 | PR-2019-05-005 | 018-M-PQP-40001-001 | PROJECT QUALITY PLAN ALL ITEMS | B1002 | 0X | 3 | 2019-06-29 | CON-BMP-VTRA-012571 | 2019-06-29 | FOR BAPCO REVIEW | 2019-07-15 |  |  | CLASS 2
076551C-000R-MR-1800-101 | MATERIAL REQUISITION FOR STEEL STRUCTURES | AL SHAFAR STEEL ENGINEERING LLC | 018IS000 | PR-2019-05-007 | 018-M-TSP-40001-001 | PAINTING SPECIFICATION ALL ITEMES | A0106 | BX | 2 | 2019-06-01 | CON-BMP-VTRA-011930 | 2019-06-01 | FOR BAPCO REVIEW | 2019-06-17 | 2019-06-11 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000908 | CLASS 2
076551C-000R-MR-1800-101 | MATERIAL REQUISITION FOR STEEL STRUCTURES | AL SHAFAR STEEL ENGINEERING LLC | 018IS000 | PR-2019-05-008 | 018-M-PQS-40001-001 | SUB VENDOR QUALIFICATION ALL ITEMS | B1401 | AX | 2 | 2019-04-03 | CON-BMP-VTRA-010975 | 2019-04-03 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-1800-101 | MATERIAL REQUISITION FOR STEEL STRUCTURES | AL SHAFAR STEEL ENGINEERING LLC | 018IS000 | PR-2019-05-009 | 018-M-INX-40002-001 | INDEX FOR VENDOR DATA BOOK FORSTEEL STRUCTURES ALL ITEMS | A0403 | AX | 2 | 2019-06-21 | CON-BMP-VTRA-012369 | 2019-06-21 | FOR BAPCO REVIEW | 2019-07-08 | 2019-07-11 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-001300 | CLASS 2
076551C-000R-MR-1800-101 | MATERIAL REQUISITION FOR STEEL STRUCTURES | AL SHAFAR STEEL ENGINEERING LLC | 018IS000 | PR-2019-05-010 | 018-M-SCH-40001-001 | MANUFACTURING SCHEDULE FOR STEEL STRUCTURES OF 000-M-MRQ-60002-001 ALL ITEMS | C1001 | AX | 2 | 2019-05-24 | CON-BMP-VTRA-011800 | 2019-05-24 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-1800-101 | MATERIAL REQUISITION FOR STEEL STRUCTURES | AL SHAFAR STEEL ENGINEERING LLC | 018IS000 | PR-2019-05-011 | 018-M-MRS-40001-001 | MONTHLY PROGRESS REPORT ASSENT ALL ITEMS | C1002 | AX | 2 | 2019-06-05 | CON-BMP-VTRA-011991 | 2019-06-05 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-1800-101 | MATERIAL REQUISITION FOR STEEL STRUCTURES | AL SHAFAR STEEL ENGINEERING LLC | 018IS000 | PR-2019-05-QC0003 | 018-M-MCD-40001-001 | WELDING BOOK (WPS/PQR QUALIFICATION REPORT) ALL ITEMS | B1304 | AX | 2 | 2019-04-04 | CON-BMP-VTRA-011008 | 2019-04-04 | FOR BAPCO REVIEW | 2019-04-19 | 2019-04-16 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000527 | CLASS 2
076551C-000R-MR-2520-001 | MATERIAL REQUISITION FOR STORAGE TANKS | NASS INDUSTRIAL SERVICES | 050D0504 | J681-NIS-PRJ-DOC-001 | 000-D-INX-40001-001 | LIST OF VENDOR'S DOCUMENTS ANDDWGS FOR STORAGE TANKS ALL ITEMS | A0001 | AX | 1 | 2019-07-09 | CON-BMP-VTRA-012776 | 2019-07-09 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-2550-001 | MATERIAL REQUISITION FOR REFRIGERATED STORAGE TANKS | PARESA SpA | 051D0001 | ELE-UTE-19-132-001 | 051-D-INX-40001-001 | LIST OF VENDOR'S DOCUMENTS ANDDRAWINGS FOR REFRIGERATED STORAGE TANKS 051D0001 051D0002 051D0003 | A0001 | AX | 2 | 2019-07-09 | CON-BMP-VTRA-012777 | 2019-07-09 | FOR BAPCO REVIEW | 2019-07-24 |  |  | CLASS 2
076551C-000R-MR-4046-001 | MATERIAL REQUISITION FOR DOSING SYSTEM | LEWA NIKKISO ITALY S.R.L. | 018M0034A | LLI2-18807-105 | 000-S-MRS-40001-001 | MONTHLY PROGRESS REPORT FOR DOSING SYSTEM ALL ITEMS | C1002 | AX | 1 | 2019-07-10 | CON-BMP-VTRA-012787 | 2019-07-10 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-4111-001 | MATERIAL REQUISITION FOR MEMBRANE UNIT | AIR PRODUCT AS | 018U1001 | 60434-0402-001 | 018-S-INX-40001-001 | DOCUMENT LIST ALL ITEMS (EX BABCO N.018-S-INX-00001-001) | A0001 | BX | 3 | 2019-01-30 | CON-BMP-VTRA-010334 | 2019-01-30 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-4111-001 | MATERIAL REQUISITION FOR MEMBRANE UNIT | AIR PRODUCT AS | 018U1001 | 60434-0506-001 | 018-S-SCH-40001-001 | ENGINEERING PROCUREMENT AND FABRICATION SCHEDULE ALL ITEMS | C1001 | BX | 2 | 2019-06-21 | CON-BMP-VTRA-012352 | 2019-06-21 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-4111-001 | MATERIAL REQUISITION FOR MEMBRANE UNIT | AIR PRODUCT AS | 018U1001 | 60434-0506-101 | 018-S-MRS-40001-001 | MONTHLY PROGRESS REPORT 018U1001 018U2001 | C1002 | DX | 2 | 2019-06-21 | CON-BMP-VTRA-012353 | 2019-06-21 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-4111-001 | MATERIAL REQUISITION FOR MEMBRANE UNIT | AIR PRODUCT AS | 018U1001 | 60434-0507-001 | 018-S-PQP-40001-001 | QUALITY PLAN (ITP) 018U1001 018U2001 | B1002 | BX | 3 | 2019-01-30 | CON-BMP-VTRA-010333 | 2019-01-30 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-4111-001 | MATERIAL REQUISITION FOR MEMBRANE UNIT | AIR PRODUCT AS | 018U1001 | 60434-0532-001 | 018-S-TSP-40003-001 | INSULATION SPECIFICATION 018U1001 | A0107 | 0X | 2 | 2019-06-26 | CON-BMP-VTRA-012467 | 2019-06-26 | FOR BAPCO REVIEW | 2019-07-10 |  |  | CLASS 2
076551C-000R-MR-4111-001 | MATERIAL REQUISITION FOR MEMBRANE UNIT | AIR PRODUCT AS | 018U1001 | 60434-0602-110 | 018-S-MCD-40003-001 | PROCESS DATA SHEET CONTROL VALVE | A3006 | AX | 2 | 2019-06-19 | CON-BMP-VTRA-012302 | 2019-06-19 | FOR BAPCO REVIEW | 2019-07-03 | 2019-07-09 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001257 | CLASS 2
076551C-000R-MR-4111-001 | MATERIAL REQUISITION FOR MEMBRANE UNIT | AIR PRODUCT AS | 018U1001 | 60434-0602-120 | 018-S-MCD-40005-001 | PROCESS DATA SHEET ON-OFF VALVE | A3006 | AX | 2 | 2019-06-19 | CON-BMP-VTRA-012302 | 2019-06-19 | FOR BAPCO REVIEW | 2019-07-03 | 2019-07-09 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001257 | CLASS 2
076551C-000R-MR-4111-001 | MATERIAL REQUISITION FOR MEMBRANE UNIT | AIR PRODUCT AS | 018U1001 | 60434-0602-130 | 018-S-MCD-40007-001 | PROCESS DATA SHEET RELIEF VALVE | A3006 | AX | 2 | 2019-06-19 | CON-BMP-VTRA-012302 | 2019-06-19 | FOR BAPCO REVIEW | 2019-07-03 | 2019-07-09 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001257 | CLASS 2
076551C-000R-MR-4111-001 | MATERIAL REQUISITION FOR MEMBRANE UNIT | AIR PRODUCT AS | 018U1001 | 60434-0602-141 | 018-S-MCD-40009-001 | DATA SHEET RESTRICTION ORIFICE | A3006 | AX | 2 | 2019-06-19 | CON-BMP-VTRA-012302 | 2019-06-19 | FOR BAPCO REVIEW | 2019-07-03 | 2019-07-09 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001257 | CLASS 2
076551C-000R-MR-4111-001 | MATERIAL REQUISITION FOR MEMBRANE UNIT | AIR PRODUCT AS | 018U1001 | 60434-0602-142 | 018-S-MCD-40011-001 | DATA SHEET FLOW ELEMENT | A3006 | AX | 2 | 2019-06-19 | CON-BMP-VTRA-012302 | 2019-06-19 | FOR BAPCO REVIEW | 2019-07-03 | 2019-07-09 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001257 | CLASS 2
076551C-000R-MR-4111-001 | MATERIAL REQUISITION FOR MEMBRANE UNIT | AIR PRODUCT AS | 018U1001 | 60434-0602-301 | 018-S-DAT-40008-001 | PROCESS DATA SHEET- PRISM SEPARATOR ALL ITEMS | A1001 | BX | 2 | 2019-05-06 | CON-BMP-VTRA-011406 | 2019-05-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-4111-001 | MATERIAL REQUISITION FOR MEMBRANE UNIT | AIR PRODUCT AS | 018U1001 | 60434-0603-001 | 018-S-CAL-40005-001 | RELIEF VALVE CALCULATION 018U1001 | A0109 | AX | 2 | 2019-06-19 | CON-BMP-VTRA-012304 | 2019-06-19 | FOR BAPCO REVIEW | 2019-07-03 | 2019-07-09 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001249 | CLASS 2
076551C-000R-MR-4111-001 | MATERIAL REQUISITION FOR MEMBRANE UNIT | AIR PRODUCT AS | 018U1001 | 60434-0603-701 | 018-S-CAL-40003-001 | MECHANICAL CALCULATION STRUCTURAL STEEL 018U10011 | A2201 | AX | 2 | 2019-05-08 | CON-BMP-VTRA-011496 | 2019-05-08 | FOR BAPCO REVIEW | 2019-05-23 | 2019-05-29 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000828 | CLASS 2
076551C-000R-MR-4111-001 | MATERIAL REQUISITION FOR MEMBRANE UNIT | AIR PRODUCT AS | 018U1001 | 60434-0603-801 | 018-S-CAL-40001-001 | MECHANICAL CALCULATION- PRISM SEPARATOR VESSEL 018U1001 | A1003 | BX | 2 | 2019-05-16 | CON-BMP-VTRA-011624 | 2019-05-16 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-4111-001 | MATERIAL REQUISITION FOR MEMBRANE UNIT | AIR PRODUCT AS | 018U1001 | 60434-0604-001 | 018-S-PFD-40001-001 | PROCESS FLOW DIAGRAM 018U1001 (EX BAPCO N.018-S-PFD-00001-001) | A0102 | BX | 2 | 2019-05-06 | CON-BMP-VTRA-011410 | 2019-05-06 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-4111-001 | MATERIAL REQUISITION FOR MEMBRANE UNIT | AIR PRODUCT AS | 018U1001 | 60434-0605-001 | 018-S-PID-40001-001 | PIPING & INSTRUMENT DIAGRAM 018U1001 (EX BAPCO N.018-S-PID- 00001-001) | A0103 | BX | 2 | 2019-05-06 | CON-BMP-VTRA-011417 | 2019-05-06 | FOR BAPCO REVIEW | 2019-05-20 | 2019-05-31 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000861 | CLASS 2
076551C-000R-MR-4111-001 | MATERIAL REQUISITION FOR MEMBRANE UNIT | AIR PRODUCT AS | 018U1001 | 60434-0606-001 | 018-S-DAT-40010-001 | UTILITY CONSUMPTION LIST 018U1001 | A3301 | AX | 2 | 2019-05-08 | CON-BMP-VTRA-011494 | 2019-05-08 | FOR BAPCO REVIEW | 2019-05-23 | 2019-05-31 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000853 | CLASS 2
076551C-000R-MR-4111-001 | MATERIAL REQUISITION FOR MEMBRANE UNIT | AIR PRODUCT AS | 018U1001 | 60434-0608-010 | 018-S-GAD-40009-001 | GENERAL ARRANGEMENT DRAWINGS ALL ITEMS | A2001 | BX | 2 | 2019-06-21 | CON-BMP-VTRA-012349 | 2019-06-21 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-4111-001 | MATERIAL REQUISITION FOR MEMBRANE UNIT | AIR PRODUCT AS | 018U1001 | 60434-0608-090 | 018-S-GAD-40005-001 | GENERAL ARRANGEMENT DRAWING PRISM SEPARATOR ASSEMBLY 018U1001 | A1103 | BX | 2 | 2019-03-12 | CON-BMP-VTRA-010661 | 2019-03-12 | FOR BAPCO REVIEW | 2019-03-27 | 2019-03-27 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000396 | CLASS 2
076551C-000R-MR-4111-001 | MATERIAL REQUISITION FOR MEMBRANE UNIT | AIR PRODUCT AS | 018U1001 | 60434-0609-001 | 018-S-PED-40001-001 | FOUNDATION LOAD DETAILS AND CALCULATION 018U1001 | A2006 | CX | 2 | 2019-03-29 | CON-BMP-VTRA-010915 | 2019-03-29 | FOR BAPCO REVIEW | 2019-04-15 | 2019-04-16 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000526 | CLASS 2
076551C-000R-MR-4111-001 | MATERIAL REQUISITION FOR MEMBRANE UNIT | AIR PRODUCT AS | 018U1001 | 60434-0610-001 | 018-S-GAD-40007-001 | TIE IN SCHEDULE 018U1001 | A2001 | AX | 2 | 2019-05-08 | CON-BMP-VTRA-011492 | 2019-05-08 | FOR BAPCO REVIEW | 2019-05-23 | 2019-05-27 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000809 | CLASS 2
076551C-000R-MR-4111-001 | MATERIAL REQUISITION FOR MEMBRANE UNIT | AIR PRODUCT AS | 018U1001 | 60434-0612-001 | 018-S-MCD-40015-001 | WIRING DIAGRAM (INTERCONNECTION DIAGRAM) 018U1001 | A3007 | AX | 2 | 2019-06-21 | CON-BMP-VTRA-012348 | 2019-06-21 | FOR BAPCO INFORMATION | 2019-07-05 |  |  | CLASS 2
076551C-000R-MR-4111-001 | MATERIAL REQUISITION FOR MEMBRANE UNIT | AIR PRODUCT AS | 018U1001 | 60434-0615-001 | 018-S-MCD-40013-001 | INSTRUMENT HOOK-UP DRAWINGS 018U1001 | A3006 | AX | 2 | 2019-05-02 | CON-BMP-VTRA-011337 | 2019-05-02 | FOR BAPCO REVIEW | 2019-05-16 | 2019-05-18 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000697 | CLASS 2
076551C-000R-MR-4111-001 | MATERIAL REQUISITION FOR MEMBRANE UNIT | AIR PRODUCT AS | 018U1001 | 60434-0616-001 | 018-S-MCD-40017-001 | ALARM AND INTERLOCK SET POINT LIST 018U1001 | A3008 | AX | 2 | 2019-06-19 | CON-BMP-VTRA-012303 | 2019-06-19 | FOR BAPCO REVIEW | 2019-07-03 |  |  | CLASS 2
076551C-000R-MR-4111-001 | MATERIAL REQUISITION FOR MEMBRANE UNIT | AIR PRODUCT AS | 018U1001 | 60434-0616-101 | 018-S-MTX-40002-001 | INTERLOCK LOGIC DIAGRAM 018U1001 | A3505 | AX | 2 | 2019-02-14 | CON-BMP-VTRA-010442 | 2019-02-14 | FOR BAPCO REVIEW | 2019-03-01 | 2019-03-06 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000257 | CLASS 2
076551C-000R-MR-4111-001 | MATERIAL REQUISITION FOR MEMBRANE UNIT | AIR PRODUCT AS | 018U1001 | 60434-0619-001 | 018-S-PRD-40001-001 | PROCESS AND INTERLOCK DESCRIPTION 018U1001 | A0101 | AX | 1 | 2019-02-12 | CON-BMP-VTRA-010397 | 2019-02-12 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-4111-001 | MATERIAL REQUISITION FOR MEMBRANE UNIT | AIR PRODUCT AS | 018U1001 | 60434-0902-010 | 018-S-TSP-40001-001 | SURFACE TREATMENT & PAINT PROCEDURE 018U1001 | A0106 | BX | 2 | 2019-05-08 | CON-BMP-VTRA-011491 | 2019-05-08 | FOR BAPCO REVIEW | 2019-05-23 | 2019-05-19 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000710 | CLASS 2
076551C-000R-MR-4111-001 | MATERIAL REQUISITION FOR MEMBRANE UNIT | AIR PRODUCT AS | 018U1001 | 60434-0902-230 | 018-S-MCD-40025-001 | WPS AND PQR - PRISM SEPARATOR VESSEL (INCL WELDING BOOK) 018U1001 | B1304 | 0X | 2 | 2019-06-26 | CON-BMP-VTRA-012466 | 2019-06-26 | FOR BAPCO REVIEW | 2019-07-10 | 2019-07-09 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001280 | CLASS 2
076551C-000R-MR-4111-001 | MATERIAL REQUISITION FOR MEMBRANE UNIT | AIR PRODUCT AS | 018U1001 | 60434-0902-320 | 018-S-PRO-40011-001 | NDE PROCEDURE 018U1001 | B1202 | AX | 2 | 2019-03-12 | CON-BMP-VTRA-010662 | 2019-03-12 | FOR BAPCO REVIEW | 2019-03-27 | 2019-03-25 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000374 | CLASS 2
076551C-000R-MR-4111-001 | MATERIAL REQUISITION FOR MEMBRANE UNIT | AIR PRODUCT AS | 018U1001 | 60434-0902-350 | 018-S-PRO-40009-001 | HEAT TREATMENT PROCEDURE 018U1001 | B1201 | 0X | 2 | 2019-06-26 | CON-BMP-VTRA-012465 | 2019-06-26 | FOR BAPCO REVIEW | 2019-07-10 | 2019-07-11 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001292 | CLASS 2
076551C-000R-MR-4111-001 | MATERIAL REQUISITION FOR MEMBRANE UNIT | AIR PRODUCT AS | 018U1001 | 60434-0902-503 | 018-S-PRO-40005-001 | FACTORY ACCEPTANCE TEST PROCEDURE | B1104 | AX | 2 | 2019-06-20 | CON-BMP-VTRA-012330 | 2019-06-20 | FOR BAPCO REVIEW | 2019-07-04 | 2019-07-04 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001164 | CLASS 2
076551C-000R-MR-4111-001 | MATERIAL REQUISITION FOR MEMBRANE UNIT | AIR PRODUCT AS | 018U1001 | 60434-0902-504 | 018-S-PRO-40013-001 | PERFORMANCE TEST PROCEDURE 018U1001 | B1104 | AX | 2 | 2019-06-20 | CON-BMP-VTRA-012330 | 2019-06-20 | FOR BAPCO REVIEW | 2019-07-04 | 2019-07-04 | 1-APPROVED BMP-ROC-VTRE-001164 | CLASS 2
076551C-000R-MR-4111-001 | MATERIAL REQUISITION FOR MEMBRANE UNIT | AIR PRODUCT AS | 018U1001 | 60434-0902-540 | 018-S-PRO-40001-001 | HYDROSTATIC TEST PROCEDURE VESSELS 018U1001 | B1103 | BX | 2 | 2019-06-20 | CON-BMP-VTRA-012341 | 2019-06-20 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-4111-001 | MATERIAL REQUISITION FOR MEMBRANE UNIT | AIR PRODUCT AS | 018U1001 | 60434-0902-542 | 018-S-PRO-40003-001 | HYDROSTATIC TEST PROCEDURE PIPING 018U1001 | B1103 | AX | 2 | 2019-06-20 | CON-BMP-VTRA-012340 | 2019-06-20 | FOR BAPCO REVIEW | 2019-07-05 | 2019-07-04 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001163 | CLASS 2
076551C-000R-MR-4111-002 | MATERIAL REQUISITION FOR PSA | LINDE AG | 023U0001 | &AK A-LD 7100 (EN) | 023-S-INX-40001-001 | LIST OF VENDOR¿S DOCUMENTS AND DRAWINGS MATERIAL REQUISITION FOR VACUUM UNIT PACKAGE 023U0001 | A0001 | AXX | 2 | 2019-06-05 | CON-BMP-VTRA-012017 | 2019-06-05 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-4111-002 | MATERIAL REQUISITION FOR PSA | LINDE AG | 023U0001 | &AK A-RA 7001 (EN) | 023-S-MRS-40001-001 | MONTHLY PROGRESS REPORT 023U0001 | C1002 | BX | 4 | 2019-06-17 | CON-BMP-VTRA-012257 | 2019-06-17 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-4111-002 | MATERIAL REQUISITION FOR PSA | LINDE AG | 023U0001 | &AK C-ZB 7001 (EN) | 023-S-PED-40001-001 | FOUNDATION LOADING PLAN ROG-PSA UNIT 023U0001 | A2006 | BX | 2 | 2019-05-14 | CON-BMP-VTRA-011575 | 2019-05-14 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-4111-002 | MATERIAL REQUISITION FOR PSA | LINDE AG | 023U0001 | &AK E-CX 7650 (EN) | 023-S-GAD-40001-001 | ELECTRICAL HEAT TRACING: CALCULATION & DESIGN 023U0001 | A4203 | AX | 2 | 2019-05-06 | CON-BMP-VTRA-011403 | 2019-05-06 | FOR BAPCO REVIEW | 2019-05-20 | 2019-06-01 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000866 | CLASS 2
076551C-000R-MR-4111-002 | MATERIAL REQUISITION FOR PSA | LINDE AG | 023U0001 | &AK E-LB 7651 (EN) | 023-S-GAD-40002-001 | HEAT TRACING BILL OF MATERIAL 023U0001 | A4203 | AX | 2 | 2019-05-06 | CON-BMP-VTRA-011403 | 2019-05-06 | FOR BAPCO REVIEW | 2019-05-20 | 2019-06-01 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000866 | CLASS 2
076551C-000R-MR-4111-002 | MATERIAL REQUISITION FOR PSA | LINDE AG | 023U0001 | &AK J-CU 7240 (EN) | 023-S-RPT-40001-001 | UTILITIES CONSUMPTION LIST 023U0001 | A1014 | AX | 2 | 2019-04-03 | CON-BMP-VTRA-010984 | 2019-04-03 | FOR BAPCO REVIEW | 2019-04-18 | 2019-04-30 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000623 | CLASS 2
076551C-000R-MR-4111-002 | MATERIAL REQUISITION FOR PSA | LINDE AG | 023U0001 | &AK J-LB 7611 (EN) | 023-S-ILD-40002-001 | INSTRUMENT HOOK UP BILL OF MATERIAL PSA SKID 023U0001 | A3406 | AX | 2 | 2019-06-11 | CON-BMP-VTRA-012147 | 2019-06-11 | FOR BAPCO REVIEW | 2019-06-25 | 2019-06-26 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001036 | CLASS 2
076551C-000R-MR-4111-002 | MATERIAL REQUISITION FOR PSA | LINDE AG | 023U0001 | &AK J-LB 7631 (EN) | 023-S-CWD-40001-001 | JUNCTION BOX ASSEMBLY / BILL OF MATERIAL 023U0001 | A3403 | AX | 2 | 2019-06-11 | CON-BMP-VTRA-012145 | 2019-06-11 | FOR BAPCO REVIEW | 2019-06-25 | 2019-06-13 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000921 | CLASS 2
076551C-000R-MR-4111-002 | MATERIAL REQUISITION FOR PSA | LINDE AG | 023U0001 | &AK J-LC 7330 (EN) | 023-S-MCD-40019-001 | FIELD CABLING LIST 023U0001 | A3007 | AX | 2 | 2019-05-06 | CON-BMP-VTRA-011411 | 2019-05-06 | FOR BAPCO REVIEW | 2019-05-20 | 2019-05-26 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000785 | CLASS 2
076551C-000R-MR-4111-002 | MATERIAL REQUISITION FOR PSA | LINDE AG | 023U0001 | &AK J-LJ 7210 (EN) | 023-S-MCD-40020-001 | INSTRUMENT INDEX 023U0001 | A3006 | AX | 1 | 2019-06-11 | CON-BMP-VTRA-012142 | 2019-06-11 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-4111-002 | MATERIAL REQUISITION FOR PSA | LINDE AG | 023U0001 | &AK J-SD 7530 (EN) | 023-S-DAT-40004-001 | SPECIFICATION: INSTRUMENT AIR STATION 023U0001 | A3101 | AX | 2 | 2019-05-14 | CON-BMP-VTRA-011579 | 2019-05-14 | FOR BAPCO REVIEW | 2019-05-29 |  |  | CLASS 2
076551C-000R-MR-4111-002 | MATERIAL REQUISITION FOR PSA | LINDE AG | 023U0001 | &AK J-SD 7540 (EN) | 023-S-DAT-40005-001 | SPECIFICATION: SOLENOID VALVES 023U0001 | A3101 | AX | 2 | 2019-05-14 | CON-BMP-VTRA-011579 | 2019-05-14 | FOR BAPCO REVIEW | 2019-05-29 |  |  | CLASS 2
076551C-000R-MR-4111-002 | MATERIAL REQUISITION FOR PSA | LINDE AG | 023U0001 | &AK J-SD 7560 (EN) | 023-S-DAT-40007-001 | SPECIFICATION: PRESSURE GAUGES023U0001 | A3101 | AX | 2 | 2019-06-11 | CON-BMP-VTRA-012144 | 2019-06-11 | FOR BAPCO REVIEW | 2019-06-25 | 2019-07-02 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001140 | CLASS 2
076551C-000R-MR-4111-002 | MATERIAL REQUISITION FOR PSA | LINDE AG | 023U0001 | &AK J-SD 7580 (EN) | 023-S-DAT-40008-001 | SPECIFICATION: FLOW ORIFICE 023U0001 | A3101 | AXX | 2 | 2019-06-11 | CON-BMP-VTRA-012143 | 2019-06-11 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-4111-002 | MATERIAL REQUISITION FOR PSA | LINDE AG | 023U0001 | &AK J-SD 7630 (EN) | 023-S-DAT-40010-001 | JUNCTION BOX SPECIFICATION 023U0001 | A3101 | AX | 1 | 2019-05-14 | CON-BMP-VTRA-011577 | 2019-05-14 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-4111-002 | MATERIAL REQUISITION FOR PSA | LINDE AG | 023U0001 | &AK J-ZH 7610 (EN) | 023-S-ILD-40001-001 | INSTRUMENT HOOK UP DRAWINGS PSA SKID 023U0001 | A3406 | AX | 2 | 2019-06-11 | CON-BMP-VTRA-012147 | 2019-06-11 | FOR BAPCO REVIEW | 2019-06-25 | 2019-06-26 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001036 | CLASS 2
076551C-000R-MR-4111-002 | MATERIAL REQUISITION FOR PSA | LINDE AG | 023U0001 | &AK L-ZP 7001 (EN) | 023-S-PPN-40001-001 | PLOT PLAN - ROG-PSA-UNIT 023U0001 | A0201 | AXX | 2 | 2019-04-05 | CON-BMP-VTRA-011025 | 2019-04-05 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-4111-002 | MATERIAL REQUISITION FOR PSA | LINDE AG | 023U0001 | &AK L-ZR 7001 (EN) | 023-S-GAD-40003-001 | GENERAL ARRANGEMENT DRAWING ROG-PSA-UNIT 023U0001 | A2001 | AX | 2 | 2019-06-25 | CON-BMP-VTRA-012426 | 2019-06-25 | FOR BAPCO REVIEW | 2019-07-09 |  |  | CLASS 2
076551C-000R-MR-4111-002 | MATERIAL REQUISITION FOR PSA | LINDE AG | 023U0001 | &AK L-ZX 7001 (EN) | 023-S-S3D-40001-001 | 3D MODEL 023U0001 | A2013 | BX | 2 | 2019-06-29 | CON-BMP-VTRA-012570 | 2019-06-29 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-4111-002 | MATERIAL REQUISITION FOR PSA | LINDE AG | 023U0001 | &AK N-SP 7001 (EN) | 023-S-PLD-40001-001 | PIPING SUPPORT SPECIFICATION 023U0001 | A1105 | AX | 2 | 2019-04-12 | CON-BMP-VTRA-011156 | 2019-04-12 | FOR BAPCO REVIEW | 2019-04-29 | 2019-05-09 | 3-REVIEWED WITH COMMENTS BMP-ROC-VTRE-000645 | CLASS 2
076551C-000R-MR-4111-002 | MATERIAL REQUISITION FOR PSA | LINDE AG | 023U0001 | &AK P-CA 7117 (EN) | 023-S-MCD-40018-001 | CAUSE AND EFFECT CHART 023U0001 | A3008 | AXX | 2 | 2019-06-22 | CON-BMP-VTRA-012381 | 2019-06-22 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-4111-002 | MATERIAL REQUISITION FOR PSA | LINDE AG | 023U0001 | &AK P-FF 7001 (EN) | 023-S-PFD-40001-001 | PFD (PROCESS FLOW DIAGRAM) 023U0001 | A0102 | AX | 2 | 2019-03-18 | CON-BMP-VTRA-010723 | 2019-03-18 | FOR BAPCO REVIEW | 2019-04-02 | 2019-04-09 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-TRE-000493 | CLASS 2
076551C-000R-MR-4111-002 | MATERIAL REQUISITION FOR PSA | LINDE AG | 023U0001 | &AK P-FP 7001 (EN) | 023-S-PID-40001-001 | P&ID (PIPING AND INSTRUMENT DIAGRAM) 023U0001 | A0103 | BX | 2 | 2019-06-17 | CON-BMP-VTRA-012259 | 2019-06-17 | FOR BAPCO REVIEW | 2019-07-02 | 2019-07-08 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001219 | CLASS 2
076551C-000R-MR-4111-002 | MATERIAL REQUISITION FOR PSA | LINDE AG | 023U0001 | &AK R-SS 7001 (EN) | 023-S-TSP-40002-001 | PIPE SPECIFICATION CS 300 023U0001 | A2102 | AX | 2 | 2019-03-19 | CON-BMP-VTRA-010751 | 2019-03-19 | FOR BAPCO REVIEW | 2019-04-03 | 2019-04-07 | 5-RETAINED FOR INFORMATION BMP-ROC-VTRE-000474 | CLASS 2
076551C-000R-MR-4111-002 | MATERIAL REQUISITION FOR PSA | LINDE AG | 023U0001 | &AK R-SS 7002 (EN) | 023-S-TSP-40003-001 | PIPE SPECIFICATION CS 150 023U0001 | A2102 | 0X | 2 | 2019-06-28 | CON-BMP-VTRA-012550 | 2019-06-28 | FOR BAPCO REVIEW | 2019-07-12 |  |  | CLASS 2
076551C-000R-MR-4111-002 | MATERIAL REQUISITION FOR PSA | LINDE AG | 023U0001 | &AK R-SS 7003 (EN) | 023-S-TSP-40004-001 | PIPE SPECIFICATION SS 150 023U0001 | A2102 | 0X | 2 | 2019-06-28 | CON-BMP-VTRA-012550 | 2019-06-28 | FOR BAPCO REVIEW | 2019-07-12 |  |  | CLASS 2
076551C-000R-MR-4111-002 | MATERIAL REQUISITION FOR PSA | LINDE AG | 023U0001 | &AK S-DN 7001 (EN) | 023-S-DAT-40012-001 | NOISE DATA SHEET 023U0001 | A0105 | AX | 2 | 2019-06-17 | CON-BMP-VTRA-012256 | 2019-06-17 | FOR BAPCO REVIEW | 2019-07-02 | 2019-07-07 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-001189 | CLASS 2
076551C-000R-MR-4111-002 | MATERIAL REQUISITION FOR PSA | LINDE AG | 023U0001 | &AK T-SA 7001 (EN) | 023-S-PQP-40002-001 | GENERAL LEGAL AND QUALITY REQUIREMENTS OF PSA PRESSURE VESSELS (ROG) 023U0001 | B1002 | CX | 4 | 2019-06-22 | CON-BMP-VTRA-012384 | 2019-06-22 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-4111-002 | MATERIAL REQUISITION FOR PSA | LINDE AG | 023U0001 | &AK T-SA 7002 (EN) | 023-S-PQP-40003-001 | GENERAL LEGAL AND QUALITY REQUIREMENTS FOR PSA VALVE SKIDS (ROG) 023U0001 | B1002 | AXX | 2 | 2019-06-05 | CON-BMP-VTRA-012018 | 2019-06-05 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-4111-002 | MATERIAL REQUISITION FOR PSA | LINDE AG | 023U0001 | &AK-A-TT 7001 (EN) | 023-S-SCH-40001-001 | ENGINEERING AND FABRICATION SCHEDULE 023U0001 | C1001 | BX | 4 | 2019-06-22 | CON-BMP-VTRA-012383 | 2019-06-22 | FOR BAPCO INFORMATION |  |  |  | CLASS 3
076551C-000R-MR-4111-002 | MATERIAL REQUISITION FOR PSA | LINDE AG | 023U0001 | &AK-J-SD 7510 (EN) | 023-S-DAT-40002-001 | SPECIFICATION GLOBE VALVES 023U0001 | A3101 | AX | 2 | 2019-05-14 | CON-BMP-VTRA-011579 | 2019-05-14 | FOR BAPCO REVIEW | 2019-05-29 |  |  | CLASS 2
076551C-000R-MR-4111-002 | MATERIAL REQUISITION FOR PSA | LINDE AG | 023U0001 | &AK-J-SD 7520 (EN) | 023-S-DAT-40003-001 | SPECIFICATION BUTTERFLY VALVES 023U0001 | A3101 | AX | 2 | 2019-05-14 | CON-BMP-VTRA-011579 | 2019-05-14 | FOR BAPCO REVIEW | 2019-05-29 | 2019-05-30 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000846 | CLASS 2
076551C-000R-MR-4111-002 | MATERIAL REQUISITION FOR PSA | LINDE AG | 023U0001 | &AK-P-MP 7111 (EN) | 023-S-PRD-40001-001 | PROCESS DESCRIPTION & CONTROL NARRATIVES 023U0001 | A0101 | AX | 2 | 2019-04-03 | CON-BMP-VTRA-010985 | 2019-04-03 | FOR BAPCO REVIEW | 2019-04-18 | 2019-04-30 | 2-REVIEWED WITH MINOR COMMENTS BMP-ROC-VTRE-000622 | CLASS 2
076551C-000R-MR-4111-002 | MATERIAL REQUISITION FOR PSA | LINDE AG | 023V0038 | &AK B-SP 7002 (EN) | 023-S-DAT-40016-001 | TAIL GAS DRUM SPECIFICATION 023V0038 | A1001 | CX | 2 | 2019-06-17 | CON-BMP-VTRA-012255 | 2019-06-17 | FOR BAPCO INFORMATION |  |  |  | CLASS 2
076551C-000R-MR-4111-002 | MATERIAL REQUISITION FOR PSA | LINDE AG | 023V0039A | &AK B-SP 7001 (EN) | 023-S-DAT-40015-001 | PSA ADSORBER SPECIFICATION 023V0039A TO 023V0039H | A1001 | CX | 2 | 2019-06-17 | CON-BMP-VTRA-012255 | 2019-06-17 | FOR BAPCO INFORMATION |  |  |  | CLASS 2