## 000-A-PRI-50009-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Callout | 4 | scott.hillman | Add document reference number. For Contractor "HSSE Requirements".
2 | Callout | 4 | Muhammad.N.Asim | Subcontractors HSSE Management System shall be in compliance with local applicable Occupational Health and Safety Standards by Ministry of Labors and ILO conventions ratified by Bahrain, SCE and IFC Requirements. Please add these standards and requirements.
3 | Callout | 4 | Muhammad.N.Asim | Replace "Subcontractor" with "Subcontractors"
4 | Callout | 4 | Muhammad.N.Asim | Please mention all the standards e.g. ISO 45001:2018, ISO 14001:2015
5 | Callout | 5 | Muhammad.N.Asim | Change "actions" with "corrective action"
6 | Callout | 5 | Muhammad.N.Asim | Replace "Subcontractor Responsibility" with Subcontractors Responsibilities"
7 | Callout | 5 | Muhammad.N.Asim | Please note that Owner also has the authority to stop the unsafe activities/work and amend the statement accordingly.
8 | Callout | 5 | Muhammad.N.Asim | Kindly be consistent as mentioned above HSSE Management System and Program so use the same in other part of documents. Please amend throughout the document.
9 | Call-out | 6 | Abdul Rahim | for vehicles entry into brown field Bapco's Fire, Health, Safety & Environment and Security departments approval is required
10 | Call-out | 7 | Mahdi Ali | Check sequence number. For unit 000, the sequence number shall be in the range of 50000 up to 89999. The sequence numbers 00048 to 00078 shall not be used.
11 | Call-out | 7 | Mahdi Ali | Unit number shall not have the suffix 'D'
12 | Callout | 8 | scott.hillman | "JV HSSE Policy" is not included in the above referenced documents - provide reference for this policy, or state the policy in this document.
13 | Callout | 8 | Muhammad.N.Asim | Add "Waste Management Plan" as a bullet point
14 | Callout | 8 | Muhammad.N.Asim | Replace "Health, Safety & Environmental Management System" with Health, Safety, Security and Environmental Management System (HSSE)" as stated in the document.
15 | Callout | 8 | Muhammad.N.Asim | Kindly provide a statement that the listed documentation must be in accordance with all relevant project HSSE requirements.
16 | Callout | 9 | Muhammad.N.Asim | Spelling mistake "Prior"
17 | Callout | 10 | Muhammad.N.Asim | add here "environmental incidents e.g. oil spillage, gas release etc."
18 | Callout | 10 | Muhammad.N.Asim | Replace "waste treatment" with "waste generation and treatment/disposal"
19 | Callout | 10 | Muhammad.N.Asim | Replace Safety Incidents with "HSSE Incidents"
20 | Callout | 11 | Mohamed Ghassan | Spelling mistake. Please replace with "minimum".
21 | Callout | 13 | Mohamed Ghassan | This section makes it seem like subcontracts will be engaged in the detailed design of the project. It is expected that the vast majority of subcontractors will be engaged during contraction phase of the project. Please rewrite this paragraph for clarity on this issue.
22 | Callout | 16 | Muhammad.N.Asim | Replace "Subcontractor" with "Subcontractors" and kindly change in other part of the document where it is required.
23 | Callout | 17 | Muhammad.N.Asim | Please include a statement in this section. The subcontractors have to identify potential emergencies associated with their activities and areas of work and prepare response plan in accordance with JV Emergency Plan.
24 | Callout | 19 | Muhammad.N.Asim | Kindly ensure subcontractor facilities will comply with local legislation (Ministerial orders) and IFC/EBR guidelines. Bahrain is also signatory of some of the ILO conventions. Please see the requirements. http://ilo.org/dyn/normlex/en/f?p=NORMLEXPUB:11200:0::NO::P11200_COUNTRY_ID:103396.
25 | Callout | 19 | Muhammad.N.Asim | Replace "Trash" with "Waste"
26 | Callout | 19 | Mohamed Ghassan | Spelling mistake, please replace with "Subcontractors"
27 | Callout | 19 | Muhammad.N.Asim | Replace "Trash" with "Waste"
28 | Callout | 19 | Muhammad.N.Asim | Kindly add the requirements set by local government and IFC/EBRD for workers accommodations.
29 | Callout | 19 | Muhammad.N.Asim | Kindly include subcontractor facilities should comply with lenders requirements IFC/EBRD "Workers’ accommodation: processes and standards"
30 | Callout | 20 | Mohamed Ghassan | Please include a summary of IFC/EBRD guidelines and Bahrain's legislation concerning worker accommodation, please refer to Table 19.1 from the ESIA for assistance. It will also be useful to provide the full version of these legislation/guidances as an appendix to this document.
31 | Callout | 20 | Muhammad.N.Asim | Subcontractor housing/accommodations facilities shall be in compliance with Ministerial Order No.(40) of 2014 With Respect to the Requirements and Specifications of Workers Accommodation and IFC/EBRD guidelines/standards
32 | Text Box | 20 | Mahdi Ali | with a dedicated area for ablution
33 | Callout | 20 | Mohamed Ghassan | Please delete "and local language(s)" and instead insert a statement to say that warning signs and labels should be available in both English and the language(s) of the workers concerned, in addition to the English MSDS.
34 | Callout | 20 | Muhammad.N.Asim | Kindly include a statement. The subcontractor should comply with local and other applicable legislation e.g. Working hours, Summer Outwork ban, lifting equipment hazards, dangerous machinery etc.
35 | Callout | 21 | Muhammad.N.Asim | Kindly include a section on Subcontractor Grievance Mechanism in this Chapter or any other relevant chapter of the document.
36 | Callout | 21 | Muhammad.N.Asim | Please add Civil Defence Department approval as it would be required for the Camps and Offices.
37 | Callout | 22 | Mohamed Ghassan | Please replace with "All Subcontractors shall submit an Environmental Management Plan (EMP) and Waste Management Plan (WMP) specific to the the nature of their work as well as all necessary JV/OWNER requirements"
38 | Callout | 22 | Mohamed Ghassan | Please rephrase this statement to say that every subcontractor will be held accountable and responsible for any and all of their own environmental and/or legal infractions and any damages resultant from them.
39 | Callout | 22 | Muhammad.N.Asim | Replace "Environmental Policy" with " HSSE Policy and Objectives" as mentioned in Section 3.2 EHS Management System.
40 | Callout | 22 | Mohamed Ghassan | Please remove this statement and replace with "Subcontractors shall not utilize any banned and strictly restricted chemicals as per Ministerial Order No. 7 of 2002 with respect to control over the import and use of banned and severly restricted chemicals and will comply with Ministerial Order No. 4 of 2006 with respect to the management of hazardous chemicals"
41 | Callout | 22 | Mohamed Ghassan | This statement does not specify a regular interval of time which subcontractors should report relevant info to JV. While this is detailed later in the document, please indicate it here.
42 | Callout | 22 | Mohamed Ghassan | Replace with: Subcontractors shall adhere to all relevant environmental mitigation measures and reflect said mitigation measures in the EMP & WMP. Subcontractor EMP and WMP shall meet all OWNER & JV requirements and stipulations as well as adhere to all relevant local legislation and international guidances.
43 | Callout | 22 | Muhammad.N.Asim | Please include here BMP ESIA, CESMP and WMP requirements.
44 | Callout | 22 | Mohamed Ghassan | Please include a statement that subcontractors must provide specific job related environmental training... e.g. if a certain subcontractor is dealing with contaminated soil then their training plan must contain specific methods for protecting their workers from any harm.
45 | Callout | 22 | Muhammad.N.Asim | Kindly revise this statement. Also change the word "Preserving" with "protecting" and "minimizing" with "avoiding or minimizing"
46 | Callout | 23 | Mohamed Ghassan | Please replace "Environmental Coordinator / Representative with "qualified environmental protection officers." Amend elsewhere as needed.
47 | Callout | 23 | Mohamed Ghassan | Please rephrase this statement to specify the precise lines of communication for subcontractors.
48 | Callout | 23 | Mohamed Ghassan | Replace with "Subcontractor shall immediately report any environmental incidents and/or incident which may pose a threat to the environment. Near misses of a similar manner must also be reported."
49 | Callout | 23 | Mohamed Ghassan | This section does not stipulate the exact needed environmental credentials needed as was done for H&S officers in section 4.3.2 of this document. Please specify.
50 | Callout | 23 | Mohamed Ghassan | Please rename this section "Incident & Near Miss Reporting"
51 | Callout | 23 | Muhammad.N.Asim | Kindly confirm Environmental Management meetings will be different than HSSE Meetings.
52 | Callout | 23 | Mohamed Ghassan | Please replace add before this sentence, "If any such incident/near miss has occurred, subcontractor..."
53 | Callout | 24 | Muhammad.N.Asim | insert here " wastewater generation and disposal" Replace "Waste Treatment" with Waste Generation and Treatment/Disposal"
54 | Callout | 24 | Muhammad.N.Asim | Kindly revise this section and include the monitoring requirements identified in the ESIA, CESMP. OESMP, ESAP and Project EMP. if a subcontractor is going to develop workers accommodation then they have to comply with wastewater treatment and effluent compliance monitoring, air quality monitoring for camp sites etc.
55 | Callout | 24 | Mohamed Ghassan | Replace with "Subcontractor shall establish a regular inspection schedule in order to ensure that all work done is compliant with all relevant environmental regulations, stipulations and recommendations."
56 | Callout | 24 | Muhammad.N.Asim | This section is does not clearly identify subcontractors basis requirements.Kindly brief on requirements of Noise Monitoring by Subcontractors.
57 | Callout | 24 | Mohamed Ghassan | This bullet point/statement is not related to incident reporting, please include this stipulation in a more appropriate section of the document such as the Environmental Monitoring section.
58 | Callout | 24 | Mohamed Ghassan | This is unclear. It is not known which 'standard inspection checklist' is being referred to here. Please clarify.
59 | Callout | 24 | Mohamed Ghassan | Replace with "Subcontractors must utilize qualified and experienced personnel to develop and conduct all relevant inspection systems and determine their regularity and/or if they will be done on a random basis. JV approval must be given for systems developed/implemented."
60 | Callout | 24 | Muhammad.N.Asim | Kindly include a statement in this section. All the Environmental Testing (air, soil, water etc.) shall be carried out by accredited/approved labs.
61 | Callout | 24 | Muhammad.N.Asim | This statement is not clear as you are talking about Air Quality Reporting. Please amend to clarify.
62 | Callout | 24 | Mohamed Ghassan | Please refer to section 5.7.1 of the CESMP for needed details and update this statement accordingly.
63 | Callout | 25 | Mohamed Ghassan | It would not be feasable to add this as a requirement for all subcontractors, e.g. a subcontractors with 15 or 20 employees would not be able to meet these demands. Please specify which types/sizes of subcontractor this would be applicable to.
64 | Callout | 25 | Mohamed Ghassan | Here it is unclear. The previous statement indicated that each subcontractor would be in charge of their own waste while this section requires the subcontractors to collect the waste of 'all users.' Please amend and be more specific.
65 | Callout | 25 | Muhammad.N.Asim | Kindly include a section on Environmental Auditing of Subcontractors
66 | Callout | 25 | Muhammad.N.Asim | Include here " The subcontractors WMP plan shall include waste streams specific to the their site activities and appropriate treatment/disposal method for each identified waste stream.
67 | Callout | 25 | Muhammad.N.Asim | Replace "mesh" with "mess"
68 | Callout | 25 | Mohamed Ghassan | Many aspects of waste management stipulated in the ESIA and CESMP are not addressed in this section (duty of care, obtaining copies of licenses for hazardous waste carriers, waste oil carriers and waste oil recycling facilities, etc.). Please revise section 5.14 of the CESMP and amend/modify to meet all need criteria.
69 | Callout | 26 | Muhammad.N.Asim | Please replace "Category of Waste" with "Categories of Waste"
70 | Callout | 27 | Muhammad.N.Asim | Please replace "mesh" with "mess"
71 | Callout | 27 | Muhammad.N.Asim | Replace "flow" with "type" or "stream "
72 | Callout | 28 | Muhammad.N.Asim | Kindly see the relevant sections of ESIA, CESMP, Project EMP to set the requirements on Subcontractors for air quality monitoring and mitigation measures.
73 | Callout | 29 | Mohamed Ghassan | Many parts of this section are related to general emergency response procedures and general best practice when handling spill-able substances (fuels, chemicals, etc.) i.e. spill prevention. Please split this section into three parts; one on basic environmental emergency response, one on the requirements of handling spill-able materials and one specifically on emergency response to spills. Please rewrite accordingly.
74 | Callout | 31 | Muhammad.N.Asim | Kindly follow the relevant legislation (local and IFC/EBRD guidelines) for the worker facilities to rewrite this section. Details on Toilets, washbasins, water cooler are stipulated in the said regulations.
75 | Callout | 31 | Mohamed Ghassan | Please refer to section 5.15 of the CESMP and revise/amend this section accordingly. Additionally, this section should make specifically clear who's responsibility it will be to attain the necessary approvals/permits for importing/utilizing hazardous chemicals (i.e. whether it will be the subcontractor or TTSJV). Additionally please state that all subcontractors must comply with Ministerial Order No. 7 of 2002 with respect to control over the import and use of banned and severly restricted chemicals and Ministerial Order No. 4 of 2006 with respect to the management of hazardous chemicals"
76 | Callout | 32 | Muhammad.N.Asim | Kindly delete this section " Erosion and Sedimentation"
77 | Callout | 33 | Muhammad.N.Asim | Kindly modify this section as per the ESIA Section 12 related to Terrestrial Ecology.
78 | Callout | 35 | Muhammad.N.Asim | Kindly include a section "Marine Ecology" and see the relevant sections of ESIA. Kindly specify the requirements for subcontractors working in marine environment (ma'ameer channel, sitra wharf).
79 | Callout | 36 | Muhammad.N.Asim | Kindly include wastewater generation and reporting in above Table 2.
80 | Callout | 37 | Mohamed Ghassan | Please delete and replace with a statement to say that JV HSSE manager will be informed in the event that a worker is sent to hospital.
81 | Callout | 37 | Muhammad.N.Asim | Kindly review the local legislation and IFC requirements regarding these items. It would be not possible for each subcontractor to comply with these requirements. Please review Ministerial order No. 1/1977,
82 | Callout | 38 | Muhammad.N.Asim | Please revise this section as per LMRA requirements and other local legislations e.g. Ministry of Health.
83 | Callout | 38 | Muhammad.N.Asim | This is contradictory to the Section 7.1 Medical where it is stated that subcontractor should have a nurse, an ambulance, a clinic....
84 | Callout | 38 | Muhammad.N.Asim | Delete "Saudi Arabia" as the project have to comply with Bahrain LMRA and Ministry of Health requirements. Kindly check there may be some specific medical requirements for employees working in food services.
85 | Callout | 38 | Muhammad.N.Asim | To develop a hearing conservation program, subcontractor should collect the baseline, identify the high noise areas/activities and conduct workplace exposure assessments. Then establish Hearing Conservation Program for workers those working in high noise area. You may need to add a section on Workplace Occupational Hazards and describe the workplace hazards, controls, exposure monitoring etc.
86 | Callout | 39 | Muhammad.N.Asim | Please note: For driving within the BAPCO refinery areas, security approval and BAPCO defensive driving training would be required.
87 | Callout | 39 | Muhammad.N.Asim | Subcontractors shall follow the JV Traffic Management Plan and Transport Management Plan. Please brief how subcontractors traffic management shall be in compliance with JV Traffic and Transport Management Plans.
88 | Callout | 40 | Muhammad.N.Asim | Please review the relevant local Ministry of Labour Regulations, LMRA requirements, ILO conventions ratified by Bahrain and IFC Guidelines to set any requirements for subcontractors. Please rewrite the section accordingly.
89 | Callout | 40 | Muhammad.N.Asim | Replace "Sunday" with "Friday"