## 000-A-PRO-50039-001-RB
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | Mahdi Ali | Always add the document title in the header
2 | Text Box | 1 | Mahdi Ali | This document was already sent for review on 6th April in transmittal BMP-ROC-TRE-00016.
5 | Callout | 4 | Rosario.Carvalho | In the event of conflict between this Procedure and the Contract, in particular Annex 1, Project Instructions (Exhibit 9) the Contract shall prevail
7 | Callout | 16 | scott.hillman | The Engineering Plan that has previously been submitted does not include detail of the QA/QC for Engineering. There has been no submitted document that defines the procedure for self checks/interdisipline checks/squad checks/KDCN procedures, and the frequency of auditing for these functions. The detail is required.
8 | Callout | 21 | Rosario.Carvalho | Reference needs to be made to the Deed of Amendment
11 | Callout | 22 | Rosario.Carvalho | Refer to Deed of Amendment in relation to MR's and MRQ's. In addition there are also specific requirements with respect to the TBE's
13 | Callout | 26 | Rosario.Carvalho | Refer to Contract for Notice period. In particular Project Instructions within Annex 1.
14 | Note | 26 | Stephen.Jackson | Refer to Contract for Notice period. In particular Project Instructions within Annex 1.
15 | Callout | 31 | scott.hillman | Define who is responsible for reviewing and approving.
16 | Callout | 31 | scott.hillman | The procedure needs to define how this is done. Consideration of impacts to other disciplines/deliverables, is re-HAZOP required etc etc. A separate procedure for the management of field changes may be required.
18 | Callout | 31 | scott.hillman | Reference number for this procedure.
19 | Callout | 33 | scott.hillman | Spelling
20 | Callout | 33 | Rosario.Carvalho | TTSJV