## 000-K-GRD-60001-001-RAP-CS
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Callout | 3 | Isamu | There is no order of priority as in case of conflict, Vendor has to bring the issue to TTSJV and Owner in writing for solution
2 | Text Box | 4 | Hasan Asad | The Owner rejected JV Technical Query K-TCQ-2 for use of Synchronous Motor.
3 | Call-out | 4 | Ebrahim | For HV motors in Zone 2 and Zone 22, the motor enclosure shall be Ex-d or Ex-e. Refer to T107 of FEED Queries
4 | Text Box | 4 | Hasan Asad | The pulsation dampeners shall be supplied with drainage facility to eliminate liquid carry-over.
5 | Text Box | 8 | alexis.martinez | GENERAL: All documents shall be show the Title and the number.
6 | Call-out | 9 | Ali Abbas | add Owner
7 | Call-out | 9 | Ali Abbas | Add Chazop
8 | Call-out | 13 | Ali Abbas | add reference to all other applicable BMPS-J class specifications, standard/Typical drawings, AVL. Also, reference to BMPS-A3 par 8.5 MCM guidelines etc. Any deviation from any J class or other class of project specifications to be listed and submitted to owner for review and approval.
9 | Text Box | 17 | Hasan Asad | A complete set of suction and discharge valves for one unit only shall be provided to cope with the compressor PM schedule after certain hours. The price shall be quoted by the vendor as 'Optional'.