## 000-K-GRD-80001-001-RAP
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | Nalini Mohan | Owner has reviewed and commented on the MR package submitted on Contractors request to solicit quotations from vendors at the earliest. This MR stands reviewed with Status Code 3.
2 | Text Box | 1 | Mahdi Ali | Add Equipment number
3 | Text Box | 1 | Isamu | Add unit number and service description respectively
4 | Callout | 4 | Isamu | and all other componenst requireing sole plates in vendor scope of supply and shipped lose for site cosntruction
5 | Callout | 3 | Syed Ahmed | Change both compressor numbers to the new numbers
6 | Note | 5 | Nalini Mohan | check
7 | Callout | 4 | Isamu | Devices
8 | Callout | 7 | Syed Ahmed | for all equipments; Pump, filters, coolers etc.
9 | Callout | 4 | Isamu | for no permissive start when engaged
10 | Text Box | 6 | Isamu | How can be combined system when you are asking for complete system to each of cylinder cooling and rod packing cooling ? Please check and correct
11 | Callout | 4 | Syed Ahmed | In addition suction and discharge pulsation dampeners shall be provided with pressure gauges and facility of Nitrogen topping up as per normal practice in the existing units.
12 | Callout | 5 | Syed Ahmed | It is desirable to have adequate lubricator reservoir capacity to reduce the frequency of reservoir refills.
13 | Callout | 3 | Isamu | lists
14 | Callout | 7 | Isamu | Make clear such vague statement
15 | Text Box | 4 | Isamu | Motor's area classification shall be indicated on its data sheet and not here
16 | Text Box | 3 | Isamu | Order of priorities are no longer applicable. Refer to BMPS-A2 and all BMPS-Ax series. Delete and direct the Vendor to refer to above spec
17 | Text Box | 13 | Isamu | Please Also list applicable BMPS.
18 | Callout | 3 | Isamu | Please complete the sentence. Is the MR for compressors only of for storage facilities and vaporization ??
19 | Text Box | 6 | Isamu | Please use complete wording as CCW is international abbreviation for Counter Clock Wise.
20 | Callout | 14 | Syed Ahmed | Pump, filters, coolers etc., shall not be mounted on top of the reservoir.
21 | Callout | 4 | Sankara | Recheck the Hazardous Area Classification
22 | Callout | 4 | Isamu | Side
23 | Text Box | 4 | Isamu | Temporary suction strainer at each stage along with spool piece to be supplied loose.
24 | Callout | 5 | Syed Ahmed | The startup control of the standby oil pump shall be actuated by pressure switch, located in the controller header downstream of the filters.
25 | Callout | 4 | Isamu | There are no drawings or sketches attached. Either to delete or attach
26 | Callout | 19 | Isamu | This is not realistic now. Revisit this statement and alter as appropriate
27 | Callout | 4 | Syed Ahmed | With DCS and local alarm notifications and horn at the field as existing compressors