## 005-A-PFD-00001-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Call-out | 1 | Abdul Rahim | add line number
2 | Callout | 1 | BD Mori | Basis for this pressure. Is the existing sphere operating pressure considered?
3 | Call-out | 1 | Abdul Rahim | bullets size will not change
4 | Callout | 1 | Julio.Aguilar | Existing PFD number for refinery LPG system to be included here
5 | Cloud+ | 1 | Julio.Aguilar | FEED PFD shows 220 psi. What is the basis for revising this pressure. Please confirm value.
6 | Callout | 1 | Salman Jaffer | Follow BMPS A-50003 for piston actuated valves
7 | Callout | 1 | BD Mori | General comment: Equipment number shall follow new numbering philosophy.
8 | Callout | 1 | Syed Ahmed | General comment: Temperature and pressure to be shown as per BMPS-A8.
9 | Callout | 1 | Salman Jaffer | General Comment: The shape and the internal Slope of all storage bullets per this document are not consistence with FEED PIDs (BRA-226581) and Data Sheets (2520-f005-SP2543-01-B page 1 of 8). Please correct as shown in the data sheet:
10 | Text Box | 1 | Mahdi Ali | General Comments applicable to all PFDs 1. Follow the Homogenization procedure for the Off-page Connectors. 2. Modifications shall be clouded as per BMPS-A8. 3. Use latest drawing borders. Unit 005 is an existing unit and JV shall officially request the native file to be sent for modifications. It is not acceptable to use the FEED PFDs as there might been some modifications to the existing PFDs. Modifications shall be clouded.
11 | Callout | 1 | BD Mori | In the P&ID XV is provided. Indicate this valve as XV.
12 | Callout | 1 | BD Mori | No instrumentation connection indicated to Vapour pressure analyser from C3 and C4 flow controller. It is not practical for operator to maintain required C3 and C4 ratio manually. Also if vapour pressure is not within the specifications, control action not identified. Detail control logic shall be incorporated.
13 | Call-out | 1 | Edgardo | Please indicate the units at the BL; refer to BMPS-A-50003 for the format; This comment applies to all BL
14 | Callout | 1 | Salman Jaffer | Please provide stream data for LPG to existing Horton Spheres after mixing point
15 | Callout | 1 | Salman Jaffer | Please provide tag number. If this analyzer is for ESD then another another analyzer has to be provided for the DCS for operator's intervention
16 | Callout | 1 | Salman Jaffer | Please refer to Bid Query T1969 regarding prevention of 2-phase flow in the LPG transfer line.
17 | Callout | 1 | Salman Jaffer | Please show FC0008
18 | Callout | 1 | BD Mori | Provide exact document reference number
19 | Call-out | 1 | Edgardo | Rewrite the unit as 051 (without the f)
20 | Call-out | 1 | Ali Abbas | show arrow direction. General comment
21 | Cloud+ | 1 | Sameer.Ahmed | Show full tag number i.e. 005V5006/005V5005
22 | Text Box | 1 | Sameer.Ahmed | This drawing is given CODE-2 as a special case to allow TTSJV to proceed with development of subsequence deliverables and procurement activities. However, TTSJV shall be responsible to incorporate the comments and complete the design before finalizing the equipment PO. PFD shall be modified to incorporate the updated streams data and H&M balance.
23 | Callout | 1 | BD Mori | This stream data shall be under hold till completion of 1/2 SGP design.
24 | Callout | 1 | BD Mori | This valve symbol is overlapping with the next line. Improve drafting.
25 | Text Box | 1 | Mahdi Ali | Where from did the JV get this number??