## 010-A-PFD-00001-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | MAK | Use the latest PFD borders that was transmitted to JV Directorate dated 9th Apr 2018. TR to coordinate with JV for the latest drawing borders.
2 | Call-out | 1 | MAK | General Comment: Enter the complete Equipment Tag, e.g. 010V0003. As per Part D of BMPS-A8, "Equipment Tags shall be placed inside the body of equipment symbol; else, at the bottom or adjacent to equipment symbol."
3 | Call-out | 1 | MAK | General Comment: Everywhere and always the complete equipment tag shall be used.
4 | Call-out | 1 | MAK | General Comment: Everywhere and always the complete equipment tag shall be used.
5 | Call-out | 1 | MAK | General Comment: Retain the border size, A1
6 | Call-out | 1 | MAK | General Comment: The total sheet no. shall be entered. In this example is 011
7 | Call-out | 1 | MAK | General Comment: The whole drawing no. e.g.: 011-A-PFD-00001-002 shall be inserted. The OPC arrow shall be scaled up to accommodate the whole number.
8 | Call-out | 1 | Sameer Foujdar | C to be corrected to 10P0004C
9 | Callout | 1 | Mohamed Ayyash | No need fot this line change. can go straight to the left all the way
10 | Text Box | 1 | Ahmed Ali | V0001A/B
11 | Text Box | 1 | Ahmed Ali | 010V0001A/B
12 | Callout | 1 | Mohamed Ayyash | space
13 | Text Box | 1 | Ahmed Ali | V0002
14 | Text Box | 1 | Ahmed Ali | V0003
15 | Text Box | 1 | Ahmed Ali | V0004
16 | Text Box | 1 | Ahmed Ali | V0005
17 | Callout | 1 | Mohamed Ayyash | Write in two lines ( similer to the other 3) i.e. MIXING VALVE
18 | Callout | 1 | Mohamed Ayyash | Dublication
19 | Callout | 1 | Robert.Kawitzki | Drawing continuation numbers missing - typical comment
20 | Call-out | 1 | Sameer Foujdar | LOW P OVERRIDE signal to be indicated on sheet no 2 and avoid re-routing through sheet no 1. It is marked as a comment in sheet no 2.
21 | Call-out | 1 | Ahmed Ali | E0020
22 | Call-out | 1 | Ali Abbas | No consistency in showing signal arrows. General comment.
23 | Text Box | 1 | Ahmed Ali | E0021
24 | Call-out | 1 | Ali Abbas | Need to clearly mark the arrows to and from selector switch. General comment.
25 | Call-out | 1 | Ahmed Ali | E0022
26 | Call-out | 1 | Ali Abbas | The low select symbol to be outside the selector switch circle.
27 | Callout | 1 | alexis.martinez | Change to 010E0035
28 | Callout | 1 | alexis.martinez | Change to 010E0021
29 | Callout | 1 | alexis.martinez | Change to hyphen symbol (-)
30 | Callout | 1 | alexis.martinez | Change to hyphen symbol (-)
31 | Callout | 1 | alexis.martinez | Change to 010E0034
32 | Callout | 1 | alexis.martinez | Change to 010E0020
33 | Callout | 1 | alexis.martinez | Change to 010E0033A/B
34 | Callout | 1 | alexis.martinez | Change to 010V0014
35 | Callout | 1 | alexis.martinez | Change to 010V0002
36 | Callout | 1 | alexis.martinez | Change to 010V0003
37 | Callout | 1 | alexis.martinez | Change to 010V0004
38 | Callout | 1 | alexis.martinez | Change to 010V0005
39 | Callout | 1 | alexis.martinez | Design pressure does not match with FEED Documents. There is not detail engineering calculation to check the value
40 | Callout | 1 | alexis.martinez | Correct. Based on Heat and Material Balance this number is 80.1 MMBtu/hr
41 | Callout | 1 | alexis.martinez | Change to 010E0022
42 | Callout | 1 | alexis.martinez | Correct. Based on Heat and Material Balance this number is 3.9 MMBtu/hr
43 | Callout | 1 | alexis.martinez | GENERAL: Include the PFD continuation number. This is a stream included in the project and cannot be considered as off plot stream.
44 | Text Box | 1 | 986131 | GENERAL COMMENT APPLICABLE TO ALL PFD'S: - As required in BMPS A8, 7.2.7 item 4 add the note stating: The data on equipment data blocks indicate the normal operating case for the unit and may not be the design case. - All tag numbers shown close to or inside the equipment to have the full equipment number including the unit number - this is based on the updated BMPS-A8 (issued on 09 April 2018)
45 | Callout | 1 | alexis.martinez | GENERAL: Include the complete equipment TAG number.
46 | Polygon Sketch to Scale | 1 | 986131 | 78.43
47 | Callout | 1 | alexis.martinez | GENERAL: Include the equipment TAG number if it is the case e.g. the pump TAG number.
48 | Polygon Sketch to Scale | 1 | 986131 | 78.43
49 | Text Box | 1 | alexis.martinez | General: The equipment TAG number shall be shown complete, like it is shown on P&ID.
50 | Polygon Sketch to Scale | 1 | 986131 | 78.44
51 | Polygon Sketch to Scale | 1 | 986131 | 78.44
52 | Callout | 1 | alexis.martinez | Add slash symbol, i.e. Crude/ kero
53 | Callout | 1 | alexis.martinez | Add stream identification number. During normal operation there is a continuos flow through the bypass, therefore the conditions shown in streams 101C and 101D are not the inlet and outlet operating condition, respectively for 010E0002 A-H.
54 | Polygon Sketch to Scale | 1 | 986131 | 78.43
55 | Polygon Sketch to Scale | 1 | 986131 | 78.43
56 | Polygon Sketch to Scale | 1 | 986131 | 78.43
57 | Callout | 1 | alexis.martinez | Correct the representation of demulsifier injection. It is not the proper representation.
58 | Callout | 1 | alexis.martinez | Valve upstream FC0109: Show the valve as normal instead of closed
59 | Polygon Sketch to Scale | 1 | 986131 | 78.44
60 | Polygon Sketch to Scale | 1 | 986131 | 78.44
61 | Polygon Sketch to Scale | 1 | 986131 | 78.44
62 | Polygon Sketch to Scale | 1 | 986131 | 78.44
63 | Polygon Sketch to Scale | 1 | 986131 | 78.44
64 | Polygon Sketch to Scale | 1 | 986131 | 78.44
65 | Polygon Sketch to Scale | 1 | 986131 | 78.44
66 | Polygon Sketch to Scale | 1 | 986131 | 78.43
67 | Polygon Sketch to Scale | 1 | 986131 | 78.44
68 | Polygon Sketch to Scale | 1 | 986131 | 78.43
69 | Text Box | 1 | 986131 | Add stream data for the all the blank diamonds marked up on the PFD.
70 | Call-out | 1 | 986131 | secondary process line show with different line thickness - as per BMPS. same applies to other train
71 | Call-out | 1 | 986131 | Break the line
72 | Call-out | 1 | 986131 | Show NNF or give a stream number
73 | Call-out | 1 | 986131 | What does this two legends mean - are they required on the PFD?
74 | Text Box | 1 | alexis.martinez | GENERAL: Equipment TAG number shall be modified based on the list and PFDs Mark-up sent to Contractor.
75 | Text Box | 1 | alexis.martinez | GENERAL: All the utility stream and the correspondent Heat and Material Balance stream number shall be shown on a separate Utility Flow Diagram (UFD).
76 | Call-out | 1 | 986131 | GENERAL: Please add the interconnecting PFD number, unless the unit is "off plot" and contractor has no information about the PFD. For the BMP project: all lines coming from existing and new units must be shown.
77 | Call-out | 1 | MAK | This indicates the Sheet No.
78 | Call-out | 1 | MAK | That's not a duplication. One is for Contractor's title block and one is for Owner's title block. However, at the final handover, Contractor's title block will be removed.
79 | Call-out | 1 | 986131 | utility line - reduce the line thickness as per standard
80 | Call-out | 1 | 986131 | utility line - reduce the line thickness as per standard. Applies this to similar utility.
81 | Call-out | 1 | MAK | Delete
82 | Text Box | 1 | Ahmed Ali | Start-up Circulation line
83 | Call-out | 1 | Ahmed Marhoon | The control system design/scheme of interconnecting streams/lines between operating units to be carefully reviewed taking into consideration the control systems provided on the same stream/line at each unit end. The current design may lead to fighting/clashing between the two independent controllers at both sides of the streams. TTSJV to globally review the system and provide a reliable configuration to meet process and safety requirements. This point has been discussed during the pre-EPC PID reviews and the closure of that item to be reflected on the PFDs. Typical comment for similar streams.
84 | Text Box | 1 | Ahmed Marhoon | Instruments Tag Numbers on PFDs to be updated based on the latest symbology sheet, instrument tagging procedure and general comments. For example, the current revision indicates inconsistency in tagging instruments provided for equipment blanketing system, dual elements ... etc. The instruments tagging on PFDs shall corrected incorporating the general comments, pre-EPC PID comments and post design development/packages detailing and ensure standardization/homogenization across BMP units.
85 | Call-out | 1 | Ahmed Marhoon | Indicate the description on override signals. For this case "Low Level Override". Typical comment.
86 | Call-out | 1 | Ahmed Marhoon | Instead of "P", indicate full form "Pressure". Typical
87 | Call-out | 1 | Ahmed Marhoon | Add signal description. Typical comment for all override signals.
88 | Call-out | 1 | Ahmed Marhoon | Location of the "SP" to be corrected. Typical comment
89 | Text Box | 1 | alexis.martinez | General: The stream descriptors shall be "Left Justified" as in the FEED PFDs.
90 | Call-out | 1 | alexis.martinez | General: Delete the Sheet no. below the connector arrow - the sheet no. shall be shown as part of the PFD drawing no shown inside the arrow e.g in this case the drawing no. shall be "010-A-PFD-00001-002"
91 | Cloud+ | 1 | A.Jabbar Mahmood | General: Delete and cover the design case with a note "The exchanger and furnace duties shown are for the Design Case: 150 MBPD of Arab Light Crude, 60 MBPD of Bahrain Crude and 15 MBPD of Rubble Crude"