## 010-E-GAD-00004-001-RAP
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Cloud+ | 1 | bapco-user | Tube to baffle clearance is not per FEED data sheet and this to be checked in 010-E-DAT-00004-001
2 | Cloud+ | 1 | bapco-user | Gaskets are different from Data sheet
3 | Callout | 1 | Robert.Kawitzki | No dimension shall be obscured - typical comment
4 | Callout | 1 | Mohamed Ayyash | Align, for better representation
5 | Cloud+ | 1 | bapco-user | Corrosion allowance 3.2 per Data sheet
6 | Typewritten Text | 1 | Mohamed Ayyash | In view B-B the baffle plate and the impingement plate (with its support plate) are not shown.
7 | Callout | 1 | Mohamed Ayyash | Overlap "correct"
8 | Callout | 1 | alexis.martinez | Design pressure on shell and tube side is not matching with design pressure on FEED datasheet. Review and confirm.
9 | Callout | 1 | Mohamed Ayyash | For better representation, don't use"center" instead use "justify"
10 | Callout | 1 | Mohamed Ayyash | 010-7CDU (correct)