## 018-A-PFD-00001-013-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Cloud |  | Hasan Asad
2 | Text Box |  | Hasan Asad | Correct to: 18E0030
3 | Text Box |  | Fatema Hashem | GENERAL COMMENT: ALL LONG BEND LINES TO BE REPRESENTED CORRECTLY ON THE PFD.
4 | Highlight |  | Fatema Hashem
5 | Cloud |  | Fatema Hashem
6 | Callout |  | Fatema Hashem | CORRECT LOCATION OF PC6011 TO UPSTREAM THE BYPASS
7 | Cloud |  | Fatema Hashem
8 | Cloud |  | Fatema Hashem
9 | Callout |  | Fatema Hashem | CORRECT XV TAG TO "XV6013A"
10 | Callout |  | Fatema Hashem | CORRECT XV TAG TO "XV6013B"
11 | Cloud |  | Fatema Hashem
12 | Arrow |  | Fatema Hashem
13 | Callout |  | Fatema Hashem | MOVE THE VESSEL TAG V0031 TO THE CORRECT VESSEL. THIS IS THE FRESH CATALYST LOADING NOZZLE NOT THE LIQUID OVERFLOW POT
14 | Cloud |  | Fatema Hashem
15 | Callout |  | Fatema Hashem | CORRECT LI TAG TO "LI6099"
16 | Cloud |  | Fatema Hashem
17 | Callout |  | Fatema Hashem | THIS ARRANGEMENT IS INCORRECT. THE PURGE OIL IS NOT GOING TO THE RELIEF VALVE, IT IS JOINING THE CATALYST SLURRY TO V0037/38
18 | Callout |  | Fatema Hashem | SHOW PI6080
19 | Cloud |  | Fatema Hashem
20 | Cloud |  | Fatema Hashem
21 | Cloud |  | Fatema Hashem
22 | Callout |  | Fatema Hashem | CORRECT "XV6094"
23 | Callout |  | Fatema Hashem | CORRECT "XV6095"
24 | Callout |  | Fatema Hashem | CORRECT "XV6096"
25 | Callout |  | Fatema Hashem | SHOW XV6095 AND XV6096 ON SHEET 12 IN ORDER TO DISTINGUISH WHICH LINE IS ASSOCIATED WITH WHICH FLARE LINE
26 | Cloud |  | Fatema Hashem
27 | Callout |  | Fatema Hashem | CORRECT "FC6009"
28 | Cloud |  | Fatema Hashem
29 | Arrow |  | Fatema Hashem
30 | Callout |  | Fatema Hashem | CORRECT TRANSPORT OIL LINE TAKE-OFF TO DOWNSTREAM FC6005 AS PER UPDATED P&ID
31 | Text Box |  | Fatema Hashem | GENERAL COMMENT: SHOW LINES CARRYING CATALYST WITH PRIMARY LINE THICKNESS, SHOW OTHER LINES AND NNF LINES WITH SECONDARY LINE THICKNESS,
32 | Callout |  | Fatema Hashem | CHANGE DESCRIPTION TO "FLUSHING" OIL
33 | Highlight |  | Fatema Hashem