## 018-F-DAT-00001-001-RAP-CS1
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Call-out | Page 4 | Rashed Almudahka | add alternate case
2 | Call-out | Page 6 | Rashed Almudahka | please confirm
3 | Call-out | Page 7 | Ahmed Bucheeri | Provide the basis of selection
4 | Call-out | Page 8 | Ahmed Bucheeri | Provide the basis of selection
5 | Callout | Page 9 | Fatema Hashem | and to include flow pass control valves
6 | Text Box | Page 9 | rob.urban | Consequences (pro's and con's) of this combination need to be discussed first before this can be considered as an option
7 | Callout | Page 9 | rob.urban | HOLD for common convection section with Recycle Hydrogen Furnace