## 019-A-MSD-00001-006-RA-CS
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Cloud+ | 1 | A.Jabbar Mahmood | Shall read "3&4"
2 | Text Box | 1 | A.Jabbar Mahmood | The indicated temperatures and pressures are not inline with the latest PFDs. Check and update.
3 | Call-out | 1 | A.Jabbar Mahmood | Shall read "MAKE-UP HYDROGEN COMPRESSION SECTION" as per PFDs
4 | Text Box | 1 | Yousif Ahmadi | General comments for 019K0002/0003/0003 1- Notes to be between separate brackets. 2- Check and confirm the SR for all three Compressors
5 | Callout | 1 | Yousif Ahmadi | Add line Spec.