## 019-C-GAD-10001-001-RAP
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Callout |  | A.Jabbar Mahmood | The design pressure of C0001R is 2575 psig per the FEED datasheet. Is the new value (2590 psig) based on revised hydrualic calculations and due to reaching a line size constraint in the HP circuit.TR to provide the calculations and obtain CLG's concurrence.
2 | Callout |  | A.Jabbar Mahmood | The inlet and outlet pressures of C0001R are 2462 and 2327 psig per the FEED datasheet. Are the new values (2467/2332 psig) based on revised hydrualic calculations and due to reaching a line size constraint in the HP circuit. TR to provide the calculations and obtain CLG's concurrence.
3 | Call-out |  | Ahmed Marhoon | Old Bapco logo to be replaced with the new logo. This is typical for all documents.
4 | Call-out |  | Ahmed Marhoon | According to the GAD, T39 - 41 are at different elevation than T42-44. If there is no technical reason for combining these two groups; split into two line items similar to the rest of Thermowell connections.
5 | Stamp |  | Raj
6 | Callout |  | A.Jabbar Mahmood | This nozzle (N47) does not exist in the FEED drawings or Licensor drawings. The nozzle however is depicted in the EDP and FEED P&IDs. We believe that this is a graphical error in the P&IDs and this additional nozzle shall not exist . TR to seek confirmation from CLG and update the P&IDs.
7 | Text Box |  | A.Jabbar Mahmood | The ID (overlay to overlay) of 5100mm shall be indicated in the drawing
8 | Call-out |  | Ahmed Marhoon | Bapco logo to be added to the frame block. Typical for all documents.
9 | Call-out |  | Ahmed Marhoon | For the Thermowells points, add reference to the typical assembly drawing. Typical for all TW points on Reactors.
10 | Call-out |  | Ahmed Marhoon | Direction to North, is it applicable for this drawing? If applicable, is it shown at the right direction? Otherwise, delete from the drawing. Typical for similar drawing.