## 019-C-GAD-10002-001-RAP
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Callout |  | A.Jabbar Mahmood | The design pressure of C0002R is 2515 psig per the FEED datasheet and Licensor datasheet. Is the new value (2575 psig) based on revised hydrualic calculations and due to reaching a line size constraint in the HP circuit. TR to advise the basis for this change and provide the calculations. CLG's concurrence is required.
2 | Callout |  | A.Jabbar Mahmood | The inlet and outlet pressures of C0002R are 2404 and 2284 psig per the FEED datasheet and Licensor datasheet. Are the new values (2453/2333 psig) based on revised hydrualic calculations and due to reaching a line size constraint in the HP circuit. TR to provide the calculations and obtain CLG's concurrence.
3 | Text Box |  | Ahmed Marhoon
4 | Call-out |  | Ahmed Marhoon | According to the GAD, T23 - 25 are at different elevation than T26 - 28. If there is no technical reason for combining these two groups; split into two line items similar to the rest of Thermowell connections.
5 | Call-out |  | Ahmed Marhoon | Refer to the typical comments on 019C0001R
6 | Stamp |  | Raj
7 | Cloud+ |  | Yousif | Should be selected as we are referring to them in ITP
8 | Callout |  | A.Jabbar Mahmood | This nozzle (N31) does not exist in the FEED drawings or Licensor drawings. The nozzle however is depicted in the EDP and FEED P&IDs. We believe that this is a graphical error in the P&IDs and this additional nozzle shall not exist . TR to seek confirmation from CLG and update the P&IDs
9 | Text Box |  | A.Jabbar Mahmood | The ID (overlay to overlay) of 4250 mm shall be indicated in the drawing