## BAPCO DOC. CODE-REV-CS
ID N° | Subject | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | A.Jabbar Mahmood | A note should be added indicating that the sizes of the column nozzles may change during the development of the detailed design. | Not all nozzle sizes are on hold and shall be fixed in order to have Vendor quotation. In any case, this is the reason why Contractor included optional prices for nozzles in RFI. | N
2 | Cloud+ | A.Jabbar Mahmood | External design pressures shall be reported as negative values (vacuum) i.e. as -14.7 psig | It is indicated external pressure. Hence, it is not necessary to include additionally -10 PSIG | N
3 | Callout | A.Jabbar Mahmood | The Liquid bottom outlet nozzle size is 10" per the FEED datasheet and P&IDs. TR to check and confirm. | It has been changed due to process reasons regarding speed criteria as per 7.10.1 BMPS-A3 | N
4 | Callout | Adnan Alothman | Corr. for heads are (6.4mm) per FEED data sheet. TR to verify | - According to CLG dwg/data sheet included in vol ii from license, 3/16" ca are specified fro the whole vessel - Material selection diagram from licensor reflects the same ca for the whole vessel - Material selection diagram and data sheet from feed also reflect 3/16" ca. Contractor supose there is a typo error, hence 4.8 mm ca shall be applied for the whole vessel. | N
5 | Callout | alexis.martinez | The equipment TAG number and the description shall be shown in all the sheets. | TTSJV is checking Owner comments to all Material Requisitions and the templates will be revised accordingly to be implemented in the OC deliverables.
6 | Call-out | bapco-user | Change the note number to 24 as note with 23 number is available | Noted. It will be implemented in revision A | Y
7 | Call-out | bapco-user | Remove this " Fixed in CS: 1/4" CA as it is duplicated | Noted. It will be implemented in revision A | Y
8 | Call-out | bapco-user | In note 21 change the word Reactor to column | Noted. It will be implemented in revision A | Y
9 | Call-out | bapco-user | Add another note: PMI shall be executed per BMPS-B9 | Noted. It will be implemented in revision A | Y
10 | Cloud+ | Ahmed Marhoon | Based to the PID, EDP's GAD and to avoid dead-legs in the level bridle, lower level tapping (45B) needs to be relocated to the side of the column. The new tapping elevation shall still cover the LLL of the operating range. | This is a preliminar sketch. This nozzle will be relocated by instrumentation department in a later stage | N