## 019-C-GAD-10007-001-RAP
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Call-out | 1 | MAK | 7
2 | Call-out | 2 | MAK | 7
3 | Call-out | 3 | MAK | 7
4 | Text Box | 1 | MAK | 3
5 | Call-out | 3 | MAK | 3
6 | Text Box | 1 | MAK | 019 - 2HCU
7 | Text Box | 2 | MAK | 019 - 2HCU
8 | Text Box | 3 | MAK | 019 - 2HCU
9 | Cloud+ | 3 | A.Jabbar Mahmood | Correct the drawing no. to GF-C13950
10 | Cloud+ | 1 | A.Jabbar Mahmood | Indicate "negative" values for the ext design pressures.
11 | Cloud+ | 1 | A.Jabbar Mahmood | N17 size is 8 as per FEED D/S and P&IDs. Check, confirm and update other documents as necessary
12 | Text Box | 3 | A.Jabbar Mahmood | There are a number of important details missing in the drawings. It is suggested that "Details A to B" presented in the process d/s be included in the mechanical drawing
13 | Text Box | 1 | MAK | Use the latest A3 Border
14 | Text Box | 2 | MAK | Use the latest A3 Border
15 | Text Box | 3 | MAK | Use the latest A3 Border