## 019-E-DAT-00004-001
ID Nº | Subject | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Stamp | Raj |  |  | -
2 | Cloud+ | A.Jabbar Mahmood | Tubeside velocity is 36.9 ft/s per CLG D/S. Verify | Velocity have been updated due to FEED design modifications in order to avoid vibrations predicted by HTRI simulations. | -
3 | Cloud+ | A.Jabbar Mahmood | Shellside velocity is 24.5 ft/s per CLG D/S. Verify | Velocity have been updated due to FEED design modifications in order to avoid vibrations predicted by HTRI simulations. | -
4 | Cloud+ | A.Jabbar Mahmood | Note 18: specify Design Case (EOR or SOR) | MOC Process: Note 18 is referring the heat exchanger design case, which, as per note 2, is 'Design Case SOR.' | -
5 | Cloud+ | A.Jabbar Mahmood | Note 31: The max shell/tube differential pressure is 430 psig per CLG D/S and as also reported in 000-E-GRD-70001-001 (section 5.6.11) | MOC Process: Maximum shell/tubes differential pressure has been increased from the value specified by CLG considering the updated design pressure for shell side (2970 psig) and tube side (2350 psig). CLG will be informed. | -
6 | Text Box | A.Jabbar Mahmood | Show Details A1 and B1 as in CLG's D/S | N/A since the baffle layout had been updated to vertical cut. | N
7 | Text Box | A.Jabbar Mahmood | Consider adding note 11 of the licensor´s datasheet for information. | Updated by D/S Note (32) "11. TUBE SUPPORT PLATES ARE CROPPED ON TOP AND BOTTOM FOR DRAINAGE PURPOSES ONLY." | Y