## 019-E-GAD-00015-001-RAP
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Call-out | 1 | Mahdi Ali | Add C/L denoting center line in all views
2 | Cloud+ | 1 | Yousif Ahmadi | All or only FH. Check and confirm
3 | Call-out | 1 | Sameer Foujdar | Design Pressure for both shell and tube side & Design Temperature for Tube side is considerably higher than the FEED data sheet for all the three Make-up Hydrogen Second Stage Intercoolers. Basis to be confirmed.
4 | Call-out | 1 | Mahdi Ali | Detail is not shown on view A-A
5 | Callout | 1 | Yousif Ahmadi | Note 7: Per FEED data sheet it is 0.4mm
6 | Callout | 1 | Yousif Ahmadi | Note 8: ASCE 7-10
7 | Cloud+ | 1 | Yousif Ahmadi | Per data sheet thickness is 18.2 mm. check and confirm
8 | Call-out | 1 | Mahdi Ali | Remove U from unit number
9 | Cloud+ | 1 | Yousif Ahmadi | SS 304L KAMPROFILE Per FEED data sheet
10 | Call-out | 1 | Sameer Foujdar | Title should read as 019K0004 MAKE-UP HYDROGEN SECOND STAGE INTERCOOLER
11 | Cloud+ | 1 | Mohamed Ayyash | View B-B does not shoe baffle plate and impingement plate along with its partial support plate.