## 019-E-GAD-00028-001-RAP-CS
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | Page 1 | MAK | Refer to the typical comments on 019-E-GAD-00026-001
2 | Cloud+ | Page 1 | A.Jabbar Mahmood | Refer to comments sent in BMP-MOC-TRE-00002 regarding the design pressure and temperature
3 | Callout | Page 1 | Mohamed Ayyash | Add "COMPRESSOR" TO THE NAME
4 | Callout | Page 1 | Mohamed Ayyash | 2HCU (CORRECT UNIT NAME)
5 | Callout | Page 1 | Mohamed Ayyash | LINES TO BE ALIGHNED FOR BETTER APEARANCE AND TO BE UNDERSTOOD
6 | Callout | Page 1 | Mohamed Ayyash | COMPANY (write the full word)
7 | Call-out | Page 1 | Sameer Foujdar | Description should read 019K0004 MAKE-UP HYDROGEN COMPRESSOR FIRST STAGE INTERCOOLER
8 | Call-out | Page 1 | Sameer Foujdar | Tube Side Fluid service is Cooling Water.
9 | Call-out | Page 1 | Sameer Foujdar | Refer to Note 21in this drawing which gives shell side steam out condition
10 | Callout | Page 1 | Adnan Alothman | The Cooling Water Design Temp. is 165 deg. F as per BMPS-A1 and FEED data sheet. Verify & confirm.
11 | Callout | Page 1 | bapco-user | Add Painting procedure
12 | Cloud+ | Page 1 | bapco-user | Joint Efficiency per FEED drawing should be 1 and hence RT will be Full
13 | Cloud+ | Page 1 | Adnan Alothman | As per FEED doc., SS304L KAMPROFILE Type is required. Check & confirm
14 | Callout | Page 1 | bapco-user | CA for floating head to be specified
15 | Callout | Page 1 | Adnan Alothman | Wind Loads to be according to ASCE 7-10