## 019-K-DAT-00002-001-RAP
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | A.Jabbar Mahmood | This datasheet shall also be reviewed and approved by the Licensor
2 | Text Box | 1 | Hasan Asad | As per Volume 2 Exhibit 6 - CDRL - Complete LCCA study shall provided and recommendations shall be considered during design.
3 | Callout | 1 | Mohamed Ayyash | Delete c
4 | Cloud+ | 1 | A.Jabbar Mahmood | This is a "Process" Data sheet not Mechnical!
5 | Callout | 1 | Mohamed Ayyash | add 0
6 | Text Box | 1 | A.Jabbar Mahmood | Owner has not received the hydraulic calculations of the HP Circuit and hence cannot verify the revised compressor head and discharge design conditions.
7 | Callout | 2 | Mohamed Ayyash | No. (Typo) apply to all document
8 | Callout | 2 | Mohamed Ayyash | increase text font
9 | Callout | 2 | Mohamed Ayyash | add 0, apply to all document
10 | Call-out | 5 | Sameer Foujdar | Rupture disc is not marked in FEED data sheet. Ensure the requirement of the same.
11 | Text Box | 5 | Sankara | Synchronous Motor Not acceptable
12 | Call-out | 6 | Ahmed Marhoon | Instrumentation Data Sheets were not provided as part of the Transmittal and hence could not be reviewed. In any case, all documents shall be generated in the client's standard format. Also all pre-fabricated installations shall meet the BMPS specifications such as BMPS-J31.
13 | Callout | 6 | Mohamed Ayyash | write 58 on the 2nd line to ovoid overlaping with the line
14 | Call-out | 9 | Sameer Foujdar | To be confirmed by vendor cooling media water or oil.
15 | Callout | 9 | Yousif Ahmadi | <31 HRC note to be written against Piston Rods Hardness
16 | Callout | 9 | Yousif Ahmadi | add "as per BMPS-K1) point 6.10.4.1 to PISTON RODS(S): MATERIAL/YIELD, PSI
17 | Callout | 10 | Mohamed Ayyash | Delete line
18 | Text Box | 13 | Sankara | This is incorrect
19 | Call-out | 14 | Ahmed Ali | 48F per BMPS-A1
20 | Callout | 20 | Mohamed Ayyash | Remove block
21 | Call-out | 21 | Ahmed Marhoon | All alarms and shutdown functions to be confirmed with/by the vendor and shall be reflected on final C&E diagram.
22 | Callout | 22 | Isamu | Delete. No room here
23 | Callout | 23 | Mohamed Ayyash | Wrong Bapco code no. Use: 019-K-DAT-0002-001
24 | Text Box | 23 | Mahdi Ali | Use Bapco number
25 | Cloud+ | 23 | A.Jabbar Mahmood | The operating pressure range to be confirmed based on the final hydrualic calculations on the H2 interconnecting network.
26 | Cloud+ | 23 | A.Jabbar Mahmood | Correct the steam out pressure to 60 psig
27 | Call-out | 23 | A.Jabbar Mahmood | The operating discharge pressure has been revised from that specified by CLG. CLG shall be informed.
28 | Call-out | 23 | Ahmed Marhoon | Smart positioner?
29 | Callout | 23 | Mohamed Ayyash | Align
30 | Call-out | 23 | A.Jabbar Mahmood | The compressor suction design pressure to be revised to 490 psig as per bidder query number T132
31 | Call-out | 23 | Ahmed Marhoon | manual or automatic?
32 | Call-out | 23 | Ahmed Marhoon | Add the required configuration for the remote system.
33 | Call-out | 23 | Ahmed Marhoon | Scope of Supply to be confirmed by Contractor.
34 | Call-out | 24 | A.Jabbar Mahmood | Indicate the operating case on which the turndown value is based
35 | Callout | 24 | Mohamed Ayyash | Wrong Bapco code no. Use: 019-K-DAT-0002-001
36 | Callout | 24 | Mohamed Ayyash | Overlapping, continue on the next line
37 | Call-out | 24 | A.Jabbar Mahmood | As per BMPS A1, the CW supply pressure at unit B.L is 65 psig
38 | Cloud+ | 24 | A.Jabbar Mahmood | Not consistent with the design pressure of 2902 psig reported in note 18. Check
39 | Call-out | 24 | A.Jabbar Mahmood | What is the basis for the max CW flow?
40 | Call-out | 24 | A.Jabbar Mahmood | As per BMPS A1, the minimum CW return pressure at unit B.L is 36 psig.
41 | Callout | 24 | Mohamed Ayyash | Align
42 | Text Box | 25 | Hasan Asad | Drain KO Drum shall be provided with manual/automatic draining facility.
43 | Callout | 25 | Mohamed Ayyash | Wrong Bapco code no. Use: 019-K-DAT-0002-001
44 | Callout | 26 | Mohamed Ayyash | Wrong Bapco code no. Use: 019-K-DAT-0002-001
45 | Text Box | 26 | Ahmed Marhoon | The following are general comments related to instrumentation and control: 1. The notes related to Instrumentation & Control provided on the Data Sheet do not capture all the technical requirements for the instruments design. All applicable BMPS-J series to be referenced (such as J2, J3, J18 …etc) for the supplier to comply with. 2. TTSJV is requested to ensure that all the specific technical/functional requirements (including AVL) are covered and detailed in the requisition specification that will be sent out to suppliers. In case this document would be the only one for MR, then all the relevant BMPS to be included in the Data Sheet notes. 3. Vendors to be notified on the fact that the final design of the system shall include all the Hazop3/SIL recommendations and approved PID post-EPC-development. 4. Since the Data Sheet is issued separately, the consistency between the different documents, that may be part of the requisition, could not be verified and hence it is the contractor’s responsibility to update the other documents impacted by any of the comments on this Data Sheet and vice versa. 5. Minimum Flow arrangement/design shall be reviewed and confirmed by the supplier. Contractor to consider the pumps protection requirements and reflux rate per process design. 6. Supplier to be notified on consideration of the Auto-Start (linked to discharge pressure) and Permissive (linked to level and MOVs status) requirements per the PID. 7. Add Design Philosophy BMPS-A3 reference section 8.5 MCM Guidelines. Monitoring system in general to meet the requirement stated in this BMPS in addition to vendor requirement. 8. Requirement of MCM to be verified with the supplier. Reference to BMPS-J15 MCM to be added accordingly. 9. Suppliers to be notified on the possibility of considering wireless instruments for non-critical monitoring devices. Reference to BMPS-J10 Wireless to be added if applicable and meeting the criteria (under development) of wireless measurement. 10. All the BN machinery monitoring probes etc. shall be factory fitted by the vendor and not at site. 11. Narrative/flow charts/cause and effect shall be provided for any control or sequence logic. 12. Assistance and involvement of the vendor during CHAZOP/Hazop workshops and study to be considered. 13. Explanatory notes to be added on the requirement of having the control performed in the plant DCS and safety functions in ESD system. 14. Scope of supply for the interposing relays to be clearly defined. 15. In addition to BMPS J Specifications, all relevant BMPS J Standard/Typical Drawings to be included. 16. Add a note to the supplier to design, fabricate and supply the instruments in accordance with the BMPS J specifications. Items such as Junction boxes, cables, wiring, ferruling, earthing, terminal strips, fitting …etc shall be installed by the vendor/contractor meeting the requirements specified on the applicable BMPS J specifications like BMPS-J31.
46 | Call-out | 27 | Sameer Foujdar | 3 Motors required one for each compressor.
47 | Callout | 27 | Mohamed Ayyash | Wrong Bapco code no. Use: 019-K-DAT-0002-001
48 | Text Box | 27 | Sankara | Delete Ex-p
49 | Text Box | 27 | Mahdi Ali | Remove c from Unit number
50 | Callout | 27 | Mohamed Ayyash | Make space
51 | Callout | 27 | Mohamed Ayyash | Correct: This is make up Hydrogen Compressors data sheet
52 | Call-out | 27 | Ahmed Marhoon | Service for Unit description to be corrected. This DS is related to 2HCU compressors.
53 | Callout | 28 | Mohamed Ayyash | Wrong Bapco code no. Use: 019-K-DAT-0002-001
54 | Callout | 28 | Mohamed Ayyash | Correct: This is make up Hydrogen Compressors data sheet