## 023-K-DAT-00001-001-RAP-CS
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Call-out | 2 | Ali Kadhem | Temperature predicted at discharge is: - FEED Data sheet: 246F - PFD H&MB: Design case (246F) and Operating case (249F) TechnipFMC to check and confirm
2 | Call-out | 2 | Ali Kadhem | The maximum allowable speed has been changed from 600 r/min in FEED datasheet to 350 r/min. TechnipFMC to check and confirm.
3 | Call-out | 3 | Ali Kadhem | The mol% to be updated based on the latest revised H&MB.
4 | Call-out | 10 | Rashed Almudahka | clarify the purpose of modifying from FEED requirement
5 | Call-out | 10 | Rashed Almudahka | tick whether provided coupling complies to API671, if not kindly explain
6 | Call-out | 11 | Rashed Almudahka | preliminary driver data sheet shall be submitted along with quotation not during detail engineering
7 | Call-out | 12 | Rashed Almudahka | clarify the purpose of modifying from FEED requirement
8 | Call-out | 14 | Rashed Almudahka | confirm stage numbers whether 1 stage or note-14 is applicable
9 | Callout | 18 | Isamu | May be deleted as it has no room in this machine
10 | Call-out | 19 | Ali Kadhem | The maximum H2 PP in the FEED Datasheet is 295psia and in this datasheet is 221psia. -TechnipFMC to provide the rational for this change. -What are the basis for the H2 PP of 295 psia and 221psia. Is the highest H2 mol% of the individual streams was used e.g. H2 mol% in 2HDU LPS Offgas pressure for the operating/design case. It is suggested to provide appropriate explanation for the basis of max H2 PP in the note no.9 as well.