## 041-A-PFD-00001-001-RA-CS
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | balagangadhar.k | 5
2 | Text Box | 1 | balagangadhar.k | A/B
3 | Text Box | 1 | balagangadhar.k | Typical for All BMP PFD Drafting:: 5. OPC's entering and leaving the PFD should be in one line from top to bottom and consistent across all PFD. See sheet 2 for comment. 6. All lines should be shown with arrows at changes in direction. 7. Arrows to be shown in instrument line connected to CV. See sheet 2 for comment. 8. As per BMPS-A8, Three different lines (main process line, Secondary Line & Minor line) to be used on PFD. The current PFDs show only main and minor lines.
4 | Callout | 1 | balagangadhar.k | 6SWS PFD/HMB shows 199
5 | Callout | 1 | balagangadhar.k | Show capacity in SCFH per BMPS-A8, Section 7 & UOM
6 | Callout | 1 | balagangadhar.k | Remove sheet no.
7 | Callout | 1 | balagangadhar.k | No Pump, Blowers
8 | Text Box | 1 | balagangadhar.k | S
9 | Text Box | 1 | balagangadhar.k | Typical for All BMP PFD Drafting: 1. Do not use # with unit short description. ex. #5SRU is not correct, just use 5SRU. 2. Equipment Tag numbers shall be prefixed with unit number at all places (inside/beside equipment, OPCs, Equipment data blocks, Notes, etc..) 3. Equipment internals including Vortex Breakers should be shown inside vessel as per BMPS-A8. 4. HMB data on PFD shall be presented in the format specified in BMPS-A8, Appendix D2.
10 | Text Box | 1 | balagangadhar.k | 5
11 | Text Box | 1 | balagangadhar.k | A/B
12 | Callout | 1 | BD Mori | Indicate Temperature and Pressure flag
13 | Callout | 1 | BD Mori | As per shutdown philosophy, 5, 6 &7 SRU T&I will be done separately for each unit outside HUB-1. In this situation V0001 and V0002 will always be in service. How to handle T&I of V0001 and V0002?
14 | Callout | 1 | Julio.Aguilar | Please indicate the document number of the connecting PFD
15 | Call-out | 1 | MAK | Total Sht. shall be indicated only, 006
16 | Call-out | 1 | MAK | Provide the whole equipment nos. e.g 041K0001A/B/C, 041V0001
17 | Call-out | 1 | MAK | Don't use #
18 | Call-out | 1 | MAK | Move/stretch to the right
19 | Call-out | 1 | MAK | 044-A-PFD-00001-007 Apply to all.
20 | Call-out | 1 | MAK | 041 - NO. 5 SULPHUR RECOVERY UNIT
21 | Call-out | 1 | MAK | 042 , 043 , 041
22 | Call-out | 1 | MAK | Change to DWG.
23 | Call-out | 1 | MAK | Always show the border size A1
24 | Text Box | 1 | MAK | Use the latest PFD border template that is part of Homogenization Procedure. SOC shall coordinate with JV Directorate.
25 | Call-out | 1 | MAK | Always enter NTS for PFDs
26 | Callout | 1 | Robert.Kawitzki | Text height and width to be to project standards - typ comment
27 | Callout | 1 | Salman Jaffer | General comment: Full tag number should be written including unit number.
28 | Callout | 1 | Salman Jaffer | Tag number of Combustion Air Blowers to be finalized based on final plot plan.
29 | Text Box | 1 | Sang.Hwang | In psig, ID, ID hyphen, i, - font shall be re-checked. It looks different from others.
30 | Callout | 1 | Syed Ahmed | Write drawing number