## 041-F-DAT-00002-001-RAP
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box |  | BD Mori | The comments in this document are also applicable to 042V4203 and 043V4303
2 | Arrow |  | BD Mori
3 | Stamp |  | Nalini Mohan
4 | Text Box |  | Nalini Mohan | Owner has reviewed and commented on the MR package submitted on Contractors request to solicit quotations from vendors at the earliest. This MR stands reviewed with Status Code 3.
5 | Cloud |  | Nalini Mohan
6 | Callout |  | Nalini Mohan | Data within the cloud should be defined by EPC Contractor
7 | Callout |  | Saeed Taher | Material and ASTM specifications to be specified for all components.
8 | Callout |  | BD Mori | 12. 550# steam produced from the steam drum shall meet the purity specifications as per BMPS-A1
9 | Callout |  | Salman Jaffer | Specify minimum pressurization temperature (MPT) requirement if applicable
10 | Callout |  | BD Mori | (Note 6)
11 | Cloud+ |  | Ahmed Marhoon | Size of level nozzles to be finalized based on vendors recommendation and taking into account the mechanical stress/load of the bridle and instruments. Add a note to the supplier to hold the size.
12 | Callout |  | Mohamed Ayyash | space
13 | Ellipse |  | Mohamed Ayyash
14 | Callout |  | Mohamed Ayyash | keep space between letters
15 | Call-out |  | Ahmed Marhoon | Details of the instrumentation connections and the operating/safe process ranges shall be finalized after detail design development and Hazop3/SIL studies.