## 044-A-PFD-00001-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | balagangadhar.k | 2
2 | Call-out | 1 | MAK | 1
3 | Call-out | 1 | MAK | 2
4 | Call-out | 1 | MAK | 3
5 | Call-out | 1 | MAK | 4
6 | Call-out | 1 | MAK | Are these nos. as per the agreed equipment list?
7 | Callout | 1 | balagangadhar.k | Check Equipment name? Flash gas KOD
8 | Call-out | 1 | MAK | Delete #
9 | Call-out | 1 | MAK | Equipment numbers shall be entered fully, e.g. 044P0007.
10 | Call-out | 1 | MAK | FEED drawing nos. shall not be used at all.
11 | Callout | 1 | Salman Jaffer | FEED have two shells for this exchanger and in this PFD it is changed to one. Confirm with Licenser.
12 | Text Box | 1 | MAK | General Comment: The equipment data shall be placed in alignment with the location of the equipment as possible.
13 | Text Box | 1 | MAK | General Comments applies to all PFDs: 1. Use the latest PFD border and off-page connectors that are part of the Homogenization Procedure. SOC shall coordinate with TTSJV. 2. Total Sheet to be shown as e.g. 010 on all the sheets. 3. Always use NTS for PFD scale. 4. Always use A1 for PFD border size.
14 | Call-out | 1 | MAK | General Comments: - # shall never be used, only 4TGTU & 3TGTU shall be entered. - Unit Nos. shall be entered correctly, e.g. 045, 044.
15 | Callout | 1 | BD Mori | Provide bed numbers
16 | Callout | 1 | BD Mori | Provide chimney tray number
17 | Callout | 1 | balagangadhar.k | Show Air cooler symbol as per LEGEND, this line to be deleted
18 | Callout | 1 | BD Mori | There are total 16 steam generators in Sulphur Plant operating with different steam generation capacity and pressure. With single phosphate dosing package with one pump in operation and other stand by, how will it ensure accurate and adequate chemical injection to all the steam generators?
19 | Text Box | 1 | balagangadhar.k | Update all equipment tag numbers as per latest equipment list (Typical for all units)
20 | Callout | 1 | balagangadhar.k | Update the drawing numbers
21 | Text Box | 1 | MAK | Verify the equipment nos. with the agreed equipment list.