## 047-A-MSD-00001-002-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Call-out | 1 | MAK | 2
2 | Text Box | 1 | balagangadhar.k | All Equipment numbers to be updated as per latest equipment list.
3 | Callout | 1 | Nalini Mohan | As per query response T1388, MSD should reflect detailed design development and confirm the requirement for HIC. FEED design is reflected as is.
4 | Call-out | 1 | MAK | Delete
5 | Text Box | 1 | MAK | Don't publish coloured PDF, instead use Black/White or Monochrome setting.
6 | Callout | 1 | Syed Ahmed | During T&I, this vessel will be under steam out by 60# steam, according to BMPS-A1-0, 60# steam temperature average from 302-400 F, please consider this point.
7 | Text Box | 1 | Nalini Mohan | For general comments refer to sht 1
8 | Callout | 1 | Dowon Pyun | Specify "N" to make a consistency with other data block composed with the same material
9 | Call-out | 1 | MAK | UNIT
10 | Callout | 1 | Dowon Pyun | Upstream and downstream line materials are CS only in shell side. Contractor to recheck material consistency.
11 | Text Box | 1 | MAK | Use the latest PFD border.