## 058-A-PFD-50001-004-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Call-out | Page 1 | 986131 | Provide a note stating that above figures would be reviewed after the SGP Off Gas (going to refinery fuel gas) composition is finalized based on SGP alternative development and LPG saturation system is finalized.
2 | Cloud+ | Page 1 | Julio.Aguilar | This pressure to be consistent with PFD No. 058-A-PFD-50001-002-Sht 4.
3 | Call-out | Page 1 | Ali Kadhem | The data for this stream (no.29) to be updated based on the latest revised H&MB for 1HRU. Please note that 1HRU design case is without the amine absorber i.e. about 4.4 mol% H2S
4 | Call-out | Page 1 | Ali Kadhem | - What is the basis for "30%", is it due to the H2 content or calorific value? - The flow need to be checked based on the latest revised 1HRU H&MB. Please note that 1HRU design case is without the amine absorber i.e. about 4.4 mol% H2S
5 | Call-out | Page 1 | Ali Kadhem | The flowrate need to be checked and revised. A preliminary calculation was done and a different value was obtained.
6 | Callout | Page 1 | Fatema Hashem | CONFIRM THAT THE REQUIRED SWEET KHUFF GAS TO 1RHCU REACTION HEATERS IS UPDATED ACCORDING TO THE NEW 2-HEATER CONFIGURATION AND TAKES INTO ACCOUNT THE FIRED DUTY FOR BOTH HYDROGEN AND OIL HEATERS
7 | Callout | Page 1 | Fatema Hashem | REVIEW THE FLOWS OF STREAM 21. PRELIMINARY CHECKS INDICATE A HIGHER FLOW MAY BE REQUIRED TO ACHIEVE THE FIRED DUTY AS PER 1RHCU UTILITIES SUMMARY