## 372-A-EQL-57001-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 3 | Adnan Alothman | 372D0279
2 | Text Box | 3 | Adnan Alothman | 372MXXXXX
3 | Text Box | 3 | Adnan Alothman | 372MXXXXX
4 | Text Box | 3 | Adnan Alothman | 372MXXXXX
5 | Text Box | 3 | Adnan Alothman | 372MXXXXX
6 | Text Box | 3 | Adnan Alothman | 372MXXXXX
7 | Text Box | 3 | Adnan Alothman | 372MXXXXX
8 | Text Box | 3 | Adnan Alothman | 372MXXXXX
9 | Text Box | 3 | Adnan Alothman | 372MXXXXX
10 | Text Box | 3 | Adnan Alothman | 372P3730A
11 | Text Box | 3 | Adnan Alothman | 372P3730A
12 | Text Box | 3 | Adnan Alothman | 372P3730B
13 | Text Box | 3 | Adnan Alothman | 372P3730B
14 | Text Box | 3 | Adnan Alothman | 372P3730C
15 | Text Box | 3 | Adnan Alothman | 372P3730C
16 | Text Box | 3 | Adnan Alothman | 372P3731A
17 | Text Box | 3 | Adnan Alothman | 372P3731A
18 | Text Box | 3 | Adnan Alothman | 372P3731B
19 | Text Box | 3 | Adnan Alothman | 372P3731B
20 | Text Box | 3 | Adnan Alothman | 372P3731C
21 | Text Box | 3 | Adnan Alothman | 372P3731C
22 | Text Box | 3 | Adnan Alothman | 372P3732A
23 | Text Box | 3 | Adnan Alothman | 372P3732A
24 | Text Box | 3 | Adnan Alothman | 372P3732B
25 | Text Box | 3 | Adnan Alothman | 372P3732B
26 | Call-out | 2 | MAK | Delete
27 | Call-out | 3 | MAK | Delete
28 | Callout | 3 | alexis.martinez | For pumps 372P0030A/B/C the operating pressure on FEED data is 111.8 psig. Review and correct.
29 | Callout | 3 | alexis.martinez | For pumps 372P0031A/B/C the operating pressure on FEED data is 112.3 psig. Review and correct.
30 | Callout | 3 | alexis.martinez | For pumps 372P0032A/B the operating pressure on FEED data is 112.3 psig. Review and correct.
31 | Callout | 3 | alexis.martinez | For the section of external material, the abbreviation "CI" is not included in the notes. Additional for pumps 372P0030A/B/C is missing the material. Review and correct
32 | Text Box | 1 | Yousif Ahmadi | General comments for all Equipment index - Use the new template - Provide Technip Group Spec. 000 GOPS 2014. - Fill the missing cells with the available information. - For new equipment in Existing units use the numbers as were agreed with Bapco.
33 | Callout | 3 | alexis.martinez | In "DRIVER" the letter "E" is not part of the driver definition. Review and correct accordingly.
34 | Cloud+ | 3 | Adnan Alothman | Motors numbers will be provided later
35 | Call-out | 3 | MAK | Refer to the Equipment Lists for the existing units and revamp areas that were sent through the Project Mailbox EN0815-PM (Bapco BMP). Follow the equipment numbering given in the lists.
36 | Call-out | 1 | MAK | Remove u from Unit No.
37 | Call-out | 1 | Raj | The Item Index needs to be re-submitted after incorporating Format Changes (Owner had provided comments to TTSJV). Some basis info like equipment tags have been checked in the Item Index as other documents like MSD, PID, Datasheets have not yet been submitted to the Owner
38 | Callout | 3 | alexis.martinez | The pumps motors are not a packages. Why they have Parent Tag Number?. Review and correct.
39 | Call-out | 2 | MAK | This template was revised by Bapco. MOC shall coordinate with JV Directorate for the revised template.
40 | Text Box | 1 | MAK | Use the latest document template which is part of the Homogenization Procedure. MOC shall coordinate with JV Directorate. Use A3 landscape document cover page.