## 000-A-PRO-50073-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Stamp | Page 1 | david.huggins
2 | Callout | Page 3 | james.wright | Add: Contractor shall use a computerized system which allows for the weighting of various activities and uses common unit of measure relative to the total project for accurate and meaningful measurement of overall project progress.
3 | Line | Page 3 | james.wright
4 | Text Box | Page 3 | james.wright | 4
5 | Line | Page 3 | james.wright
6 | Text Box | Page 3 | james.wright | has proposed
7 | Call-out | Page 4 | Raj | Replace of by or
8 | Line | Page 4 | james.wright
9 | Text Box | Page 4 | james.wright | Other services
10 | Line | Page 4 | james.wright
11 | Text Box | Page 4 | james.wright | Site
12 | Callout | Page 4 | james.wright | Add: The weighting proposed by the Contractor other than those fixed in the Contract will require Owners approval
13 | Text Box | Page 4 | james.wright | Any change will require Owners approval prior to implementation
14 | Ellipse | Page 5 | Raj
15 | Call-out | Page 5 | Raj | Check if detailed engg & Proc. figures have interchanged by error. Engg should be higher no. than Proj Mmgmnt and Procurement
16 | Text Box | Page 5 | Ravi Kumar | Add one more row: Operation of the units upto PAC and assign weightage
17 | Callout | Page 5 | james.wright | Show Budget (Est) Man-hours Column
18 | Callout | Page 5 | james.wright | Include detail as found in Exhibit 4 - Progress Measurement, Items 4.1 and 4.2
19 | Text Box | Page 5 | james.wright | Include statement regarding drawing / document / deliverable schedule and roll up (per Exhibit 4, Para 4.3 - Basis / Source for Home Office progress measurement)
20 | Line | Page 5 | james.wright
21 | Callout | Page 5 | james.wright | Figures are wrong way around. DE should be 58.88%
22 | Rectangle | Page 5 | james.wright
23 | Line | Page 6 | james.wright
24 | Callout | Page 6 | james.wright | progressed in line with the verified
25 | Callout | Page 6 | james.wright | Add: Distribution of percentage at various stages of procurement for each individual requisition will be kept the same for calculating procurement progress.
26 | Callout | Page 6 | james.wright | Add: A Procurement Status Report will indicate planned, forecast and actual status and the numbers in the summary form at each stage to reflect actual progress (Exhibit 4, Item 4.3.2)
27 | Callout | Page 6 | james.wright | Include EDMS detail according to Exhibit 4, Item 4.3.1
28 | Text Box | Page 6 | james.wright | Reference to table of rules of credit
29 | Text Box | Page 6 | james.wright | This report shall then form the basis of feeding the status to the CPM Schedule
30 | Arrow | Page 6 | Jeung.Kim
31 | Text Box | Page 6 | Jeung.Kim
32 | Callout | Page 7 | james.wright | Achieved progress shall be reported based on the rules of credit as detailed in this procedure (Add rules of credit for Sub-Contract Services) Refer Exhibit 4, Item 5.1.3 - Subcontracts
33 | Text Box | Page 7 | james.wright | / complexity
34 | Text Box | Page 7 | james.wright | (Refer to attachment ROC's)
35 | Text Box | Page 7 | james.wright | This will include all SC's to be issued from Contractors H/O as well as from the Site
36 | Callout | Page 7 | james.wright | Make reference to Invoicing Procedure that will capture the requirement for the placement of a Bank Guarantee for all purchased equipment / materials. Requirements for Insurance will be confirmed. This requirement is per Annex 12 - Price and payment procedures, Para 6 - Materials intended for the works. This means that if a Guarantee is not in place, Progress % will be measured and reported, however payment will not be made at the Invoice level.
37 | Text Box | Page 8 | james.wright | Add: Include detailed methodology of evaluation for each discipline / category as outlined in Exhibit 4, Para 5 - Progress Evaluation
38 | Callout | Page 9 | Nalini Mohan | Why equipment MRs are listed in Process. They are already captured in other disciplines
39 | Call-out | Page 10 | Ravi Kumar | MR start is not a deliverable; it is an internal activity of JV; progress weightage cannot be assigned
40 | Line | Page 10 | james.wright
41 | Text Box | Page 10 | james.wright | This applies only for MR's
42 | Callout | Page 12 | james.wright
43 | Text Box | Page 13 | james.wright | Add section on how Payment Linked Milestones will be handled and certified (Per Annex 12 - Price and payment procedures, Exhibit B - Invoice Schedule & Procedure, Item ii - Adjustments to Invoicing Schedule for Payment Linked Milestones) Add Complete table of Payment Linked Milestones as per Annex 12 - Price and payment procedures, Exhibit B - Invoice Schedule & Procedure, Table 2 - Schedule of Payment Linked Milestones
44 | Call-out | Page 14 | Ravi Kumar | make it simple : TM to stand for Technical Memorandum
45 | Callout | Page 16 | james.wright | Preliminary. To be finalized in line with Level 3 Schedule and final PMS
46 | Callout | Page 17 | james.wright | Preliminary. To be finalized in line with Level 3 Schedule and final PMS