## 000-C-ITP-70003-001-RAP
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Callout | 1 | Mohamed Ayyash | Typo, Should read No. (apply to all sheets. | Noted, will be updated at next rev. | Y
2 | Callout | 1 | Mohamed Ayyash | Align subject with project name for better representation | Noted, will be updated at next rev. | Y
3 | Callout | 1 | Yousif Ahmadi | Change to all Technip to TR | Noted, will be implemented according to new project template | Y
4 | Callout | 2 | Yousif Ahmadi | Stress Relief of Heads "W" | Not agree. Not necessary to be a witness for inspection level. "R" point will be implemented as per contractual checklist BMPS-C-50115 for repairs and intermediate NDE. | N
5 | Callout | 2 | Yousif Ahmadi | Edge Preparation NDE (VI, PT, MT) "W" | Not agree. Not necessary to be a witness for inspection level. "R" point will be implemented as per contractual checklist BMPS-C-50115 for repairs and intermediate NDE. | N
6 | Callout | 2 | Yousif Ahmadi | NDE Prior to Welding (UT,MT,PT,VI,DC) "W" | Not agree. Not necessary to be a witness for inspection level. "R" point will be implemented as per contractual checklist BMPS-C-50115 for repairs and intermediate NDE. | N