## 000-G-ITP-60002-001-RAP
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Call-out | 2 | Jawad Alawi | Add : Preshipment Inspection
2 | Text Box | 3 | Ahmed Bucheeri | Specify applicable Doc.
3 | Text Box | 3 | Ahmed Bucheeri | Add WPS & PQR for reviwing
4 | Text Box | 3 | Hasan Asad | Shall be agreed basis final test plan.
5 | Text Box | 3 | Hasan Asad | Add: Seal inspection
6 | Text Box | 3 | Hasan Asad | If HV Motor, partial discharge test shall be carried out.
7 | Text Box | 3 | Hasan Asad | Vibration & Brg Temp. Test
8 | Text Box | 4 | Ahmed Bucheeri | Specify applicable Doc.
9 | Text Box | 4 | Ahmed Bucheeri | Add WPS & PQR for reviwing
10 | Text Box | 5 | Ahmed Bucheeri | Specify applicable Doc.
11 | Text Box | 5 | Ahmed Bucheeri | Add WPS & PQR for reviwing
12 | Text Box | 7 | Ahmed Bucheeri | Specify applicable Doc.
13 | Text Box | 7 | Ahmed Bucheeri | Add WPS & PQR for reviwing
14 | Text Box | 8 | Ahmed Bucheeri | Add WPS & PQR for reviwing
15 | Text Box | 10 | Sankara | Add LV motors also.
16 | Text Box | 11 | Ebrahim | Low voltage indoor distribution boards shall be intended for lighting and small power users and services. IEC 60439-1 is for LV Switchgear. Is the scope to supply LV Indoor Distribution Boards or Switchgear?